## Summary
Work plan summary:
5GS RRM Test Cases (TS 38.533, TS 38.522)
|  |  | Overall |  | FR1 |  | FR2 |  | FR1+FR2
| 5GS RRM Test Cases (TS 38.533, TS 38.522) | SA Option 2 (SA NR) | 85.47% |  | 100% |  | 64.33% |  | 94.25%
|  | NSA Option 3 (EN-DC) | 88.95% |  | 100% |  | 73.16% |  | 98.21%
SA Option 5
NSA Option 4 (NE-DC)
NSA Option 7 (NGEN-DC)
|  | Area | 5GS RRM test case statistics
|  |  | Overall number of test cases |  | Number of test cases applicable for FR1 |  | Number of test cases applicable for FR2 |  | Number of FR1+FR2 specific test cases
|  |  | Overall | Completed | Overall | Completed | Overall | Completed | Overall | Completed
| 5GS RRM Test Cases (TS 38.533, TS 38.522) | SA Option 2 (SA NR) | 153 | 102 | 83 | 83 | 63 | 15 | 7 | 4
|  | NSA Option 3 (EN-DC) | 134 | 94 | 68 | 68 | 61 | 22 | 5 | 4
SA Option 5
|  | NSA Option 4 (NE-DC) | 0 | 0
|  | NSA Option 7 (NGEN-DC) | 0 | 0

## 5GS RRM
WP Title: | 5GS RRM Test Cases (TS 38.533, TS 38.522) | [10 empty] | WP item applicability | [13 empty] | End of work plan columns. Note! Do not remove this column.
RAN-CN interface options dependency
WP Scope: | This part of the work plan covers RRM test cases for SA and NSA. | [10 empty] | 5GC/NR |  |  |  | 5GC/LTE |  | EPC/LTE |  |  |  | 5GC/NR master |  | 5GC / LTE master
WP Resp: | Adrian Cardalda-Garcia, Rohde & Schwarz |  |  |  | Adrian.Cardalda-Garcia@rohde-schwarz.com
TS Resp: | Adrian Cardalda-Garcia, Rohde & Schwarz |  |  |  | Adrian.Cardalda-Garcia@rohde-schwarz.com | [6 empty] | SA | [5 empty] | NSA
[12 empty] | Opt.2 |  |  |  | Opt.5 |  | Opt.3 |  |  |  | Opt.4 |  | Opt.7
WP Item ID | Is test case | TS | Clause | Title | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | WP item compl. | 1st Target | FR1 | FR2 | FR1+FR2 |  |  | 1st Target | FR1 | FR2 | FR1+FR2
[11 empty] | Overall |  | 85.47% | [5 empty] | 88.95%
[11 empty] | Overall vs FR1,FR2 and FR1+FR2 |  | 100% | 64.33% | 94.25% |  |  |  | 100% | 73.16% | 98.21%
Phase 1
Phase 2
[11 empty] | Phase 3 |  | 100% | 100% | 100% |  |  |  | 100%
[11 empty] | Phase 4 |  | 100% | [5 empty] | 100% | 100% | 100%
[11 empty] | Phase 5 |  | 100% | 100% | 100% |  |  |  | 100%
[11 empty] | Phase 6 |  | 100% | [5 empty] | 100% | 100% | 100%
[11 empty] | Phase 7 |  | 100% | [5 empty] | 100%
[11 empty] | Phase 8 |  | 100% | [5 empty] | 100%
[11 empty] | Phase 9 |  | 100% | [5 empty] | 100%
[11 empty] | Phase 10 |  |  | 100% |  |  |  |  | 100%
[11 empty] | Phase 11 |  | 100% | 100% | 100% |  |  |  | 100% | 100%
[11 empty] | Phase 12 |  | 100% | 100% |  |  |  |  | 100% | 100% | 100%
[11 empty] | Phase 13 |  |  | 27.92% | 23.33% |  |  |  |  | 100%
[11 empty] | Phase 14 | [8 empty] | 34.62% | 30%
[7 empty] | Overall# WP items: Phase 1 # WP items: Phase 2# WP items: Phase 3# WP items: Phase 4# WP items: Phase 5# WP items: Phase 6# WP items: Phase 7# WP items: Phase 8# WP items: Phase 9# WP items: Phase 10# WP items: Phase 11# WP items: Phase 12# WP items: Phase 13# WP items: Phase 14# WP items: | [5 empty] | 117 0 0 40 13 13 16 1 19 11 0 3 1 0 0 | 97 0 0 27 0 4 0 0 0 0 3 5 10 48 0 | 40 0 0 27 0 3 0 0 0 0 0 7 0 3 0 |  |  |  | 103 0 0 2 32 10 14 14 6 14 7 1 3 0 0 | 95 0 0 0 26 0 5 0 0 0 0 5 10 10 39 | 39 0 0 0 26 0 5 0 0 0 0 0 7 0 1
Start of work plan items. Note! Do not remove this row. Introduce new work plan rows/items below this row.
EN-DC with PSCell in FR1
|  | 38.533 | 4 | EN-DC with PSCell in FR1 | New clause |  |  |  | Tests in this area are only for NSA Option 3 | 0 | [5 empty] | 1 |  | 1 |  |  |  | 1 |  | 1
|  | 38.533 | 4.1 | Void | New sub-clause |  |  |  | Empty clause so that numbering will match for SA and NSA | 0 |  | 1 |  |  |  | 1 | [5 empty] | 1 |  | 1
|  | 38.533 | 4.2 | Void | New sub-clause |  |  |  | Empty clause so that numbering will match for SA and NSA | 0 |  | 1 |  |  |  | 1 |  | 1 | [5 empty] | 1
|  | 38.533 | 4.3 | RRC_CONNECTED state mobility | New sub-clause |  |  |  |  | 0 |  | 1 |  |  |  | 1 |  | 1 |  |  |  | 1
|  | 38.533 | 4.3.1 | Void | New sub-clause |  |  |  | Empty clause so that numbering will match for SA and NSA | 0 |  | 1 |  |  |  | 1 |  | 1 |  |  |  | 1
|  | 38.533 | 4.3.2 | RRC connection mobility control | New sub-clause |  |  |  |  | 0 |  | 1 |  |  |  | 1 |  | 1 |  |  |  | 1
|  | 38.533 | 4.3.2.1 | Void | New sub-clause |  |  |  | Empty clause so that numbering will match for SA and NSA | 0 |  | 1 |  |  |  | 1 |  | 1 |  |  |  | 1
|  | 38.533 | 4.3.2.2 | Random access | New sub-clause |  |  |  |  | 0 |  | 1 |  |  |  | 1 |  | 1 |  |  |  | 1
78 | Y | 38533 | 4.3.2.2.1 | EN-DC FR1 contention based random access | Test in A.4.3.2.2.1 in TS 38.133 | Anritsu | Opt 3: RAN5#85 (Nov-19) | R5-192477 R5-199583 | RAN4 Phase 1 | 1 | 100% |  |  |  |  | 1 |  | 6 | 100%
79 | Y | 38533 | 4.3.2.2.2 | EN-DC FR1 non-contention based random access | Test in A.4.3.2.2.2 in TS 38.133 | Anritsu | Opt 3: RAN5#85 (Nov-19) | R5-192478 R5-199583 | RAN4 Phase 1 | 1 | 100% | 1 |  |  |  | 1 |  | 6 | 100%
|  | 38.533 | 4.3.2.3 | Void | New sub-clause |  |  |  | Empty clause so that numbering will match for SA and NSA | 0 |  | 1 |  |  |  | 1 |  | 1 |  |  |  | 1
|  | 38.533 | 4.4 | Timing | New sub-clause |  |  |  |  | 0 |  | 1 |  |  |  | 1 |  | 1 |  |  |  | 1
|  | 38.533 | 4.4.1 | UE transmit timing | New sub-clause |  |  |  |  | 0 |  | 1 |  |  |  | 1 |  | 1 |  |  |  | 1
30 | Y | 38533 | 4.4.1.1 | EN-DC FR1 UE transmit timing accuracy | Test in A.4.4.1.1 in TS 38.133 | Qualcomm | Opt 3: RAN5#82 (Feb-19) | R5-188001 R5-192503 | RAN4 Phase 1 | 1 | 100% | 1 |  |  |  | 1 |  | 3 | 100%
|  | 38.533 | 4.4.2 | UE timer accuracy | New sub-clause |  |  |  |  | 0 |  | 1 |  |  |  | 1 |  | 1 |  |  |  | 1
|  | 38.533 | 4.4.3 | Timing advance | New sub-clause |  |  |  |  | 0 |  | 1 |  |  |  | 1 |  | 1 |  |  |  | 1
80 | Y | 38533 | 4.4.3.1 | EN-DC FR1 timing advance adjustment accuracy | Test in A.4.4.3 in TS 38.133 | Qualcomm | Opt 3: RAN5#82 (Feb-19) | R5-188011 R5-192678 | RAN4 Phase 1 | 1 | 100% | 1 |  |  |  | 1 |  | 3 | 100%
|  | 38.533 | 4.5 | Signalling characteristics | New sub-clause |  |  |  |  | 0 |  | 1 |  |  |  | 1 |  | 1 |  |  |  | 1
|  | 38.533 | 4.5.1 | Radio link monitoring | New sub-clause |  |  |  |  | 0 |  | 1 |  |  |  | 1 |  | 1 |  |  |  | 1
32 | Y | 38.533 | 4.5.1.1 | EN-DC FR1 radio link monitoring out-of-sync test for PSCell configured with SSB-based RLM RS in non-DRX mode | Test in A.4.5.1.1 in TS 38.133 | Qualcomm | Opt 3: RAN5#84 (Aug-19) | R5-190897 R5-195024 R5-197618 | RAN4 Phase 1 | 1 | 100% | 1 |  |  |  | 1 |  | 5 | 100%
33 | Y | 38.533 | 4.5.1.2 | EN-DC FR1 radio link monitoring in-sync test for PSCell configured with SSB-based RLM RS in non-DRX mode | Test in A.4.5.1.2 in TS 38.133 | Qualcomm | Opt 3: RAN5#84 (Aug-19) | R5-190900 R5-192674 R5-195035 R5-197612 | RAN4 Phase 1 | 1 | 100% | 1 |  |  |  | 1 |  | 5 | 100%
34 | Y | 38.533 | 4.5.1.3 | EN-DC FR1 radio link monitoring out-of-sync test for PSCell configured with SSB-based RLM RS in DRX mode | Test in A.4.5.1.3 in TS 38.133 | Qualcomm | Opt 3: RAN5#84 (Aug-19) | R5-190898 R5-195025 R5-197619 | RAN4 Phase 1 | 1 | 100% | 1 |  |  |  | 1 |  | 5 | 100%
35 | Y | 38.533 | 4.5.1.4 | EN-DC FR1 radio link monitoring in-sync test for PSCell configured with SSB-based RLM RS in DRX mode | Test in A.4.5.1.4 in TS 38.133 | Qualcomm | Opt 3: RAN5#84 (Aug-19) | R5-190901 R5-192675 R5-194702 R5-195043 R5-197612 | RAN4 Phase 1 | 1 | 100% | 1 |  |  |  | 1 |  | 5 | 100%
199 | Y | 38.533 | 4.5.1.5 | EN-DC FR1 radio link monitoring out-of-sync test for PSCell configured with CSI-RS-based RLM RS in non-DRX mode | Test in A.4.5.1.5 in TS 38.133 | Huawei | Opt 3: RAN5#85 (Nov-19) | R5-190512 R5-195045 R5-197426 R5-199364 |  | 1 | 100% | 1 |  |  |  | 1 |  | 6 | 100%
200 | Y | 38.533 | 4.5.1.6 | EN-DC FR1 radio link monitoring in-sync test for PSCell configured with CSI-RS-based RLM RS in non-DRX mode | Test in A.4.5.1.6 in TS 38.133 | Huawei | Opt 3: RAN5#85 (Nov-19) | R5-190513 R5-193758 R5-197427 R5-199368 |  | 1 | 100% | 1 |  |  |  | 1 |  | 6 | 100%
201 | Y | 38.533 | 4.5.1.7 | EN-DC FR1 radio link monitoring out-of-sync test for PSCell configured with CSI-RS-based RLM RS in DRX mode | Test in A.4.5.1.7 in TS 38.133 | Huawei | Opt 3: RAN5#85 (Nov-19) | R5-190514 R5-193759 R5-197428 R5-199365 |  | 1 | 100% | 1 |  |  |  | 1 |  | 6 | 100%
202 | Y | 38.533 | 4.5.1.8 | EN-DC FR1 radio link monitoring in-sync test for PSCell configured with CSI-RS-based RLM RS in DRX mode | Test in A.4.5.1.8 in TS 38.133 | Huawei | Opt 3: RAN5#85 (Nov-19) | R5-190515 R5-193760 R5-197429 R5-199369 |  | 1 | 100% | 1 |  |  |  | 1 |  | 6 | 100%
|  | 38.533 | 4.5.2 | Interruption | New sub-clause |  |  |  |  | 0 |  | 1 |  |  |  | 1 |  | 1 |  |  |  | 1
52 | Y | 38.533 | 4.5.2.1 | EN-DC FR1 interruptions at transitions between active and non-active during DRX in synchronous EN-DC | Test in A.4.5.2.1.1 in TS 38.133 | Huawei | Opt 3: RAN5#85 (Nov-19) | R5-190516 R5-197430 R5-197794 | RAN4 Phase 1 | 1 | 100% | 1 |  |  |  | 1 |  | 6 | 100%
53 | Y | 38.533 | 4.5.2.2 | EN-DC FR1 interruptions at transitions between active and non-active during DRX in asynchronous EN-DC | Test in A.4.5.2.1.2 in TS 38.133 | Huawei | Opt 3: RAN5#85 (Nov-19) | R5-190517 R5-197431 R5-197795 | RAN4 Phase 1 | 1 | 100% | 1 |  |  |  | 1 |  | 6 | 100%
56 | Y | 38.533 | 4.5.2.3 | EN-DC FR1 interruptions during measurements on deactivated NR SCC in synchronous EN-DC | Test in A.4.5.2.1.3 in TS 38.133 | Huawei | Opt 3: RAN5#86 (Feb-20) | R5-190518 R5-197432 R5-201063 | RAN4 Phase 1 | 1 | 100% | 1 |  |  |  | 1 |  | 7 | 100%
57 | Y | 38.533 | 4.5.2.4 | EN-DC FR1 interruptions during measurements on deactivated NR SCC in asynchronous EN-DC | Test in A.4.5.2.1.4 in TS 38.133 | Huawei | Opt 3: RAN5#86 (Feb-20) | R5-190519 R5-197433 R5-201064 | RAN4 Phase 1 | 1 | 100% | 1 |  |  |  | 1 |  | 7 | 100%
58 | Y | 38.533 | 4.5.2.5 | EN-DC FR1 interruptions during measurements on deactivated E-UTRAN SCC in synchronous EN-DC | Test in A.4.5.2.1.5 in TS 38.133 | Huawei | Opt 3: RAN5#87 (May-20) | R5-190520 R5-197434 R5-202996 | RAN4 Phase 1 | 1 | 100% | 1 |  |  |  | 1 |  | 8 | 100%
59 | Y | 38.533 | 4.5.2.6 | EN-DC FR1 interruptions during measurements on deactivated E-UTRAN SCC in asynchronous EN-DC | Test in A.4.5.2.1.6 in TS 38.133 | Huawei | Opt 3: RAN5#87 (May-20) | R5-190907 R5-197435 R5-202997 | RAN4 Phase 1 | 1 | 100% | 1 |  |  |  | 1 |  | 8 | 100%
|  | 38.533 | 4.5.3 | Scell activation and deactivation delay | New sub-clause |  |  |  |  | 0 |  | 1 |  |  |  | 1 |  | 1 |  |  |  | 1
48 | Y | 38.533 | 4.5.3.1 | EN-DC FR1 SCell activation and deactivation of known SCell in non-DRX for 160ms SCell measurement cycle | Test in A.4.5.3.1 in TS 38.133 | Bureau Veritas | Opt 3: RAN5#87 (May-20) | R5-190680 R5-194340 R5-195013 R5-196503 R5-202998 | RAN4 Phase 1 | 1 | 100% | 1 |  |  |  | 1 |  | 8 | 100%
49 | Y | 38.533 | 4.5.3.2 | EN-DC FR1 SCell activation and deactivation of known Scell in non-DRX for 320ms SCell measurement cycle | Test in A.4.5.3.2 in TS 38.133 | Bureau Veritas | Opt 3: RAN5#87 (May-20) | R5-190681 R5-195013 R5-196503 R5-202999 | RAN4 Phase 1 | 1 | 100% | 1 |  |  |  | 1 |  | 8 | 100%
50 | Y | 38.533 | 4.5.3.3 | EN-DC FR1 SCell activation and deactivation of unknown SCell in non-DRX | Test in A.4.5.3.3 in TS 38.133 | Bureau Veritas | Opt 3: RAN5#87 (May-20) | R5-190682 R5-195013 R5-196503 R5-203000 | RAN4 Phase 1 | 1 | 100% | 1 |  |  |  | 1 |  | 8 | 100%
|  | 38.533 | 4.5.4 | UE UL carrier RRC reconfiguration delay | New sub-clause |  |  |  |  | 0 |  | 1 |  |  |  | 1 |  | 1 |  |  |  | 1
161 | Y | 38.533 | 4.5.4.1 | EN-DC FR1 UE UL carrier RRC reconfiguration delay | Test in A.4.5.4 in TS 38.133 | Samsung | Opt 3: RAN5#87 (May-20) | R5-202700 | RAN4 Phase 1 | 1 | 100% | 1 |  |  |  | 1 |  | 8 | 100%
|  | 38.533 | 4.5.5 | Beam failure detecion and link recovery procedures | New sub-clause |  |  |  |  | 0 |  | 1 |  |  |  | 1 |  | 1 |  |  |  | 1
162 | Y | 38.533 | 4.5.5.1 | EN-DC FR1 SSB-based beam failure detection and link recovery in non-DRX | Test in A.4.5.5.1 in TS 38.133 | Huawei, Hisilicon | Opt 3: RAN5#88 (Aug-20) | R5-196738 R5-203828 |  | 1 | 100% | 1 |  |  |  | 1 |  | 9 | 100%
163 | Y | 38.533 | 4.5.5.2 | EN-DC FR1 SSB-based beam failure detection and link recovery in DRX | Test in A.4.5.5.2 in TS 38.133 | Huawei, Hisilicon | Opt 3: RAN5#88 (Aug-20) | R5-196739 R5-203829 |  | 1 | 100% | 1 |  |  |  | 1 |  | 9 | 100%
164 | Y | 38.533 | 4.5.5.3 | EN-DC FR1 CSI-RS-based beam failure detection and link recovery in non-DRX | Test in A.4.5.5.3 in TS 38.133 | CAICT | Opt 3: RAN5#88 (Aug-20) | R5-203830 |  | 1 | 100% | 1 |  |  |  | 1 |  | 9 | 100%
165 | Y | 38.533 | 4.5.5.4 | EN-DC FR1 CSI-RS-based beam failure detection and link recovery in DRX | Test in A.4.5.5.4 in TS 38.133 | CAICT | Opt 3: RAN5#88 (Aug-20) | R5-193872 R5-203831 |  | 1 | 100% | 1 |  |  |  | 1 |  | 9 | 100%
|  | 38.533 | 4.5.6 | Active BWP switch delay | New sub-clause |  |  |  |  | 0 |  | 1 |  |  |  | 1 |  | 1 |  |  |  | 1
|  | 38.533 | 4.5.6.1 | DCI-based and timer-based active BWP switch | New sub-clause |  |  |  |  | 0 |  | 1 |  |  |  | 1 |  | 1 |  |  |  | 1
166 | Y | 38.533 | 4.5.6.1.1 | EN-DC FR1 DCI-based DL active BWP switch in non-DRX in synchronous EN-DC | Test in A.4.5.6.1.1 in TS 38.133 | Huawei, Hisilicon | Opt 3: RAN5#88 (Aug-20) | R5-191492 R5-203833 |  | 1 | 100% | 1 |  |  |  | 1 |  | 9 | 100%
64 | Y | 38.533 | 4.5.6.1.2 | EN-DC FR1 DCI-based DL active BWP switch with SCell in non-DRX in synchronous EN-DC | Test in A.4.5.6.1.2 in TS 38.133 | Huawei, Hisilicon | Opt 3: RAN5#88 (Aug-20) | R5-191492 R5-203834 |  | 1 | 100% | 1 |  |  |  | 1 |  | 9 | 100%
|  | 38.533 | 4.5.6.2 | RRC-based active BWP switch | New sub-clause
167 | Y | 38.533 | 4.5.6.2.1 | EN-DC FR1 RRC-based DL active BWP switch in non-DRX in synchronous EN-DC | Test in A.4.5.6.2.1 in TS 38.133 | Huawei, Hisilicon | Opt 3: RAN5#88 (Aug-20) | R5-191492 R5-203836 |  | 1 | 100% | 1 |  |  |  | 1 |  | 9 | 100%
|  | 38.533 | 4.5.7 | PSCell addition and release delay | New sub-clause
184 | Y | 38.533 | 4.5.7.1 | EN-DC FR1 addition and release delay of known PSCell | Test in A.4.5.7.1 in TS 38.133 | Rohde&Schwarz | Opt 3: RAN5#90 (Feb-21) | R5-196737 R5-206797 R5-211615 |  | 1 | 100% | 1 |  |  |  | 1 |  | 11 | 100% |  |  | 1
|  | 38.533 | 4.6 | Measurement procedures | New sub-clause |  |  |  |  | 0 |  | 1 |  |  |  | 1 |  | 1 |  |  |  | 1
|  | 38.533 | 4.6.1 | Intra-frequency measurements | New sub-clause |  |  |  |  | 0 |  | 1 |  |  |  | 1 |  | 1 |  |  |  | 1
1 | Y | 38533 | 4.6.1.1 | EN-DC FR1 event-triggered reporting without gap in non-DRX | Test in A.4.6.1.1.1 in TS 38.133 | Bureau Veritas | Opt 3: RAN5#83 (May-19) | R5-190889 R5-192481 R5-195020 | RAN4 Phase 1 | 1 | 100% | 1 |  |  |  | 1 |  | 4 | 100% |  |  | 1 |  | 1
2 | Y | 38533 | 4.6.1.2 | EN-DC FR1 event-triggered reporting without gap in DRX | Test in A.4.6.1.1.2 in TS 38.133 | Bureau Veritas | Opt 3: RAN5#83 (May-19) | R5-190890 R5-192482 R5-195020 | RAN4 Phase 1 | 1 | 100% | 1 |  |  |  | 1 |  | 4 | 100%
3 | Y | 38533 | 4.6.1.3 | EN-DC FR1 event-triggered reporting with gap in non-DRX | Test in A.4.6.1.1.3 in TS 38.133 | Huawei | Opt 3: RAN5#84 (Aug-19) | R5-190883 R5-192063 R5-197402 | RAN4 Phase 1 | 1 | 100% | 1 |  |  |  | 1 |  | 5 | 100%
4 | Y | 38533 | 4.6.1.4 | EN-DC FR1 event-triggered reporting with gap in DRX | Test in A.4.6.1.1.4 in TS 38.133 | Huawei | Opt 3: RAN5#84 (Aug-19) | R5-190884 R5-192064 R5-197403 | RAN4 Phase 1 | 1 | 100% | 1 |  |  |  | 1 |  | 5 | 100%
5 | Y | 38533 | 4.6.1.5 | EN-DC FR1 event-triggered reporting without gap in non-DRX with SSB time index detection | Test in A.4.6.1.1.5 in TS 38.133 | Huawei | Opt 3: RAN5#84 (Aug-19) | R5-192500 R5-197404 | RAN4 Phase 1 | 1 | 100% | 1 |  |  |  | 1 |  | 5 | 100%
6 | Y | 38533 | 4.6.1.6 | EN-DC FR1 event-triggered reporting with gap in non-DRX with SSB time index detection | Test in A.4.6.1.1.6 in TS 38.133 | Huawei | Opt 3: RAN5#84 (Aug-19) | R5-190882 R5-192062 R5-197405 | RAN4 Phase 1 | 1 | 100% | 1 |  |  |  | 1 |  | 5 | 100%
|  | 38.533 | 4.6.2 | Inter-frequency measurements | New sub-clause |  |  |  |  | 0 |  | 1 |  |  |  | 1 |  | 1 |  |  |  | 1
81 | Y | 38533 | 4.6.2.1 | EN-DC FR1-FR1 event-triggered reporting in non-DRX | Test in A.4.6.2.1 in TS 38.133 | Ericsson | Opt 3: RAN5#83 (May-19) | R5-187997 R5-192492 R5-195174 | RAN4 Phase 1 | 1 | 100% | 1 |  |  |  | 1 |  | 4 | 100%
82 | Y | 38533 | 4.6.2.2 | EN-DC FR1-FR1 event-triggered reporting in DRX | Test in A.4.6.2.2 in TS 38.133 | Ericsson | Opt 3: RAN5#83 (May-19) | R5-187997 R5-192493 R5-195175 | RAN4 Phase 1 | 1 | 100% | 1 |  |  |  | 1 |  | 4 | 100%
85 | Y | 38533 | 4.6.2.5 | EN-DC FR1-FR1 event-triggered reporting in non-DRX with SSB time index detection | Test in A.4.6.2.5 in TS 38.133 | Ericsson | Opt 3: RAN5#83 (May-19) | R5-187997 R5-192494 R5-195176 | RAN4 Phase 1 | 1 | 100% | 1 |  |  |  | 1 |  | 4 | 100%
86 | Y | 38533 | 4.6.2.6 | EN-DC FR1-FR1 event-triggered reporting in DRX with SSB time index detection | Test in A.4.6.2.6 in TS 38.133 | Ericsson | Opt 3: RAN5#83 (May-19) | R5-187997 R5-192495 R5-195177 | RAN4 Phase 1 | 1 | 100% | 1 |  |  |  | 1 |  | 4 | 100%
|  | 38.533 | 4.6.4 | L1-RSRP for beam reporting | New sub-clause |  |  |  |  | 0 |  | 1 |  |  |  | 1 |  | 1 |  |  |  | 1
276 | Y | 38533 | 4.6.4.1 | EN-DC FR1 SSB-based L1-RSRP measurement in non-DRX | Test in A.4.6.3.1 in TS 38.133 | Ericsson | Opt 3: RAN5#86 (Feb-20) | R5-196675 R5-198578 R5-201045 |  | 1 | 100% | 1 |  |  |  | 1 |  | 7 | 100%
277 | Y | 38533 | 4.6.4.2 | EN-DC FR1 SSB-based L1-RSRP measurement in DRX | Test in A.4.6.3.2 in TS 38.133 | Ericsson | Opt 3: RAN5#86 (Feb-20) | R5-196676 R5-199390 R5-201046 |  | 1 | 100% | 1 |  |  |  | 1 |  | 7 | 100%
278 | Y | 38533 | 4.6.4.3 | EN-DC FR1 CSI-RS-based L1-RSRP measurement in non-DRX | Test in A.4.6.3.3 in TS 38.133 | Ericsson | Opt 3: RAN5#86 (Feb-20) | R5-196677 R5-199391 R5-201047 |  | 1 | 100% | 1 |  |  |  | 1 |  | 7 | 100%
279 | Y | 38533 | 4.6.4.4 | EN-DC FR1 CSI-RS-based L1-RSRP measurement in DRX | Test in A.4.6.3.4 in TS 38.133 | Ericsson | Opt 3: RAN5#86 (Feb-20) | R5-197436 R5-198581 R5-201048 |  | 1 | 100% | 1 |  |  |  | 1 |  | 7 | 100%
|  | 38.533 | 4.7 | Measurement performance requirements | New sub-clause |  |  |  |  | 0 |  | 1 |  |  |  | 1 |  | 1 |  |  |  | 1
|  | 38.533 | 4.7.1 | SS-RSRP | New sub-clause |  |  |  |  | 0 |  | 1 |  |  |  | 1 |  | 1 |  |  |  | 1
|  | 38.533 | 4.7.1.1 | Intra-frequency measurements | New sub-clause
24 | Y | 38.533 | 4.7.1.1.1 | EN-DC FR1 SS-RSRP absolute measurement accuracy | Test in A.4.7.1.1 in TS 38.133 | Rohde&Schwarz | Opt 3: RAN5#84 (Aug-19) | R5-188002 R5-190478 R5-191486 R5-197568 | RAN4 Phase 1 | 1 | 100% | 1 |  |  |  | 1 |  | 5 | 100% |  |  | 1
156 | Y | 38.533 | 4.7.1.1.2 | EN-DC FR1 SS-RSRP relative measurement accuracy | Test in A.4.7.1.1 in TS 38.133 | Rohde&Schwarz | Opt 3: RAN5#84 (Aug-19) | R5-188002 R5-190478 R5-191486 R5-197568 | RAN4 Phase 1 | 1 | 100% | 1 |  |  |  | 1 |  | 5 | 100% |  |  | 1
|  | 38.533 | 4.7.1.2 | Inter-frequency measurements
26 | Y | 38.533 | 4.7.1.2.1 | EN-DC FR1-FR1 SS-RSRP absolute measurement accuracy | Test in A.4.7.1.2 in TS 38.133 | Rohde&Schwarz | Opt 3: RAN5#86 (Feb-20) | R5-188002 R5-190478 R5-191486 R5-201039 | RAN4 Phase 1 | 1 | 100% | 1 |  |  |  | 1 |  | 7 | 100% |  |  | 1
157 | Y | 38.533 | 4.7.1.2.2 | EN-DC FR1-FR1 SS-RSRP relative measurement accuracy | Test in A.4.7.1.2 in TS 38.133 | Rohde&Schwarz | Opt 3: RAN5#86 (Feb-20) | R5-188002 R5-190478 R5-191486 R5-201039 | RAN4 Phase 1 | 1 | 100% | 1 |  |  |  | 1 |  | 7 | 100% |  |  | 1
|  | 38.533 | 4.7.2 | SS-RSRQ | New sub-clause |  |  |  |  | 0 |  | 1 |  |  |  | 1 |  | 1 |  |  |  | 1
67 | Y | 38.533 | 4.7.2.1 | EN-DC FR1 SS-RSRQ measurement accuracy | Test in A.4.7.2.1 in TS 38.133 | Rohde&Schwarz | Opt 3: RAN5#86 (Feb-20) | R5-190479 R5-191487 | RAN4 Phase 2 | 1 | 100% | 1 |  |  |  | 1 |  | 7 | 100%
89 | Y | 38.533 | 4.7.2.2.1 | EN-DC FR1-FR1 SS-RSRQ absolute measurement accuracy | Test in A.4.7.2.2 in TS 38.133 | Rohde&Schwarz | Opt 3: RAN5#86 (Feb-20) | R5-190479 R5-191487 R5-200276 | RAN4 Phase 2 | 1 | 100% | 1 |  |  |  | 1 |  | 7 | 100%
311 | Y | 38.533 | 4.7.2.2.2 | EN-DC FR1-FR1 SS-RSRQ relative measurement accuracy | Test in A.4.7.2.2 in TS 38.133 | Rohde&Schwarz | Opt 3: RAN5#86 (Feb-20) | R5-200276 |  | 1 | 100% | 1 |  |  |  | 1 |  | 7 | 100%
|  | 38.533 | 4.7.3 | SS-SINR | New sub-clause |  |  |  |  | 0 |  | 1 |  |  |  | 1 |  | 1 |  |  |  | 1
232 | Y | 38.533 | 4.7.3.1 | EN-DC FR1 SS-SINR measurement accuracy | Test in A.4.7.3.1 in TS 38.133 | Rohde&Schwarz | Opt 3: RAN5#86 (Feb-20) | R5-196740 R5-200277 |  | 1 | 100% | 1 |  |  |  | 1 |  | 7 | 100%
233 | Y | 38.533 | 4.7.3.2.1 | EN-DC FR1-FR1 SS-SINR absolute measurement accuracy | Test in A.4.7.3.2 in TS 38.133 | Rohde&Schwarz | Opt 3: RAN5#86 (Feb-20) | R5-196741 R5-200278 |  | 1 | 100% | 1 |  |  |  | 1 |  | 7 | 100%
312 | Y | 38.533 | 4.7.3.2.2 | EN-DC FR1-FR1 SS-SINR relative measurement accuracy | Test in A.4.7.3.2 in TS 38.133 | Rohde&Schwarz | Opt 3: RAN5#86 (Feb-20) | R5-200278 |  | 1 | 100% | 1 |  |  |  | 1 |  | 7 | 100%
|  | 38.533 | 4.7.4 | L1-RSRP for beam reporting | New sub-clause |  |  |  |  | 0 |  | 1 |  |  |  | 1 |  | 1 |  |  |  | 1
168 | Y | 38.533 | 4.7.4.1.1 | EN-DC FR1 SSB-based L1-RSRP absolute measurement accuracy | Test in A.4.7.4.1 in TS 38.133 | Rohde&Schwarz | Opt 3: RAN5#88 (Aug-20) | R5-190480 R5-191488 R5-204878 |  | 1 | 100% | 1 |  |  |  | 1 |  | 9 | 100% |  |  | 1
313 | Y | 38.533 | 4.7.4.1.2 | EN-DC FR1 SSB-based L1-RSRP relative measurement accuracy | Test in A.4.7.4.1 in TS 38.133 | Rohde&Schwarz | Opt 3: RAN5#88 (Aug-20) | R5-204775 |  | 1 | 100% | 1 |  |  |  | 1 |  | 9 | 100% |  |  | 1
169 | Y | 38.533 | 4.7.4.2.1 | EN-DC FR1 CSI-RS-based L1-RSRP absolute measurement accuracy | Test in A.4.7.4.2 in TS 38.133 | Rohde&Schwarz | Opt 3: RAN5#88 (Aug-20) | R5-190480 R5-191488 R5-204879 |  | 1 | 100% | 1 |  |  |  | 1 |  | 9 | 100% |  |  | 1
314 | Y | 38.533 | 4.7.4.2.2 | EN-DC FR1 CSI-RS-based L1-RSRP relative measurement accuracy | Test in A.4.7.4.2 in TS 38.133 | Rohde&Schwarz | Opt 3: RAN5#88 (Aug-20) | R5-204776 |  | 1 | 100% | 1 |  |  |  | 1 |  | 9 | 100% |  |  | 1
|  | 38.533 | 4.7.5 | SFTD | New sub-clause |  |  |  |  | 0 |  | 1 |  |  |  | 1 |  | 1 |  |  |  | 1
234 | Y | 38.533 | 4.7.5.1 | EN-DC FR1 SFTD measurement accuracy | Test in A.4.7.5.1 in TS 38.133 | Rohde&Schwarz | Opt 3: RAN5#89 (Nov-20) | R5-206906 |  | 1 | 100% | 1 |  |  |  | 1 |  | 10 | 100%
EN-DC with PSCell in FR2
|  | 38.533 | 5 | EN-DC with PSCell in FR2 | New clause |  |  |  | Tests in this area are only for NSA Option 3 | 0 | [5 empty] | 1 |  | 1 |  |  |  | 1 |  | 1
|  | 38.533 | 5.1 | Void | New sub-clause |  |  |  | Empty clause so that numbering will match for SA and NSA | 0 |  | 1 |  |  |  | 1 | [5 empty] | 1 |  | 1
|  | 38.533 | 5.2 | Void | New sub-clause |  |  |  | Empty clause so that numbering will match for SA and NSA | 0 |  | 1 |  |  |  | 1 |  | 1 | [5 empty] | 1
|  | 38.533 | 5.3 | RRC_CONNECTED state mobility | New sub-clause |  |  |  |  | 0 |  | 1 |  |  |  | 1 |  | 1 |  |  |  | 1
|  | 38.533 | 5.3.1 | Void | New sub-clause |  |  |  | Empty clause so that numbering will match for SA and NSA | 0 |  | 1 |  |  |  | 1 |  | 1 |  |  |  | 1
|  | 38.533 | 5.3.2 | RRC connection mobility control | New sub-clause |  |  |  |  | 0 |  | 1 |  |  |  | 1 |  | 1 |  |  |  | 1
|  | 38.533 | 5.3.2.1 | Void | New sub-clause |  |  |  | Empty clause so that numbering will match for SA and NSA | 0 |  | 1 |  |  |  | 1 |  | 1 |  |  |  | 1
|  | 38.533 | 5.3.2.2 | Random access | New sub-clause |  |  |  |  | 0 |  | 1 |  |  |  | 1 |  | 1 |  |  |  | 1
90 | Y | 38533 | 5.3.2.2.1 | EN-DC FR2 contention based random access | Test in A.5.3.2.2.1 in TS 38.133 | Anritsu | Opt 3: RAN5#93 (Nov-21) | R5-212731 R5-214413 | RAN4 Phase 1 | 1 | 90% | 1 |  |  |  | 1 |  | 14 |  | 90%
91 | Y | 38533 | 5.3.2.2.2 | EN-DC FR2 non-contention based random access | Test in A.5.3.2.2.2 in TS 38.133 | Anritsu | Opt 3: RAN5#93 (Nov-21) | R5-212732 R5-214413 | RAN4 Phase 1 | 1 | 90% | 1 |  |  |  | 1 |  | 14 |  | 90%
|  | 38.533 | 5.3.2.3 | Void | New sub-clause |  |  |  | Empty clause so that numbering will match for SA and NSA | 0 |  | 1 |  |  |  | 1 |  | 1 |  |  |  | 1
|  | 38.533 | 5.4 | Timing | New sub-clause |  |  |  |  | 0 |  | 1 |  |  |  | 1 |  | 1 |  |  |  | 1
|  | 38.533 | 5.4.1 | UE transmit timing | New sub-clause |  |  |  |  | 0 |  | 1 |  |  |  | 1 |  | 1 |  |  |  | 1
31 | Y | 38533 | 5.4.1.1 | EN-DC FR2 UE transmit timing accuracy | Test in A.5.4.1.1 in TS 38.133 | Qualcomm | Opt 3: RAN5#90 (Feb-21) | R5-195034 R5-199535 R5-206221 R5-210816 | RAN4 Phase 1 | 1 | 100% | 1 |  |  |  | 1 |  | 11 |  | 100%
|  | 38.533 | 5.4.2 | UE timer accuracy | New sub-clause |  |  |  |  | 0 |  | 1 |  |  |  | 1 |  | 1 |  |  |  | 1
|  | 38.533 | 5.4.3 | Timing advance | New sub-clause |  |  |  |  | 0 |  | 1 |  |  |  | 1 |  | 1 |  |  |  | 1
92 | Y | 38533 | 5.4.3.1 | EN-DC FR2 timing advance adjustment accuracy | Test in A.5.4.3.1 in TS 38.133 | Qualcomm | Opt 3: RAN5#90 (Feb-21) | R5-195029 R5-196925 R5-204068 R5-206222 R5-211622 | RAN4 Phase 1 | 1 | 100% | 1 |  |  |  | 1 |  | 11 |  | 100%
|  | 38.533 | 5.5 | Signalling characteristics | New sub-clause |  |  |  |  | 0 |  | 1 |  |  |  | 1 |  | 1 |  |  |  | 1
|  | 38.533 | 5.5.1 | Radio Link Monitoring | New sub-clause |  |  |  |  | 0 |  | 1 |  |  |  | 1 |  | 1 |  |  |  | 1
36 | Y | 38.533 | 5.5.1.1 | EN-DC FR2 radio link monitoring out-of-sync test for PSCell configured with SSB-based RLM RS in non-DRX mode | Test in A.5.5.1.1 in TS 38.133 | Qualcomm | Opt 3: RAN5#93 (Nov-21) | R5-195030 R5-197397 | RAN4 Phase 1 | 1 | 30% | 1 |  |  |  | 1 |  | 14 |  | 30%
37 | Y | 38.533 | 5.5.1.2 | EN-DC FR2 radio link monitoring in-sync test for PSCell configured with SSB-based RLM RS in non-DRX mode | Test in A.5.5.1.2 in TS 38.133 | Qualcomm | Opt 3: RAN5#93 (Nov-21) | R5-195032 R5-199533 | RAN4 Phase 1 | 1 | 50% | 1 |  |  |  | 1 |  | 14 |  | 50%
38 | Y | 38.533 | 5.5.1.3 | EN-DC FR2 radio link monitoring out-of-sync test for PSCell configured with SSB-based RLM RS in DRX mode | Test in A.5.5.1.3 in TS 38.133 | Qualcomm | Opt 3: RAN5#93 (Nov-21) | R5-195031 R5-197398 | RAN4 Phase 1 | 1 | 30% | 1 |  |  |  | 1 |  | 14 |  | 30%
39 | Y | 38.533 | 5.5.1.4 | EN-DC FR2 radio link monitoring in-sync test for PSCell configured with SSB-based RLM RS in DRX mode | Test in A.5.5.1.4 in TS 38.133 | Qualcomm | Opt 3: RAN5#93 (Nov-21) | R5-195033 R5-199534 | RAN4 Phase 1 | 1 | 50% | 1 |  |  |  | 1 |  | 14 |  | 50%
205 | Y | 38.533 | 5.5.1.5 | EN-DC FR2 radio link monitoring out-of-sync test for PSCell configured with CSI-RS-based RLM RS in non-DRX mode | Test in A.5.5.1.5 in TS 38.133 | Huawei, Hisilicon | Opt 3: RAN5#93 (Nov-21) | R5-197411 R5-206686 |  | 1 | 30% | 1 |  |  |  | 1 |  | 14 |  | 30%
206 | Y | 38.533 | 5.5.1.6 | EN-DC FR2 radio link monitoring in-sync test for PSCell configured with CSI-RS-based RLM RS in non-DRX mode | Test in A.5.5.1.6 in TS 38.133 | Huawei, Hisilicon | Opt 3: RAN5#93 (Nov-21) | R5-197412 R5-206686 |  | 1 | 30% | 1 |  |  |  | 1 |  | 14 |  | 30%
207 | Y | 38.533 | 5.5.1.7 | EN-DC FR2 radio link monitoring out-of-sync test for PSCell configured with CSI-RS-based RLM RS in DRX mode | Test in A.5.5.1.7 in TS 38.133 | Huawei, Hisilicon | Opt 3: RAN5#93 (Nov-21) | R5-197413 R5-206686 |  | 1 | 30% | 1 |  |  |  | 1 |  | 14 |  | 30%
208 | Y | 38.533 | 5.5.1.8 | EN-DC FR2 radio link monitoring in-sync test for PSCell configured with CSI-RS-based RLM RS in DRX mode | Test in A.5.5.1.8 in TS 38.133 | Huawei, Hisilicon | Opt 3: RAN5#93 (Nov-21) | R5-197414 R5-206686 |  | 1 | 30% | 1 |  |  |  | 1 |  | 14 |  | 30%
280 | Y | 38.533 | 5.5.1.9 | EN-DC FR2 radio link monitoring UE scheduling restrictions | Test in A.5.5.1.9 in TS 38.133 | Huawei, Hisilicon | Opt 3: RAN5#93 (Nov-21) | R5-205960 R5-206686 |  | 1 | 30% | 1 |  |  |  | 1 |  | 14 |  | 30%
|  | 38.533 | 5.5.2 | Interruption | New sub-clause |  |  |  |  | 0 |  | 1 |  |  |  | 1 |  | 1 |  |  |  | 1
54 | Y | 38.533 | 5.5.2.1 | EN-DC FR2 interruptions at transitions between active and non-active during DRX in synchronous EN-DC | Test in A.5.5.2.1 in TS 38.133 | Huawei | Opt 3: RAN5#92 (Aug-21) | R5-190908 R5-195623 R5-204069 R5-216098 | RAN4 Phase 1 | 1 | 100% | 1 |  |  |  | 1 |  | 13 |  | 100%
55 | Y | 38.533 | 5.5.2.2 | EN-DC FR2 interruptions at transitions between active and non-active during DRX in asynchronous EN-DC | Test in A.5.5.2.2 in TS 38.133 | Huawei | Opt 3: RAN5#92 (Aug-21) | R5-190909 R5-195624 R5-204069 R5-216098 | RAN4 Phase 1 | 1 | 100% | 1 |  |  |  | 1 |  | 13 |  | 100%
60 | Y | 38.533 | 5.5.2.3 | EN-DC FR2 interruptions during measurements on deactivated NR SCC in synchronous EN-DC | Test in A.5.5.2.3 in TS 38.133 | Huawei | Opt 3: RAN5#93 (Nov-21) | R5-190910 R5-195625 | RAN4 Phase 1 | 1 | 50% | 1 |  |  |  | 1 |  | 14 |  | 50%
61 | Y | 38.533 | 5.5.2.4 | EN-DC FR2 interruptions during measurements on deactivated NR SCC in asynchronous EN-DC | Test in A.5.5.2.4 in TS 38.133 | Huawei | Opt 3: RAN5#93 (Nov-21) | R5-190911 R5-195626 | RAN4 Phase 1 | 1 | 50% | 1 |  |  |  | 1 |  | 14 |  | 50%
62 | Y | 38.533 | 5.5.2.5 | EN-DC FR2 interruptions during measurements on deactivated E-UTRAN SCC in synchronous EN-DC | Test in A.5.5.2.5 in TS 38.133 | Huawei | Opt 3: RAN5#93 (Nov-21) | R5-190912 R5-195627 | RAN4 Phase 1 | 1 | 50% | 1 |  |  |  | 1 |  | 14 |  | 50%
63 | Y | 38.533 | 5.5.2.6 | EN-DC FR2 interruptions during measurements on deactivated E-UTRAN SCC in asynchronous EN-DC | Test in A.5.5.2.6 in TS 38.133 | Huawei | Opt 3: RAN5#93 (Nov-21) | R5-190913 R5-195628 | RAN4 Phase 1 | 1 | 50% | 1 |  |  |  | 1 |  | 14 |  | 50%
|  | 38.533 | 5.5.3 | Scell activation and deactivation delay | New sub-clause |  |  |  |  | 0 |  | 1 |  |  |  | 1 |  | 1 |  |  |  | 1
51 | Y | 38533 | 5.5.3.1 | EN-DC FR2 SCell activation and deactivation intra-band in non-DRX | Test in A.5.5.3.1 in TS 38.133 | Bureau Veritas | Opt 3: RAN5#93 (Nov-21) | R5-190891 R5-205961 R5-210176 | RAN4 Phase 1 | 1 | 30% | 1 |  |  |  | 1 |  | 14 |  | 30%
256 | Y | 38533 | 5.5.3.2 | EN-DC FR2-FR1 SCell activation and deactivation of known SCell in non-DRX for 160ms SCell measurement cycle | Test in A.5.5.3.2 in TS 38.133 | Qualcomm | Opt 3: RAN5#93 (Nov-21) |  |  | 1 | 0% | 1 |  |  |  | 1 |  | 14 |  | 0%
|  | 38533 | 5.5.3.3 | Void | Test has been removed from RAN4 |  |  |  |  | 1 |  | 1 |  |  |  | 1
|  | 38533 | 5.5.3.4 | Void | Test has been removed from RAN4 |  |  |  |  | 1 |  | 1 |  |  |  | 1
255 | Y | 38533 | 5.5.3.5 | EN-DC FR1-FR2 SCell activation and deactivation in non-DRX | Test in A.5.5.3.5 in TS 38.133 | Qualcomm | Opt 3: RAN5#93 (Nov-21) |  |  | 1 | 0% | 1 |  |  |  | 1 |  | 14 |  | 0%
|  | 38.533 | 5.5.4 | UE UL carrier RRC reconfiguration delay | New sub-clause |  |  |  |  | 0 |  | 1 |  |  |  | 1 |  | 1 |  |  |  | 1
|  | 38.533 | 5.5.5 | Beam failure detection and link recovery procedures | New sub-clause |  |  |  |  | 0 |  | 1 |  |  |  | 1 |  | 1 |  |  |  | 1
209 | Y | 38.533 | 5.5.5.1 | EN-DC FR2 SSB-based beam failure detection and link recovery in non-DRX | Test in A.5.5.5.1 in TS 38.133 | Huawei, Hisilicon | Opt 3: RAN5#93 (Nov-21) | R5-199392 R5-206687 R5-210180 | RAN4 Phase 1 | 1 | 30% | 1 |  |  |  | 1 |  | 14 |  | 30%
210 | Y | 38.533 | 5.5.5.2 | EN-DC FR2 SSB-based beam failure detection and link recovery in DRX | Test in A.5.5.5.2 in TS 38.133 | Huawei, Hisilicon | Opt 3: RAN5#93 (Nov-21) | R5-199393 R5-206687 R5-210180 | RAN4 Phase 1 | 1 | 30% | 1 |  |  |  | 1 |  | 14 |  | 30%
211 | Y | 38.533 | 5.5.5.3 | EN-DC FR2 CSI-RS-based beam failure detection and link recovery in non-DRX | Test in A.5.5.5.3 in TS 38.133 | Huawei, Hisilicon | Opt 3: RAN5#93 (Nov-21) | R5-197415 R5-206687 R5-210180 | RAN4 Phase 1 | 1 | 30% | 1 |  |  |  | 1 |  | 14 |  | 30%
212 | Y | 38.533 | 5.5.5.4 | EN-DC FR2 CSI-RS-based beam failure detection and link recovery in DRX | Test in A.5.5.5.4 in TS 38.133 | Huawei, Hisilicon | Opt 3: RAN5#93 (Nov-21) | R5-197416 R5-206687 R5-210180 | RAN4 Phase 1 | 1 | 30% | 1 |  |  |  | 1 |  | 14 |  | 30%
308 | Y | 38.533 | 5.5.5.5 | EN-DC FR2 scheduling available restriction during SSB-based beam failure detection and link recovery in non-DRX | Test in A.5.5.5.5 in TS 38.133 | Huawei, Hisilicon | Opt 3: RAN5#93 (Nov-21) | R5-202746 R5-206687 R5-210180 |  | 1 | 30% | 1 |  |  |  | 1 |  | 14 |  | 30%
|  | 38.533 | 5.5.6 | Active BWP switch delay | New sub-clause |  |  |  |  | 0 |  | 1 |  |  |  | 1 |  | 1 |  |  |  | 1
|  | 38.533 | 5.5.6.1 | DCI-based and timer-based active BWP switch | New sub-clause
170 | Y | 38.533 | 5.5.6.1.1 | EN-DC FR2 DCI-based DL active BWP switch in non-DRX in synchronous EN-DC | Test in A.5.5.6.1.1 in TS 38.133 | Rohde&Schwarz | Opt 3: RAN5#93 (Nov-21) | R5-191494 | RAN4 Phase 1 | 1 | 10% | 1 |  |  |  | 1 |  | 14 |  | 10%
65 | Y | 38.533 | 5.5.6.1.2 | EN-DC PSCell FR2 DL active BWP switch with FR2 SCell in non-DRX in synchronous EN-DC | Test in A.5.5.6.1.2 in TS 38.133 | Rohde&Schwarz | Opt 3: RAN5#93 (Nov-21) | R5-191494 | RAN4 Phase 1 | 1 | 10% | 1 |  |  |  | 1 |  | 14 |  | 10%
|  | 38.533 | 5.5.6.2 | RRC-based active BWP switch | New sub-clause
213 | Y | 38.533 | 5.5.6.2.1 | EN-DC FR2 RRC-based DL active BWP switch in non-DRX in synchronous EN-DC | Test in A.5.5.6.2.1 in TS 38.133 | Qualcomm | Opt 3: RAN5#93 (Nov-21) | R5-197399 | RAN4 Phase 1 | 1 | 20% | 1 |  |  |  | 1 |  | 14 |  | 20%
|  | 38.533 | 5.5.7 | PSCell addition and release delay | New sub-clause
259 | Y | 38.533 | 5.5.7.1 | EN-DC FR2 addition and release delay of known PSCell | Test in A.5.5.7.1 in TS 38.133 | Rohde&Schwarz | Opt 3: RAN5#93 (Nov-21) |  |  | 1 | 0% | 1 |  |  |  | 1 |  | 14 |  | 0% |  | 1
|  | 38.533 | 5.5.8 | Active TCI state switch delay | New sub-clause
309 | Y | 38.533 | 5.5.8.1 | EN-DC FR2 MAC-CE based active TCI state switch for a known TCI state | Test in A.5.5.8.1 in TS 38.133 | Huawei, Hisilicon | Opt 3: RAN5#93 (Nov-21) | R5-201408 |  | 1 | 30% | 1 |  |  |  | 1 |  | 14 |  | 30% |  | 1
310 | Y | 38.533 | 5.5.8.2 | EN-DC FR2 RRC based active TCI state switch for a known TCI state | Test in A.5.5.8.2 in TS 38.133 | Huawei, Hisilicon | Opt 3: RAN5#93 (Nov-21) | R5-201409 |  | 1 | 30% | 1 |  |  |  | 1 |  | 14 |  | 30% |  | 1
|  | 38.533 | 5.6 | Measurement procedures | New sub-clause |  |  |  |  | 0 |  | 1 |  |  |  | 1 |  | 1 |  |  |  | 1
|  | 38.533 | 5.6.1 | Intra-frequency measurements | New sub-clause |  |  |  |  | 0 |  | 1 |  |  |  | 1 |  | 1 |  |  |  | 1
7 | Y | 38533 | 5.6.1.1 | EN-DC FR2 event-triggered reporting without gap in non-DRX | Test in A.5.6.1.1.1 in TS 38.133 | Huawei | Opt 3: RAN5#93 (Nov-21) | R5-197407 R5-201679 | RAN4 Phase 1 | 1 | 40% | 1 |  |  |  | 1 |  | 14 |  | 40%
8 | Y | 38533 | 5.6.1.2 | EN-DC FR2 event-triggered reporting without gap in DRX | Test in A.5.6.1.1.2 in TS 38.133 | Huawei | Opt 3: RAN5#91 (May-21) | R5-197408 R5-201680 R5-214113 | RAN4 Phase 1 | 1 | 100% | 1 |  |  |  | 1 |  | 12 |  | 100%
9 | Y | 38533 | 5.6.1.3 | EN-DC FR2 event-triggered reporting with gap in non-DRX | Test in A.5.6.1.1.3 in TS 38.133 | Huawei | Opt 3: RAN5#93 (Nov-21) | R5-197409 R5-201681 | RAN4 Phase 1 | 1 | 40% | 1 |  |  |  | 1 |  | 14 |  | 40%
10 | Y | 38533 | 5.6.1.4 | EN-DC FR2 event-triggered reporting with gap in DRX | Test in A.5.6.1.1.4 in TS 38.133 | Huawei | Opt 3: RAN5#91 (May-21) | R5-197410 R5-201682 R5-214113 | RAN4 Phase 1 | 1 | 100% | 1 |  |  |  | 1 |  | 12 |  | 100%
|  | 38.533 | 5.6.2 | Inter-frequency measurements | New sub-clause |  |  |  |  | 0 |  | 1 |  |  |  | 1 |  | 1 |  |  |  | 1
93 | Y | 38533 | 5.6.2.1 | EN-DC FR2-FR2 event-triggered reporting in non-DRX | Test in A.5.6.2.1 in TS 38.133 | Ericsson | Opt 3: RAN5#91 (May-21) | R5-187998 R5-191937 R5-194549 R5-196666 R5-198582 R5-205813 R5-211623 R5-214108 | RAN4 Phase 1 | 1 | 100% | 1 |  |  |  | 1 |  | 12 |  | 100%
94 | Y | 38533 | 5.6.2.2 | EN-DC FR2-FR2 event-triggered reporting in DRX | Test in A.5.6.2.2 in TS 38.133 | Ericsson | Opt 3: RAN5#92 (Aug-21) | R5-187998 R5-191938 R5-194550 R5-196667 R5-198583 R5-205814 R5-215425 | RAN4 Phase 1 | 1 | 100% | 1 |  |  |  | 1 |  | 13 |  | 100%
95 | Y | 38533 | 5.6.2.3 | EN-DC FR2-FR2 event-triggered reporting in non-DRX with SSB time index detection | Test in A.5.6.2.3 in TS 38.133 | Ericsson | Opt 3: RAN5#91 (May-21) | R5-187998 R5-191939 R5-194551 R5-196668 R5-198584 R5-205815 R5-211624 R5-214109 | RAN4 Phase 1 | 1 | 100% | 1 |  |  |  | 1 |  | 12 |  | 100%
96 | Y | 38533 | 5.6.2.4 | EN-DC FR2-FR2 event-triggered reporting in DRX with SSB time index detection | Test in A.5.6.2.4 in TS 38.133 | Ericsson | Opt 3: RAN5#92 (Aug-21) | R5-187998 R5-191940 R5-194552 R5-196669 R5-198585 R5-205816 R5-215426 | RAN4 Phase 1 | 1 | 100% | 1 |  |  |  | 1 |  | 13 |  | 100%
83 | Y | 38533 | 5.6.2.5 | EN-DC FR1-FR2 event-triggered reporting in non-DRX | Test in A.5.6.2.5 in TS 38.133 | Ericsson | Opt 3: RAN5#91 (May-21) | R5-187997 R5-191930 R5-194553 R5-196670 R5-198586 R5-205817 R5-213927 | RAN4 Phase 1 | 1 | 100% | 1 |  |  |  | 1 |  | 12 |  |  | 100%
84 | Y | 38533 | 5.6.2.6 | EN-DC FR1-FR2 event-triggered reporting in DRX | Test in A.5.6.2.6 in TS 38.133 | Ericsson | Opt 3: RAN5#91 (May-21) | R5-187997 R5-191931 R5-194554 R5-196671 R5-198587 R5-205818 R5-213928 | RAN4 Phase 1 | 1 | 100% | 1 |  |  |  | 1 |  | 12 |  |  | 100%
87 | Y | 38533 | 5.6.2.7 | EN-DC FR1-FR2 event-triggered reporting in non-DRX with SSB time index detection | Test in A.5.6.2.7 in TS 38.133 | Ericsson | Opt 3: RAN5#91 (May-21) | R5-187997 R5-191934 R5-194555 R5-196672 R5-198588 R5-205819 R5-213929 | RAN4 Phase 1 | 1 | 100% | 1 |  |  |  | 1 |  | 12 |  |  | 100%
88 | Y | 38533 | 5.6.2.8 | EN-DC FR1-FR2 event-triggered reporting in DRX with SSB time index detection | Test in A.5.6.2.8 in TS 38.133 | Ericsson | Opt 3: RAN5#91 (May-21) | R5-187997 R5-191935 R5-194556 R5-196673 R5-198589 R5-205820 R5-213930 | RAN4 Phase 1 | 1 | 100% | 1 |  |  |  | 1 |  | 12 |  |  | 100%
|  | 38.533 | 5.6.3 | L1-RSRP for beam reporting | New sub-clause |  |  |  |  | 0 |  | 1 |  |  |  | 1 |  | 1 |  |  |  | 1
281 | Y | 38533 | 5.6.3.1 | EN-DC FR2 SSB-based L1-RSRP measurement in non-DRX | Test in A.5.6.3.1 in TS 38.133 | Ericsson | Opt 3: RAN5#92 (Aug-21) | R5-196680 R5-204116 R5-215417 |  | 1 | 100% | 1 |  |  |  | 1 |  | 13 |  | 100%
282 | Y | 38533 | 5.6.3.2 | EN-DC FR2 SSB-based L1-RSRP measurement in DRX | Test in A.5.6.3.2 in TS 38.133 | Ericsson | Opt 3: RAN5#92 (Aug-21) | R5-196681 R5-204942 R5-215418 |  | 1 | 100% | 1 |  |  |  | 1 |  | 13 |  | 100%
283 | Y | 38533 | 5.6.3.3 | EN-DC FR2 CSI-RS-based L1-RSRP measurement in non-DRX | Test in A.5.6.3.3 in TS 38.133 | Ericsson | Opt 3: RAN5#93 (Nov-21) | R5-196682 R5-204118 R5-215419 |  | 1 | 50% | 1 |  |  |  | 1 |  | 14 |  | 50%
284 | Y | 38533 | 5.6.3.4 | EN-DC FR2 CSI-RS-based L1-RSRP measurement in DRX | Test in A.5.6.3.4 in TS 38.133 | Ericsson | Opt 3: RAN5#93 (Nov-21) | R5-196943 R5-204119 R5-215420 |  | 1 | 50% | 1 |  |  |  | 1 |  | 14 |  | 50%
|  | 38.533 | 5.7 | Measurement performance requirements | New sub-clause |  |  |  |  | 0 |  | 1 |  |  |  | 1 |  | 1 |  |  |  | 1
|  | 38.533 | 5.7.1 | SS-RSRP | New sub-clause |  |  |  |  | 0 |  | 1 |  |  |  | 1 |  | 1 |  |  |  | 1
25 | Y | 38.533 | 5.7.1.1 | EN-DC FR2 SS-RSRP measurement accuracy | Test in A.5.7.1.1 in TS 38.133 | Rohde&Schwarz | Opt 3: RAN5#91 (May-21) | R5-202064 R5-212024 | RAN4 Phase 1 | 1 | 100% | 1 |  |  |  | 1 |  | 12 |  | 100% |  | 1
27 | Y | 38.533 | 5.7.1.2 | EN-DC FR2-FR2 SS-RSRP measurement accuracy | Test in A.5.7.1.2 in TS 38.133 | Rohde&Schwarz | Opt 3: RAN5#92 (Aug-21) | R5-202065 R5-216048 | RAN4 Phase 1 | 1 | 100% | 1 |  |  |  | 1 |  | 13 |  | 100% |  | 1
203 | Y | 38.533 | 5.7.1.3 | EN-DC FR1-FR2 SS-RSRP measurement accuracy | Test in A.5.7.1.3 in TS 38.133 | Rohde&Schwarz | Opt 3: RAN5#93 (Nov-21) | R5-202066 |  | 1 | 30% | 1 |  |  |  | 1 |  | 14 |  |  | 30% | 1
|  | 38.533 | 5.7.2 | SS-RSRQ | New sub-clause |  |  |  |  | 0 |  | 1 |  |  |  | 1 |  | 1 |  |  |  | 1
70 | Y | 38.533 | 5.7.2.1 | EN-DC FR2 SS-RSRQ measurement accuracy | Test in A.5.7.2.1 in TS 38.133 | Rohde&Schwarz | Opt 3: RAN5#91 (May-21) | R5-202068 R5-212025 | RAN4 Phase 2 | 1 | 100% | 1 |  |  |  | 1 |  | 12 |  | 100%
97 | Y | 38.533 | 5.7.2.2 | EN-DC FR2-FR2 SS-RSRQ measurement accuracy | Test in A.5.7.2.2 in TS 38.133 | Rohde&Schwarz | Opt 3: RAN5#92 (Aug-21) | R5-202069 R5-216049 | RAN4 Phase 2 | 1 | 100% | 1 |  |  |  | 1 |  | 13 |  | 100%
|  | 38.533 | 5.7.3 | SS-SINR | New sub-clause |  |  |  |  | 0 |  | 1 |  |  |  | 1 |  | 1 |  |  |  | 1
236 | Y | 38.533 | 5.7.3.1 | EN-DC FR2 SS-SINR measurement accuracy | Test in A.5.7.3.1 in TS 38.133 | Rohde&Schwarz | Opt 3: RAN5#91 (May-21) | R5-202071 R5-212026 |  | 1 | 100% | 1 |  |  |  | 1 |  | 12 |  | 100%
237 | Y | 38.533 | 5.7.3.2 | EN-DC FR2-FR2 SS-SINR measurement accuracy | Test in A.5.7.3.2 in TS 38.133 | Rohde&Schwarz | Opt 3: RAN5#92 (Aug-21) | R5-202072 R5-216050 |  | 1 | 100% | 1 |  |  |  | 1 |  | 13 |  | 100%
|  | 38.533 | 5.7.4 | L1-RSRP for beam reporting | New sub-clause |  |  |  |  | 0 |  | 1 |  |  |  | 1 |  | 1 |  |  |  | 1
171 | Y | 38.533 | 5.7.4.1 | EN-DC FR2 SSB-based L1-RSRP measurement accuracy | Test in A.5.7.4.1 in TS 38.133 | Rohde&Schwarz | Opt 3: RAN5#93 (Nov-21) |  |  | 1 | 0% | 1 |  |  |  | 1 |  | 14 |  | 0% |  | 1
172 | Y | 38.533 | 5.7.4.2 | EN-DC FR2 CSI-RS-based L1-RSRP measurement accuracy | Test in A.5.7.4.2 in TS 38.133 | Rohde&Schwarz | Opt 3: RAN5#93 (Nov-21) |  |  | 1 | 0% | 1 |  |  |  | 1 |  | 14 |  | 0% |  | 1
NR standalone in FR1
|  | 38.533 | 6 | NR standalone in FR1 | New clause |  |  |  | Tests in this area are only for SA Option 2 | 0 | [5 empty] | 1 |  | 1 |  |  |  | 1 |  | 1
|  | 38.533 | 6.1 | RRC_IDLE state mobility | New sub-clause |  |  |  |  | 0 |  | 1 |  |  |  | 1 | [5 empty] | 1 |  | 1
|  | 38.533 | 6.1.1 | NR cell re-selection | New sub-clause
186 | Y | 38533 | 6.1.1.1 | NR SA FR1 cell re-selection | Test in A.6.1.1.1 in TS 38.133 | Huawei | Opt 2: RAN5#83 (May-19) | R5-190914 R5-193784 | RAN4 Phase 1 | 1 | 100% | 3 | 100%
187 | Y | 38533 | 6.1.1.2 | NR SA FR1-FR1 cell re-selection | Test in A.6.1.1.2 in TS 38.133 | Huawei | Opt 2: RAN5#84 (Aug-19) | R5-190915 R5-193785 R5-195568 | RAN4 Phase 1 | 1 | 100% | 4 | 100%
|  | 38.533 | 6.1.2 | NR – E-UTRA cell re-selection | New sub-clause
188 | Y | 38533 | 6.1.2.1 | NR SA FR1 – E-UTRA cell re-selection to higher priority E-UTRA | Test in A.6.1.2.1 in TS 38.133 | Huawei | Opt 2: RAN5#84 (Aug-19) | R5-190916 R5-193786 R5-195569 | RAN4 Phase 1 | 1 | 100% | 4 | 100%
189 | Y | 38533 | 6.1.2.2 | NR SA FR1 – E-UTRA cell re-selection to lower priority E-UTRA | Test in A.6.1.2.2 in TS 38.133 | Huawei | Opt 2: RAN5#84 (Aug-19) | R5-190917 R5-193787 R5-197366 | RAN4 Phase 1 | 1 | 100% | 4 | 100%
|  | 38.533 | 6.2 | RRC_INACTIVE state mobility | New sub-clause |  |  |  |  | 0 |  | 1 |  |  |  | 1 |  | 1 | [5 empty] | 1
|  | 38.533 | 6.3 | RRC_CONNECTED state mobility | New sub-clause |  |  |  |  | 0 |  | 1 |  |  |  | 1 |  | 1 |  |  |  | 1
|  | 38.533 | 6.3.1 | Handover | New sub-clause |  |  |  |  | 0 |  | 1 |  |  |  | 1 |  | 1 |  |  |  | 1
71 | Y | 38.533 | 6.3.1.1 | NR SA FR1 handover with known target cell | Test in A.6.3.1.1 in TS 38.133 | Qualcomm | Opt 2: RAN5#85 (Nov-19) | R5-199550 | RAN4 Phase 2 | 1 | 100% | 5 | 100%
72 | Y | 38.533 | 6.3.1.2 | NR SA FR1 handover with unknown target cell | Test in A.6.3.1.2 in TS 38.133 | Qualcomm | Opt 2: RAN5#85 (Nov-19) | R5-197400 R5-199551 | RAN4 Phase 2 | 1 | 100% | 5 | 100%
185 | Y | 38.533 | 6.3.1.3 | NR SA FR1-FR1 handover with unknown target cell | Test in A.6.3.1.3 in TS 38.133 | Qualcomm | Opt 2: RAN5#85 (Nov-19) | R5-197401 R5-199552 | RAN4 Phase 2 | 1 | 100% | 5 | 100%
190 | Y | 38.533 | 6.3.1.4 | NR SA FR1 – E-UTRA handover with known target cell | Test in A.6.3.1.4 in TS 38.133 | Huawei | Opt 2: RAN5#84 (Aug-19) | R5-190918 R5-193788 R5-195571 | RAN4 Phase 2 | 1 | 100% | 4 | 100%
191 | Y | 38.533 | 6.3.1.5 | NR SA FR1 – E-UTRA handover with unknown target cell | Test in A.6.3.1.5 in TS 38.133 | Huawei | Opt 2: RAN5#84 (Aug-19) | R5-190919 R5-195180 R5-197611 | RAN4 Phase 2 | 1 | 100% | 4 | 100%
|  | 38.533 | 6.3.2 | RRC connection mobility control | New sub-clause |  |  |  |  | 0 |  | 1 |  |  |  | 1 |  | 1 |  |  |  | 1
|  | 38.533 | 6.3.2.1 | RRC re-establishment | New sub-clause |  |  |  |  | 0 |  | 1 |  |  |  | 1 |  | 1 |  |  |  | 1
238 | Y | 38533 | 6.3.2.1.1 | NR SA FR1 RRC re-establishment | Test in A.6.3.2.1.1 in TS 38.133 | Huawei, Hisilicon | Opt 2: RAN5#86 (Feb-20) | R5-193762 R5-195573 R5-200987 |  | 1 | 100% | 6 | 100%
239 | Y | 38533 | 6.3.2.1.2 | NR SA FR1 - FR1 RRC re-establishment | Test in A.6.3.2.1.2 in TS 38.133 | Huawei, Hisilicon | Opt 2: RAN5#86 (Feb-20) | R5-193763 R5-195574 R5-200988 |  | 1 | 100% | 6 | 100%
261 | Y | 38533 | 6.3.2.1.3 | NR SA FR1 RRC re-establishment without serving cell timing | Test in A.6.3.2.1.3 in TS 38.133 | Huawei, Hisilicon | Opt 2: RAN5#88 (Aug-20) | R5-202833 R5-203837 |  | 1 | 100% | 8 | 100%
|  | 38.533 | 6.3.2.2 | Random access | New sub-clause |  |  |  |  | 0 |  | 1 |  |  |  | 1 |  | 1 |  |  |  | 1
98 | Y | 38533 | 6.3.2.2.1 | NR SA FR1 contention based random access | Test in A.6.3.2.2.1 in TS 38.133 | Anritsu | Opt 2: RAN5#83 (May-19) | R5-192479 R5-195018 | RAN4 Phase 1 | 1 | 100% | 3 | 100%
99 | Y | 38533 | 6.3.2.2.2 | NR SA FR1 non-contention based random access | Test in A.6.3.2.2.2 in TS 38.133 | Anritsu | Opt 2: RAN5#83 (May-19) | R5-192480 R5-195019 | RAN4 Phase 1 | 1 | 100% | 3 | 100%
|  | 38.533 | 6.3.2.3 | RRC connection release with redirection | New sub-clause |  |  |  |  | 0 |  | 1 |  |  |  | 1 |  | 1 |  |  |  | 1
240 | Y | 38533 | 6.3.2.3.1 | NR SA FR1 RRC connection release with redirection | Test in A.6.3.2.3.1 in TS 38.133 | Huawei, Hisilicon | Opt 2: RAN5#86 (Feb-20) | R5-193764 R5-195575 R5-200708 |  | 1 | 100% | 6 | 100%
241 | Y | 38533 | 6.3.2.3.2 | NR SA FR1 – E-UTRA RRC connection release with redirection | Test in A.6.3.2.3.2 in TS 38.133 | Huawei, Hisilicon | Opt 2: RAN5#86 (Feb-20) | R5-193765 R5-195576 R5-200709 |  | 1 | 100% | 6 | 100%
|  | 38.533 | 6.4 | Timing | New sub-clause |  |  |  |  | 0 |  | 1 |  |  |  | 1 |  | 1 |  |  |  | 1
|  | 38.533 | 6.4.1 | UE transmit timing | New sub-clause |  |  |  |  | 0 |  | 1 |  |  |  | 1 |  | 1 |  |  |  | 1
192 | Y | 38533 | 6.4.1.1 | NR SA FR1 transmit timing accuracy | Test in A.6.4.1.1 in TS 38.133 | Qualcomm | Opt 2: RAN5#84 (Aug-19) | R5-197364 |  | 1 | 100% | 4 | 100%
|  | 38.533 | 6.4.2 | UE timer accuracy | New sub-clause |  |  |  |  | 0 |  | 1 |  |  |  | 1 |  | 1 |  |  |  | 1
|  | 38.533 | 6.4.3 | Timing advance | New sub-clause |  |  |  |  | 0 |  | 1 |  |  |  | 1 |  | 1 |  |  |  | 1
100 | Y | 38533 | 6.4.3.1 | NR SA FR1 timing advance adjustment accuracy | Test in A.6.4.3 in TS 38.133 | Qualcomm | Opt 2: RAN5#84 (Aug-19) | R5-190894 R5-195026 R5-197361 | RAN4 Phase 1 | 1 | 100% | 4 | 100%
|  | 38.533 | 6.5 | Signalling characteristics | New sub-clause |  |  |  |  | 0 |  | 1 |  |  |  | 1 |  | 1 |  |  |  | 1
|  | 38.533 | 6.5.1 | Radio Link Monitoring | New sub-clause |  |  |  |  | 0 |  | 1 |  |  |  | 1 |  | 1 |  |  |  | 1
40 | Y | 38.533 | 6.5.1.1 | NR SA FR1 radio link monitoring out-of-sync test for PCell configured with SSB-based RLM RS in non-DRX mode | Test in A.6.5.1.1 in TS 38.133 | Qualcomm | Opt 2: RAN5#84 (Aug-19) | R5-190896 R5-195027 R5-197612 | RAN4 Phase 1 | 1 | 100% | 4 | 100%
41 | Y | 38.533 | 6.5.1.2 | NR SA FR1 radio link monitoring in-sync test for PCell configured with SSB-based RLM RS in non-DRX mode | Test in A.6.5.1.2 in TS 38.133 | Qualcomm | Opt 2: RAN5#84 (Aug-19) | R5-190902 R5-192676 R5-194703 R5-195041 R5-197620 | RAN4 Phase 1 | 1 | 100% | 4 | 100%
42 | Y | 38.533 | 6.5.1.3 | NR SA FR1 radio link monitoring out-of-sync test for PCell configured with SSB-based RLM RS in DRX mode | Test in A.6.5.1.3 in TS 38.133 | Qualcomm | Opt 2: RAN5#84 (Aug-19) | R5-190893 R5-195028 R5-197612 | RAN4 Phase 1 | 1 | 100% | 4 | 100%
43 | Y | 38.533 | 6.5.1.4 | NR SA FR1 radio link monitoring in-sync test for PCell configured with SSB-based RLM RS in DRX mode | Test in A.6.5.1.4 in TS 38.133 | Qualcomm | Opt 2: RAN5#84 (Aug-19) | R5-190903 R5-192677 R5-194704 R5-195042 R5-197621 | RAN4 Phase 1 | 1 | 100% | 4 | 100%
214 | Y | 38.533 | 6.5.1.5 | NR SA FR1 radio link monitoring out-of-sync test for PCell configured with CSI-RS-based RLM RS in non-DRX mode | Test in A.6.5.1.5 in TS 38.133 | Huawei | Opt 2: RAN5#85 (Nov-19) | R5-190921 R5-193766 R5-195180 R5-195577 R5-199366 | RAN4 Phase 1 | 1 | 100% | 5 | 100%
215 | Y | 38.533 | 6.5.1.6 | NR SA FR1 radio link monitoring in-sync test for PCell configured with CSI-RS-based RLM RS in non-DRX mode | Test in A.6.5.1.6 in TS 38.133 | Huawei | Opt 2: RAN5#85 (Nov-19) | R5-190922 R5-193767 R5-195578 R5-199370 | RAN4 Phase 1 | 1 | 100% | 5 | 100%
216 | Y | 38.533 | 6.5.1.7 | NR SA FR1 radio link monitoring out-of-sync test for PCell configured with CSI-RS-based RLM RS in DRX mode | Test in A.6.5.1.7 in TS 38.133 | Huawei | Opt 2: RAN5#85 (Nov-19) | R5-190923 R5-193768 R5-195579 R5-199367 | RAN4 Phase 1 | 1 | 100% | 5 | 100%
217 | Y | 38.533 | 6.5.1.8 | NR SA FR1 radio link monitoring in-sync test for PCell configured with CSI-RS-based RLM RS in DRX mode | Test in A.6.5.1.8 in TS 38.133 | Huawei | Opt 2: RAN5#85 (Nov-19) | R5-190924 R5-193769 R5-195580 R5-199371 | RAN4 Phase 1 | 1 | 100% | 5 | 100%
|  | 38.533 | 6.5.2 | Interruption | New sub-clause |  |  |  |  | 0 |  | 1 |  |  |  | 1 |  | 1 |  |  |  | 1
242 | Y | 38533 | 6.5.2.1 | NR SA FR1 interruptions during measurements on deactivated NR SCC | Test in A.6.5.2.1 in TS 38.133 | CAICT | Opt 2: RAN5#88 (Aug-20) | R5-195038 R5-203839 |  | 1 | 100% | 8 | 100%
|  | 38.533 | 6.5.3 | Scell activation and deactivation delay | New sub-clause |  |  |  |  | 0 |  | 1 |  |  |  | 1 |  | 1 |  |  |  | 1
243 | Y | 38533 | 6.5.3.1 | NR SA FR1 SCell activation and deactivation of known SCell in non-DRX for 160ms SCell measurement cycle | Test in A.6.5.3.1 in TS 38.133 | CAICT | Opt 2: RAN5#88 (Aug-20) | R5-203840 |  | 1 | 100% | 8 | 100%
244 | Y | 38533 | 6.5.3.2 | NR SA FR1 SCell activation and deactivation of known SCell in non-DRX for 320ms SCell measurement cycle | Test in A.6.5.3.2 in TS 38.133 | CAICT | Opt 2: RAN5#88 (Aug-20) | R5-203841 |  | 1 | 100% | 8 | 100%
245 | Y | 38533 | 6.5.3.3 | NR SA FR1 SCell activation and deactivation of unknown SCell in non-DRX | Test in A.6.5.3.3 in TS 38.133 | CAICT | Opt 2: RAN5#88 (Aug-20) | R5-203842 |  | 1 | 100% | 8 | 100%
|  | 38.533 | 6.5.4 | UE UL carrier RRC reconfiguration delay | New sub-clause |  |  |  |  | 0 |  | 1 |  |  |  | 1 |  | 1 |  |  |  | 1
193 | Y | 38.533 | 6.5.4.1 | NR SA FR1 UE UL carrier RRC reconfiguration delay | Test in A.6.5.4 in TS 38.133 | Huawei | Opt 2: RAN5#87 (May-20) | R5-190920 R5-203092 | RAN4 Phase 1 | 1 | 100% | 7 | 100%
|  | 38.533 | 6.5.5 | Beam failure detecion and link recovery procedures | New sub-clause |  |  |  |  | 0 |  | 1 |  |  |  | 1 |  | 1 |  |  |  | 1
218 | Y | 38.533 | 6.5.5.1 | NR SA FR1 SSB-based beam failure detection and link recovery in non-DRX | Test in A.6.5.5.1 in TS 38.133 | Huawei,Hisilicon | Opt 2: RAN5#88 (Aug-20) | R5-203095 R5-203843 | RAN4 Phase 1 | 1 | 100% | 8 | 100%
219 | Y | 38.533 | 6.5.5.2 | NR SA FR1 SSB-based beam failure detection and link recovery in DRX | Test in A.6.5.5.2 in TS 38.133 | Huawei,Hisilicon | Opt 2: RAN5#88 (Aug-20) | R5-203096 R5-203844 | RAN4 Phase 1 | 1 | 100% | 8 | 100%
220 | Y | 38.533 | 6.5.5.3 | NR SA FR1 CSI-RS-based beam failure detection and link recovery in non-DRX | Test in A.6.5.5.3 in TS 38.133 | Huawei,Hisilicon | Opt 2: RAN5#88 (Aug-20) | R5-192484 R5-193771 R5-195581 R5-203097 R5-203845 | RAN4 Phase 1 | 1 | 100% | 8 | 100%
221 | Y | 38.533 | 6.5.5.4 | NR SA FR1 CSI-RS-based beam failure detection and link recovery in DRX | Test in A.6.5.5.4 in TS 38.133 | Huawei,Hisilicon | Opt 2: RAN5#88 (Aug-20) | R5-192485 R5-193772 R5-195582 R5-203098 R5-203846 | RAN4 Phase 1 | 1 | 100% | 8 | 100%
|  | 38.533 | 6.5.6 | Active BWP switch delay | New sub-clause |  |  |  |  | 0 |  | 1 |  |  |  | 1 |  | 1 |  |  |  | 1
|  | 38.533 | 6.5.6.1 | DCI-based and timer-based active BWP switch | New sub-clause |  |  |  |  | 0 |  | 1
146 | Y | 38.533 | 6.5.6.1.1 | NR SA FR1-FR1 DCI-based DL active BWP switch in non-DRX | Test in A.6.5.6.1.1 in TS 38.133 | Huawei, Hisilicon | Opt 2: RAN5#88 (Aug-20) | R5-191493 R5-203848 |  | 1 | 100% | 8 | 100%
260 | Y | 38.533 | 6.5.6.1.2 | NR SA FR1 DCI-based DL active BWP switch in non-DRX | Test in A.6.5.6.1.2 in TS 38.133 | Huawei, Hisilicon | Opt 2: RAN5#88 (Aug-20) | R5-203849 |  | 1 | 100% | 8 | 100%
|  | 38.533 | 6.5.6.2 | RRC-based active BWP switch | New sub-clause |  |  |  |  | 0 |  | 1
194 | Y | 38.533 | 6.5.6.2.1 | NR SA FR1 RRC-based DL active BWP switch in non-DRX | Test in A.6.5.6.2.1 in TS 38.133 | Huawei, Hisilicon | Opt 2: RAN5#88 (Aug-20) | R5-191493 R5-203851 |  | 1 | 100% | 8 | 100%
|  | 38.533 | 6.6 | Measurement procedures | New sub-clause |  |  |  |  | 0 |  | 1 |  |  |  | 1 |  | 1 |  |  |  | 1
|  | 38.533 | 6.6.1 | Intra-frequency measurements | New sub-clause |  |  |  |  | 0 |  | 1 |  |  |  | 1 |  | 1 |  |  |  | 1
11 | Y | 38533 | 6.6.1.1 | NR SA FR1 event-triggered reporting without gap in non-DRX | Test in A.6.6.1.1.1 in TS 38.133 | Huawei | Opt 2: RAN5#83 (May-19) | R5-190874 R5-193790 | RAN4 Phase 1 | 1 | 100% | 3 | 100%
12 | Y | 38533 | 6.6.1.2 | NR SA FR1 event-triggered reporting without gap in DRX | Test in A.6.6.1.1.2 in TS 38.133 | Huawei | Opt 2: RAN5#83 (May-19) | R5-190875 R5-193791 | RAN4 Phase 1 | 1 | 100% | 3 | 100%
13 | Y | 38533 | 6.6.1.3 | NR SA FR1 event-triggered reporting with gap in non-DRX | Test in A.6.6.1.1.3 in TS 38.133 | Huawei | Opt 2: RAN5#83 (May-19) | R5-190876 R5-193792 | RAN4 Phase 1 | 1 | 100% | 3 | 100%
14 | Y | 38533 | 6.6.1.4 | NR SA FR1 event-triggered reporting with gap in DRX | Test in A.6.6.1.1.4 in TS 38.133 | Huawei | Opt 2: RAN5#83 (May-19) | R5-190877 R5-193793 | RAN4 Phase 1 | 1 | 100% | 3 | 100%
15 | Y | 38533 | 6.6.1.5 | NR SA FR1 event-triggered reporting without gap in non-DRX with SSB index reading | Test in A.6.6.1.1.5 in TS 38.133 | Huawei | Opt 2: RAN5#83 (May-19) | R5-190878 R5-193794 | RAN4 Phase 1 | 1 | 100% | 3 | 100%
16 | Y | 38533 | 6.6.1.6 | NR SA FR1 event-triggered reporting with gap in non-DRX with SSB index reading | Test in A.6.6.1.1.6 in TS 38.133 | Huawei | Opt 2: RAN5#83 (May-19) | R5-190879 R5-193795 | RAN4 Phase 1 | 1 | 100% | 3 | 100%
|  | 38.533 | 6.6.2 | Inter-frequency measurements | New sub-clause |  |  |  |  | 0 |  | 1 |  |  |  | 1 |  | 1 |  |  |  | 1
101 | Y | 38533 | 6.6.2.1 | NR SA FR1-FR1 event-triggered reporting in non-DRX | Test in A.6.6.2.1 in TS 38.133 | Ericsson | Opt 2: RAN5#83 (May-19) | R5-187999 R5-192496 R5-195186 | RAN4 Phase 1 | 1 | 100% | 3 | 100%
102 | Y | 38533 | 6.6.2.2 | NR SA FR1-FR1 event-triggered reporting in DRX | Test in A.6.6.2.2 in TS 38.133 | Ericsson | Opt 2: RAN5#83 (May-19) | R5-187999 R5-192497 R5-195187 | RAN4 Phase 1 | 1 | 100% | 3 | 100%
105 | Y | 38533 | 6.6.2.5 | NR SA FR1-FR1 event-triggered reporting in non-DRX with SSB time index detection | Test in A.6.6.2.3 in TS 38.133 | Ericsson | Opt 2: RAN5#83 (May-19) | R5-187999 R5-192498 R5-195188 |  | 1 | 100% | 3 | 100%
106 | Y | 38533 | 6.6.2.6 | NR SA FR1-FR1 event-triggered reporting in DRX with SSB time index detection | Test in A.6.6.2.4 in TS 38.133 | Ericsson | Opt 2: RAN5#83 (May-19) | R5-187999 R5-192499 R5-195189 |  | 1 | 100% | 3 | 100%
|  | 38.533 | 6.6.3 | Inter-RAT measurements | New sub-clause |  |  |  |  | 0 |  | 1 |  |  |  | 1 |  | 1 |  |  |  | 1
21 | Y | 38.533 | 6.6.3.1 | NR SA FR1 – E-UTRAN event-triggered reporting in non-DRX | Test in A.6.6.3.1 in TS 38.133 | Bureau Veritas | Opt 2: RAN5#85 (Nov-19) | R5-190892 R5-195184 R5-197804 | RAN4 Phase 1 | 1 | 100% | 5 | 100%
246 | Y | 38.533 | 6.6.3.2 | NR SA FR1 – E-UTRAN event-triggered reporting in DRX | Test in A.6.6.3.2 in TS 38.133 | Huawei, Hisilicon | Opt 2: RAN5#85 (Nov-19) | R5-195182 R5-197805 |  | 1 | 100% | 5 | 100%
|  | 38.533 | 6.6.4 | L1-RSRP for beam reporting | New sub-clause |  |  |  |  | 0 |  | 1 |  |  |  | 1 |  | 1 |  |  |  | 1
285 | Y | 38533 | 6.6.4.1 | NR SA FR1 SSB-based L1-RSRP measurement in non-DRX | Test in A.6.6.4.1 in TS 38.133 | Ericsson | Opt 2: RAN5#86 (Feb-20) | R5-198692 R5-201049 |  | 1 | 100% | 6 | 100% |  |  | 1 |  | 6
286 | Y | 38533 | 6.6.4.2 | NR SA FR1 SSB-based L1-RSRP measurement in DRX | Test in A.6.6.4.2 in TS 38.133 | Ericsson | Opt 2: RAN5#86 (Feb-20) | R5-198693 R5-201050 |  | 1 | 100% | 6 | 100% |  |  | 1
287 | Y | 38533 | 6.6.4.3 | NR SA FR1 CSI-RS-based L1-RSRP measurement in non-DRX | Test in A.6.6.4.3 in TS 38.133 | Ericsson | Opt 2: RAN5#86 (Feb-20) | R5-198694 R5-201051 |  | 1 | 100% | 6 | 100% |  |  | 1
288 | Y | 38533 | 6.6.4.4 | NR SA FR1 CSI-RS-based L1-RSRP measurement in DRX | Test in A.6.6.4.4 in TS 38.133 | Ericsson | Opt 2: RAN5#86 (Feb-20) | R5-198695 R5-201052 |  | 1 | 100% | 6 | 100% |  |  | 1
|  | 38.533 | 6.7 | Measurement performance requirements | New sub-clause |  |  |  |  | 0 |  | 1 |  |  |  | 1 |  | 1 |  |  |  | 1
|  | 38.533 | 6.7.1 | SS-RSRP | New sub-clause |  |  |  |  | 0 |  | 1 |  |  |  | 1 |  | 1 |  |  |  | 1
|  | 38.533 | 6.7.1.1 | Intra-frequency measurements
22 | Y | 38.533 | 6.7.1.1.1 | NR SA FR1 SS-RSRP absolute measurement accuracy | Test in A.6.7.1.1 in TS 38.133 | Rohde&Schwarz | Opt 2: RAN5#84 (Aug-19) | R5-187996 R5-190481 R5-191489 R5-197569 | RAN4 Phase 1 | 1 | 100% | 4 | 100% |  |  | 1 | [5 empty] | 1
158 | Y | 38.533 | 6.7.1.1.2 | NR SA FR1 SS-RSRP relative measurement accuracy | Test in A.6.7.1.1 in TS 38.133 | Rohde&Schwarz | Opt 2: RAN5#84 (Aug-19) | R5-187996 R5-190481 R5-191489 R5-197569 | RAN4 Phase 1 | 1 | 100% | 4 | 100% |  |  | 1 | [5 empty] | 1
|  | 38.533 | 6.7.1.2 | Inter-frequency measurements
28 | Y | 38.533 | 6.7.1.2.1 | NR SA FR1-FR1 SS-RSRP absolute measurement accuracy | Test in A.6.7.1.2 in TS 38.133 | Rohde&Schwarz | Opt 2: RAN5#86 (Feb-20) | R5-187996 R5-190481 R5-191489 R5-200279 | RAN4 Phase 1 | 1 | 100% | 6 | 100% |  |  | 1 | [5 empty] | 1
159 | Y | 38.533 | 6.7.1.2.2 | NR SA FR1-FR1 SS-RSRP relative measurement accuracy | Test in A.6.7.1.2 in TS 38.133 | Rohde&Schwarz | Opt 2: RAN5#86 (Feb-20) | R5-187996 R5-190481 R5-191489 R5-200279 | RAN4 Phase 1 | 1 | 100% | 6 | 100% |  |  | 1 | [5 empty] | 1
|  | 38.533 | 6.7.2 | SS-RSRQ | New sub-clause |  |  |  |  | 0 |  | 1 |  |  |  | 1 |  | 1 |  |  |  | 1
68 | Y | 38.533 | 6.7.2.1 | NR SA FR1 SS-RSRQ measurement accuracy | Test in A.6.7.2.1 in TS 38.133 | Rohde&Schwarz | Opt 2: RAN5#86 (Feb-20) | R5-190482 R5-191490 R5-201041 | RAN4 Phase 2 | 1 | 100% | 6 | 100% |  |  | 1
109 | Y | 38.533 | 6.7.2.2.1 | NR SA FR1-FR1 SS-RSRQ absolute measurement accuracy | Test in A.6.7.2.2 in TS 38.133 | Rohde&Schwarz | Opt 2: RAN5#86 (Feb-20) | R5-190482 R5-191490 R5-200281 | RAN4 Phase 2 | 1 | 100% | 6 | 100%
315 | Y | 38.533 | 6.7.2.2.2 | NR SA FR1-FR1 SS-RSRQ relative measurement accuracy | Test in A.6.7.2.2 in TS 38.133 | Rohde&Schwarz | Opt 2: RAN5#86 (Feb-20) | R5-200281 | RAN4 Phase 2 | 1 | 100% | 6 | 100%
|  | 38.533 | 6.7.3 | SS-SINR | New sub-clause |  |  |  |  | 0 |  | 1 |  |  |  | 1 |  | 1 |  |  |  | 1
247 | Y | 38.533 | 6.7.3.1 | NR SA FR1 SS-SINR measurement accuracy | Test in A.6.7.3.1 in TS 38.133 | Rohde&Schwarz | Opt 2: RAN5#86 (Feb-20) | R5-196742 R5-200282 |  | 1 | 100% | 6 | 100% |  |  | 1
248 | Y | 38.533 | 6.7.3.2.1 | NR SA FR1-FR1 SS-SINR absolute measurement accuracy | Test in A.6.7.3.2 in TS 38.133 | Rohde&Schwarz | Opt 2: RAN5#86 (Feb-20) | R5-196743 R5-200283 |  | 1 | 100% | 6 | 100%
316 | Y | 38.533 | 6.7.3.2.2 | NR SA FR1-FR1 SS-SINR relative measurement accuracy | Test in A.6.7.3.2 in TS 38.133 | Rohde&Schwarz | Opt 2: RAN5#86 (Feb-20) | R5-200283 |  | 1 | 100% | 6 | 100%
|  | 38.533 | 6.7.4 | L1-RSRP for beam reporting | New sub-clause |  |  |  |  | 0 |  | 1 |  |  |  | 1 |  | 1 |  |  |  | 1
195 | Y | 38.533 | 6.7.4.1.1 | NR SA FR1 SSB-based L1-RSRP absolute measurement accuracy | Test in A.6.7.4.1 in TS 38.133 | Rohde&Schwarz | Opt 2: RAN5#88 (Aug-20) | R5-190483 R5-191491 R5-204880 |  | 1 | 100% | 8 | 100%
317 | Y | 38.533 | 6.7.4.1.2 | NR SA FR1 SSB-based L1-RSRP relative measurement accuracy | Test in A.6.7.4.1 in TS 38.133 | Rohde&Schwarz | Opt 2: RAN5#88 (Aug-20) | R5-204778 |  | 1 | 100% | 8 | 100%
196 | Y | 38.533 | 6.7.4.2.1 | NR SA FR1 CSI-RS-based L1-RSRP absolute measurement accuracy | Test in A.6.7.4.2 in TS 38.133 | Rohde&Schwarz | Opt 2: RAN5#88 (Aug-20) | R5-190483 R5-191491 R5-204881 |  | 1 | 100% | 8 | 100%
318 | Y | 38.533 | 6.7.4.2.2 | NR SA FR1 CSI-RS-based L1-RSRP relative measurement accuracy | Test in A.6.7.4.2 in TS 38.133 | Rohde&Schwarz | Opt 2: RAN5#88 (Aug-20) | R5-204779 |  | 1 | 100% | 8 | 100%
|  | 38.533 | 6.7.5 | E-UTRAN RSRP
262 | Y | 38.533 | 6.7.5.1 | NR SA FR1 – E-UTRAN RSRP absolute measurement accuracy | Test in A.6.7.5.1 in TS 38.133 | Rohde&Schwarz | Opt 2: RAN5#89 (Nov-20) | R5-206798 |  | 1 | 100% | 9 | 100% |  |  | 1 | [5 empty] | 1
|  | 38.533 | 6.7.6 | E-UTRAN RSRQ
264 | Y | 38.533 | 6.7.6.1 | NR SA FR1 – E-UTRAN RSRQ absolute measurement accuracy | Test in A.6.7.6.1 in TS 38.133 | Rohde&Schwarz | Opt 2: RAN5#89 (Nov-20) | R5-206843 |  | 1 | 100% | 9 | 100% |  |  | 1 | [5 empty] | 1
|  | 38.533 | 6.7.7 | E-UTRAN RS-SINR
266 | Y | 38.533 | 6.7.7.1 | NR SA FR1 – E-UTRAN RS-SINR absolute measurement accuracy | Test in A.6.7.7.1 in TS 38.133 | Rohde&Schwarz | Opt 2: RAN5#89 (Nov-20) | R5-206907 |  | 1 | 100% | 9 | 100% |  |  | 1 | [5 empty] | 1
NR standalone in FR2
|  | 38.533 | 7 | NR standalone in FR2 | New clause |  |  |  | Tests in this area are only for SA Option 2 | 0 | [5 empty] | 1 |  | 1 |  |  |  | 1 |  | 1
|  | 38.533 | 7.1 | RRC_IDLE state mobility | New sub-clause |  |  |  |  | 0 |  | 1 |  |  |  | 1 | [5 empty] | 1 |  | 1
|  | 38.533 | 7.1.1 | NR cell re-selection | New sub-clause
173 | Y | 38533 | 7.1.1.1 | NR SA FR2 cell re-selection | Test in A.7.1.1.1 in TS 38.133 | Huawei, Hisilicon | Opt 2: RAN5#93 (Nov-21) | R5-195605 R5-202751 R5-204735 | RAN4 Phase 1 | 1 | 60% | 13 |  | 60%
174 | Y | 38533 | 7.1.1.2 | NR SA FR2-FR2 cell re-selection | Test in A.7.1.1.2 in TS 38.133 | Huawei, Hisilicon | Opt 2: RAN5#93 (Nov-21) | R5-195606 R5-202752 R5-204736 | RAN4 Phase 1 | 1 | 60% | 13 |  | 60%
|  | 38.533 | 7.2 | RRC_INACTIVE state mobility | New sub-clause |  |  |  |  | 0 |  | 1 |  |  |  | 1 |  | 1 | [5 empty] | 1
|  | 38.533 | 7.3 | RRC_CONNECTED state mobility | New sub-clause |  |  |  |  | 0 |  | 1 |  |  |  | 1 |  | 1 |  |  |  | 1
|  | 38.533 | 7.3.1 | Handover | New sub-clause |  |  |  |  | 0 |  | 1 |  |  |  | 1 |  | 1 |  |  |  | 1
73 | Y | 38.533 | 7.3.1.1 | NR SA FR1-FR2 handover with unknown target cell | Test in A.7.3.1.1 in TS 38.133 | Qualcomm | Opt 2: RAN5#93 (Nov-21) |  | RAN4 Phase 2 | 1 | 0% | 13 |  |  | 0%
74 | Y | 38.533 | 7.3.1.2 | NR SA FR2 handover with unknown target cell | Test in A.7.3.1.2 in TS 38.133 | Qualcomm | Opt 2: RAN5#93 (Nov-21) |  | RAN4 Phase 2 | 1 | 0% | 13 |  | 0%
75 | Y | 38.533 | 7.3.1.3 | NR SA FR2-FR2 handover with unknown target cell | Test in A.7.3.1.3 in TS 38.133 | Qualcomm | Opt 2: RAN5#93 (Nov-21) |  | RAN4 Phase 2 | 1 | 0% | 13 |  | 0%
|  | 38.533 | 7.3.2 | RRC connection mobility control | New sub-clause |  |  |  |  | 0 |  | 1 |  |  |  | 1 |  | 1 |  |  |  | 1
|  | 38.533 | 7.3.2.1 | RRC re-establishment | New sub-clause |  |  |  |  | 0 |  | 1 |  |  |  | 1 |  | 1 |  |  |  | 1
249 | Y | 38533 | 7.3.2.1.1 | NR SA FR2 RRC re-establishment | Test in A.7.3.2.1.1 in TS 38.133 | Ericsson | Opt 2: RAN5#93 (Nov-21) | R5-196660 |  | 1 | 30% | 13 |  | 30%
250 | Y | 38533 | 7.3.2.1.2 | NR SA FR2 - FR2 RRC re-establishment | Test in A.7.3.2.1.2 in TS 38.133 | Ericsson | Opt 2: RAN5#93 (Nov-21) | R5-196661 |  | 1 | 30% | 13 |  | 30%
267 | Y | 38533 | 7.3.2.1.3 | NR SA FR2 RRC re-establishment without serving cell timing | Test in A.7.3.2.1.3 in TS 38.133 | Huawei, Hisilicon | Opt 2: RAN5#93 (Nov-21) | R5-202835 R5-205963 |  | 1 | 30% | 13 |  | 30%
|  | 38.533 | 7.3.2.2 | Random access | New sub-clause |  |  |  |  | 0 |  | 1 |  |  |  | 1 |  | 1 |  |  |  | 1
110 | Y | 38533 | 7.3.2.2.1 | NR SA FR2 contention based random access | Test in A.7.3.2.2.1 in TS 38.133 | Anritsu | Opt 2: RAN5#93 (Nov-21) | R5-206799 | RAN4 Phase 1 | 1 | 60% | 13 |  | 60%
111 | Y | 38533 | 7.3.2.2.2 | NR SA FR2 non-contention based random access | Test in A.7.3.2.2.2 in TS 38.133 | Anritsu | Opt 2: RAN5#93 (Nov-21) | R5-206799 | RAN4 Phase 1 | 1 | 60% | 13 |  | 60%
|  | 38.533 | 7.3.2.3 | RRC connection release with redirection | New sub-clause |  |  |  |  | 0 |  | 1 |  |  |  | 1 |  | 1 |  |  |  | 1
251 | Y | 38533 | 7.3.2.3.1 | NR SA FR2 RRC connection release with redirection | Test in A.7.3.2.3.1 in TS 38.133 | Qualcomm | Opt 2: RAN5#93 (Nov-21) |  |  | 1 | 0% | 13 |  | 0%
|  | 38.533 | 7.4 | Timing | New sub-clause |  |  |  |  | 0 |  | 1 |  |  |  | 1 |  | 1 |  |  |  | 1
|  | 38.533 | 7.4.1 | UE transmit timing | New sub-clause |  |  |  |  | 0 |  | 1 |  |  |  | 1 |  | 1 |  |  |  | 1
175 | Y | 38533 | 7.4.1.1 | NR SA FR2 transmit timing accuracy | Test in A.7.4.1.1 in TS 38.133 | Qualcomm | Opt 2: RAN5#93 (Nov-21) |  |  | 1 | 0% | 13 |  | 0%
|  | 38.533 | 7.4.2 | UE timer accuracy | New sub-clause |  |  |  |  | 0 |  | 1 |  |  |  | 1 |  | 1 |  |  |  | 1
|  | 38.533 | 7.4.3 | Timing advance | New sub-clause |  |  |  |  | 0 |  | 1 |  |  |  | 1 |  | 1 |  |  |  | 1
112 | Y | 38533 | 7.4.3.1 | NR SA FR2 timing advanced adjustment accuracy | Test in A.7.4.3.1 in TS 38.133 | Qualcomm | Opt 2: RAN5#93 (Nov-21) |  | RAN4 Phase 1 | 1 | 0% | 13 |  | 0%
|  | 38.533 | 7.5 | Signalling characteristics | New sub-clause |  |  |  |  | 0 |  | 1 |  |  |  | 1 |  | 1 |  |  |  | 1
|  | 38.533 | 7.5.1 | Radio Link Monitoring | New sub-clause |  |  |  |  | 0 |  | 1 |  |  |  | 1 |  | 1 |  |  |  | 1
44 | Y | 38.533 | 7.5.1.1 | NR SA FR2 radio link monitoring out-of-sync test for PCell configured with SSB-based RLM RS in non-DRX mode | Test in A.7.5.1.1 in TS 38.133 | Qualcomm | Opt 2: RAN5#93 (Nov-21) |  | RAN4 Phase 1 | 1 | 0% | 13 |  | 0%
45 | Y | 38.533 | 7.5.1.2 | NR SA FR2 radio link monitoring in-sync test for PCell configured with SSB-based RLM RS in non-DRX mode | Test in A.7.5.1.2 in TS 38.133 | Qualcomm | Opt 2: RAN5#93 (Nov-21) |  | RAN4 Phase 1 | 1 | 0% | 13 |  | 0%
46 | Y | 38.533 | 7.5.1.3 | NR SA FR2 radio link monitoring out-of-sync test for PCell configured with SSB-based RLM RS in DRX mode | Test in A.7.5.1.3 in TS 38.133 | Qualcomm | Opt 2: RAN5#93 (Nov-21) |  | RAN4 Phase 1 | 1 | 0% | 13 |  | 0%
47 | Y | 38.533 | 7.5.1.4 | NR SA FR2 radio link monitoring in-sync test for PCell configured with SSB-based RLM RS in DRX mode | Test in A.7.5.1.4 in TS 38.133 | Qualcomm | Opt 2: RAN5#93 (Nov-21) |  | RAN4 Phase 1 | 1 | 0% | 13 |  | 0%
224 | Y | 38.533 | 7.5.1.5 | NR SA FR2 radio link monitoring out-of-sync test for PCell configured with CSI-RS-based RLM RS in non-DRX mode | Test in A.7.5.1.5 in TS 38.133 | Qualcomm | Opt 2: RAN5#93 (Nov-21) |  | RAN4 Phase 1 | 1 | 0% | 13 |  | 0%
225 | Y | 38.533 | 7.5.1.6 | NR SA FR2 radio link monitoring in-sync test for PCell configured with CSI-RS-based RLM RS in non-DRX mode | Test in A.7.5.1.6 in TS 38.133 | Qualcomm | Opt 2: RAN5#93 (Nov-21) |  | RAN4 Phase 1 | 1 | 0% | 13 |  | 0%
226 | Y | 38.533 | 7.5.1.7 | NR SA FR2 radio link monitoring out-of-sync test for PCell configured with CSI-RS-based RLM RS in DRX mode | Test in A.7.5.1.7 in TS 38.133 | Qualcomm | Opt 2: RAN5#93 (Nov-21) |  | RAN4 Phase 1 | 1 | 0% | 13 |  | 0%
227 | Y | 38.533 | 7.5.1.8 | NR SA FR2 radio link monitoring in-sync test for PCell configured with CSI-RS-based RLM RS in DRX mode | Test in A.7.5.1.8 in TS 38.133 | Qualcomm | Opt 2: RAN5#93 (Nov-21) |  | RAN4 Phase 1 | 1 | 0% | 13 |  | 0%
289 | Y | 38.533 | 7.5.1.9 | NR SA FR2 radio link monitoring UE scheduling restrictions | Test in A.7.5.1.9 in TS 38.133 | Huawei, Hisilicon | Opt 2: RAN5#93 (Nov-21) | R5-202836 |  | 1 | 30% | 13 |  | 30% |  | 1
|  | 38.533 | 7.5.2 | Interruption | New sub-clause |  |  |  |  | 0 |  | 1 |  |  |  | 1 |  | 1 |  |  |  | 1
252 | Y | 38533 | 7.5.2.1 | NR SA FR2 interruptions during measurements on deactivated NR SCC | Test in A.7.5.2.1 in TS 38.133 | Qualcomm | Opt 2: RAN5#93 (Nov-21) |  |  | 1 | 0% | 13 |  | 0%
|  | 38.533 | 7.5.3 | Scell activation and deactivation delay | New sub-clause |  |  |  |  | 0 |  | 1 |  |  |  | 1 |  | 1 |  |  |  | 1
176 | Y | 38.533 | 7.5.3.1 | NR SA FR2-FR2 intra-band SCell activation and deactivation delay | Test in A.7.5.3.1 in TS 38.133 | Samsung | Opt 2: RAN5#93 (Nov-21) | R5-202753 R5-204034 R5-210177 |  | 1 | 30% | 13 |  | 30%
177 | Y | 38.533 | 7.5.3.2 | NR SA FR1-FR2 inter-band SCell activation and deactivation delay | Test in A.7.5.3.2 in TS 38.133 | Samsung | Opt 2: RAN5#93 (Nov-21) | R5-202753 R5-204034 R5-210177 |  | 1 | 30% | 13 |  | 30%
|  | 38.533 | 7.5.4 | Void | New sub-clause |  |  |  |  | 0 |  | 1 |  |  |  | 1 |  | 1 |  |  |  | 1
|  | 38.533 | 7.5.5 | Beam failure detecion and link recovery procedures | New sub-clause |  |  |  |  | 0 |  | 1 |  |  |  | 1 |  | 1 |  |  |  | 1
228 | Y | 38.533 | 7.5.5.1 | NR SA FR2 SSB-based beam failure detection and link recovery in non-DRX | Test in A.7.5.5.1 in TS 38.133 | Huawei,Hisilicon | Opt 2: RAN5#93 (Nov-21) | R5-192487 R5-193774 R5-195629 R5-210182 |  | 1 | 60% | 13 |  | 60%
229 | Y | 38.533 | 7.5.5.2 | NR SA FR2 SSB-based beam failure detection and link recovery in DRX | Test in A.7.5.5.2 in TS 38.133 | Huawei,Hisilicon | Opt 2: RAN5#93 (Nov-21) | R5-192488 R5-193775 R5-195630 R5-210182 |  | 1 | 60% | 13 |  | 60%
230 | Y | 38.533 | 7.5.5.3 | NR SA FR2 CSI-RS-based beam failure detection and link recovery in non-DRX | Test in A.7.5.5.3 in TS 38.133 | Huawei,Hisilicon | Opt 2: RAN5#93 (Nov-21) | R5-192489 R5-193776 R5-195631 R5-210182 |  | 1 | 60% | 13 |  | 60%
231 | Y | 38.533 | 7.5.5.4 | NR SA FR2 CSI-RS-based beam failure detection and link recovery in DRX | Test in A.7.5.5.4 in TS 38.133 | Huawei,Hisilicon | Opt 2: RAN5#93 (Nov-21) | R5-192490 R5-193777 R5-195632 R5-210182 |  | 1 | 60% | 13 |  | 60%
325 | Y | 38.533 | 7.5.5.5 | NR SA FR2 scheduling availability restriction during SSB-based beam failure detection and link recovery in non-DRX | Test in A.7.5.5.5 in TS 38.133 | ZTE | Opt 2: RAN5#93 (Nov-21) | R5-204884 R5-210182 |  | 1 | 30% | 13 |  | 30%
|  | 38.533 | 7.5.6 | Active BWP switch delay | New sub-clause |  |  |  |  | 0 |  | 1 |  |  |  | 1 |  | 1 |  |  |  | 1
|  | 38.533 | 7.5.6.1 | DCI-based and timer-based active BWP switch | New sub-clause |  |  |  |  | 0 |  | 1
147 | Y | 38.533 | 7.5.6.1.1 | NR SA FR2 2DL CA DCI-based DL active BWP switch in non-DRX | Test in A.7.5.6.1.1 in TS 38.133 | Rohde&Schwarz | Opt 2: RAN5#93 (Nov-21) | R5-191495 |  | 1 | 10% | 13 |  | 10%
198 | Y | 38.533 | 7.5.6.1.2 | NR SA FR1-FR2 DCI-based DL active BWP switch in non-DRX | Test in A.7.5.6.1.1 in TS 38.133 | Rohde&Schwarz | Opt 2: RAN5#93 (Nov-21) | R5-191495 |  | 1 | 10% | 13 |  |  | 10%
268 | Y | 38.533 | 7.5.6.1.3 | NR SA FR2 DCI-based DL active BWP switch in non-DRX | Test in A.7.5.6.1.3 in TS 38.133 | Huawei, Hisilicon | Opt 2: RAN5#93 (Nov-21) | R5-201415 |  | 1 | 30% | 13 |  | 30%
|  | 38.533 | 7.5.6.2 | RRC-based active BWP switch | New sub-clause |  |  |  |  | 0 |  | 1
197 | Y | 38.533 | 7.5.6.2.1 | NR SA FR2 RRC-based DL active BWP switch in non-DRX | Test in A.7.5.6.2.1 in TS 38.133 | Rohde&Schwarz | Opt 2: RAN5#93 (Nov-21) | R5-191495 |  | 1 | 10% | 13 |  | 10%
|  | 38.533 | 7.5.7 | PSCell addition and release delay | New sub-clause
321 | Y | 38.533 | 7.5.7.1 | NR SA FR2 addition and release delay of known PSCell | Test in A.7.5.7.1 in TS 38.133 | Samsung | Opt 2: RAN5#93 (Nov-21) | R5-202754 R5-204036 |  | 1 | 30% | 13 |  | 30% |  | 1 |  | 8 |  |  |  | 1
322 | Y | 38.533 | 7.5.7.2 | NR SA FR2 addition and release delay of unknown PSCell | Test in A.7.5.7.2 in TS 38.133 | Samsung | Opt 2: RAN5#93 (Nov-21) | R5-202754 R5-204036 |  | 1 | 30% | 13 |  | 30% |  | 1 |  | 8 |  |  |  | 1
|  | 38.533 | 7.5.8 | Active TCI state switch delay | New sub-clause
|  | 38.533 | 7.5.8.1 | MAC-CE based active TCI state switch
323 | Y | 38.533 | 7.5.8.1.1 | NR SA FR2 MAC-CE based active TCI state switch for a known TCI state | Test in A.7.5.8.1 in TS 38.133 | Qualcomm | Opt 2: RAN5#93 (Nov-21) |  |  | 1 | 0% | 13 |  | 0% |  | 1 |  | 8 |  |  |  | 1
|  | 38.533 | 7.5.8.2 | RRC based active TCI state switch
324 | Y | 38.533 | 7.5.8.2.1 | NR SA FR2 RRC based active TCI state switch for a known TCI state | Test in A.7.5.8.2 in TS 38.133 | Qualcomm | Opt 2: RAN5#93 (Nov-21) |  |  | 1 | 0% | 13 |  | 0% |  | 1 |  | 8 |  |  |  | 1
|  | 38.533 | 7.6 | Measurement procedures | New sub-clause |  |  |  |  | 0 |  | 1 |  |  |  | 1 |  | 1 |  |  |  | 1
|  | 38.533 | 7.6.1 | Intra-frequency measurements | New sub-clause |  |  |  |  | 0 |  | 1 |  |  |  | 1 |  | 1 |  |  |  | 1
17 | Y | 38.533 | 7.6.1.1 | NR SA FR2 event-triggered reporting without gap in non-DRX | Test in A.7.6.1.1.1 in TS 38.133 | Huawei | Opt 2: RAN5#93 (Nov-21) | R5-193779 R5-195633 | RAN4 Phase 1 | 1 | 60% | 13 |  | 60%
18 | Y | 38.533 | 7.6.1.2 | NR SA FR2 event-triggered reporting without gap in DRX | Test in A.7.6.1.1.2 in TS 38.133 | Huawei | Opt 2: RAN5#93 (Nov-21) | R5-193780 R5-195634 | RAN4 Phase 1 | 1 | 60% | 13 |  | 60%
19 | Y | 38.533 | 7.6.1.3 | NR SA FR2 event-triggered reporting with gap in non-DRX | Test in A.7.6.1.1.3 in TS 38.133 | Huawei | Opt 2: RAN5#93 (Nov-21) | R5-193781 R5-197607 | RAN4 Phase 1 | 1 | 60% | 13 |  | 60%
20 | Y | 38.533 | 7.6.1.4 | NR SA FR2 event-triggered reporting with gap in DRX | Test in A.7.6.1.1.4 in TS 38.133 | Huawei | Opt 2: RAN5#93 (Nov-21) | R5-193782 R5-195636 | RAN4 Phase 1 | 1 | 60% | 13 |  | 60%
|  | 38.533 | 7.6.2 | Inter-frequency measurements | New sub-clause |  |  |  |  | 0 |  | 1 |  |  |  | 1 |  | 1 |  |  |  | 1
113 | Y | 38.533 | 7.6.2.1 | NR SA FR2-FR2 event-triggered reporting in non-DRX | Test in A.7.6.2.1 in TS 38.133 | Ericsson | Opt 2: RAN5#91 (May-21) | R5-188000 R5-191946 R5-195044 R5-198594 R5-202096 R5-205821 R5-211633 R5-214109 | RAN4 Phase 1 | 1 | 100% | 11 |  | 100%
114 | Y | 38.533 | 7.6.2.2 | NR SA FR2-FR2 event-triggered reporting in DRX | Test in A.7.6.2.2 in TS 38.133 | Ericsson | Opt 2: RAN5#92 (Aug-21) | R5-188000 R5-191947 R5-194564 R5-198595 R5-202097 R5-205822 R5-215427 | RAN4 Phase 1 | 1 | 100% | 12 |  | 100%
115 | Y | 38.533 | 7.6.2.3 | NR SA FR2-FR2 event-triggered reporting in non-DRX with SSB time index detection | Test in A.7.6.2.3 in TS 38.133 | Ericsson | Opt 2: RAN5#91 (May-21) | R5-188000 R5-191948 R5-194565 R5-198596 R5-202098 R5-205823 R5-211634 R5-214109 | RAN4 Phase 1 | 1 | 100% | 11 |  | 100%
116 | Y | 38.533 | 7.6.2.4 | NR SA FR2-FR2 event-triggered reporting in DRX with SSB time index detection | Test in A.7.6.2.4 in TS 38.133 | Ericsson | Opt 2: RAN5#92 (Aug-21) | R5-188000 R5-191949 R5-194566 R5-198597 R5-202099 R5-205824 R5-215428 | RAN4 Phase 1 | 1 | 100% | 12 |  | 100%
178 | Y | 38.533 | 7.6.2.5 | NR SA FR1-FR2 event-triggered reporting in non-DRX | Test in A.7.6.2.5 in TS 38.133 | Ericsson | Opt 2: RAN5#91 (May-21) | R5-190906 R5-191950 R5-194567 R5-198598 R5-202100 R5-205825 R5-213227 | Moved from 6.6.2.3 | 1 | 100% | 11 |  |  | 100%
179 | Y | 38.533 | 7.6.2.6 | NR SA FR1-FR2 event-triggered reporting in DRX | Test in A.7.6.2.6 in TS 38.133 | Ericsson | Opt 2: RAN5#91 (May-21) | R5-190906 R5-191951 R5-194568 R5-198599 R5-202101 R5-205826 R5-213228 | Moved from 6.6.2.4 | 1 | 100% | 11 |  |  | 100%
180 | Y | 38.533 | 7.6.2.7 | NR SA FR1-FR2 event-triggered reporting in non-DRX with SSB time index detection | Test in A.7.6.2.7 in TS 38.133 | Ericsson | Opt 2: RAN5#91 (May-21) | R5-190906 R5-191952 R5-194569 R5-199397 R5-202102 R5-205827 R5-213229 | Moved from 6.6.2.7 | 1 | 100% | 11 |  |  | 100%
181 | Y | 38.533 | 7.6.2.8 | NR SA FR1-FR2 event-triggered reporting in DRX with SSB time index detection | Test in A.7.6.2.8 in TS 38.133 | Ericsson | Opt 2: RAN5#91 (May-21) | R5-190906 R5-191953 R5-194570 R5-198601 R5-202103 R5-205828 R5-213230 | Moved from 6.6.2.8 | 1 | 100% | 11 |  |  | 100%
|  | 38.533 | 7.6.3 | L1-RSRP for beam reporting | New sub-clause |  |  |  |  | 0 |  | 1 |  |  |  | 1 |  | 1 |  |  |  | 1
290 | Y | 38533 | 7.6.3.1 | NR SA FR2 SSB-based L1-RSRP measurement in non-DRX | Test in A.7.6.3.1 in TS 38.133 | Ericsson | Opt 2: RAN5#92 (Aug-21) | R5-198696 R5-204122 R5-215421 |  | 1 | 100% | 12 |  | 100% |  | 1 |  | 6
291 | Y | 38533 | 7.6.3.2 | NR SA FR2 SSB-based L1-RSRP measurement in DRX | Test in A.7.6.3.2 in TS 38.133 | Ericsson | Opt 2: RAN5#92 (Aug-21) | R5-198697 R5-204123 R5-215422 |  | 1 | 100% | 12 |  | 100% |  | 1
292 | Y | 38533 | 7.6.3.3 | NR SA FR2 CSI-RS-based L1-RSRP measurement in non-DRX | Test in A.7.6.3.3 in TS 38.133 | Ericsson | Opt 2: RAN5#93 (Nov-21) | R5-198698 R5-204124 R5-215423 |  | 1 | 50% | 13 |  | 50% |  | 1
293 | Y | 38533 | 7.6.3.4 | NR SA FR2 CSI-RS-based L1-RSRP measurement in DRX | Test in A.7.6.3.4 in TS 38.133 | Ericsson | Opt 2: RAN5#93 (Nov-21) | R5-198699 R5-204125 R5-215424 |  | 1 | 50% | 13 |  | 50% |  | 1
|  | 38.533 | 7.7 | Measurement performance requirements | New sub-clause |  |  |  |  | 0 |  | 1 |  |  |  | 1 |  | 1 |  |  |  | 1
|  | 38.533 | 7.7.1 | SS-RSRP | New sub-clause |  |  |  |  | 0 | [11 empty] | 1
23 | Y | 38.533 | 7.7.1.1 | NR SA FR2 SS-RSRP measurement accuracy | Test in A.7.7.1.1 in TS 38.133 | Rohde&Schwarz | Opt 2: RAN5#92 (Aug-21) | R5-202074 R5-214198 | RAN4 Phase 1 | 1 | 100% | 12 |  | 100% | [7 empty] | 1
29 | Y | 38.533 | 7.7.1.2 | NR SA FR2-FR2 SS-RSRP measurement accuracy | Test in A.7.7.1.2 in TS 38.133 | Rohde&Schwarz | Opt 2: RAN5#92 (Aug-21) | R5-202075 R5-216052 | RAN4 Phase 1 | 1 | 100% | 12 |  | 100% |  | 1 | [5 empty] | 1
|  | 38.533 | 7.7.1.3 | Inter-frequency measurements between FR1 and FR2
222 | Y | 38.533 | 7.7.1.3.1 | NR SA FR1-FR2 SS-RSRP measurement accuracy | Test in A.7.7.1.3 in TS 38.133 | Huawei,Hisilicon | Opt 2: RAN5#93 (Nov-21) | R5-192483 R5-202835 | RAN4 Phase 2 | 1 | 60% | 13 |  |  | 60%
|  | 38.533 | 7.7.1.3.2 | Void | Test in A.7.7.1.3 in TS 38.133 | Huawei,Hisilicon |  | R5-192484 R5-201395 | Should be voided | 1 |  | 7
|  | 38.533 | 7.7.2 | SS-RSRQ | New sub-clause |  |  |  |  | 0 |  | 1 |  |  |  | 1 |  | 1 |  |  |  | 1
69 | Y | 38.533 | 7.7.2.1 | NR SA FR2 SS-RSRQ measurement accuracy | Test in A.7.7.2.1 in TS 38.133 | Rohde&Schwarz | Opt 2: RAN5#92 (Aug-21) | R5-202077 R5-214199 | RAN4 Phase 2 | 1 | 100% | 12 |  | 100%
117 | Y | 38.533 | 7.7.2.2 | NR SA FR2-FR2 SS-RSRQ measurement accuracy | Test in A.7.7.2.2 in TS 38.133 | Rohde&Schwarz | Opt 2: RAN5#92 (Aug-21) | R5-202078 R5-214195 | RAN4 Phase 2 | 1 | 100% | 12 |  | 100%
|  | 38.533 | 7.7.3 | SS-SINR | New sub-clause |  |  |  |  | 0 |  | 1 |  |  |  | 1 |  | 1 |  |  |  | 1
253 | Y | 38.533 | 7.7.3.1 | NR SA FR2 SS-SINR measurement accuracy | Test in A.7.7.3.1 in TS 38.133 | Rohde&Schwarz | Opt 2: RAN5#92 (Aug-21) | R5-202080 R5-214200 |  | 1 | 100% | 12 |  | 100%
254 | Y | 38.533 | 7.7.3.2 | NR SA FR2-FR2 SS-SINR measurement accuracy | Test in A.7.7.3.2 in TS 38.133 | Rohde&Schwarz | Opt 2: RAN5#92 (Aug-21) | R5-202081 R5-216053 |  | 1 | 100% | 12 |  | 100%
|  | 38.533 | 7.7.4 | L1-RSRP for beam reporting | New sub-clause |  |  |  |  | 0 |  | 1 |  |  |  | 1 |  | 1 |  |  |  | 1
182 | Y | 38.533 | 7.7.4.1 | NR SA FR2 SSB-based L1-RSRP measurement accuracy | Test in A.7.7.4.1 in TS 38.133 | Rohde&Schwarz | Opt 2: RAN5#93 (Nov-21) |  |  | 1 | 0% | 13 |  | 0%
183 | Y | 38.533 | 7.7.4.2 | NR SA FR2 CSI-RS-based L1-RSRP measurement accuracy | Test in A.7.7.4.2 in TS 38.133 | Rohde&Schwarz | Opt 2: RAN5#93 (Nov-21) |  |  | 1 | 0% | 13 |  | 0%
E-UTRA – NR Inter-RAT
|  | 38.533 | 8 | E-UTRA – NR Inter-RAT with E-UTRA serving cell | New clause |  |  |  |  | 0 |  | 1 |  |  |  | 1 |  | 1 |  |  |  | 1
|  | 38.533 | 8.1 | Void | New sub-clause |  |  |  |  | 0 |  | 1 |  |  |  | 1 | [5 empty] | 1 |  | 1
|  | 38.533 | 8.2 | RRC_IDLE state mobility | New sub-clause |  |  |  |  | 0 |  | 1 |  |  |  | 1 |  | 1 | [5 empty] | 1
|  | 38.533 | 8.2.1 | Inter-RAT cell re-selection | New sub-clause
269 | Y | 38.533 | 8.2.1.1 | E-UTRA – NR FR1 cell re-selection to higher priority NR target cell | Test in A.8.2.1.1 in TS 38.133 | Huawei, Hisilicon | Opt 2: RAN5#89 (Nov-20) | R5-197820 R5-201396 R5-206800 |  | 1 | 100% | 9 | 100%
|  | 38.533 | 8.3 | RRC_CONNECTED state mobility | New sub-clause |  |  |  |  | 0 |  | 1 |  |  |  | 1 |  | 1 |  |  |  | 1
|  | 38.533 | 8.3.1 | Inter-RAT cell handover | New sub-clause
294 | Y | 38.533 | 8.3.1.1 | E-UTRA – NR FR1 handover with known target cell | Test in A.8.3.1.1 in TS 38.133 | Huawei, Hisilicon | Opt 2: RAN5#89 (Nov-20) | R5-199399 R5-202837 R5-206801 |  | 1 | 100% | 9 | 100%
|  | 38.533 | 8.4 | Measurement procedures | New sub-clause |  |  |  |  | 0 |  | 1 |  |  |  | 1 |  | 1 |  |  |  | 1
|  | 38.533 | 8.4.1 | SFTD measurement delay | New sub-clause
270 | Y | 38.533 | 8.4.1.1 | E-UTRA – NR FR1 SFTD measurement delay in non-DRX for SA and NSA | Test in A.8.4.1.1 in TS 38.133 | Huawei, Hisilicon | Opt 2: RAN5#89 (Nov-20) Opt 3: RAN5#89 (Nov-20) | R5-199400 R5-201398 R5-205953 |  | 1 | 100% | 9 | 100% |  |  |  |  | 10 | 100%
271 | Y | 38.533 | 8.4.1.2 | E-UTRA – NR FR1 SFTD measurement delay in DRX for SA and NSA | Test in A.8.4.1.2 in TS 38.133 | Huawei, Hisilicon | Opt 2: RAN5#89 (Nov-20) Opt 3: RAN5#89 (Nov-20) | R5-199401 R5-201399 R5-205954 |  | 1 | 100% | 9 | 100% |  |  |  |  | 10 | 100%
|  | 38.533 | 8.4.2 | Inter-RAT measurements | New sub-clause
272 | Y | 38.533 | 8.4.2.1 | E-UTRA event-triggered reporting of a NR FR1 neighbour cell without SSB time index detection in non-DRX | Test in A.8.4.2.1 in TS 38.133 | Huawei, Hisilicon | Opt 2: RAN5#89 (Nov-20) Opt 3: RAN5#89 (Nov-20) | R5-195608 R5-201400 R5-206802 |  | 1 | 100% | 9 | 100% |  |  |  |  | 10 | 100%
273 | Y | 38.533 | 8.4.2.2 | E-UTRA event-triggered reporting of a NR FR1 neighbour cell without SSB time index detection in DRX | Test in A.8.4.2.2 in TS 38.133 | Huawei, Hisilicon | Opt 2: RAN5#89 (Nov-20) Opt 3: RAN5#89 (Nov-20) | R5-195609 R5-201401 R5-206803 |  | 1 | 100% | 9 | 100% |  |  |  |  | 10 | 100%
274 | Y | 38.533 | 8.4.2.3 | E-UTRA event-triggered reporting of a NR FR1 neighbour cell with SSB time index detection in non-DRX | Test in A.8.4.2.3 in TS 38.133 | Huawei, Hisilicon | Opt 2: RAN5#89 (Nov-20) Opt 3: RAN5#89 (Nov-20) | R5-195610 R5-201402 R5-206804 |  | 1 | 100% | 9 | 100% |  |  |  |  | 10 | 100%
275 | Y | 38.533 | 8.4.2.4 | E-UTRA event-triggered reporting of a NR FR1 neighbour cell with SSB time index detection in DRX | Test in A.8.4.2.4 in TS 38.133 | Huawei, Hisilicon | Opt 2: RAN5#89 (Nov-20) Opt 3: RAN5#89 (Nov-20) | R5-195611 R5-201403 R5-206805 |  | 1 | 100% | 9 | 100% |  |  |  |  | 10 | 100%
295 | Y | 38.533 | 8.4.2.5 | E-UTRA event-triggered reporting of a NR FR2 neighbour cell without SSB time index detection in non-DRX | Test in A.8.4.2.5 in TS 38.133 | Bureau Veritas | Opt 2: RAN5#93 (Nov-21) Opt 3: RAN5#93 (Nov-21) | R5-199405 R5-201686 |  | 1 | 50% | 13 |  | 50% |  |  |  | 14 |  | 50%
297 | Y | 38.533 | 8.4.2.6 | E-UTRA event-triggered reporting of a NR FR2 neighbour cell without SSB time index detection in DRX | Test in A.8.4.2.6 in TS 38.133 | Bureau Veritas | Opt 2: RAN5#93 (Nov-21) Opt 3: RAN5#93 (Nov-21) | R5-199406 R5-201687 |  | 1 | 50% | 13 |  | 50% |  |  |  | 14 |  | 50%
296 | Y | 38.533 | 8.4.2.7 | E-UTRA event-triggered reporting of a NR FR2 neighbour cell with SSB time index detection in non-DRX | Test in A.8.4.2.7 in TS 38.133 | Bureau Veritas | Opt 2: RAN5#93 (Nov-21) Opt 3: RAN5#93 (Nov-21) | R5-199407 R5-201688 |  | 1 | 50% | 13 |  | 50% |  |  |  | 14 |  | 50%
298 | Y | 38.533 | 8.4.2.8 | E-UTRA event-triggered reporting of a NR FR2 neighbour cell with SSB time index detection in DRX | Test in A.8.4.2.8 in TS 38.133 | Bureau Veritas | Opt 2: RAN5#93 (Nov-21) Opt 3: RAN5#93 (Nov-21) | R5-199408 R5-201689 |  | 1 | 50% | 13 |  | 50% |  |  |  | 14 |  | 50%
|  | 38.533 | 8.5 | Measurement performance requirements | New sub-clause |  |  |  |  | 0 |  | 1 |  |  |  | 1 |  | 1 |  |  |  | 1
|  | 38.533 | 8.5.1 | SFTD measurement accuracy | New sub-clause
299 | Y | 38.533 | 8.5.1.1 | E-UTRA – NR FR1 SFTD measurement accuracy | Test in A.8.5.1.1 in TS 38.133 | Huawei, Hisilicon | Opt 2: RAN5#92 (Aug-21) Opt 3: RAN5#92 (Aug-21) | R5-199402 R5-201404 R5-215914 |  | 1 | 100% | 12 | 100% |  |  |  |  | 13 |  | 100%
|  | 38.533 | 8.5.2 | Inter-RAT | New sub-clause
|  | 38.533 | 8.5.2.1 | SS-RSRP | New sub-clause
|  | 38.533 | 8.5.2.1.1 | FR1 target cell | New sub-clause
300 | Y | 38.533 | 8.5.2.1.1.1 | E-UTRA SS-RSRP absolute measurement accuracy of a NR FR1 neighbour cell | Test in A.8.5.2.1.1 in TS 38.133 | Rohde&Schwarz | Opt 2: RAN5#88 (Aug-20) Opt 3: RAN5#88 (Aug-20) | R5-202055 R5-203234 |  | 1 | 100% | 8 | 100% |  |  |  |  | 9 | 100%
|  | 38.533 | 8.5.2.1.1.2 | Void
302 | Y | 38.533 | 8.5.2.1.2 | E-UTRA SS-RSRP absolute measurement accuracy of a NR FR2 neighbour cell | Test in A.8.5.2.1.2 in TS 38.133 | Rohde&Schwarz | Opt 2: RAN5#90 (Feb-21) Opt 3: RAN5#90 (Feb-21) | R5-202056 R5-205063 R5-211635 |  | 1 | 100% | 10 |  | 100% |  |  |  | 11 |  | 100%
|  | 38.533 | 8.5.2.2 | SS-RSRQ | New sub-clause
304 | Y | 38.533 | 8.5.2.2.1 | E-UTRA SS-RSRQ absolute measurement accuracy of a NR FR1 neighbour cell | Test in A.8.5.2.2.1 in TS 38.133 | Rohde&Schwarz | Opt 2: RAN5#88 (Aug-20) Opt 3: RAN5#88 (Aug-20) | R5-202058 R5-203235 |  | 1 | 100% | 8 | 100% |  |  |  |  | 9 | 100%
305 | Y | 38.533 | 8.5.2.2.2 | E-UTRA SS-RSRQ absolute measurement accuracy of a NR FR2 neighbour cell | Test in A.8.5.2.2.2 in TS 38.133 | Rohde&Schwarz | Opt 2: RAN5#90 (Feb-21) Opt 3: RAN5#90 (Feb-21) | R5-202059 R5-206844 R5-211635 |  | 1 | 100% | 10 |  | 100% |  |  |  | 11 |  | 100%
|  | 38.533 | 8.5.2.3 | SS-SINR | New sub-clause
306 | Y | 38.533 | 8.5.2.3.1 | E-UTRA SS-SINR absolute measurement accuracy of a NR FR1 neighbour cell | Test in A.8.5.2.3.1 in TS 38.133 | Rohde&Schwarz | Opt 2: RAN5#88 (Aug-20) Opt 3: RAN5#88 (Aug-20) | R5-202061 R5-204783 |  | 1 | 100% | 8 | 100% |  |  |  |  | 9 | 100%
307 | Y | 38.533 | 8.5.2.3.2 | E-UTRA SS-SINR absolute measurement accuracy of a NR FR2 neighbour cell | Test in A.8.5.2.3.2 in TS 38.133 | Rohde&Schwarz | Opt 2: RAN5#90 (Feb-21) Opt 3: RAN5#90 (Feb-21) | R5-202062 R5-206909 R5-211635 |  | 1 | 100% | 10 |  | 100% |  |  |  | 11 |  | 100%
Annexes
|  | 38.533 | A | RRM test configurations | New clause |  |  |  |  | 0 |  | 1 |  |  |  | 1 |  | 1 |  |  |  | 1 |  | 1
76 |  | 38.533 | A.1 | Reference Measurement Channels | New sub-clause | Rohde&Schwarz | Opt 2: RAN5#83 (May-19) Opt 3: RAN5#83 (May-19) | R5-185614 R5-187847 |  | 1 | 100% | 3 | 100% | 100% | 100% | 1 |  | 4 | 100% | 100% | 100% | 1 |  | 1
77 |  | 38.533 | A.2 | Reference OCGN configurations | New sub-clause | Rohde&Schwarz | Opt 2: RAN5#83 (May-19) Opt 3: RAN5#83 (May-19) | R5-185614 R5-187847 |  | 1 | 100% | 3 | 100% | 100% | 100% | 1 |  | 4 | 100% | 100% | 100% | 1 |  | 1
143 |  | 38.533 | A.3 | Reference SSB configurations | New sub-clause | Rohde&Schwarz | Opt 2: RAN5#83 (May-19) Opt 3: RAN5#83 (May-19) | R5-187847 |  | 1 | 100% | 3 | 100% | 100% | 100% | 1 |  | 4 | 100% | 100% | 100%
144 |  | 38.533 | A.4 | Reference SMTC configurations | New sub-clause | Rohde&Schwarz | Opt 2: RAN5#83 (May-19) Opt 3: RAN5#83 (May-19) | R5-187847 |  | 1 | 100% | 3 | 100% | 100% | 100% | 1 |  | 4 | 100% | 100% | 100%
118 |  | 38.533 | A.5 | Reference DRX configurations | New sub-clause | Rohde&Schwarz | Opt 2: RAN5#83 (May-19) Opt 3: RAN5#83 (May-19) | R5-188005 |  | 1 | 100% | 3 | 100% | 100% | 100% | 1 |  | 4 | 100% | 100% | 100%
122 |  | 38.533 | A.6 | EN-DC test setup | New sub-clause | Rohde&Schwarz | Opt 2: RAN5#83 (May-19) Opt 3: RAN5#83 (May-19) | R5-188005 |  | 1 | 100% | 3 | 100% | 100% | 100% | 1 |  | 4 | 100% | 100% | 100%
123 |  | 38.533 | A.7 | Reference PRACH configurations | New sub-clause | Rohde&Schwarz | Opt 2: RAN5#83 (May-19) Opt 3: RAN5#83 (May-19) | R5-188005 |  | 1 | 100% | 3 | 100% | 100% | 100% | 1 |  | 4 | 100% | 100% | 100%
124 |  | 38.533 | A.8 | Reference BWP configurations | New sub-clause | Rohde&Schwarz | Opt 2: RAN5#83 (May-19) Opt 3: RAN5#83 (May-19) | R5-188005 |  | 1 | 100% | 3 | 100% | 100% | 100% | 1 |  | 4 | 100% | 100% | 100%
|  | 38.533 | B | Conditions for RRM requirements applicability for operating bands | New clause |  |  |  |  | 1 |  | 1 |  |  |  | 1 |  | 1 |  |  |  | 1 |  | 1
125 |  | 38.533 | B.1 | Conditions for NR RRC_IDLE state mobility | New sub-clause | Rohde&Schwarz | Opt 2: RAN5#83 (May-19) Opt 3: RAN5#83 (May-19) | R5-188005 |  | 1 | 100% | 3 | 100% | 100% | 100% | 1 |  | 4 | 100% | 100% | 100% | 1 |  | 1
126 |  | 38.533 | B.2 | Conditions for NR RRC_CONNECTED state | New sub-clause | Rohde&Schwarz | Opt 2: RAN5#83 (May-19) Opt 3: RAN5#83 (May-19) | R5-188005 |  | 1 | 100% | 3 | 100% | 100% | 100% | 1 |  | 4 | 100% | 100% | 100% | 1 |  | 1
127 |  | 38.533 | B.3 | RRM requirement exceptions | New sub-clause | Rohde&Schwarz | Opt 2: RAN5#83 (May-19) Opt 3: RAN5#83 (May-19) | R5-188005 |  | 1 | 100% | 3 | 100% | 100% | 100% | 1 |  | 4 | 100% | 100% | 100% | 1 |  | 1
|  | 38.533 | C | Downlink physical channels and propagation conditions | New clause
|  | 38.533 | C.1 | Downlink physical channels
150 |  | 38.533 | C.1.1 | General | New sub-clause | Rohde&Schwarz | Opt 2: RAN5#83 (May-19) Opt 3: RAN5#83 (May-19) | R5-188005 |  | 1 | 100% | 3 | 100% | 100% | 100% | 1 |  | 4 | 100% | 100% | 100%
151 |  | 38.533 | C.1.2 | Default downlink signal levels | New sub-clause | Rohde&Schwarz | Opt 2: RAN5#83 (May-19) Opt 3: RAN5#83 (May-19) | R5-188005 |  | 1 | 100% | 3 | 100% | 100% | 100% | 1 |  | 4 | 100% | 100% | 100%
152 |  | 38.533 | C.1.3 | Setup | New sub-clause | Rohde&Schwarz | Opt 2: RAN5#83 (May-19) Opt 3: RAN5#83 (May-19) | R5-188005 |  | 1 | 100% | 3 | 100% | 100% | 100% | 1 |  | 4 | 100% | 100% | 100%
|  | 38.533 | C.2 | Propagation conditions | New sub-clause
153 |  | 38.533 | C.2.1 | No interference | New sub-clause | Rohde&Schwarz | Opt 2: RAN5#83 (May-19) Opt 3: RAN5#83 (May-19) | R5-188005 |  | 1 | 100% | 3 | 100% | 100% | 100% | 1 |  | 4 | 100% | 100% | 100%
154 |  | 38.533 | C.2.2 | Static propagation conditions | New sub-clause | Rohde&Schwarz | Opt 2: RAN5#83 (May-19) Opt 3: RAN5#83 (May-19) | R5-188005 |  | 1 | 100% | 3 | 100% | 100% | 100% | 1 |  | 4 | 100% | 100% | 100%
155 |  | 38.533 | C.2.3 | Multi-path fading propagation conditions | New sub-clause | Rohde&Schwarz | Opt 2: RAN5#83 (May-19) Opt 3: RAN5#83 (May-19) | R5-188005 |  | 1 | 100% | 3 | 100% | 100% | 100% | 1 |  | 4 | 100% | 100% | 100%
|  | 38.533 | D | Deviations from standard test configurations | New clause
120 |  | 38.533 | D.1 | Test cases with different numerologies | New sub-clause | Rohde&Schwarz | Opt 2: RAN5#83 (May-19) Opt 3: RAN5#83 (May-19) | R5-188005 |  | 1 | 100% | 3 | 100% | 100% | 100% | 1 |  | 4 | 100% | 100% | 100%
128 |  | 38.533 | D.2 | EN-DC test cases with different EN-DC configurations | New sub-clause | Rohde&Schwarz | Opt 2: RAN5#83 (May-19) Opt 3: RAN5#83 (May-19) | R5-188005 |  | 1 | 100% | 3 | 100% | 100% | 100% | 1 |  | 4 | 100% | 100% | 100%
129 |  | 38.533 | D.3 | Carrier aggregation test cases with different CA configurations | New sub-clause | Rohde&Schwarz | Opt 2: RAN5#83 (May-19) Opt 3: RAN5#83 (May-19) | R5-188005 |  | 1 | 100% | 3 | 100% | 100% | 100% | 1 |  | 4 | 100% | 100% | 100%
130 |  | 38.533 | D.4 | Antenna connection for 4Rx capable Ues | New sub-clause | Rohde&Schwarz | Opt 2: RAN5#83 (May-19) Opt 3: RAN5#83 (May-19) | R5-188005 |  | 1 | 100% | 3 | 100% | 100% | 100% | 1 |  | 4 | 100% | 100% | 100%
|  | 38.533 | E | Cell configuration mapping | New clause
149 |  | 38.533 | E.1 | Test frequency selection | New sub-clause | Rohde&Schwarz | Opt 2: RAN5#83 (May-19) Opt 3: RAN5#83 (May-19) | R5-188005 |  | 1 | 100% | 3 | 100% | 100% | 100% | 1 |  | 4 | 100% | 100% | 100%
131 |  | 38.533 | E.2 | Cell configuration mapping for EN-DC FR1 test cases in Chapter 4 | New sub-clause | Rohde&Schwarz | Opt 3: RAN5#85 (Nov-19) | R5-188005 |  | 1 | 100% | 5 |  |  |  | 1 |  | 6 | 100%
132 |  | 38.533 | E.3 | Cell configuration mapping for EN-DC FR2 test cases in Chapter 5 | New sub-clause | Rohde&Schwarz | Opt 3: RAN5#85 (Nov-19) | R5-188005 |  | 1 | 100% | 5 |  |  |  | 1 |  | 6 | 100% | 100% | 100%
133 |  | 38.533 | E.4 | Cell configuration mapping for SA FR1 test cases in Chapter 6 | New sub-clause | Rohde&Schwarz | Opt 2: RAN5#85 (Nov-19) | R5-188005 |  | 1 | 100% | 5 | 100% |  |  | 1 |  | 6
134 |  | 38.533 | E.5 | Cell configuration mapping for SA FR2 test cases in Chapter 7 | New sub-clause | Rohde&Schwarz | Opt 2: RAN5#85 (Nov-19) | R5-188005 |  | 1 | 100% | 5 |  | 100% |  | 1 |  | 6
|  | 38.533 | F | Measurement uncertainties and test tolerances | New clause
135 |  | 38.533 | F.1 | Acceptable uncertainty of test system (normative) | New sub-clause | Rohde&Schwarz | Opt 2: RAN5#85 (Nov-19) Opt 3: RAN5#85 (Nov-19) | R5-188005 |  | 1 | 100% | 5 | 100% | 100% | 100% | 1 |  | 6 | 100% | 100% | 100%
136 |  | 38.533 | F.2 | Interpretation of measurement results (normative) | New sub-clause | Rohde&Schwarz | Opt 2: RAN5#85 (Nov-19) Opt 3: RAN5#85 (Nov-19) | R5-188005 |  | 1 | 100% | 5 | 100% | 100% | 100% | 1 |  | 6 | 100% | 100% | 100%
137 |  | 38.533 | F.3 | Test tolerance and derivation of test requirements (informative) | New sub-clause | Rohde&Schwarz | Opt 2: RAN5#85 (Nov-19) Opt 3: RAN5#85 (Nov-19) | R5-188005 |  | 1 | 100% | 5 | 100% | 100% | 100% | 1 |  | 6 | 100% | 100% | 100%
|  | 38.533 | G | Statistical testing | New clause
138 |  | 38.533 | G.1 | General | New sub-clause | Rohde&Schwarz | Opt 2: RAN5#91 (May-21) Opt 3: RAN5#91 (May-21) | R5-188005 |  | 1 | 100% | 11 | 100% | 100% | 100% | 1 |  | 12 | 100% | 100% | 100%
139 |  | 38.533 | G.2 | Statistical testing of delay and UE measurements performance in RRM tests | New sub-clause | Rohde&Schwarz | Opt 2: RAN5#91 (May-21) Opt 3: RAN5#91 (May-21) | R5-188005 |  | 1 | 100% | 11 | 100% | 100% | 100% | 1 |  | 12 | 100% | 100% | 100%
140 |  | 38.533 | G.3 | Theory to derive the numbers in Table F.2.3-1 (informative) | New sub-clause | Rohde&Schwarz | Opt 2: RAN5#91 (May-21) Opt 3: RAN5#91 (May-21) | R5-188005 |  | 1 | 100% | 11 | 100% | 100% | 100% | 1 |  | 12 | 100% | 100% | 100%
|  | 38.586 | H | Default message contents for RRM | New clause
Common Sections
|  | 38.533 | 3A | Requirements for support of RRM | New clause
141 |  | 38.533 | 3A.1 | General | New sub-clause | Rohde&Schwarz | Opt 2: RAN5#83 (May-19) Opt 3: RAN5#83 (May-19) | R5-186706 |  | 1 | 100% | 3 | 100% | 100% | 100% | 1 |  | 4 | 100% | 100% | 100% | 1 |  | 1
142 |  | 38.533 | 3A.2 | Requirement classification for statistical testing | New sub-clause | Rohde&Schwarz | Opt 2: RAN5#83 (May-19) Opt 3: RAN5#83 (May-19) | R5-186706 |  | 1 | 100% | 3 | 100% | 100% | 100% | 1 |  | 4 | 100% | 100% | 100% | 1 |  | 1
121 |  | 38.533 | 3A.3 | Reference antenna configuration | New sub-clause | Rohde&Schwarz | Opt 2: RAN5#83 (May-19) Opt 3: RAN5#83 (May-19) | R5-186706 |  | 1 | 100% | 3 | 100% | 100% | 100% | 1 |  | 4 | 100% | 100% | 100% | 1 |  | 1
148 |  | 38533 | 3A.4 | NR band groups | New sub-clause | Rohde&Schwarz | Opt 2: RAN5#83 (May-19) Opt 3: RAN5#83 (May-19) | R5-186706 |  | 1 | 100% | 3 | 100% | 100% | 100% | 1 |  | 4 | 100% | 100% | 100% | 1 |  | 1
160 |  | 38533 | 3A.5 | NR operating band configurations | New sub-clause | Rohde&Schwarz | Opt 2: RAN5#83 (May-19) Opt 3: RAN5#85 (Nov-19) | R5-186706 |  | 1 | 100% | 3 | 100% | 100% | 100% | 1 |  | 6 | 100% | 100% | 100%
Inter-RAT
|  | 38.533 | FFS | FFS | FFS |  |  |  | Place holder for potential LTE - NR inter RAT tests with serving cell in LTE | 0 |  | 1 |  |  |  | 1 |  | 1 |  |  |  | 1 |  | 1
[10 empty] | 0 |  | 1 |  |  |  | 1 |  | 1 |  |  |  | 1 |  | 1
End of work plan items. Note! Do not remove this row. Introduce new work plan rows/items above this row.
|  | Template to be used when introducing new work plan rows/items: 1. Select the template row by putting the cursor on the template row number (leftmost column, before column A), right-click and select 'Copy'; Or, select and copy an existing WP Item row. 2. Select the row in the work plan section where you want to put the template row before. Note! must be between the work plan start and end rows (black colored rows). Right-click and select 'Insert copied Cells'. 3. Fill in the work plan row details. - Fill in 'TS', 'Clause', Title', 'Test purpose/Task','Company' (if already assigned) and 'Comments' (if any). - The following cells are automatically filled in (do not remove the formula in column G): 'Target' (column G, set based on the WP item's assigned impacted options and phase per each option) and 'WP item compl.' (column K). 4. Assign a WP item ID number by double-click on the WP item number cell in column A (or add manually unique numbers per WP item). 5. Set impacted areas (starting from column M): - Assign WP item's impact for an option by setting the cell value for the work item row to '0%' for the option (columns N, P, R, T, V). - Assign WP item's RAN5 delivery phase within the option (1 or 2, set to 1 as default in the template row below) - Remove assigment for an WP item and option by leaving the cell value as empty (remove the content, select the cell and preess <Delete>). For WP items for protocol test cases please see seperate guideline for how to specify the test purposes using the TP tracking tool macros. | [7 empty] | WP item wight factor is set to reflect the relative weight--> between different typ of WP item tasks (Reference: a test case have the weight = 1) |  | Set phase within option 2 (default is 1) --> > | Set completion for option 2 --> (leave empty if not applicable)…. | Set completion for option 2 --> (leave empty if not applicable)…. | Set completion for option 2 --> (leave empty if not applicable)…. | Set phase within option 5 (default is 1) --> > | Set completion for option 5 --> (leave empty if not applicable)…. | Set phase within option 3 (default is 1) --> > | Set completion for option 3 --> (leave empty if not applicable)…. | Set completion for option 3 --> (leave empty if not applicable)…. | Set completion for option 3 --> (leave empty if not applicable)…. | Set phase within option 4 (default is 1) --> > | Set completion for option 4 --> (leave empty if not applicable)…. | Set phase within option 7 (default is 1) --> > | Set completion for option 7 --> (leave empty if not applicable)….
<WP item#, must be unique within the sub-area WP> |  | 38.533 | x.y.z | <Example of WP task applicable to RAN-CN interface option 3.> |  |  | Opt 3: RAN5#91 (May-21) |  |  |  | 0% | 1 |  |  |  | 1 |  | 12 | 0% | 0% | 0% | 1 |  | 1
Note on A7: Unique ID for WP items (unique within the sub-area work plan) Note! As WP item numbers may be referenced from outside of this WP that means: - Do not change number for WP items that have been published. - Do not re-use WP item numbers if a WP item is deleted
Note on B7: Y = the WP Pitem is a test case.
Note on K7: The WP item's weight number is used to set the reletive weights between WP items used in the overall calculation of completeness. Setting it to 0 for a WP item means that it will not be included at all in the calculation.