## Summary
Work plan summary:
NR Transmitter and Receiver Test Cases – Range 1 and Range 2 Interworking operation with other radios (TS 38.521-3)
|  |  | Overall |  | FR1 |  | FR2 |  | FR1+FR2
| NR Transmitter and Receiver Test Cases – Range 1 and Range 2 Interworking operation with other radios (TS 38.521-3) | SA Option 2 (SA NR) | 100% | [5 empty] | 100%
|  | NSA Option 3 (EN-DC) | 86.33% |  | 92.98% |  | 73.35% |  | 90.11%
SA Option 5
|  | NSA Option 4 (NE-DC) | 80.17% |  | 84.42% |  | 64.08% |  | 94.33%
|  | NSA Option 7 (NGEN-DC) | 72.6%
|  | Area | SA Option 2 (SA NR) test case statistics
|  |  | Overall number of test cases |  | Number of FR1 test cases |  | Number of FR2 test cases |  | Number of FR1+FR2 test cases
|  |  | Overall | Completed for at least one of FR1, FR2 or FR1+FR2 | Overall | Completed | Overall | Completed | Overall | Completed
| NR Transmitter and Receiver Test Cases – Range 1 and Range 2 Interworking operation with other radios (TS 38.521-3) | SA Option 2 (SA NR) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | NSA Option 3 (EN-DC) | 193 | 116 | 127 | 105 | 66 | 11 | 2 | 2
SA Option 5
|  | NSA Option 4 (NE-DC) | 166 | 100 | 126 | 93 | 41 | 8 | 1 | 1
|  | NSA Option 7 (NGEN-DC) | 161 | 87

## RF Tx Rx Iw Range 1 and 2
WP Title: | NR Transmitter and Receiver Test Cases – Range 1 and Range 2 Interworking operation with other radios (TS 38.521-3) | [10 empty] | WP item applicability | [15 empty] | End of work plan columns. Note! Do not remove this column.
RAN-CN interface options dependency
WP Scope: | This part of the work plan covers NR Transmitter and Receiver Test Cases – Range 1 and Range 2 Interworking operation with other radios (TS 38.521-3) | [10 empty] | 5GC/NR |  |  |  | 5GC/LTE | EPC/LTE |  |  |  | 5GC/NR master |  |  |  | 5GC / LTE master
WP Resp: | Wang, Kevin, Qualcomm Technologies, Inc |  |  |  | kevinw@qti.qualcomm.com
TS Resp: | Wang, Kevin, Qualcomm Technologies, Inc |  |  |  | kevinw@qti.qualcomm.com | [6 empty] | SA |  |  |  |  | NSA
[12 empty] | Opt.2 |  |  |  | Opt.5 | Opt.3 |  |  |  | Opt.4 |  |  |  | Opt.7
WP Item ID | Is test case | TS | Clause | Title | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | WP item compl. | 1st Target | FR1 | FR2 | FR1+FR2 |  | 1st Target | FR1 | FR2 | FR1+FR2 | 1st Target | FR1 | FR2 | FR1+FR2
[11 empty] | Overall |  | 100% |  |  |  |  | 86.33% |  |  |  | 80.17% |  |  | 72.6%
[11 empty] | Overall vs FR1,FR2 and FR1+FR2 |  |  |  | 100% |  |  | 92.98% | 73.35% | 90.11% |  | 84.42% | 64.08% | 94.33%
[11 empty] | Phase 1 | [10 empty] | 84.42% | 64.08% | 94.33% | 72.6%
Phase 1.5
[11 empty] | Phase 2 | [6 empty] | 100%
[11 empty] | Phase 3 | [6 empty] | 100% | 100% | 100%
[11 empty] | Phase 4 |  |  |  | 100% |  |  | 100% | 100% | 100%
[11 empty] | Phase 5 |  |  |  | 100% |  |  | 100% |  | 100%
[11 empty] | Phase 6 |  |  |  | 100% |  |  | 100% | 100% | 100%
[11 empty] | Phase 7 |  |  |  | 100% |  |  | 100% | 100% | 100%
[11 empty] | Phase 8 | [6 empty] | 100% | 100% | 100%
[11 empty] | Phase 9 | [6 empty] | 100% | 100% | 100%
[11 empty] | Phase 10 |  |  |  | 100% |  |  | 100% | 100% | 100%
[11 empty] | Phase 11 | [6 empty] | 100%
[11 empty] | Phase 12 | [6 empty] | 100%
[11 empty] | Phase 13 | [7 empty] | 100%
[11 empty] | Phase 14 | [6 empty] | 62.73% | 62.99% | 45.29%
[7 empty] | Overall# WP items: Phase 1.5 # WP items: Phase 2# WP items: Phase 3# WP items: Phase 4# WP items Phase 5# WP items Phase 6# WP items Phase 7# WP items Phase 8# WP items Phase 9# WP items Phase 10# WP items Phase 11# WP items Phase 12# WP items Phase 13# WP items Phase 14# WP items | [5 empty] | 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 | 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 | 31 9 0 0 16 1 1 4 0 0 0 0 0 0 0 | 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 |  | 168 62 21 13 17 15 3 11 23 3 0 0 0 0 0 | 100 78 0 2 4 0 1 2 4 8 0 0 0 0 0 | 44 19 0 1 4 1 4 2 4 9 0 0 0 0 0 |  | 167 167 0 0 0 0 0 0 0 0 0 0 0 0 0 | 65 63 0 0 0 0 0 0 0 0 0 0 0 0 0 | 31 31 0 0 0 0 0 0 0 0 0 0 0 0 0 | 212 212 0 0 0 0 0 0 0 0 0 0 0 0 0
Start of work plan items. Note! Do not remove this row. Introduce new work plan rows/items below this row.
Identified test cases/tasks
Operating bands and Channel arrangement (Section 5)
1 |  | 38.521-3 | 5.1 | General |  | Qualcomm | Opt 2: RAN5#90 (Feb-21) Opt 3: RAN5#89 (Nov-20) Opt 4: RAN5#93 (Nov-21) Opt 7: FFS | R5-186233 R5-186308 |  | 0.5 | 100% | 10 |  |  | 100% | 1 | 10 | 100% | 100% | 100% | 1 | 100% | 100% | 100% | 1 | 100%
2 |  | 38.521-3 | 5.2 | Operating Bands |  | Qualcomm | Opt 3: RAN5#89 (Nov-20) Opt 4: RAN5#93 (Nov-21) Opt 7: FFS | R5-181807 R5-186232 R5-192441 |  | 0.5 | 70% |  |  |  |  | 1 | 10 | 100% | 100% |  | 1 | 50% | 50% |  | 1 | 50%
3 |  | 38.521-3 | 5.2A | Operating bands for CA | Test Configuration | Qualcomm | Opt 2: RAN5#84 (Aug-19) | R5-181807 R5-186232 R5-192440 |  | 0.5 | 100% | 4 |  |  | 100% | 1
5 |  | 38.521-3 | 5.3 | UE Channel Bandwidth | Test Configuration | Bureau Veritas | Opt 2: RAN5#90 (Feb-21) Opt 3: RAN5#89 (Nov-20) Opt 4: RAN5#93 (Nov-21) Opt 7: FFS | R5-181690; R5-181828; R5-184579 R5-185869 R5-187153 |  | 0.5 | 75% | 10 |  |  | 100% | 1 | 10 | 100% | 100% | 100% | 1 | 50% | 50% | 50% | 1 | 50%
6 |  | 38.521-3 | 5.4 | Channel arrangement |  | Qualcomm | Opt 2: RAN5#90 (Feb-21) Opt 3: RAN5#89 (Nov-20) Opt 4: RAN5#93 (Nov-21) Opt 7: FFS | R5-181828 R5-184897 R5-186232 |  | 0.5 | 75% | 10 |  |  | 100% | 1 | 10 | 100% | 100% | 100% | 1 | 50% | 50% | 50% | 1 | 50%
7 |  | 38.521-3 | 5.5 | Configuration | Test Configuration | Bureau Veritas | Opt 2: RAN5#90 (Feb-21) Opt 3: RAN5#89 (Nov-20) Opt 4: RAN5#93 (Nov-21) Opt 7: FFS | R5-181828 R5-183708 R5-184579 R5-185869 R5-186153 R5-194954 |  | 0.5 | 75% | 10 |  |  | 100% | 1 | 10 | 100% | 100% | 100% | 1 | 50% | 50% | 50% | 1 | 50%
Transmitter Characteristics (Section 6)
|  | 38.521-3 | 6.1 | General |  |  |  | R5-185563 R5-186291
|  | 38.521-3 | 6.2 | Transmitter power
|  | 38.521-3 | 6.2A | Transmitter power for CA without EN-DC
|  | 38.521-3 | 6.2A.1 | UE maximum output power for CA
8 |  | 38.521-3 | 6.2A.1.1 | UE maximum output power for inter-band NR CA between FR 1 and FR 2 without EN-DC |  | Huawei | Opt 2: RAN5#84 (Aug-19) | R5-194947 | FR1+FR2 Testability. Content Complete with no TC details added | 0.4 | 100% | 4 |  |  | 100% | 1
|  | 38.521-3 | 6.2A.2 | UE maximum output power reduction for CA
9 |  | 38.521-3 | 6.2A.2.1 | UE maximum output power reduction for inter-band NR CA between FR 1 and FR 2 without EN-DC |  | Ericsson | Opt 2: RAN5#84 (Aug-19) | R5-193311 R5-194404 | FR1+FR2 Testability. No TC details added | 0.4 | 100% | 4 |  |  | 100% | 1
|  | 38.521-3 | 6.2A.3 | UE additional maximum output power reduction for CA
10 |  | 38.521-3 | 6.2A.3.1 | UE additional maximum output power reduction for inter-band NR CA between FR 1 and FR 2 without EN-DC |  | Ericsson | Opt 2: RAN5#84 (Aug-19) | R5-194462 | FR1+FR2 Testability. No TC details added | 0.4 | 100% | 4 |  |  | 100% | 1
|  | 38.521-3 | 6.2A.4 | Configured output power for CA
11 |  | 38.521-3 | 6.2A.4.1 | UE Configured output power level for inter-band NR CA between FR 1 and FR 2 without EN-DC |  | Huawei | Opt 2: RAN5#84 (Aug-19) | R5-194947 | FR1+FR2 Testability. No TC details added | 0.4 | 100% | 4 |  |  | 100% | 1
|  | 38.521-3 | 6.2A.4.2 | ΔTIB,c for CA
12 |  | 38.521-3 | 6.2A.4.2.1 | ΔTIB,c for Inter-band CA between FR1 and FR2 |  | Bureau Veritas | Opt 2: RAN5#87 (May-20) |  | No additional updates as per core spec. Can be considered complete. Mark table void. | 0.4 | 100% | 7 |  |  | 100% | 1
|  | 38.521-3 | 6.2B | Transmitter power for DC
|  | 38.521-3 | 6.2B.1 | UE Maximum Output Power for DC
13 | Y | 38.521-3 | 6.2B.1.1 | UE Maximum Output Power for Intra-Band Contiguous EN-DC |  | Huawei | Opt 3: RAN5#93 (Nov-21) | R5-183962 R5-185472 R5-190994 R5-192004 R5-193460 R5-202945 | Pending ongoing RAN4 discussion on minimum requirement | 1 | 80% | [5 empty] | 14 | 80% | [8 empty] | 0
14 | Y | 38.521-3 | 6.2B.1.2 | UE Maximum Output Power for Intra-Band non-Contiguous EN-DC |  | Huawei | Opt 3: RAN5#93 (Nov-21) | R5-185473 R5-190992 R5-192005 R5-193461 R5-202946 | Pending ongoing RAN4 discussion on minimum requirement | 1 | 80% | [5 empty] | 14 | 80%
15 | Y | 38.521-3 | 6.2B.1.3 | UE Maximum Output Power for Inter-Band EN-DC within FR1 |  | Huawei | Opt 3: RAN5#84 (Aug-19) | R5-183962 R5-185474 R5-190990 R5-192006 R5-193462 R5-193912 R5-201855 R5-210497 R5-211873 |  | 1 | 100% | [5 empty] | 5 | 100%
15 | Y | 38.521-3 | 6.2B.1.3A | UE Maximum Output Power for Inter-Band NE-DC within FR1 |  | CMCC, Qualcomm, Ericsson | Opt 4: RAN5#93 (Nov-21) | R5-216039 | Message contents are FFS | 1 | 50% | [9 empty] | 1 | 50%
16 |  | 38.521-3 | 6.2B.1.4 | UE Maximum Output Power for Inter-Band EN-DC including FR2
17 | Y | 38.521-3 | 6.2B.1.4.1 | UE Maximum Output Power for Inter-Band EN-DC including FR2 - EIRP and TRP |  | Huawei | Opt 3: Opt 4: RAN5#93 (Nov-21) Opt 7: FFS | R5-192694 | Editor's note: The following aspects are either missing or not yet determined: - The referred test case 6.2.1.1 in TS 38.521-2 is incomplete for power class 1, 2 and 4. - The following aspects of the clause are for future consideration: - Test Procedures for EIRP beam peak Extreme Conditions are FFS | 1 | 100% | [5 empty] | 3MT1 |  | 100% |  | 1 |  | 100% |  | 1 | 100%
18 | Y | 38.521-3 | 6.2B.1.4.2 | UE Maximum Output Power for Inter-Band EN-DC including FR2 (1 NR CC) - Spherical Coverage |  | Huawei | Opt 3: RAN5#88 (Aug-20) MU: RAN5#88 (Aug-20) TT: RAN5#88 (Aug-20) Opt 4: RAN5#93 (Nov-21) Opt 7: FFS |  | Test is complete for PC3. | 1 | 100% | [5 empty] | 9MT1 |  | 100% |  | 1 |  | 100% |  | 1 | 100%
|  | 38.521-3 | 6.2B.1.4_1 | UE Maximum Output Power for Inter-Band EN-DC including FR2 ((>1 NR CC)
|  | 38.521-3 | 6.2B.1.4_1.1 | UE Maximum Output Power for Inter-Band EN-DC including FR2 (2 NR CCs) | [5 empty] | 0
19 |  | 38.521-3 | 6.2B.1.4_1.1.1 | UE Maximum Output Power for Inter-Band EN-DC including FR2 (2 NR CCs) - EIRP and TRP |  |  |  |  | Placeholder for TC numbering structure. Status tracked in Rel16 WP. | 0
20 |  | 38.521-3 | 6.2B.1.4_1.1.2 | UE Maximum Output Power for Inter-Band EN-DC including FR2 2 NR CCs) - Spherical Coverage |  |  |  |  | Placeholder for TC numbering structure. Status tracked in Rel16 WP. | 0
|  | 38.521-3 | 6.2B.1.4_1.2 | UE Maximum Output Power for Inter-Band EN-DC including FR2 (3 NR CCs) | [5 empty] | 0
21 |  | 38.521-3 | 6.2B.1.4_1.2.1 | UE Maximum Output Power for Inter-Band EN-DC including FR2 (3 NR CCs) - EIRP and TRP |  |  |  |  | Placeholder for TC numbering structure. Status tracked in Rel16 WP. | 0
22 |  | 38.521-3 | 6.2B.1.4_1.2.2 | UE Maximum Output Power for Inter-Band EN-DC including FR2 (3 NR CCs) - Spherical Coverage |  |  |  |  | Placeholder for TC numbering structure. Status tracked in Rel16 WP. | 0
|  | 38.521-3 | 6.2B.1.4_1.3 | UE Maximum Output Power for Inter-Band EN-DC including FR2 4 NR CCs) | [5 empty] | 0
23 |  | 38.521-3 | 6.2B.1.4_1.3.1 | UE Maximum Output Power for Inter-Band EN-DC including FR2 (4 NR CCs) - EIRP and TRP |  |  |  |  | Placeholder for TC numbering structure. Status tracked in Rel16 WP. | 0
24 |  | 38.521-3 | 6.2B.1.4_1.3.2 | UE Maximum Output Power for Inter-Band EN-DC including FR2 (4 NR CCs) - Spherical Coverage |  |  |  |  | Placeholder for TC numbering structure. Status tracked in Rel16 WP. | 0
25 | Y | 38.521-3 | 6.2B.1.4D | UE Maximum Output Power for Inter-Band EN-DC including FR2 for UL MIMO |  | Huawei | Opt 3: RAN5#93 (Nov-21) MU: RAN5#93 (Aug-21) TT: RAN5#93 (Aug-21) | R5-202732 | MOP test in 38.521-2 is incomplete. | 1 | 80% | [5 empty] | 14MT1 |  | 80%
26 |  | 38.521-3 | 6.2B.1.5 | UE Maximum Output Power for Inter-Band EN-DC including both FR1 and FR2 |  | Huawei | Opt 3: - Opt 4: RAN5#93 (Nov-21) Opt 7: FFS |  | No TC details needed. FR1+FR2 testability issue. | 0.4 | 100% | [5 empty] | 6MT3 |  |  | 100% | 1 |  |  | 100% | 1 | 100%
27 |  | 38.521-3 | 6.2B.1.5D | UE Maximum Output Power for Inter-Band EN-DC including both FR1 and FR2 for UL MIMO |  | Huawei | Opt 3: RAN5#88 (Aug-20) MU: RAN5#88 (Aug-20) TT: RAN5#88 (Aug-20) Opt 4: RAN5#93 (Nov-21) Opt 7: FFS | R5-202829 | FR1+FR2 Testability. Basic text to add..No TC details needed. | 0.4 | 100% | [5 empty] | 9MT1 |  |  | 100% | 1 |  |  | 100% | 1 | 100%
|  | 38.521-3 | 6.2B.2 | UE Maximum Output Power reduction for DC
|  | 38.521-3 | 6.2B.2.0 | General
28 | Y | 38.521-3 | 6.2B.2.1 | UE Maximum Output Power reduction for Intra-Band Contiguous EN-DC |  | Ericsson | Opt 3: RAN5#82 (Feb-19) Opt 4: RAN5#93 (Nov-21) Opt 7: FFS | R5-183707 R5-186234 R5-190829 R5-193457 R5-211873 R5-211872 R5-215194 |  | 1 | 100% | [5 empty] | 3 | 100% |  |  | 1 | 100% |  |  | 1 | 100%
29 | Y | 38.521-3 | 6.2B.2.2 | UE Maximum Output Power reduction for Intra-Band non-Contiguous EN-DC |  | Ericsson | Opt 3: RAN5#85 (Nov-19) Opt 4: RAN5#93 (Nov-21) Opt 7: FFS | R5-186237 R5-190831 |  | 1 | 100% | [5 empty] | 6 | 100% |  |  | 1 | 100% |  |  | 1 | 100%
30 | Y | 38.521-3 | 6.2B.2.3 | UE Maximum Output power reduction for inter-band EN-DC within FR1 (1 NR CC) |  | Ericsson | Opt 3: RAN5#83 (May-19) | R5-186293 R5-193450 |  | 1 | 100% | [5 empty] | 4 | 100%
31 | Y | 38.521-3 | 6.2B.2.3A | UE Maximum Output power reduction for inter-band NE-DC within FR1 |  |  | Opt 4: RAN5#93 (Nov-21) |  |  | 1 | 0% | [9 empty] | 1 | 0%
32 | Y | 38.521-3 | 6.2B.2.4 | UE Maximum Output power reduction for inter-band EN-DC including FR2 (1 NR CC) |  | Ericsson | Opt 3: RAN5#93 (Nov-21) MU: RAN5#93 (Aug-21) TT: RAN5#93 (Aug-21) Opt 4: RAN5#93 (Nov-21) Opt 7: FFS | R5-187816 |  | 1 | 43.33% | [5 empty] | 14MT3 |  | 70% |  | 1 |  | 30% |  | 1 | 30%
|  | 38.521-3 | 6.2B.2.4_1 | UE Maximum Output power reduction for inter-band EN-DC including (>2 CCs)
33 |  | 38.521-3 | 6.2B.2.4_1.1 | UE Maximum Output power reduction for inter-band EN-DC including FR2 (3 CCs) |  |  |  |  | Placeholder for TC numbering structure. Status tracked in Rel16 WP. | 0
34 |  | 38.521-3 | 6.2B.2.4_1.2 | UE Maximum Output power reduction for inter-band EN-DC including FR2 (4 CCs) |  |  |  |  | Placeholder for TC numbering structure. Status tracked in Rel16 WP. | 0
35 |  | 38.521-3 | 6.2B.2.4_1.3 | UE Maximum Output power reduction for inter-band EN-DC including FR2 (5 CCs) |  |  |  |  | Placeholder for TC numbering structure. Status tracked in Rel16 WP. | 0
36 | Y | 38.521-3 | 6.2B.2.4D | UE Maximum Output power reduction for inter-band EN-DC including FR2 for UL-MIMO |  | Ericsson | Opt 3: RAN5#93 (Nov-21) MU: RAN5#93 (Aug-21) TT: RAN5#93 (Aug-21) Opt 4: RAN5#93 (Nov-21) Opt 7: FFS | R5-187816 | Refers back to SA UL-MIMO test. Anchor-agnostic. | 1 | 0% | [5 empty] | 14MT3 |  | 0% |  | 1 |  | 0% |  | 1 | 0%
37 |  | 38.521-3 | 6.2B.2.5 | UE Maximum Output power reduction for inter-band EN-DC including both FR1 and FR2 |  | Ericsson | Opt 3: RAN5#83 (May-19) MU: RAN5#84 (Aug-19) TT: RAN5#84 (Aug-19) Opt 4: RAN5#93 (Nov-21) Opt 7: FFS | R5-193451 | FR1+FR2 Testability. No TC details added | 0.4 | 100% | [5 empty] | 4MT3 |  |  | 100% | 1 |  |  | 100% | 1 | 100%
38 |  | 38.521-3 | 6.2B.2.5D | UE Maximum Output power reduction for inter-band EN-DC including both FR1 and FR2 for UL-MIMO |  | Ericsson | Opt 3: RAN5#93 (Nov-21) MU: RAN5#93 (Aug-21) TT: RAN5#93 (Aug-21) | R5-193451 | FR1+FR2 Testability. Basic text to add..No TC details needed. | 0.4 | 0% | [5 empty] | 14MT1 |  |  | 0%
|  | 38.521-3 | 6.2B.3 | UE additional maximum output power reduction for EN-DC
39 | Y | 38.521-3 | 6.2B.3.1 | UE additional maximum output power reduction for intra-band contiguous EN-DC |  | Ericsson | Opt 3: RAN5#84 (Aug-19) Opt 4: RAN5#93 (Nov-21) Opt 7: FFS | R5-180086; R5-182016 R5-185469 R5-186236 R5-188024 R5-190838 R5-193453 R5-193498 R5-211871 |  | 1 | 100% | [5 empty] | 5 | 100% |  |  | 1 | 100% |  |  | 1 | 100%
40 | Y | 38.521-3 | 6.2B.3.2 | UE additional maximum output power reduction for intra-band non-contiguous EN-DC |  | Ericsson | Opt 3: RAN5#93 (Nov-21) Opt 4: RAN5#93 (Nov-21) Opt 7: FFS | R5-185470 R5-193498 R5-194944 R5-211871 | Test can be 100% completed for at least 1 NS value at RAN5#87. Wgap parameters to be decided by RAN5. | 1 | 91.67% | [5 empty] | 14 | 95% |  |  | 1 | 90% |  |  | 1 | 90%
41 | Y | 38.521-3 | 6.2B.3.3 | UE additional Maximum Output power reduction for inter-band EN-DC within FR1 (1 NR CC) |  | Ericsson | Opt 3: RAN5#86 (Feb-20) Opt 4: RAN5#93 (Nov-21) Opt 7: FFS | R5-193455 R5-211871 |  | 1 | 100% | [5 empty] | 7 | 100% |  |  | 1 | 100% |  |  | 1 | 100%
42 | Y | 38.521-3 | 6.2B.3.4 | UE Additional Maximum Output power reduction for inter-band EN-DC including FR2 (1 NR CC) |  | Ericsson | Opt 3: RAN5#93 (Nov-21) MU: RAN5#93 (Aug-21) TT: RAN5#93 (Aug-21) Opt 4: RAN5#93 (Nov-21) Opt 7: FFS | R5-190839 | Test requirements in referenced TS 38.521-2 [9] test case is incomplete due to missing Test Tolerance | 1 | 46.67% | [5 empty] | 14MT3 |  | 60% |  | 1 |  | 40% |  | 1 | 40%
|  | 38.521-3 | 6.2B.3.4_1 | UE Additional Maximum Output power reduction for inter-band EN-DC including FR2 (> 2 CCs)
43 |  | 38.521-3 | 6.2B.3.4_1.1 | UE Additional Maximum Output power reduction for inter-band EN-DC including FR2 (3 CCs) |  |  |  |  | Placeholder for TC numbering structure. Status tracked in Rel16 WP. | 0
44 |  | 38.521-3 | 6.2B.3.4_1.2 | UE Additional Maximum Output power reduction for inter-band EN-DC including FR2 (4 CCs) |  |  |  |  | Placeholder for TC numbering structure. Status tracked in Rel16 WP. | 0
45 |  | 38.521-3 | 6.2B.3.4_1.3 | UE Additional Maximum Output power reduction for inter-band EN-DC including FR2 (5 CCs) |  |  |  |  | Placeholder for TC numbering structure. Status tracked in Rel16 WP. | 0
46 | Y | 38.521-3 | 6.2B.3.4D | UE Additional Maximum Output power reduction for inter-band EN-DC including FR2 for UL-MIMO |  | Ericsson | Opt 3: RAN5#93 (Nov-21) MU: RAN5#93 (Aug-21) TT: RAN5#93 (Aug-21) Opt 4: RAN5#93 (Nov-21) Opt 7: FFS |  | Refers back to SA UL-MIMO test. Anchor-agnostic. | 1 | 0% | [5 empty] | 14MT3 |  | 0% |  | 1 |  | 0% |  | 1 | 0%
47 |  | 38.521-3 | 6.2B.3.5 | UE Additional Maximum Output power reduction for inter-band EN-DC including both FR1 and FR2 |  | Ericsson | Opt 3: RAN5#83 (May-19) MU: RAN5#84 (Aug-19) TT: RAN5#84 (Aug-19) Opt 4: RAN5#93 (Nov-21) Opt 7: FFS | R5-193499 | FR1+FR2 Testability. No TC details added | 0.4 | 100% | [5 empty] | 4MT3 |  |  | 100% | 1 |  |  | 100% | 1 | 100%
48 |  | 38.521-3 | 6.2B.3.5D | UE Additional Maximum Output power reduction for inter-band EN-DC including both FR1 and FR2 |  | Ericsson | Opt 3: RAN5#93 (Nov-21) MU: RAN5#93 (Aug-21) TT: RAN5#93 (Aug-21) |  | FR1+FR2 Testability. No TC details needed. | 0.4 | 0% | [5 empty] | 14MT1 |  |  | 0%
|  | 38.521-3 | 6.2B.4 | Configured output power for EN DC
|  | 38.521-3 | 6.2B.4.1 | Configured output power level for EN DC
49 | Y | 38.521-3 | 6.2B.4.1.1 | Configured output power level for intra-band contiguous EN-DC |  | Huawei | Opt 3: RAN5#90 (Feb-21) Opt 4: RAN5#93 (Nov-21) Opt 7: FFS | R5-185332 R5-192689 R5-211698 R5-210944 R5-211872 | Pending ongoing RAN4 discussion on minimum requirement | 1 | 86.67% | [5 empty] | 11 | 100% |  |  | 1 | 80% |  |  | 1 | 80%
50 | Y | 38.521-3 | 6.2B.4.1.2 | Configured output power level for intra-band non-contiguous EN-DC |  | Huawei | Opt 3: RAN5#90 (Feb-21) Opt 4: RAN5#93 (Nov-21) Opt 7: FFS | R5-185333 R5-192690 R5-211698 R5-210944 | Pending ongoing RAN4 discussion on minimum requirement | 1 | 86.67% | [5 empty] | 11 | 100% |  |  | 1 | 80% |  |  | 1 | 80%
51 | Y | 38.521-3 | 6.2B.4.1.3 | Configured Output power level for inter-band EN-DC within FR1 |  | Huawei | Opt 3: RAN5#90 (Feb-21) | R5-185507 R5-192443 R5-211698 R5-210944 |  | 1 | 100% | [5 empty] | 11 | 100%
52 | Y | 38.521-3 | 6.2B.4.1.3A | Configured Output power level for inter-band NE-DC within FR1 |  |  | Opt 4: RAN5#93 (Nov-21) Opt 7: FFS |  |  | 1 | 0% | [9 empty] | 1 | 0% |  |  | 1 | 0%
53 | Y | 38.521-3 | 6.2B.4.1.4 | Configured Output power level for inter-band EN-DC including FR2 (1 NR CC) |  | Huawei | Opt 3: RAN5#93 (Nov-21) MU: RAN5#93 (Aug-21) TT: RAN5#93 (Aug-21) | R5-185198 | No test point defined in 38.521-2 | 1 | 60% | [5 empty] | 14MT3 |  | 60%
54 |  | 38.521-3 | 6.2B.4.1.5 | Configured Output Power for Inter-Band EN-DC including both FR1 and FR2 |  | Huawei | Opt 3: - Opt 4: RAN5#93 (Nov-21) Opt 7: FFS | R5-185199 | Min conf requirements are updated in core spec. Editor's note to be re-visited | 0.4 | 100% | [5 empty] | 6MT3 |  |  | 100% | 1 |  |  | 100% | 1 | 100%
|  | 38.521-3 | 6.2B.4.2 | ΔTIB,c for EN-DC |  |  |  | R5-184580
55 |  | 38.521-3 | 6.2B.4.2.1 | ΔTIB,c for Intra-band contiguous EN-DC |  | Bureau Veritas | Opt 3: RAN5#84 (Aug-19) Opt 4: RAN5#93 (Nov-21) Opt 7: FFS |  | Not Applicable as per core spec | 0.1 | 100% | [5 empty] | 5 | 100% |  |  | 1 | 100% |  |  | 1 | 100%
56 |  | 38.521-3 | 6.2B.4.2.2 | ΔTIB,c for Intra-band non-contiguous EN-DC |  | Bureau Veritas | Opt 3: RAN5#84 (Aug-19) Opt 4: RAN5#93 (Nov-21) Opt 7: FFS |  | Not Applicable as per core spec | 0.1 | 100% | [5 empty] | 5 | 100% |  |  | 1 | 100% |  |  | 1 | 100%
57 |  | 38.521-3 | 6.2B.4.2.3 | ΔTIB,c for Inter-band EN-DC within FR1 |  | Bureau Veritas | Opt 3: RAN5#93 (Nov-21) | R5-184580 | Correct 3GPP style for 2bands and 3 bands so it appears on navigation pane | 0.5 | 90% | [5 empty] | 14 | 90%
58 |  | 38.521-3 | 6.2B.4.2.3A | ΔTIB,c for Inter-band NE-DC within FR1 |  |  | Opt 4: RAN5#93 (Nov-21) Opt 7: FFS |  |  | 1 | 0% | [9 empty] | 1 | 0% |  |  | 1 | 0%
59 |  | 38.521-3 | 6.2B.4.2.4 | ΔTIB,c for Inter-band EN-DC including FR2 |  | Bureau Veritas | Opt 3: RAN5#93 (Nov-21) MU: RAN5#93 (Aug-21) TT: RAN5#93 (Aug-21) | R5-184580 |  | 0.5 | 50% | [5 empty] | 14MT3 |  | 50%
60 |  | 38.521-3 | 6.2B.4.2.5 | ΔTIB,c for Inter-band EN-DC including both FR1 and FR2 |  | Bureau Veritas | Opt 3: RAN5#93 (Nov-21) MU: RAN5#93 (Aug-21) TT: RAN5#93 (Aug-21) |  |  | 0.4 | 0% | [5 empty] | 14MT3 |  |  | 0%
|  | 38.521-3 | 6.2B.5 | Configured Output Power for NR-DC
|  | 38.521-3 | 6.2B.5.1 | Configured Output power Level
61 |  | 38.521-3 | 6.2B.5.1.1 | Configured Output Power Level for Inter-band NR-DC between FR1 and FR2 |  | Huawei | Opt 2: RAN5#87 (May-20) | R5-202830 | Core Requirements and band combinations were added for NR-NR DC. To be completed at RAN5#84 | 0.4 | 100% | 7 |  |  | 100%
|  | 38.521-3 | 6.3 | Output power dynamics
|  | 38.521-3 | 6.3A | Output Power Dynamics for CA without EN-DC
|  | 38.521-3 | 6.3B | Output power dynamics for DC |  |  |  |  | Add title for completeness
|  | 38.521-3 | 6.3B.1 | Minimum Output Power for EN-DC
62 | Y | 38.521-3 | 6.3B.1.1 | Minimum Output power for intra-band contiguous EN-DC |  | SGS Wireless | Opt 3: RAN5#84 (Aug-19) Opt 4: RAN5#93 (Nov-21) Opt 7: FFS | R5-185206 | Working assumption note can be removed. MU/TT can now be completed as SA test is complete and anchor-agnostic is applied per test contents here. | 1 | 100% | [5 empty] | 5 | 100% |  |  | 1 | 100% |  |  | 1 | 100%
63 | Y | 38.521-3 | 6.3B.1.2 | Minimum output power for intra-band non-contiguous EN-DC |  | SGS Wireless | Opt 3: RAN5#84 (Aug-19) Opt 4: RAN5#93 (Nov-21) Opt 7: FFS | R5-185207 | SA reqs should apply per Core spec. Editor's note to be reviewed and test completed | 1 | 100% | [5 empty] | 5 | 100% |  |  | 1 | 100% |  |  | 1 | 100%
64 | Y | 38.521-3 | 6.3B.1.3 | Minimum output power for inter-band EN-DC within FR1 (1 NR CC) |  | SGS Wireless | Opt 3: RAN5#80 (Aug-18) Opt 4: RAN5#93 (Nov-21) Opt 7: FFS | R5-185208 |  | 1 | 100% | [5 empty] | 1.5 | 100% |  |  | 1 | 100% |  |  | 1 | 100%
65 | Y | 38.521-3 | 6.3B.1.4 | Minimum output power for inter-band EN-DC including FR2 (1 NR CC) |  | SGS Wireless | Opt 3: RAN5#89 (Nov-20) MU: RAN5#89 (Nov-20)) TT: RAN5#89 (Nov-20) | R5-192459 |  | 1 | 100% | [5 empty] | 10MT3 |  | 100%
|  | 38.521-3 | 6.3B.1.4_1 | Minimum output power for inter-band EN-DC including FR2 (>1 NR CC)
66 |  | 38.521-3 | 6.3B.1.4_1.1 | Minimum output power for inter-band EN-DC including FR2 (2 NR CCs) |  |  |  |  | Placeholder for TC numbering structure. Status tracked in Rel16 WP. | 0
67 |  | 38.521-3 | 6.3B.1.4_1.2 | Minimum output power for inter-band EN-DC including FR2 (3 NR CCs) |  |  |  |  | Placeholder for TC numbering structure. Status tracked in Rel16 WP. | 0
68 |  | 38.521-3 | 6.3B.1.4_1.3 | Minimum output power for inter-band EN-DC including FR2 (4 NR CCs) |  |  |  |  | Placeholder for TC numbering structure. Status tracked in Rel16 WP. | 0
69 | Y | 38.521-3 | 6.3B.1.4D | Minimum output power for inter-band EN-DC including FR2 for UL MIMO |  | SGS Wireless | Opt 3: RAN5#93 (Nov-21) MU: RAN5#93 (Aug-21) TT: RAN5#93 (Aug-21) Opt 4: RAN5#93 (Nov-21) Opt 7: FFS |  | Refers back to SA UL-MIMO test. Anchor-agnostic. | 1 | 90% | [5 empty] | 14MT1 |  | 90% |  | 1 |  | 90% |  | 1 | 90%
|  | 38.521-3 | 6.3B.2 | Transmit OFF Power for EN-DC |  |  | Opt 4: RAN5#93 (Nov-21) |  |  |  | 0% | [9 empty] | 1 |  | 0%
70 | Y | 38.521-3 | 6.3B.2.1 | Transmit OFF Power for intra-band contiguous EN-DC |  | SGS Wireless | Opt 3: RAN5#84 (Aug-19) Opt 4: RAN5#93 (Nov-21) Opt 7: FFS | R5-186296 |  | 1 | 100% | [5 empty] | 5 | 100% |  |  | 1 | 100% |  |  | 1 | 100%
71 | Y | 38.521-3 | 6.3B.2.2 | Transmit OFF Power for intra-band non-contiguous EN-DC |  | SGS Wireless | Opt 3: RAN5#84 (Aug-19) Opt 4: RAN5#93 (Nov-21) Opt 7: FFS | R5-186301 |  | 1 | 100% | [5 empty] | 5 | 100% |  |  | 1 | 100% |  |  | 1 | 100%
72 | Y | 38.521-3 | 6.3B.2.3 | Transmit OFF Power for inter-band EN-DC within FR1 |  | SGS Wireless | Opt 3: RAN5#84 (Aug-19) Opt 4: RAN5#93 (Nov-21) Opt 7: FFS | R5-186297 |  | 1 | 100% | [5 empty] | 5 | 100% |  |  | 1 | 100% |  |  | 1 | 100%
73 | Y | 38.521-3 | 6.3B.2.4 | Transmit OFF Power for inter-band EN-DC including FR2 (1 NR CC) |  | SGS Wireless | Opt 3: RAN5#88 (Aug-20) MU: RAN5#88 (Aug-20) TT: RAN5#88 (Aug-20) Opt 4: RAN5#93 (Nov-21) Opt 7: FFS |  |  | 1 | 100% | [5 empty] | 9MT2 |  | 100% |  | 1 |  | 100% |  | 1 | 100%
|  | 38.521-3 | 6.3B.2.4_1 | Transmit OFF Power for inter-band EN-DC including FR2 (>2 CCs) | Header
74 |  | 38.521-3 | 6.3B.2.4_1.1 | Transmit OFF Power for inter-band EN-DC including FR2 (3 CCs) |  |  |  | R5-211099 | Placeholder for TC numbering structure. Status tracked in Rel16 WP. | 0
75 |  | 38.521-3 | 6.3B.2.4_1.2 | Transmit OFF Power for inter-band EN-DC including FR2 (4 CCs) |  |  |  |  | Placeholder for TC numbering structure. Status tracked in Rel16 WP. | 0
76 |  | 38.521-3 | 6.3B.2.4_1.3 | Transmit OFF Power for inter-band EN-DC including FR2 (5 CCs) |  |  |  |  | Placeholder for TC numbering structure. Status tracked in Rel16 WP. | 0
77 | Y | 38.521-3 | 6.3B.2.4D | Transmit OFF Power for inter-band EN-DC including FR2 for UL-MIMO |  | SGS Wireless | Opt 3: RAN5#93 (Nov-21) MU: RAN5#93 (Aug-21) TT: RAN5#93 (Aug-21) Opt 4: RAN5#93 (Nov-21) Opt 7: FFS | R5-215882 | Refers back to SA UL-MIMO test. Anchor-agnostic. The referred test case 6.3D.2 in TS 38.521-2 is incomplete | 1 | 30% | [5 empty] | 14MT1 |  | 90% |  | 1 |  | 0% |  | 1 | 0%
|  | 38.521-3 | 6.3B.3 | Tx ON/OFF time mask/PUCCH time mask for EN-DC
78 | Y | 38.521-3 | 6.3B.3.1 | Tx ON/OFF time mask for intra-band contiguous EN-DC |  | SGS Wireless | Opt 3: RAN5#81 (Nov-18) Opt 4: RAN5#93 (Nov-21) Opt 7: FFS | R5-188020 |  | 1 | 100% | [5 empty] | 2 | 100% |  |  | 1 | 100% |  |  | 1 | 100%
79 | Y | 38.521-3 | 6.3B.3.2 | Tx ON/OFF time mask for intra-band non-contiguous EN-DC |  | SGS Wireless | Opt 3: RAN5#81 (Nov-18) Opt 4: RAN5#93 (Nov-21) Opt 7: FFS | R5-188021 |  | 1 | 100% | [5 empty] | 2 | 100% |  |  | 1 | 100% |  |  | 1 | 100%
80 | Y | 38.521-3 | 6.3B.3.3 | Tx ON/OFF time mask for inter-band EN-DC within FR1 (1 NR CC) |  | SGS Wireless | Opt 3: RAN5#81 (Nov-18) Opt 4: RAN5#93 (Nov-21) Opt 7: FFS | R5-188022 |  | 1 | 100% | [5 empty] | 2 | 100% |  |  | 1 | 100% |  |  | 1 | 100%
81 | Y | 38.521-3 | 6.3B.3.4 | Tx ON/OFF time mask for inter-band EN-DC including FR2 (1 NR CC) |  | SGS Wireless | Opt 3: RAN5#93 (Nov-21) MU: RAN5#93 (Aug-21) TT: RAN5#93 (Aug-21) Opt 4: RAN5#93 (Nov-21) Opt 7: FFS |  | The referred test case 6.3.3.2 in TS 38.521-2 is incomplete | 1 | 83.33% | [5 empty] | 14MT3 |  | 90% |  | 1 |  | 90% |  | 1 | 70%
|  | 38.521-3 | 6.3B.3.4_1 | Tx ON/OFF time mask for inter-band EN-DC including FR2 (>2 CCs)
82 |  | 38.521-3 | 6.3B.3.4_1.1 | Tx ON/OFF time mask for inter-band EN-DC including FR2 (3 CCs) |  |  |  |  | Placeholder for TC numbering structure. Status tracked in Rel16 WP. | 0
83 |  | 38.521-3 | 6.3B.3.4_1.2 | Tx ON/OFF time mask for inter-band EN-DC including FR2 (4 CCs) |  |  |  |  | Placeholder for TC numbering structure. Status tracked in Rel16 WP. | 0
84 |  | 38.521-3 | 6.3B.3.4_1.3 | Tx ON/OFF time mask for inter-band EN-DC including FR2 (5 CCs) |  |  |  |  | Placeholder for TC numbering structure. Status tracked in Rel16 WP. | 0
85 | Y | 38.521-3 | 6.3B.3.4D | Tx ON/OFF time mask for inter-band EN-DC including FR2 for UL-MIMO |  | SGS Wireless | Opt 3: RAN5#93 (Nov-21) MU: RAN5#93 (Aug-21) TT: RAN5#93 (Aug-21) Opt 4: RAN5#93 (Nov-21) Opt 7: FFS | R5-215883 | Refers back to SA UL-MIMO test. Anchor-agnostic. The referred test case 6.3D.3 in TS 38.521-2 is incomplete | 1 | 30% | [5 empty] | 14MT1 |  | 90% |  | 1 |  | 0% |  | 1 | 0%
|  |  | 6.3B.4 | PRACH Time Mask for EN-DC |  |  |  |  | move Editor's note within .1
86 | Y | 38.521-3 | 6.3B.4.1 | PRACH Time Mask for intra-band contiguous EN-DC |  | SGS Wireless | Opt 3: RAN5#83 (May-19) Opt 4: RAN5#93 (Nov-21) Opt 7: FFS | R5-192600 R5-194948 |  | 1 | 100% | [5 empty] | 4 | 100% |  |  | 1 | 100% |  |  | 1 | 100%
87 | Y | 38.521-3 | 6.3B.4.2 | PRACH Time Mask for intra-band non-contiguous EN-DC |  | SGS Wireless | Opt 3: RAN5#83 (May-19) Opt 4: RAN5#93 (Nov-21) Opt 7: FFS | R5-192601 R5-194949 |  | 1 | 100% | [5 empty] | 4 | 100% |  |  | 1 | 100% |  |  | 1 | 100%
88 | Y | 38.521-3 | 6.3B.4.3 | PRACH Time Mask for inter-band EN-DC within FR1 (1 NR CC) |  | SGS Wireless | Opt 3: RAN5#83 (May-19) Opt 4: RAN5#93 (Nov-21) Opt 7: FFS | R5-192442 R5-195950 |  | 1 | 100% | [5 empty] | 4 | 100% |  |  | 1 | 100% |  |  | 1 | 100%
89 | Y | 38.521-3 | 6.3B.4.4 | PRACH Time Mask for inter-band EN-DC including FR2 |  | SGS Wireless | Opt 3: RAN5#93 (Nov-21) MU: RAN5#93 (Aug-21) TT: RAN5#93 (Aug-21) Opt 4: RAN5#93 (Nov-21) Opt 7: FFS | R5-215884 | The referred test case 6.3.3.4 in TS 38.521-2 is incomplete | 1 | 30% | [5 empty] | 14MT3 |  | 90% |  | 1 |  | 0% |  | 1 | 0%
|  | 38.521-3 | 6.3B.4.4_1 | PRACH Time Mask for inter-band EN-DC including FR2 (>2 CCs)
90 |  | 38.521-3 | 6.3B.4.4_1.1 | PRACH Time Mask for inter-band EN-DC including FR2 (3 CCs) |  |  |  |  | Placeholder for TC numbering structure. Status tracked in Rel16 WP. | 0
91 |  | 38.521-3 | 6.3B.4.4_1.2 | PRACH Time Mask for inter-band EN-DC including FR2 (4 CCs) |  |  |  |  | Placeholder for TC numbering structure. Status tracked in Rel16 WP. | 0
92 |  | 38.521-3 | 6.3B.4.4_1.3 | PRACH Time Mask for inter-band EN-DC including FR2 (5 CCs) |  |  |  |  | Placeholder for TC numbering structure. Status tracked in Rel16 WP. | 0
93 | Y | 38.521-3 | 6.3B.4.4D | PRACH time mask for inter-band EN-DC including FR2 for UL-MIMO |  | SGS Wireless | Opt 3: RAN5#93 (Nov-21) MU: RAN5#93 (Aug-21) TT: RAN5#93 (Aug-21) Opt 4: RAN5#93 (Nov-21) Opt 7: FFS |  | Refers back to SA UL-MIMO test. Anchor-agnostic. | 1 | 0% | [5 empty] | 14MT1 |  | 0% |  | 1 |  | 0% |  | 1 | 0%
|  |  | 6.3B.5 | Output power dynamics for EN-DC with UL sharing from UE perspective
94 |  | 38.521-3 | 6.3B.5.1 | E-UTRA and NR switching time mask for TDM based UL sharing from UE perspective |  | SGS Wireless | Opt 3: RAN5#83 (May-19) Opt 4: RAN5#93 (Nov-21) Opt 7: FFS | R5-195091 | ON_ON not tested. No test case details added | 0.3 | 100% | [5 empty] | 4 | 100% |  |  | 1 | 100% |  |  | 1 | 100%
|  |  | 6.3B.6 | Output power dynamics for intra-band EN-DC without dual PA capability
95 |  | 38.521-3 | 6.3B.6.1 | E-UTRA to NR and NR to E-UTRA Switching time mask for intra-band non-contiguous scenario |  | SGS Wireless | Opt 3: RAN5#83 (May-19) Opt 4: RAN5#93 (Nov-21) Opt 7: FFS | R5-195091 | ON_ON not tested. No test case details added | 0.3 | 100% | [5 empty] | 4 | 100% |  |  | 1 | 100% |  |  | 1 | 100%
|  |  | 6.3B.7 | Output power dynamics for intra-band EN-DC with dual PA capability |  | Huawei | Opt 3: RAN5#83 (May-19) Opt 4: RAN5#93 (Nov-21) Opt 7: FFS |  | Not testable. No test case details added | 0.3 | 100% | [5 empty] | 4 | 100% |  |  | 1 | 100% |  |  | 1 | 100%
|  |  | 6.3B.8 | Power Control for EN-DC
|  |  | 6.3B.8.1 | Absolute Power Tolerance for EN-DC
96 | Y | 38.521-3 | 6.3B.8.1.1 | Absolute Power Tolerance for intra-band contiguous EN-DC |  | Samsung | Opt 3: RAN5#87 (May-20) Opt 4: RAN5#93 (Nov-21) Opt 7: FFS | R5-202901 |  | 1 | 100% | [5 empty] | 8 | 100% |  |  | 1 | 100% |  |  | 1 | 100%
97 | Y | 38.521-3 | 6.3B.8.1.2 | Absolute Power Tolerance for intra-band non-contiguous EN-DC |  | Samsung | Opt 3: RAN5#87 (May-20) Opt 4: RAN5#93 (Nov-21) Opt 7: FFS | R5-202901 |  | 1 | 100% | [5 empty] | 8 | 100% |  |  | 1 | 100% |  |  | 1 | 100%
98 | Y | 38.521-3 | 6.3B.8.1.3 | Absolute Power Tolerance for inter-band EN-DC within FR1 (1 NR CC) |  | Samsung | Opt 3: RAN5#87 (May-20) Opt 4: RAN5#93 (Nov-21) Opt 7: FFS | R5-202901 |  | 1 | 100% | [5 empty] | 8 | 100% |  |  | 1 | 100% |  |  | 1 | 100%
99 | Y | 38.521-3 | 6.3B.8.1.4 | Absolute Power Tolerance for inter-band EN-DC including FR2 (1 NR CC) |  | Samsung | Opt 3: RAN5#93 (Nov-21) MU: RAN5#93 (Aug-21) TT: RAN5#93 (Aug-21) | R5-202901 R5-210117 R5-210498 | The referred test case 6.3.4.2 in TS 38.521-2 [9] is incomplete | 1 | 70% | [5 empty] | 14MT3 |  | 70%
|  |  | 6.3B.8.2 | Relative Power Tolerance for EN-DC
100 | Y | 38.521-3 | 6.3B.8.2.1 | Relative Power Tolerance for intra-band contiguous EN-DC |  | Samsung | Opt 3: RAN5#87 (May-20) Opt 4: RAN5#93 (Nov-21) Opt 7: FFS | R5-202901 |  | 1 | 100% | [5 empty] | 8 | 100% |  |  | 1 | 100% |  |  | 1 | 100%
101 | Y | 38.521-3 | 6.3B.8.2.2 | Relative Power Tolerance for intra-band non-contiguous EN-DC |  | Samsung | Opt 3: RAN5#87 (May-20) Opt 4: RAN5#93 (Nov-21) Opt 7: FFS | R5-202901 |  | 1 | 100% | [5 empty] | 8 | 100% |  |  | 1 | 100% |  |  | 1 | 100%
102 | Y | 38.521-3 | 6.3B.8.2.3 | Relative Power Tolerance for inter-band EN-DC within FR1 (1 NR CC) |  | Samsung | Opt 3: RAN5#87 (May-20) Opt 4: RAN5#93 (Nov-21) Opt 7: FFS | R5-202901 |  | 1 | 100% | [5 empty] | 8 | 100% |  |  | 1 | 100% |  |  | 1 | 100%
103 | Y | 38.521-3 | 6.3B.8.2.4 | Relative Power Tolerance for inter-band EN-DC including FR2 (1 NR CC) |  | Samsung | Opt 3: RAN5#93 (Nov-21) MU: RAN5#93 (Aug-21) TT: RAN5#93 (Aug-21) | R5-202901 R5-210117 R5-210498 | The referred test case 6.3.4.2 in TS 38.521-2 [9] is incomplete | 1 | 70% | [5 empty] | 14MT3 |  | 70%
|  |  | 6.3B.8.3 | Aggregate Power Tolerance for EN-DC
104 | Y | 38.521-3 | 6.3B.8.3.1 | Aggregate Power Tolerance for intra-band contiguous EN-DC |  | Samsung | Opt 3: RAN5#87 (May-20) Opt 4: RAN5#93 (Nov-21) Opt 7: FFS | R5-202901 |  | 1 | 100% | [5 empty] | 8 | 100% |  |  | 1 | 100% |  |  | 1 | 100%
105 | Y | 38.521-3 | 6.3B.8.3.2 | Aggregate Power Tolerance for intra-band non-contiguous EN-DC |  | Samsung | Opt 3: RAN5#87 (May-20) Opt 4: RAN5#93 (Nov-21) Opt 7: FFS | R5-202901 |  | 1 | 100% | [5 empty] | 8 | 100% |  |  | 1 | 100% |  |  | 1 | 100%
106 | Y | 38.521-3 | 6.3B.8.3.3 | Aggregate Power Tolerance for inter-band EN-DC within FR1 (1 NR CC) |  | Samsung | Opt 3: RAN5#87 (May-20) Opt 4: RAN5#93 (Nov-21) Opt 7: FFS | R5-202901 |  | 1 | 100% | [5 empty] | 8 | 100% |  |  | 1 | 100% |  |  | 1 | 100%
107 | Y | 38.521-3 | 6.3B.8.3.4 | Aggregate Power Tolerance for inter-band EN-DC including FR2 (1 NR CC) |  | Samsung | Opt 3: RAN5#93 (Nov-21) MU: RAN5#93 (Aug-21) TT: RAN5#93 (Aug-21) | R5-202901 R5-210117 R5-210498 | The referred test case 6.3.4.2 in TS 38.521-2 [9] is incomplete | 1 | 70% | [5 empty] | 14MT3 |  | 70%
|  | 38.521-3 | 6.4 | Transmit signal quality
|  | 38.521-3 | 6.4A | Transmit Signal Quality for inter-band NR CA between FR and FR2 without EN-DC
108 |  | 38.521-3 | 6.4A.1 | Frequency error for inter-band NR CA between FR 1 and FR 2 without EN-DC |  | SGS Wireless | Opt 2: RAN5#86 (Feb-20) | R5-194947 | FR1+FR2 Testability. No TC details added | 0.4 | 100% | 6 |  |  | 100%
|  | 38.521-3 | 6.4A.2 | Transmit Modulation Quality for inter-band NR CA without EN-DC
109 |  | 38.521-3 | 6.4A.2.1 | Error Vector Magnitude for inter-band NR CA between FR 1 and FR 2 without EN-DC |  | SGS Wireless | Opt 2: RAN5#85 (Nov-19) | R5-194947 | FR1+FR2 Testability. No TC details added | 0.4 | 100% | 5 |  |  | 100% | 1
110 |  | 38.521-3 | 6.4A.2.2 | Carrier Leakage for inter-band NR CA between FR 1 and FR 2 without EN-DC |  | SGS Wireless | Opt 2: RAN5#84 (Aug-19) | R5-194947 | FR1+FR2 Testability. No TC details added | 0.4 | 100% | 4 |  |  | 100% | 1
111 |  | 38.521-3 | 6.4A.2.3 | In-band Emissions for inter-band NR CA between FR 1 and FR 2 without EN-DC |  | SGS Wireless | Opt 2: RAN5#84 (Aug-19) | R5-194947 | FR1+FR2 Testability. No TC details added | 0.4 | 100% | 4 |  |  | 100% | 1
112 |  | 38.521-3 | 6.4A.2.4 | EVM Equalizer Spectral Flatness for inter-band NR CA between FR 1 and FR 2 without EN-DC |  | SGS Wireless | Opt 2: RAN5#84 (Aug-19) | R5-194947 | FR1+FR2 Testability. No TC details added | 0.4 | 100% | 4 |  |  | 100% | 1
|  | 38.521-3 | 6.4B | Transmit Signal Quality for DC
|  | 38.521-3 | 6.4B.1 | Frequency Error for DC
113 | Y | 38.521-3 | 6.4B.1.1 | Frequency Error for intra-band contiguous EN-DC |  | SGS Wireless | Opt 3: RAN5#84 (Aug-19) Opt 4: RAN5#93 (Nov-21) Opt 7: FFS |  |  | 1 | 100% | [5 empty] | 5 | 100% |  |  | 1 | 100% |  |  | 1 | 100%
114 | Y | 38.521-3 | 6.4B.1.2 | Frequency Error for intra-band non-contiguous EN-DC |  | SGS Wireless | Opt 3: RAN5#84 (Aug-19) Opt 4: RAN5#93 (Nov-21) Opt 7: FFS |  |  | 1 | 100% | [5 empty] | 5 | 100% |  |  | 1 | 100% |  |  | 1 | 100%
115 | Y | 38.521-3 | 6.4B.1.3 | Frequency Error for inter-band EN-DC within FR1 (1 NR CC) |  | SGS Wireless | Opt 3: RAN5#84 (Aug-19) |  |  | 1 | 100% | [5 empty] | 5 | 100%
116 | Y | 38.521-3 | 6.4B.1.3A | Frequency Error for inter-band NE-DC within FR1 |  | CMCC | Opt 4: RAN5#93 (Nov-21) Opt 7: FFS | R5-215871 |  | 1 | 100% | [9 empty] | 1 | 100% |  |  | 1 | 100%
117 | Y | 38.521-3 | 6.4B.1.4 | Frequency Error for inter-band EN-DC including FR2 (1 NR CC) |  | SGS Wireless | Opt 3: RAN5#83 (May-19) MU: RAN5#84 (Aug-19) TT: RAN5#84 (Aug-19) Opt 4: RAN5#93 (Nov-21) Opt 7: FFS | R5-192454 R5-195411 | Update TC# | 1 | 100% | [5 empty] | 4MT3 |  | 100% |  | 1 |  | 100% |  | 1 | 100%
|  |  | 6.4B.1.4_1 | Frequency Error for inter-band EN-DC including FR2 ((>1 NR CC)
118 |  | 38.521-3 | 6.4B.1.4_1.1 | Frequency Error for inter-band EN-DC including FR2 (2 NR CCs) |  |  |  | R5-211697 | Placeholder for TC numbering structure. Status tracked in Rel16 WP. | 0
119 |  | 38.521-3 | 6.4B.1.4_1.2 | Frequency Error for inter-band EN-DC including FR2 (3 NR CCs) |  |  |  | R5-211697 | Placeholder for TC numbering structure. Status tracked in Rel16 WP. | 0
120 |  | 38.521-3 | 6.4B.1.4_1.3 | Frequency Error for inter-band EN-DC including FR2 (4 NR CCs) |  |  |  | R5-211697 | Placeholder for TC numbering structure. Status tracked in Rel16 WP. | 0
121 | Y | 38.521-3 | 6.4B.1.4D | Frequency error for inter-band EN-DC including FR2 for UL-MIMO |  | SGS Wireless | Opt 3: RAN5#93 (Nov-21) MU: RAN5#93 (Aug-21) TT: RAN5#93 (Aug-21) |  | Refers back to SA UL-MIMO test. Anchor-agnostic. | 1 | 0% | [5 empty] | 14MT3 |  | 0%
122 |  | 38.521-3 | 6.4B.1.5D | Frequency error for inter-band EN-DC including both FR1 and FR2 for UL-MIMO |  | SGS Wireless | Opt 3: RAN5#93 (Nov-21) MU: RAN5#93 (Aug-21) TT: RAN5#93 (Aug-21) |  | FR1+FR2 Testability. Basic text to add..No TC details needed. | 0.4 | 0% | [5 empty] | 14MT3 |  |  | 0%
|  | 38.521-3 | 6.4B.2 | Transmit Modulation Quality DC |  |  |  |  | Add title for completeness
|  | 38.521-3 | 6.4B.2.1 | Transmit Modulation Quality for intra-band contiguous EN-DC
123 | Y | 38.521-3 | 6.4B.2.1.1 | Error Vector Magnitude for intra-band contiguous EN-DC |  | LGE | Opt 3: RAN5#82 (Feb-19) Opt 4: RAN5#93 (Nov-21) Opt 7: FFS | R5-187828 R5-192608 |  | 1 | 100% | [5 empty] | 3 | 100% |  |  | 1 | 100% |  |  | 1 | 100%
124 | Y | 38.521-3 | 6.4B.2.1.2 | Carrier Leakage for intra-band contiguous EN-DC |  | LGE | Opt 3: RAN5#82 (Feb-19) Opt 4: RAN5#93 (Nov-21) Opt 7: FFS | R5-187829 R5-192607 R5-194400 |  | 1 | 100% | [5 empty] | 3 | 100% |  |  | 1 | 100% |  |  | 1 | 100%
125 | Y | 38.521-3 | 6.4B.2.1.3 | In-band Emissions for intra-band contiguous EN-DC |  | LGE | Opt 3: RAN5#83 (May-19) Opt 4: RAN5#93 (Nov-21) Opt 7: FFS | R5-188019 R5-192609 R5-194400 |  | 1 | 100% | [5 empty] | 4 | 100% |  |  | 1 | 100% |  |  | 1 | 100%
126 | Y | 38.521-3 | 6.4B.2.1.4 | EVM Equalizer Flatness for intra-band contiguous EN-DC |  | LGE | Opt 3: RAN5#85 (Nov-19) Opt 4: RAN5#93 (Nov-21) Opt 7: FFS |  |  | 1 | 100% | [5 empty] | 6 | 100% |  |  | 1 | 100% |  |  | 1 | 100%
|  | 38.521-3 | 6.4B.2.2 | Transmit Modulation Quality for intra-band non-contiguous EN-DC
127 | Y | 38.521-3 | 6.4B.2.2.1 | Error Vector Magnitude for intra-band non-contiguous EN-DC |  | KTL | Opt 3: RAN5#84 (Aug-19) Opt 4: RAN5#93 (Nov-21) Opt 7: FFS | R5-187822 |  | 1 | 100% | [5 empty] | 5 | 100% |  |  | 1 | 100% |  |  | 1 | 100%
128 | Y | 38.521-3 | 6.4B.2.2.2 | Carrier Leakage for intra-band non-contiguous EN-DC |  | KTL | Opt 3: RAN5#81 (Nov-18) Opt 4: RAN5#93 (Nov-21) Opt 7: FFS | R5-187823 |  | 1 | 100% | [5 empty] | 2 | 100% |  |  | 1 | 100% |  |  | 1 | 100%
129 | Y | 38.521-3 | 6.4B.2.2.3 | In-band Emissions for intra-band non-contiguous EN-DC |  | KTL | Opt 3: RAN5#84 (Aug-19) Opt 4: RAN5#93 (Nov-21) Opt 7: FFS | R5-188012 |  | 1 | 100% | [5 empty] | 5 | 100% |  |  | 1 | 100% |  |  | 1 | 100%
130 | Y | 38.521-3 | 6.4B.2.2.4 | EVM Equalizer Flatness for intra-band non contiguous EN-DC |  | KTL | Opt 3: RAN5#83 (May-19) Opt 4: RAN5#93 (Nov-21) Opt 7: FFS | R5-195162 |  | 1 | 100% | [5 empty] | 4 | 100% |  |  | 1 | 100% |  |  | 1 | 100%
|  | 38.521-3 | 6.4B.2.3 | Transmit Modulation Quality for inter-band EN-DC within FR1
131 | Y | 38.521-3 | 6.4B.2.3.1 | Error Vector Magnitude for inter-band EN-DC within FR1 (1 NR CC) |  | KTL | Opt 3: RAN5#81 (Nov-18) | R5-187825 |  | 1 | 100% | [5 empty] | 2 | 100%
132 | Y | 38.521-3 | 6.4B.2.3.2 | Carrier Leakage for inter-band EN-DC within FR1 (1 NR CC) |  | KTL | Opt 3: RAN5#81 (Nov-18) | R5-187826 |  | 1 | 100% | [5 empty] | 2 | 100%
133 | Y | 38.521-3 | 6.4B.2.3.3 | In-band Emissions for inter-band EN-DC within FR1 (1 NR CC) |  | KTL | Opt 3: RAN5#81 (Nov-18) | R5-187827 |  | 1 | 100% | [5 empty] | 2 | 100%
134 | Y | 38.521-3 | 6.4B.2.3.4 | EVM Equalizer Flatness for inter-band EN-DC within FR1 (1 NR CC) |  | KTL | Opt 3: RAN5#83 (May-19) | R5-194941 |  | 1 | 100% | [5 empty] | 4 | 100%
|  | 38.521-3 | 6.4B.2.3A | Transmit Modulation Quality for inter-band NE-DC within FR1
135 | Y | 38.521-3 | 6.4B.2.3A.1 | Error Vector Magnitude for inter-band NE-DC within FR1 |  | CMCC | Opt 4: RAN5#93 (Nov-21) Opt 7: FFS | R5-215872 |  | 1 | 50% | [9 empty] | 1 | 100% |  |  | 1 | 0%
136 | Y | 38.521-3 | 6.4B.2.3A.2 | Carrier Leakage for inter-band NE-DC within FR1 |  | CMCC | Opt 4: RAN5#93 (Nov-21) Opt 7: FFS | R5-215873 |  | 1 | 50% | [9 empty] | 1 | 100% |  |  | 1 | 0%
137 | Y | 38.521-3 | 6.4B.2.3A.3 | In-band Emissions for inter-band NE-DC within FR1 |  | CMCC | Opt 4: RAN5#93 (Nov-21) Opt 7: FFS | R5-215874 |  | 1 | 50% | [9 empty] | 1 | 100% |  |  | 1 | 0%
138 | Y | 38.521-3 | 6.4B.2.3A.4 | EVM Equalizer Flatness for inter-band NE-DC within FR1 |  |  | Opt 4: RAN5#93 (Nov-21) Opt 7: FFS |  | Currently out of scope per RAN5 leadership. Needs support from interested companies | 1 | 0% | [9 empty] | 1 | 0% |  |  | 1 | 0%
|  | 38.521-3 | 6.4B.2.4 | Transmit Modulation Quality for inter-band EN-DC including FR2
139 | Y | 38.521-3 | 6.4B.2.4.1 | Error Vector Magnitude for inter-band EN-DC including FR2 (1 NR CC) |  | Rohde&Schwarz | Opt 3: RAN5#93 (Nov-21) MU: RAN5#93 (Aug-21) TT: RAN5#93 (Aug-21) | R5-192455 R5-193315 | The referred test case 6.4.2.1 in TS 38.521-2 is incomplete | 1 | 70% | [5 empty] | 14MT3 |  | 70%
|  | 38.521-3 | 6.4B.2.4.1_1 | Error Vector Magnitude for inter-band EN-DC including FR2 ((>1 NR CC)
140 |  | 38.521-3 | 6.4B.2.4.1_1.1 | Error Vector Magnitude for inter-band EN-DC including FR2 (2 NR CCs) |  |  |  |  | Placeholder for TC numbering structure. Status tracked in Rel16 WP. | 0
141 |  | 38.521-3 | 6.4B.2.4.1_1.2 | Error Vector Magnitude for inter-band EN-DC including FR2 (3 NR CCs) |  |  |  |  | Placeholder for TC numbering structure. Status tracked in Rel16 WP. | 0
142 |  | 38.521-3 | 6.4B.2.4.1_1.3 | Error Vector Magnitude for inter-band EN-DC including FR2 (4 NR CCs) |  |  |  |  | Placeholder for TC numbering structure. Status tracked in Rel16 WP. | 0
143 | Y | 38.521-3 | 6.4B.2.4.1D | Error Vector Magnitude for inter-band EN-DC including FR2 for UL MIMO |  | Rohde&Schwarz | Opt 3: RAN5#93 (Nov-21) MU: RAN5#93 (Aug-21) TT: RAN5#93 (Aug-21) |  | Refers back to SA UL-MIMO test. Anchor-agnostic. | 1 | 80% | [5 empty] | 14MT3 |  | 80%
144 | Y | 38.521-3 | 6.4B.2.4.2 | Carrier Leakage for inter-band EN-DC including FR2 (1 NR CC) |  | Rohde&Schwarz | Opt 3: RAN5#93 (Nov-21) MU: RAN5#93 (Aug-21) TT: RAN5#93 (Aug-21) | R5-192455 R5-193315 | The referred test case 6.4.2.1 in TS 38.521-2 is incomplete | 1 | 70% | [5 empty] | 14MT3 |  | 70%
|  | 38.521-3 | 6.4B.2.4.2_1 | Carrier Leakage for inter-band EN-DC including FR2 (>1 NR CC) |  |  |  |  | Placeholder for TC numbering structure. Status tracked in Rel16 WP.
145 |  | 38.521-3 | 6.4B.2.4.2_1.1 | Carrier Leakage for inter-band EN-DC including FR2 (2 NR CCs) |  |  |  | R5-211099 | Placeholder for TC numbering structure. Status tracked in Rel16 WP. | 0
146 |  | 38.521-3 | 6.4B.2.4.2_1.2 | Carrier Leakage for inter-band EN-DC including FR2 (3 NR CCs) |  |  |  |  | Placeholder for TC numbering structure. Status tracked in Rel16 WP. | 0
147 |  | 38.521-3 | 6.4B.2.4.2_1.3 | Carrier Leakage for inter-band EN-DC including FR2 (4 NR CCs) |  |  |  |  | Placeholder for TC numbering structure. Status tracked in Rel16 WP. | 0
148 | Y | 38.521-3 | 6.4B.2.4.2D | Carrier Leakage for inter-band EN-DC including FR2 for UL MIMO |  | Rohde&Schwarz | Opt 3: RAN5#93 (Nov-21) MU: RAN5#93 (Aug-21) TT: RAN5#93 (Aug-21) |  | Refers back to SA UL-MIMO test. Anchor-agnostic. | 1 | 80% | [5 empty] | 14MT3 |  | 80%
149 | Y | 38.521-3 | 6.4B.2.4.3 | In-band Emissions for inter-band EN-DC including FR2 (1 NR CC) |  | Rohde&Schwarz | Opt 3: RAN5#93 (Nov-21) MU: RAN5#93 (Aug-21) TT: RAN5#93 (Aug-21) | R5-192455 R5-193315 | The referred test case 6.4.2.1 in TS 38.521-2 is incomplete | 1 | 70% | [5 empty] | 14MT3 |  | 70%
|  | 38.521-3 | 6.4B.2.4.3_1 | In-band Emissions for inter-band EN-DC including FR2 (>2 CCs)
150 |  | 38.521-3 | 6.4B.2.4.3_1.1 | In-band Emissions for inter-band EN-DC including FR2 (3 CCs) |  | LG Electronics | Opt 3: RAN5#93 (Nov-21) MU: RAN5#93 (Aug-21) TT: RAN5#93 (Aug-21) | R5-210415 | Placeholder for TC numbering structure. Status tracked in Rel16 WP. | 0 | 50% | [5 empty] | 14MT3 |  | 50%
151 |  | 38.521-3 | 6.4B.2.4.3_1.2 | In-band Emissions for inter-band EN-DC including FR2 (4 CCs) |  | LG Electronics |  | R5-210416 | Placeholder for TC numbering structure. Status tracked in Rel16 WP. | 0
152 |  | 38.521-3 | 6.4B.2.4.3_1.3 | In-band Emissions for inter-band EN-DC including FR2 (5 CCs) |  | LG Electronics |  | R5-210417 | Placeholder for TC numbering structure. Status tracked in Rel16 WP. | 0
153 | Y | 38.521-3 | 6.4B.2.4.3D | In-band Emissions for inter-band EN-DC including FR2 for UL MIMO |  | Rohde&Schwarz | Opt 3: RAN5#93 (Nov-21) MU: RAN5#93 (Aug-21) TT: RAN5#93 (Aug-21) |  | Refers back to SA UL-MIMO test. Anchor-agnostic. | 1 | 80% | [5 empty] | 14MT3 |  | 80%
154 | Y | 38.521-3 | 6.4B.2.4.4 | EVM Equalizer Flatness for inter-band EN-DC including FR2 (1 NR CC) |  | Rohde&Schwarz | Opt 3: RAN5#93 (Nov-21) MU: RAN5#93 (Aug-21) TT: RAN5#93 (Aug-21) | R5-192455 R5-193315 | The referred test case 6.4.2.1 in TS 38.521-2 is incomplete | 1 | 70% | [5 empty] | 14MT3 |  | 70%
|  | 38.521-3 | 6.4B.2.4.4_1 | EVM Equalizer Flatness for inter-band EN-DC including FR2 (>2 CCs) | Header
155 |  | 38.521-3 | 6.4B.2.4.4_1.1 | EVM Equalizer Flatness for inter-band EN-DC including FR2 (3 CCs) |  |  |  |  | Placeholder for TC numbering structure. Status tracked in Rel16 WP. | 0
156 |  | 38.521-3 | 6.4B.2.4.4_1.2 | EVM Equalizer Flatness for inter-band EN-DC including FR2 (4 CCs) |  |  |  |  | Placeholder for TC numbering structure. Status tracked in Rel16 WP. | 0
157 |  | 38.521-3 | 6.4B.2.4.4_1.3 | EVM Equalizer Flatness for inter-band EN-DC including FR2 (5 CCs) |  |  |  |  | Placeholder for TC numbering structure. Status tracked in Rel16 WP. | 0
158 | Y | 38.521-3 | 6.4B.2.4.4D | EVM Equalizer Flatness for inter-band EN-DC including FR2 for UL-MIMO |  | Rohde&Schwarz | Opt 3: RAN5#93 (Nov-21) MU: RAN5#93 (Aug-21) TT: RAN5#93 (Aug-21) |  | Refers back to SA UL-MIMO test. Anchor-agnostic. | 1 | 80% | [5 empty] | 14MT3 |  | 80%
| Y | 38.521-3 | 6.4B.2.4.5 | EVM spectral flatness for pi/2 BPSK modulation for inter-band EN-DC including FR2 (1 NR CC) |  | Rohde&Schwarz | <Autofilled> | R5-215888 | The referred test case 6.4.2.5 in TS 38.521-2 [9] is incomplete |  | 70% | [7 empty] | 70%
|  | 38.521-3 | 6.5 | Output RF spectrum emissions
|  | 38.521-3 | 6.5A | Output RF spectrum emissions for CA without EN-DC
159 |  | 38.521-3 | 6.5A.1 | Occupied Bandwidth for CA without EN-DC |  | Keysight | Opt 2: RAN5#84 (Aug-19) | R5-194947 | FR1+FR2 Testability. No TC details added | 0.4 | 100% | 4 |  |  | 100%
|  | 38.521-3 | 6.5A.2 | Out of Band Emissions for CA without EN-DC | [11 empty] | 1
160 |  | 38.521-3 | 6.5A.2.1 | Spectrum emissions mask for CA without EN-DC |  | Keysight | Opt 2: RAN5#84 (Aug-19) |  | No test case details. Add snippet per agreed template | 0.4 | 100% | 4 |  |  | 100%
161 |  | 38.521-3 | 6.5A.2.2 | Additional Spectrum emissions mask for CA without EN-DC |  | Ericsson | Opt 2: RAN5#84 (Aug-19) | R5-193459 | FR1+FR2 Testability. No TC details added | 0.4 | 100% | 4 |  |  | 100%
162 |  | 38.521-3 | 6.5A.2.3 | Adjacent channel leakage ratio for CA without EN-DC |  | Ericsson | Opt 2: RAN5#84 (Aug-19) | R5-191340 | FR1+FR2 Testability. No TC details added. Needs to be updated per agreed template | 0.4 | 100% | 4 |  |  | 100%
|  | 38.521-3 | 6.5A.3 | Spurious Emissions for CA without EN-DC | [11 empty] | 1
163 |  | 38.521-3 | 6.5A.3.1 | General Spurious Emissions for inter-band CA without EN-DC |  | Qualcomm | Opt 2: RAN5#84 (Aug-19) | R5-194947 | FR1+FR2 Testability. No TC details added | 0.4 | 100% | 4 |  |  | 100%
164 |  | 38.521-3 | 6.5A.3.2 | Spurious Emission band UE co-existence for CA without EN-DC |  | Qualcomm |  |  | deleted | 0 |  | 10
|  | 38.521-3 | 6.5B | Output RF spectrum emissions for DC
|  | 38.521-3 | 6.5B.1 | Occupied bandwidth for EN-DC
165 | Y | 38.521-3 | 6.5B.1.1 | Occupied bandwidth for intra-band contiguous EN-DC |  | Keysight | Opt 3: RAN5#93 (Nov-21) Opt 4: RAN5#93 (Nov-21) Opt 7: FFS | R5-183709 R5-186303 R5-188013 R5-211696 | measurement uncertainty for ENBW > 100 MHz is FFS | 1 | 76.67% | [5 empty] | 14 | 90% |  |  | 1 | 90% |  |  | 1 | 50%
166 | Y | 38.521-3 | 6.5B.1.2 | Occupied bandwidth for intra-band non-contiguous EN-DC |  | Keysight | Opt 3: RAN5#93 (Nov-21) Opt 4: RAN5#93 (Nov-21) Opt 7: FFS | R5-187821 R5-210301 |  | 1 | 73.33% | [5 empty] | 14 | 100% |  |  | 1 | 70% |  |  | 1 | 50%
167 | Y | 38.521-3 | 6.5B.1.3 | Occupied bandwidth for inter-band EN-DC within FR1 (1 NR CC) |  | Keysight | Opt 3: RAN5#81 (Nov-18) Opt 4: RAN5#93 (Nov-21) Opt 7: FFS | R5-185479 R5-186302 R5-190995 |  | 1 | 100% | [5 empty] | 2 | 100% |  |  | 1 | 100% |  |  | 1 | 100%
168 | Y | 38.521-3 | 6.5B.1.4 | Occupied bandwidth for inter-band EN-DC including FR2 (1 NR CC) |  | Keysight | Opt 3: RAN5#93 (Nov-21) MU: RAN5#93 (Aug-21) TT: RAN5#93 (Aug-21) Opt 4: RAN5#93 (Nov-21) Opt 7: FFS | R5-192456 R5-211928 |  | 1 | 56.67% | [5 empty] | 14MT2 |  | 70% |  | 1 |  | 50% |  | 1 | 50%
|  | 38.521-3 | 6.5B.1.4_1 | Occupied bandwidth for inter-band EN-DC including FR2 ((>1 NR CC)
169 |  | 38.521-3 | 6.5B.1.4_1.1 | Occupied bandwidth for inter-band EN-DC including FR2 (2 NR CCs) |  |  |  | R5-211928 | Placeholder for TC numbering structure. Status tracked in Rel16 WP. | 0
170 |  | 38.521-3 | 6.5B.1.4_1.2 | Occupied bandwidth for inter-band EN-DC including FR2 (3 NR CCs) |  |  |  | R5-211928 | Placeholder for TC numbering structure. Status tracked in Rel16 WP. | 0
171 |  | 38.521-3 | 6.5B.1.4_1.3 | Occupied bandwidth for inter-band EN-DC including FR2 (4 NR CCs) |  |  |  | R5-211928 | Placeholder for TC numbering structure. Status tracked in Rel16 WP. | 0
172 | Y | 38.521-3 | 6.5B.1.4D | Occupied bandwidth for inter-band EN-DC including FR2 for UL MIMO |  | Keysight | Opt 3: RAN5#93 (Nov-21) MU: RAN5#93 (Aug-21) TT: RAN5#93 (Aug-21) | R5-210302 | Referenced 38.521-2 is not completed. | 1 | 70% | [5 empty] | 14MT3 |  | 70%
|  | 38.521-3 | 6.5B.2 | Out of Band emissions for EN-DC
|  | 38.521-3 | 6.5B.2.1 | Out of Band Emissions for intra-band contiguous EN-DC
173 | Y | 38.521-3 | 6.5B.2.1.1 | Spectrum emissions mask for intra-band contiguous EN-DC |  | Keysight | Opt 3: RAN5#81 (Nov-18) Opt 4: RAN5#93 (Nov-21) Opt 7: FFS | R5-186230 R5-188014 R5-210387 |  | 1 | 100% | [5 empty] | 2 | 100% |  |  | 1 | 100% |  |  | 1 | 100%
174 | Y | 38.521-3 | 6.5B.2.1.2 | Additional Spectrum emissions mask for intra-band contiguous EN-DC |  | Ericsson | Opt 3: RAN5#81 (Nov-18) Opt 4: RAN5#93 (Nov-21) Opt 7: FFS | R5-180087; R5-182018 R5-185200 R5-186295 R5-188023 R5-190840 R5-193456 R5-194945 |  | 1 | 100% | [5 empty] | 2 | 100% |  |  | 1 | 100% |  |  | 1 | 100%
175 | Y | 38.521-3 | 6.5B.2.1.3 | Adjacent channel leakage ratio for intra-band contiguous EN-DC |  | Ericsson | Opt 3: RAN5#81 (Nov-18) Opt 4: RAN5#93 (Nov-21) Opt 7: FFS | R5-182016 R5-187820 |  | 1 | 100% | [5 empty] | 2 | 100% |  |  | 1 | 100% |  |  | 1 | 100%
|  | 38.521-3 | 6.5B.2.2 | Out-of-band emissions for Intra-band non-contiguous EN-DC
176 | Y | 38.521-3 | 6.5B.2.2.1 | Spectrum emissions mask for intra-band non-contiguous EN-DC |  | Keysight | Opt 3: RAN5#90 (Feb-21) Opt 4: RAN5#93 (Nov-21) Opt 7: FFS | R5-193180 R5-211694 |  | 1 | 86.67% | [5 empty] | 11 | 100% |  |  | 1 | 80% |  |  | 1 | 80%
177 | Y | 38.521-3 | 6.5B.2.2.2 | Additional Spectrum emissions mask for intra-band non-contiguous EN-DC |  | Ericsson | Opt 3: RAN5#93 (Nov-21) Opt 4: RAN5#93 (Nov-21) Opt 7: FFS | R5-215890 | For Wgap < NR ΔfOOB + E-UTRA ΔfOOB, test description and test requirements are FFS | 1 | 80% | [5 empty] | 14 | 80% |  |  | 1 | 80% |  |  | 1 | 80%
178 | Y | 38.521-3 | 6.5B.2.2.3 | Adjacent channel leakage ratio for intra-band non-contiguous EN-DC |  | Keysight | Opt 3: RAN5#93 (Nov-21) Opt 4: RAN5#93 (Nov-21) Opt 7: FFS | R5-193181 R5-211695 | Testing of none simultaneous LTE-NR transmission is FFS. | 1 | 80% | [5 empty] | 14 | 80% |  |  | 1 | 80% |  |  | 1 | 80%
|  | 38.521-3 | 6.5B.2.3 | Out-of-band emissions for Inter-band EN-DC within FR1
179 | Y | 38.521-3 | 6.5B.2.3.1 | Spectrum emissions mask for Inter-band EN-DC within FR1 (1 NR CC) |  | Keysight | Opt 3: RAN5#80 (Aug-18) | R5-183710 R5-185480 R5-186302 R5-215890 |  | 1 | 100% | [5 empty] | 1.5 | 100%
180 | Y | 38.521-3 | 6.5B.2.3.2 | Additional Spectrum emissions mask for Inter-band EN-DC within FR1 (1 NR CC) |  | Ericsson | Opt 3: RAN5#84 (Aug-19) | R5-215890 |  | 1 | 100% | [5 empty] | 5 | 100%
181 | Y | 38.521-3 | 6.5B.2.3.3 | Adjacent channel leakage ratio for inter-band EN-DC within FR1 (1 NR CC) |  | Keysight | Opt 3: RAN5#80 (Aug-18) | R5-183711 R5-185481 R5-186302 R5-215890 |  | 1 | 100% | [5 empty] | 1.5 | 100%
|  | 38.521-3 | 6.5B.2.3A | Out-of-band emissions for Inter-band NE-DC within FR1
182 | Y | 38.521-3 | 6.5B.2.3A.1 | Spectrum emissions mask for Inter-band NE-DC within FR1 |  | CMCC | Opt 4: RAN5#93 (Nov-21) Opt 7: FFS | R5-215875 |  | 1 | 50% | [9 empty] | 1 | 100% |  |  | 1 | 0%
183 | Y | 38.521-3 | 6.5B.2.3A.2 | Additional Spectrum emissions mask for Inter-band NE-DC within FR1 |  | CMCC | Opt 4: RAN5#93 (Nov-21) Opt 7: FFS | R5-215876 |  | 1 | 50% | [9 empty] | 1 | 100% |  |  | 1 | 0%
184 | Y | 38.521-3 | 6.5B.2.3A.3 | Adjacent channel leakage ratio for inter-band NE-DC within FR1 |  | CMCC | Opt 4: RAN5#93 (Nov-21) Opt 7: FFS | R5-215877 |  | 1 | 50% | [9 empty] | 1 | 100% |  |  | 1 | 0%
|  | 38.521-3 | 6.5B.2.4 | Out-of-band emissions for Inter-band EN-DC including FR2
185 | Y | 38.521-3 | 6.5B.2.4.1 | Spectrum emissions mask for Inter-band EN-DC including FR2 (1 NR CC) |  | Sporton | Opt 3: RAN5#83 (May-19) MU: RAN5#83 (May-19) TT: RAN5#83 (May-19) Opt 4: RAN5#93 (Nov-21) Opt 7: FFS | R5-192457 R5-195411 |  | 1 | 100% | [5 empty] | 4MT2 |  | 100% |  | 1 |  | 100% |  | 1 | 100%
|  | 38.521-3 | 6.5B.2.4.1_1 | Spectrum emissions mask for Inter-band EN-DC including FR2 (>1 NR CC)
|  |  | 6.5B.2.4.1_1.1 | Spectrum emissions mask for Inter-band EN-DC including FR2 (2 NR CCs) |  |  |  |  | Placeholder for TC numbering structure. Status tracked in Rel16 WP.
|  |  | 6.5B.2.4.1_1.2 | Spectrum emissions mask for Inter-band EN-DC including FR2 (3 NR CCs) |  |  |  |  | Placeholder for TC numbering structure. Status tracked in Rel16 WP.
|  |  | 6.5B.2.4.1_1.3 | Spectrum emissions mask for Inter-band EN-DC including FR2 (4 NR CCs) |  |  |  |  | Placeholder for TC numbering structure. Status tracked in Rel16 WP.
189 | Y | 38.521-3 | 6.5B.2.4.1D | Spectrum emissions mask for inter-band EN-DC including FR2 for UL-MIMO |  | Sporton | Opt 3: RAN5#93 (Nov-21) MU: RAN5#93 (Aug-21) TT: RAN5#93 (Aug-21) |  | Refers back to SA UL-MIMO test. Anchor-agnostic. | 1 | 90% | [5 empty] | 14MT3 |  | 90%
185 |  | 38.521-3 | 6.5B.2.4.2 | VOID |  | Sporton |  |  | Add clause and make VOID to align with 38.521-2 | 0
185 | Y | 38.521-3 | 6.5B.2.4.3 | Adjacent channel leakage ratio for Inter-band EN-DC including FR2 (1 NR CC) |  | Sporton | Opt 3: RAN5#83 (May-19) MU: RAN5#83 (May-19) TT: RAN5#83 (May-19) Opt 4: RAN5#93 (Nov-21) Opt 7: FFS | R5-192457 R5-192458 R5-195411 |  | 1 | 100% | [5 empty] | 4MT2 |  | 100% |  | 1 |  | 100% |  | 1 | 100%
|  | 38.521-3 | 6.5B.2.4.3_1 | Spectrum emissions mask for Inter-band EN-DC including FR2 (>1 NR CC)
192 |  | 38.521-3 | 6.5B.2.4.3_1.1 | Adjacent channel leakage ratio for Inter-band EN-DC including FR2 (2 NR CCs) |  |  |  |  | Placeholder for TC numbering structure. Status tracked in Rel16 WP.
193 |  | 38.521-3 | 6.5B.2.4.3_1.2 | Adjacent channel leakage ratio for Inter-band EN-DC including FR2 (3 NR CCs) |  |  |  |  | Placeholder for TC numbering structure. Status tracked in Rel16 WP.
194 |  | 38.521-3 | 6.5B.2.4.3_1.3 | Adjacent channel leakage ratio for Inter-band EN-DC including FR2 ( NR CCs) |  |  |  |  | Placeholder for TC numbering structure. Status tracked in Rel16 WP.
195 | Y | 38.521-3 | 6.5B.2.4D.3 | Adjacent channel leakage ratio for inter-band EN-DC including FR2 for UL MIMO |  | Sporton | Opt 3: RAN5#93 (Nov-21) MU: RAN5#93 (Aug-21) TT: RAN5#93 (Aug-21) |  | Refers back to SA UL-MIMO test. Anchor-agnostic. | 1 | 90% | [5 empty] | 14MT3 |  | 90%
|  | 38.521-3 | 6.5B.3 | Spurious emissions for EN-DC
|  | 38.521-3 | 6.5B.3.1 | Spurious Emissions for intra-band contiguous EN-DC
196 | Y | 38.521-3 | 6.5B.3.1.1 | General Spurious Emissions for intra-band contiguous EN-DC |  | Qualcomm | Opt 3: RAN5#81 (Nov-18) Opt 4: RAN5#93 (Nov-21) Opt 7: FFS | R5-185205 R5-186299 R5-190835 R5-192604 |  | 1 | 100% | [5 empty] | 2 | 100% |  |  | 1 | 100% |  |  | 1 | 100%
197 | Y | 38.521-3 | 6.5B.3.1.2 | Spurious Emission band UE co-existence for intra-band contiguous EN-DC |  | Qualcomm | Opt 3: RAN5#81 (Nov-18) Opt 4: RAN5#93 (Nov-21) Opt 7: FFS | R5-186299 R5-192604 |  | 1 | 100% | [5 empty] | 2 | 100% |  |  | 1 | 100% |  |  | 1 | 100%
|  | 38.521-3 | 6.5B.3.2 | Spurious Emissions for intra-band non-contiguous EN-DC
198 | Y | 38.521-3 | 6.5B.3.2.1 | General Spurious Emissions for intra-band non-contiguous EN-DC |  | Qualcomm | Opt 3: RAN5#82 (Feb-19) Opt 4: RAN5#93 (Nov-21) Opt 7: FFS | R5-186300 R5-192603 |  | 1 | 100% | [5 empty] | 3 | 100% |  |  | 1 | 100% |  |  | 1 | 100%
199 | Y | 38.521-3 | 6.5B.3.2.2 | Spurious Emission band UE co-existence for intra-band non-contiguous EN-DC |  | Qualcomm | Opt 3: RAN5#88 (Aug-20) | R5-188018 R5-192603 | This test can be completed at RAN5#87. No dependencies | 1 | 100% | [5 empty] | 9 | 100% |  |  | 1 |  |  |  | 1
|  | 38.521-3 | 6.5B.3.3 | Spurious emissions for Inter-band EN-DC within FR1
200 | Y | 38.521-3 | 6.5B.3.3.1 | General Spurious Emissions for Inter-band EN-DC within FR1 |  | Qualcomm | Opt 3: RAN5#80 (Aug-18) | R5-185205 R5-190834 R5-192605 R5-202725 |  | 1 | 100% | [5 empty] | 1.5 | 100%
201 | Y | 38.521-3 | 6.5B.3.3.2 | Spurious Emission band UE co-existence for Inter-band EN-DC within FR1 |  | Qualcomm | Opt 3: RAN5#81 (Nov-18) | R5-186239 R5-190834 R5-192605 R5-202725 R5-211872 |  | 1 | 100% | [5 empty] | 2 | 100%
|  | 38.521-3 | 6.5B.3.3A | Spurious emissions for Inter-band NE-DC within FR1
202 | Y | 38.521-3 | 6.5B.3.3A.1 | General Spurious Emissions for Inter-band NE-DC within FR1 |  | CMCC | Opt 4: RAN5#93 (Nov-21) Opt 7: FFS | R5-215878 |  | 1 | 100% | [9 empty] | 1 | 100% |  |  | 1 | 100%
203 | Y | 38.521-3 | 6.5B.3.3A.2 | Spurious Emission band UE co-existence for Inter-band NE-DC within FR1 |  |  | Opt 4: RAN5#93 (Nov-21) Opt 7: FFS |  |  | 1 | 0% | [9 empty] | 1 | 0% |  |  | 1 | 0%
|  | 38.521-3 | 6.5B.3.4 | Spurious emissions for Inter-band including FR2
204 | Y | 38.521-3 | 6.5B.3.4.1 | General Spurious Emissions for Inter-band including FR2 (1 NR CC) |  | Qualcomm | Opt 3: RAN5#88 (Aug-20) MU: RAN5#88 (Aug-20) TT: RAN5#88 (Aug-20) Opt 4: RAN5#93 (Nov-21) Opt 7: FFS | R5-187831 R5-211928 |  | 1 | 100% | [5 empty] | 9MT2 |  | 100% |  | 1 | 100% |  |  | 1 | 100%
|  | 38.521-3 | 6.5B.3.4.1_1 | General Spurious Emissions for Inter-band including FR2 ((>1 NR CC)
205 |  | 38.521-3 | 6.5B.3.4.1_1.1 | General Spurious Emissions for Inter-band including FR2 (2 NR CCs) |  |  |  | R5-211928 | Placeholder for TC numbering structure. Status tracked in Rel16 WP. | 0
206 |  | 38.521-3 | 6.5B.3.4.1_1.2 | General Spurious Emissions for Inter-band including FR2 (3 NR CCs) |  |  |  | R5-211928 | Placeholder for TC numbering structure. Status tracked in Rel16 WP. | 0
207 |  | 38.521-3 | 6.5B.3.4.1_1.3 | General Spurious Emissions for Inter-band including FR2 (4 NR CCs) |  |  |  | R5-211928 | Placeholder for TC numbering structure. Status tracked in Rel16 WP. | 0
208 | Y | 38.521-3 | 6.5B.3.4.1D | General Spurious Emissions for inter-band EN-DC including FR2 for UL MIMO |  | Qualcomm | Opt 3: RAN5#93 (Nov-21) MU: RAN5#93 (Aug-21) TT: RAN5#93 (Aug-21) | R5-211928 | Refers back to SA UL-MIMO test. Anchor-agnostic. 38.521-2 test is incomplete. Editor's note has to be updated. | 1 | 70% | [5 empty] | 14MT3 |  | 70%
209 | Y | 38.521-3 | 6.5B.3.4.2 | Spurious emission band UE co-existence for Inter-band including FR2 (1 NR CC) |  | Qualcomm | Opt 3: RAN5#93 (Nov-21) MU: RAN5#93 (Aug-21) TT: RAN5#93 (Aug-21) | R5-182035 R5-185556 R5-186285 R5-192453 R5-211928 |  | 1 | 70% | [5 empty] | 14MT2 |  | 70%
|  |  | 6.5B.3.4.2_1 | Spurious emission band UE co-existence for Inter-band including FR2 (>2 CCs)
210 |  | 38.521-3 | 6.5B.3.4.2_1.1 | Spurious emission band UE co-existence for Inter-band including FR2 (3 CCs) |  |  |  |  | Placeholder for TC numbering structure. Status tracked in Rel16 WP. | 0
211 |  | 38.521-3 | 6.5B.3.4.2_1.2 | Spurious emission band UE co-existence for Inter-band including FR2 (4 CCs) |  |  |  |  | Placeholder for TC numbering structure. Status tracked in Rel16 WP. | 0
212 |  | 38.521-3 | 6.5B.3.4.2_1.3 | Spurious emission band UE co-existence for Inter-band including FR2 (5 CCs) |  |  |  |  | Placeholder for TC numbering structure. Status tracked in Rel16 WP. | 0
213 | Y | 38.521-3 | 6.5B.3.4.2D | Spurious emission band UE co-existence for inter-band EN-DC including FR2 for UL-MIMO |  | Qualcomm | Opt 3: RAN5#93 (Nov-21) MU: RAN5#93 (Aug-21) TT: RAN5#93 (Aug-21) |  | Refers back to SA UL-MIMO test. Anchor-agnostic. Check update status | 1 | 0% | [5 empty] | 14MT3 |  | 0%
|  | 38.521-3 | 6.5B.3.5 | Spurious emissions for Inter-band including FR1 and FR2
214 |  | 38.521-3 | 6.5B.3.5.1 | General Spurious Emissions for Inter-band including FR1 and FR2 |  | Qualcomm | Opt 3: RAN5#84 (Aug-19) MU: RAN5#84 (Aug-19) TT: RAN5#84 (Aug-19) Opt 4: RAN5#93 (Nov-21) Opt 7: FFS |  | No test case details. Add snippet per agreed template | 0.4 | 100% | [5 empty] | 5MT3 |  |  | 100% | 1 |  |  | 100% | 1 | 100%
215 |  | 38.521-3 | 6.5B.3.5.1D | General Spurious Emissions for inter-band EN-DC including FR1 and FR2 for UL-MIMO |  | Qualcomm | Opt 3: RAN5#88 (Aug-20) MU: RAN5#88 (Aug-20) TT: RAN5#88 (Aug-20) | ?? | FR1+FR2 Testability. Basic text to add..No TC details needed. | 0.4 | 100% | [5 empty] | 9MT3 |  |  | 100% | 1
216 |  | 38.521-3 | 6.5B.3.5.2 | Spurious emission band UE co-existence for Inter-band including FR1 and FR2 |  | Qualcomm | Opt 3: RAN5#88 (Aug-20) MU: RAN5#88 (Aug-20) TT: RAN5#88 (Aug-20) Opt 4: RAN5#93 (Nov-21) Opt 7: FFS |  | No test case details. Add snippet per agreed template | 0.4 | 100% | [5 empty] | 9MT2 |  |  | 100% | 1 |  |  | 100% | 1 | 100%
217 |  | 38.521-3 | 6.5B.3.5.2D | Spurious emission band UE co-existence for inter-band EN-DC including FR1 and FR2 for UL-MIMO |  | Qualcomm | Opt 3: RAN5#88 (Aug-20) MU: RAN5#88 (Aug-20) TT: RAN5#88 (Aug-20) |  | FR1+FR2 Testability. Basic text to add..No TC details needed. | 0.4 | 100% | [5 empty] | 9MT3 |  |  | 100%
|  | 38.521-3 | 6.5B.4 | Additional Spurious Emissions for EN-DC
218 | Y | 38.521-3 | 6.5B.4.1 | Additional Spurious Emissions for Intra-band contiguous EN-DC |  | Qualcomm | Opt 3: RAN5#81 (Nov-18) Opt 4: RAN5#93 (Nov-21) Opt 7: FFS | R5-188015 R5-192606 |  | 1 | 100% | [5 empty] | 2 | 100% |  |  | 1 | 100% |  |  | 1 | 100%
219 | Y | 38.521-3 | 6.5B.4.2 | Additional Spurious Emissions for Intra-band non-contiguous EN-DC |  | Qualcomm | Opt 3: RAN5#93 (Nov-21) Opt 4: RAN5#93 (Nov-21) Opt 7: FFS | R5-188016 R5-192606 R5-214080 | Remains: MU and TT is missing in annex F for this test case | 1 | 76.67% | [5 empty] | 14 | 90% |  |  | 1 | 70% |  |  | 1 | 70%
220 | Y | 38.521-3 | 6.5B.4.3 | Additional Spurious Emissions for Inter-band EN-DC within FR1 |  | Qualcomm | Opt 3: RAN5#81 (Nov-18) Opt 4: RAN5#93 (Nov-21) Opt 7: FFS | R5-188017 R5-192606 |  | 1 | 100% | [5 empty] | 2 | 100% |  |  | 1 | 100% |  |  | 1 | 100%
|  | 38.521-3 | 6.5B.5 | Transmit Intermodulation
221 | Y | 38.521-3 | 6.5B.5.1 | Transmit Intermodulation for Intra-band contiguous EN-DC |  | Docomo | Opt 3: RAN5#93 (Nov-21) Opt 4: RAN5#93 (Nov-21) Opt 7: FFS | R5-215230 | No test case details are specified | 1 | 10% | [5 empty] | 14 | 30% |  |  | 1 | 0% |  |  | 1 | 0%
222 | Y | 38.521-3 | 6.5B.5.2 | Transmit Intermodulation for Intra-band non-contiguous EN-DC |  | Docomo | Opt 3: RAN5#93 (Nov-21) Opt 4: RAN5#93 (Nov-21) Opt 7: FFS | R5-215230 | No test case details are specified | 1 | 10% | [5 empty] | 14 | 30% |  |  | 1 | 0% |  |  | 1 | 0%
223 | Y | 38.521-3 | 6.5B.5.3 | Transmit Intermodulation for Inter-band EN-DC within FR1 (1 NR CC) |  | Docomo | Opt 3: RAN5#82 (Feb-19) | R5-191084 R5-210499 | some formatting/editorial cleanup needed | 1 | 100% | [5 empty] | 3 | 100%
224 | Y | 38.521-3 | 6.5B.5.3A | Transmit Intermodulation for Inter-band NE-DC within FR1 |  | CMCC | Opt 4: RAN5#93 (Nov-21) | R5-215879 |  | 1 | 100% | [9 empty] | 1 | 100%
225 |  | 38.521-3 | 6.5B.5.4 | Transmit Intermodulation for inter-band EN-DC within FR2 |  | Docomo | Opt 3: RAN5#93 (Nov-21) MU: RAN5#93 (Aug-21) TT: RAN5#93 (Aug-21) |  | Make Void to align with TS 38.521-2 | 0 | 0% | [5 empty] | 14MT3 |  | 0%
226 |  | 38.521-3 | 6.5B.5.5 | Transmit Intermodulation for inter-band EN-DC including FR1 and FR2 |  | Docomo | Opt 3: RAN5#93 (Nov-21) MU: RAN5#93 (Aug-21) TT: RAN5#93 (Aug-21) |  | Make Void to align with TS 38.521-2 | 0 | 0% | [5 empty] | 14MT3 |  |  | 0%
|  | 38.521-4 | 6.6B | Beam Correspondence for DC
|  | 38.521-5 | 6.6B.1 | Void
227 |  | 38.521-6 | 6.6B.2 | Void | [5 empty] | 0
228 |  | 38.521-7 | 6.6B.3 | Void | [5 empty] | 0
231 | Y | 38.521-3 | 6.6B.4 | Beam Correspondence for inter-band EN-DC including FR2 (2 CCs) - EIRP |  | Apple | Opt 3: RAN5#93 (Nov-21) MU: RAN5#93 (Aug-21) TT: RAN5#93 (Aug-21) |  | The referred test case 6.6.1 in TS 38.521-2 is incomplete | 1 | 80% | [5 empty] | 14MT3 |  | 80%
Receiver Characteristics (section 7)
|  | 38.521-3 | 7.1 | General |  |  |  | R5-185563 |  | 0.1 | [5 empty] | 1
|  | 38.521-3 | 7.2 | Void | [5 empty] | 0.1 | [5 empty] | 1
|  | 38.521-3 | 7.3 | Void
|  | 38.521-3 | 7.3A | Reference sensitivity for CA without EN-DC
|  | 38.521-3 | 7.3A.1 | General |  |  |  |  | Update to align with core spec
235 |  | 38.521-3 | 7.3A.2 | Reference sensitivity power level for CA without EN-DC |  | Qualcomm | Opt 2: RAN5#87 (May-20) |  | No test case details. Add snippet per agreed template | 0.4 | 100% | 7 |  |  | 100% | 1
236 |  | 38.521-3 | 7.3A.3 | ΔRIB,c for CA |  | Qualcomm | Opt 2: RAN5#87 (May-20) |  |  | 0.5 | 100% | 7 |  |  | 100%
237 |  | 38.521-3 | 7.3A.4 | Reference sensitivity exceptions due to UL harmonic interference for CA |  | Qualcomm |  |  | VOID | 0
|  | 38.521-3 | 7.3B | Reference sensitivity level for DC
|  | 38.521-3 | 7.3B.1 | General
|  | 38.521-3 | 7.3B.2 | Reference Sensitivity for EN-DC
238 |  | 38.521-3 | 7.3B.2.0 | Minimum Conformance Requirements |  | Qualcomm | Opt 3: RAN5#93 (Nov-21) Opt 4: RAN5#93 (Nov-21) Opt 7: FFS | R5-183961 R5-185204 R5-186304 |  | 0.5 | 90% | [5 empty] | 14 | 90% | 90% | 90% | 1 | 90% | 90% | 90% | 1 | 90%
239 | Y | 38.521-3 | 7.3B.2.1 | Reference sensitivity for Intra-band Contiguous EN-DC (2 CCs) |  | Qualcomm | Opt 3: RAN5#81 (Nov-18) Opt 4: RAN5#93 (Nov-21) Opt 7: FFS | R5-183961 R5-185204 R5-186304 R5-190844 R5-192438 R5-193313 R5-211715 R5-211010 |  | 1 | 100% | [5 empty] | 2 | 100% |  |  | 1 | 100% | 100% | 100% | 1 | 100%
240 | Y | 38.521-3 | 7.3B.2.2 | Reference sensitivity for Intra-band Non-Contiguous EN-DC (2 CCs) |  | Qualcomm | Opt 3: RAN5#81 (Nov-18) Opt 4: RAN5#93 (Nov-21) Opt 7: FFS | R5-186306 R5-190843 R5-192438 R5-211876 |  | 1 | 100% | [5 empty] | 2 | 100% |  |  | 1 | 100% |  |  | 1 | 100%
241 | Y | 38.521-3 | 7.3B.2.3 | Reference sensitivity for Inter-band EN-DC within FR1 (2 CCs) |  | Qualcomm | Opt 3: RAN5#80 (Aug-18) Opt 4: RAN5#93 (Nov-21) Opt 7: FFS | R5-183961 R5-185204 R5-186305 R5-188026 R5-190842 R5-193500 R5-211874 R5-211875 R5-211877 R5-211878 R5-211879 R5-211880 |  | 1 | 100% | [5 empty] | 1.5 | 100% |  |  | 1 | 100% |  |  | 1 | 100%
|  | 38.521-3 | 7.3B.2.3_1 | Reference sensitivity for EN-DC within FR1 (>2 CCs)
242 | Y | 38.521-3 | 7.3B.2.3_1.1 | Reference sensitivity for EN-DC within FR1 (3 CCs) |  | Qualcomm | Opt 3: RAN5#83 (May-19) Opt 4: RAN5#93 (Nov-21) Opt 7: FFS | R5-193500 R5-211711 R5-211017 |  | 1 | 100% | [5 empty] | 4 | 100% |  |  | 1 | 100% |  |  | 1 | 100%
243 | Y | 38.521-3 | 7.3B.2.3_1.2 | Reference sensitivity for EN-DC within FR1 (4 CCs) |  | Qualcomm | Opt 3: RAN5#87 (May-20) Opt 4: RAN5#93 (Nov-21) Opt 7: FFS | R5-202906 R5-211882 |  | 1 | 100% | [5 empty] | 8 | 100% |  |  | 1 | 100% |  |  | 1 | 100%
244 | Y | 38.521-3 | 7.3B.2.3_1.3 | Reference sensitivity for EN-DC within FR1 (5 CCs) |  | Qualcomm | Opt 3: RAN5#88 (Aug-20) |  |  | 1 | 100% | [5 empty] | 9 | 100% |  |  | 1
245 | Y | 38.521-3 | 7.3B.2.3_1.4 | Reference sensitivity for EN-DC within FR1 (6 CCs) |  | Qualcomm | Opt 3: RAN5#93 (Nov-21) Opt 7: FFS |  |  | 1 | 0% | [5 empty] | 14 | 0% | [6 empty] | 1 | 0%
246 | Y | 38.521-3 | 7.3B.2.3A | Reference sensitivity for Inter-band NE-DC within FR1 (2 CCs) |  |  | Opt 4: RAN5#93 (Nov-21) |  |  | 1 | 0% | [9 empty] | 1 | 0%
247 | Y | 38.521-3 | 7.3B.2.4 | Reference sensitivity for Inter-band EN-DC including FR2 (1 NR CC) |  | Qualcomm | Opt 3: RAN5#NR5 (May-19) MU: RAN5#NR5 (Apr-19) TT: RAN5#NR5 (Apr-19) Opt 4: RAN5#93 (Nov-21) Opt 7: FFS | R5-187832 |  | 1 | 100% | [5 empty] | 4MT1 |  | 100% |  | 1 |  | 100% |  | 1 | 100%
|  | 38.521-3 | 7.3B.2.4_1 | Reference sensitivity for Inter-band EN-DC including FR2 (>1 NR CCs) |  | Qualcomm |  | R5-187832
248 | Y | 38.521-3 | 7.3B.2.4_1.1 | Reference sensitivity for Inter-band EN-DC including FR2 (2 NR CCs) |  | Qualcomm | Opt 3: RAN5#93 (Nov-21) MU: RAN5#93 (Aug-21) TT: RAN5#93 (Aug-21) Opt 4: RAN5#93 (Nov-21) Opt 7: FFS | R5-187832 R5-215832 | SA test not complete | 1 | 80% | [5 empty] | 14MT1 |  | 80% |  | 1 |  | 80% |  | 1 | 80%
249 | Y | 38.521-3 | 7.3B.2.4_1.2 | Reference sensitivity for Inter-band EN-DC including FR2 (3 NRCCs) |  | Qualcomm | Opt 3: RAN5#93 (Nov-21) MU: RAN5#93 (Aug-21) TT: RAN5#93 (Aug-21) Opt 4: RAN5#93 (Nov-21) Opt 7: FFS | R5-187832 R5-215832 | SA test not complete | 1 | 80% | [5 empty] | 14MT1 |  | 80% |  | 1 |  | 80% |  | 1 | 80%
250 | Y | 38.521-3 | 7.3B.2.4_1.3 | Reference sensitivity for Inter-band EN-DC including FR2 (4 NR CCs) |  | Qualcomm | Opt 3: RAN5#93 (Nov-21) MU: RAN5#93 (Aug-21) TT: RAN5#93 (Aug-21) Opt 4: RAN5#93 (Nov-21) Opt 7: FFS | R5-187832 R5-215832 | SA test not complete | 1 | 80% | [5 empty] | 14MT1 |  | 80% |  | 1 |  | 80% |  | 1 | 80%
251 | Y | 38.521-3 | 7.3B.2.4_1.4 | Reference sensitivity for Inter-band EN-DC including FR2 (5 NR CCs) |  | Qualcomm | Opt 3: RAN5#93 (Nov-21) MU: RAN5#93 (Aug-21) TT: RAN5#93 (Aug-21) Opt 4: RAN5#93 (Nov-21) Opt 7: FFS | R5-187832 R5-215832 | SA test not complete | 1 | 73.33% | [5 empty] | 14MT1 |  | 70% |  | 1 |  | 80% |  | 1 | 70%
| Y | 38.521-3 | 7.3B.2.4_1.5 | Reference sensitivity for Inter-band EN-DC including FR2 (6 NR CCs) |  | Qualcomm | Opt 3: RAN5#93 (Nov-21) MU: RAN5#93 (Aug-21) TT: RAN5#93 (Aug-21) | R5-215832 | SA test not complete |  | 70% | [5 empty] | 14MT1 |  | 70% |  | 1
| Y | 38.521-3 | 7.3B.2.4_1.6 | Reference sensitivity for Inter-band EN-DC including FR2 (7 NR CCs) |  | Qualcomm | Opt 3: RAN5#93 (Nov-21) MU: RAN5#93 (Aug-21) TT: RAN5#93 (Aug-21) | R5-215832 |  |  | 70% | [5 empty] | 14MT1 |  | 70% |  | 1
| Y | 38.521-3 | 7.3B.2.4_1.7 | Reference sensitivity for Inter-band EN-DC including FR2 (8 NR CCs) |  | Qualcomm | Opt 3: RAN5#93 (Nov-21) MU: RAN5#93 (Aug-21) TT: RAN5#93 (Aug-21) | R5-215832 |  |  | 70% | [5 empty] | 14MT1 |  | 70% |  | 1
252 | Y | 38.521-3 | 7.3B.2.4D | Reference sensitivity for inter-band EN-DC including FR2 for UL MIMO |  | Qualcomm | Opt 3: RAN5#93 (Nov-21) MU: RAN5#93 (Aug-21) TT: RAN5#93 (Aug-21) |  |  | 1 | 90% | [5 empty] | 14MT3 |  | 90% |  | 1
253 | Y | 38.521-3 | 7.3B.2.5 | Reference sensitivity for Inter-band EN-DC including FR1 and FR2 |  | Qualcomm | Opt 3: RAN5#88 (Aug-20) MU: RAN5#88 (Aug-20) TT: RAN5#88 (Aug-20) | R5-187832 | FR1+FR2 Testability. No TC details added | 0.4 | 100% | [5 empty] | 9MT1 |  |  | 100%
254 | Y | 38.521-3 | 7.3B.2.5D | Reference sensitivity for inter-band EN-DC including FR1 and FR2 for UL MIMO |  | Qualcomm | Opt 3: RAN5#88 (Aug-20) MU: RAN5#88 (Aug-20) TT: RAN5#88 (Aug-20) |  | FR1+FR2 Testability. Basic text to add..No TC details needed. | 0.4 | 100% | [5 empty] | 9MT3 |  |  | 100%
|  | 38.521-3 | 7.3B.3 | ΔRIB,c for EN-DC
|  | 38.521-3 | 7.3B.3.0 | General
|  | 38.521-3 | 7.3B.3.1 | Reference Sensitivity ΔRIB,c for Intra-band contiguous EN-DC
255 |  | 38.521-3 | 7.3B.3.2 | Reference Sensitivity ΔRIB,c for Intra-band non-contiguous EN-DC |  | Qualcomm | Opt 3: RAN5#87 (May-20) Opt 4: RAN5#93 (Nov-21) Opt 7: FFS |  |  | 0.5 | 100% | [5 empty] | 8 | 100% |  |  | 1 | 100% |  |  | 1 | 100%
|  | 38.521-3 | 7.3B.3.3 | Reference Sensitivity ΔRIB,c for Inter-band EN-DC within FR1
256 |  | 38.521-3 | 7.3B.3.3.1 | Reference Sensitivity ΔRIB,c forΔRIB,c for EN-DC in two bands within FR1 |  | Qualcomm | Opt 3: RAN5#87 (May-20) Opt 4: RAN5#93 (Nov-21) Opt 7: FFS | R5-183961 R5-186305 |  | 0.5 | 100% | [5 empty] | 8 | 100% |  |  | 1 | 100% |  |  | 1 | 100%
257 |  | 38.521-3 | 7.3B.3.3.2 | Reference Sensitivity ΔRIB,c for EN-DC three bands within FR1 |  | Qualcomm | Opt 3: RAN5#87 (May-20) Opt 4: RAN5#93 (Nov-21) Opt 7: FFS | R5-183961 R5-186305 |  | 0.5 | 100% | [5 empty] | 8 | 100% |  |  | 1 | 100% |  |  | 1 | 100%
258 |  | 38.521-3 | 7.3B.3.3.3 | Reference Sensitivity ΔRIB,c for EN-DC four bands within FR1 |  | Qualcomm | Opt 3: RAN5#87 (May-20) Opt 4: RAN5#93 (Nov-21) Opt 7: FFS | R5-183961 R5-186305 |  | 0.5 | 100% | [5 empty] | 8 | 100% |  |  | 1 | 100% |  |  | 1 | 100%
259 |  | 38.521-3 | 7.3B.3.3.4 | Reference Sensitivity ΔRIB,c for EN-DC five bands within FR1 |  | Qualcomm | Opt 3: RAN5#87 (May-20) Opt 4: RAN5#93 (Nov-21) Opt 7: FFS | R5-183961 R5-186305 |  | 0.5 | 100% | [5 empty] | 8 | 100% |  |  | 1 | 100% |  |  | 1 | 100%
260 |  | 38.521-3 | 7.3B.3.3.5 | Reference Sensitivity ΔRIB,c for EN-DC six bands within FR1 |  | Qualcomm | Opt 3: RAN5#87 (May-20) Opt 4: RAN5#93 (Nov-21) Opt 7: FFS | R5-183961 R5-186305 |  | 0.5 | 100% | [5 empty] | 8 | 100% |  |  | 1 | 100% |  |  | 1 | 100%
|  | 38.521-3 | 7.3B.3.4 | Reference Sensitivity ΔRIB,c for Inter-band EN-DC including FR2
261 |  | 38.521-3 | 7.3B.3.4.1 | Reference Sensitivity ΔRIB,c for Inter-band EN-DC in two bands including FR2 |  | Qualcomm | Opt 3: RAN5#88 (Aug-20) MU: RAN5#88 (Aug-20) TT: RAN5#88 (Aug-20) | R5-187833 |  | 0.5 | 100% | [5 empty] | 9MT1 |  | 100%
262 |  | 38.521-3 | 7.3B.3.4.2 | Reference Sensitivity ΔRIB,c for Inter-band EN-DC in three bands including FR2 |  | Qualcomm | Opt 3: RAN5#88 (Aug-20) MU: RAN5#88 (Aug-20) TT: RAN5#88 (Aug-20) | R5-187833 |  | 0.5 | 100% | [5 empty] | 9MT1 |  | 100%
263 |  | 38.521-3 | 7.3B.3.4.3 | Reference Sensitivity ΔRIB,c for Inter-band EN-DC in four bands including FR2 |  | Qualcomm | Opt 3: RAN5#88 (Aug-20) MU: RAN5#88 (Aug-20) TT: RAN5#88 (Aug-20) | R5-187833 |  | 0.5 | 100% | [5 empty] | 9MT1 |  | 100%
264 |  | 38.521-3 | 7.3B.3.4.4 | Reference Sensitivity ΔRIB,c for Inter-band EN-DC in five bands including FR2 |  | Qualcomm | Opt 3: RAN5#88 (Aug-20) MU: RAN5#88 (Aug-20) TT: RAN5#88 (Aug-20) | R5-187833 |  | 0.5 | 100% | [5 empty] | 9MT1 |  | 100%
268 |  | 38.521-3 | 7.3B.3.4.5 | Reference Sensitivity ΔRIB,c for Inter-band EN-DC in six bands including FR1 and FR2 |  | Qualcomm | Opt 3: RAN5#88 (Aug-20) MU: RAN5#88 (Aug-20) TT: RAN5#88 (Aug-20) | R5-187833 |  | 0.4 | 100% | [5 empty] | 9MT1 |  |  | 100%
|  | 38.521-3 | 7.3B.3.5 | Reference Sensitivity ΔRIB,c for Inter-band EN-DC including FR1 and FR2 |  | Qualcomm | Opt 3: RAN5#88 (Aug-20) MU: RAN5#88 (Aug-20) TT: RAN5#88 (Aug-20) | R5-215266 |  |  | 100% | [5 empty] | 9MT1 |  |  | 100%
387 | Y | 38.521-3 | 7.3B.4 | EIS Spherical Coverage for Inter-band EN-DC including FR2 (1 NR CC) |  | Rohde&Schwarz | Opt 3: RAN5#93 (Nov-21) MU: RAN5#93 (Aug-21) TT: RAN5#93 (Aug-21) | R5-211712 | The referred test case 7.3.4 in TS 38.521-2 is incomplete | 0.4 | 80% | [5 empty] | 14MT3 |  | 80%
|  | 38.521-3 | 7.4 | Void
269 |  | 38.521-3 | 7.4A | Maximum Input Level for CA |  | Huawei | Opt 2: RAN5#84 (Aug-19) |  | No test case details. Add snippet per agreed template | 0.4 | 100% | 4 |  |  | 100% | 1
|  | 38.521-3 | 7.4B | Maximum Input Level for DC
270 |  | 38.521-3 | 7.4B.0 | Minimum Conformance Requirements |  | Huawei | Opt 3: RAN5#93 (Nov-21) Opt 4: RAN5#93 (Nov-21) Opt 7: FFS | R5-190498 R5-191999 |  | 0.5 | 80% | [5 empty] | 14 | 80% |  |  | 1 | 80% |  |  | 1 | 80%
271 | Y | 38.521-3 | 7.4B.1 | Maximum Input Level for intra-band contiguous EN-DC (2 CCs) |  | Huawei | Opt 3: RAN5#83 (May-19) Opt 4: RAN5#93 (Nov-21) Opt 7: FFS | R5-185201 R5-190857 R5-193257 |  | 1 | 100% | [5 empty] | 4 | 100% |  |  | 1 | 100% |  |  | 1 | 100%
272 | Y | 38.521-3 | 7.4B.2 | Maximum Input Level for intra-band non-contiguous EN-DC (2 CCs) |  | Huawei | Opt 3: RAN5#83 (May-19) Opt 4: RAN5#93 (Nov-21) Opt 7: FFS | R5-185202 R5-192626 R5-193316 |  | 1 | 100% | [5 empty] | 4 | 100% |  |  | 1 | 100% |  |  | 1 | 100%
273 | Y | 38.521-3 | 7.4B.3 | Maximum Input Level for inter-band EN-DC within FR1 (2 CCs) |  | Huawei | Opt 3: RAN5#81 (Nov-18) | R5-185203 R5-188027 |  | 1 | 100% | [5 empty] | 2 | 100%
|  | 38.521-3 | 7.4B.3_1 | Maximum Input Level for EN-DC within FR1 (>2 CCs) |  | Huawei
274 | Y | 38.521-3 | 7.4B.3_1.1 | Maximum Input Level for EN-DC within FR1 (3 CCs) |  | Huawei | Opt 3: RAN5#93 (Nov-21) Opt 4: RAN5#93 (Nov-21) Opt 7: FFS |  | Testing of intra-band contiguous EN-DC is FFS | 1 | 50% | [5 empty] | 14 | 50% |  |  | 1 | 50% |  |  | 1 | 50%
275 | Y | 38.521-3 | 7.4B.3_1.2 | Maximum Input Level for EN-DC within FR1 (4 CCs) |  | Huawei | Opt 3: RAN5#93 (Nov-21) Opt 4: RAN5#93 (Nov-21) Opt 7: FFS |  | Testing of intra-band contiguous EN-DC is FFS | 1 | 50% | [5 empty] | 14 | 50% |  |  | 1 | 50% |  |  | 1 | 50%
276 | Y | 38.521-3 | 7.4B.3_1.3 | Maximum Input Level for EN-DC within FR1 (5 CCs) |  | Huawei | Opt 3: RAN5#93 (Nov-21) Opt 4: RAN5#93 (Nov-21) Opt 7: FFS |  | Testing of intra-band contiguous EN-DC is FFS | 1 | 50% | [5 empty] | 14 | 50% |  |  | 1 | 50% |  |  | 1 | 50%
277 | Y | 38.521-3 | 7.4B.3_1.4 | Maximum Input Level for EN-DC within FR1 (6 CCs) |  | Huawei | Opt 3: RAN5#93 (Nov-21) Opt 4: RAN5#93 (Nov-21) Opt 7: FFS |  | Testing of intra-band contiguous EN-DC is FFS | 1 | 50% | [5 empty] | 14 | 50% |  |  | 1 | 50% |  |  | 1 | 50%
278 | Y | 38.521-3 | 7.4B.3A | Maximum Input Level for inter-band NE-DC within FR1 (2 CCs) |  | CMCC | Opt 4: RAN5#93 (Nov-21) | R5-215891 |  | 1 | 100% | [9 empty] | 1 | 100%
279 | Y | 38.521-3 | 7.4B.4 | Maximum Input Level for inter-band EN-DC including FR2 (1 NR CC) |  | Huawei | Opt 3: RAN5#93 (Nov-21) MU: RAN5#93 (Aug-21) TT: RAN5#93 (Aug-21) Opt 4: RAN5#93 (Nov-21) Opt 7: FFS | R5-193317 | The referred test case 7.4 in TS 38.521-2 is incomplete | 1 | 70% | [5 empty] | 14MT3 |  | 70% |  | 1 |  | 70% |  | 1 | 70%
|  | 38.521-3 | 7.4B.4_1 | Maximum Input Level for inter-band EN-DC including FR2 (>1 NR CC) | [5 empty] | 0
280 | Y | 38.521-3 | 7.4B.4_1.1 | Maximum Input Level for inter-band EN-DC including FR2 (2 NR CCs) |  | Huawei | Opt 3: RAN5#93 (Nov-21) MU: RAN5#93 (Aug-21) TT: RAN5#93 (Aug-21) Opt 4: RAN5#93 (Nov-21) Opt 7: FFS |  | The referred test case 7.4A.1 in TS 38.521-2 is incomplete | 1 | 50% | [5 empty] | 14MT3 |  | 50% |  | 1 |  | 50% |  | 1 | 50%
281 | Y | 38.521-3 | 7.4B.4_1.2 | Maximum Input Level for inter-band EN-DC including FR2 (3 NR CCs) |  | Huawei | Opt 3: RAN5#93 (Nov-21) MU: RAN5#93 (Aug-21) TT: RAN5#93 (Aug-21) Opt 4: RAN5#93 (Nov-21) Opt 7: FFS |  | The referred test case 7.4A.1 and 7.4A.2 in TS 38.521-2 is incomplete | 1 | 50% | [5 empty] | 14MT3 |  | 50% |  | 1 |  | 50% |  | 1 | 50%
282 | Y | 38.521-3 | 7.4B.4_1.3 | Maximum Input Level for inter-band EN-DC including FR2 (4 NR CCs) |  | Huawei | Opt 3: RAN5#93 (Nov-21) MU: RAN5#93 (Aug-21) TT: RAN5#93 (Aug-21) Opt 4: RAN5#93 (Nov-21) Opt 7: FFS |  | The referred test case 7.4A.1, 7.4A.2 and 7.4A.3 in TS 38.521-2 is incomplete | 1 | 50% | [5 empty] | 14MT3 |  | 50% |  | 1 |  | 50% |  | 1 | 50%
283 | Y | 38.521-3 | 7.4B.4_1.4 | Maximum Input Level for inter-band EN-DC including FR2 (5 NR CCs) |  | Huawei | Opt 3: RAN5#93 (Nov-21) MU: RAN5#93 (Aug-21) TT: RAN5#93 (Aug-21) Opt 4: RAN5#93 (Nov-21) Opt 7: FFS |  | The referred test case 7.4A.4 in TS 38.521-2 is incomplete | 1 | 50% | [5 empty] | 14MT3 |  | 50% |  | 1 |  | 50% |  | 1 | 50%
284 | Y | 38.521-3 | 7.4B.4D | Maximum Input Level for inter-band EN-DC including FR2 for UL MIMO |  | Huawei | Opt 3: RAN5#93 (Nov-21) MU: RAN5#93 (Aug-21) TT: RAN5#93 (Aug-21) Opt 4: RAN5#93 (Nov-21) Opt 7: FFS |  | No test case is needed | 1 | 70% | [5 empty] | 14MT3 |  | 90% |  | 1 |  | 90% |  | 1 | 30%
285 |  | 38.521-3 | 7.4B.5 | Maximum Input Level for inter-band EN-DC including both FR1 and FR2 |  | Huawei | Opt 3: - Opt 4: RAN5#93 (Nov-21) Opt 7: FFS |  | No test case details. Add snippet per agreed template | 0.4 | 100% | [5 empty] | 6MT3 |  |  | 100% | 1 |  |  | 100% | 1 | 100%
286 |  | 38.521-3 | 7.4B.5D | Maximum Input Level for inter-band EN-DC including FR1 and FR2 for UL MIMO |  | Huawei | Opt 3: RAN5#88 (Aug-20) MU: RAN5#88 (Aug-20) TT: RAN5#88 (Aug-20) |  | FR1+FR2 Testability. Basic text to add..No TC details needed. | 0.4 | 100% | [5 empty] | 9MT3 |  |  | 100%
|  | 38.521-3 | 7.5 | Void
287 |  | 38.521-3 | 7.5A | Adjacent Channel Selectivity for CA |  | CMCC | Opt 2: RAN5#84 (Aug-19) |  | No test case details. Add snippet per agreed template | 0.4 | 100% | 4 |  |  | 100% | 1
|  | 38.521-3 | 7.5B | Adjacent Channel Selectivity for DC
288 |  |  | 7.5B.0 | Minimum Conformance Requirements |  | CMCC | Opt 3: RAN5#93 (Nov-21) | R5-185503 R5-194951 R5-215897 |  | 0.5 | 90% | [5 empty] | 14 | 90%
289 | Y | 38.521-3 | 7.5B.1 | Adjacent Channel Selectivity for intra-band contiguous EN-DC (2 CCs) |  | CMCC | Opt 3: RAN5#93 (Nov-21) Opt 4: RAN5#93 (Nov-21) Opt 7: FFS | R5-185503 R5-192423 | Maximum Test System Uncertainty analysis is incomplete | 1 | 70% | [5 empty] | 14 | 70% |  |  | 1 | 70% |  |  | 1 | 70%
290 | Y | 38.521-3 | 7.5B.2 | Adjacent Channel Selectivity for intra-band non-contiguous EN-DC (2 CCs) |  | CMCC | Opt 3: RAN5#93 (Nov-21) Opt 4: RAN5#93 (Nov-21) Opt 7: FFS | R5-185504 R5-192611 R5-193033 R5-211014 | The test point selection analysis is incomplete. Maximum Test System Uncertainty analysis is incomplete | 1 | 56.67% | [5 empty] | 14 | 70% |  |  | 1 | 70% |  |  | 1 | 30%
291 | Y | 38.521-3 | 7.5B.3 | Adjacent Channel Selectivity for inter-band EN-DC within FR1 (1 NR CC) |  | CMCC | Opt 3: RAN5#81 (Nov-18) Opt 4: RAN5#93 (Nov-21) Opt 7: FFS | R5-185505 R5-188025 R5-192425 R5-193032 |  | 1 | 100% | [5 empty] | 2 | 100% |  |  | 1 | 100% |  |  | 1 | 100%
|  | 38.521-3 | 7.5B.3_1 | Adjacent Channel Selectivity for inter-band EN-DC within FR1 (>2 CCs) |  | CMCC
292 | Y | 38.521-3 | 7.5B.3_1.1 | Adjacent Channel Selectivity for EN-DC within FR1 (2 NR CCs) |  | CMCC | Opt 3: RAN5#87 (May-20) Opt 4: RAN5#93 (Nov-21) Opt 7: FFS |  | R5-202904 | 1 | 100% | [5 empty] | 8 | 100% |  |  | 1 | 100% |  |  | 1 | 100%
293 | Y | 38.521-3 | 7.5B.3_1.2 | Adjacent Channel Selectivity for EN-DC within FR1 (3 NR CCs) |  | CMCC | Opt 3: RAN5#88 (Aug-20) |  |  | 1 | 100% | [5 empty] | 9 | 100%
294 | Y | 38.521-3 | 7.5B.3_1.3 | Adjacent Channel Selectivity for EN-DC within FR1 (4 NR CCs) |  | CMCC | Opt 3: RAN5#93 (Nov-21) Opt 4: RAN5#93 (Nov-21) Opt 7: FFS | R5-215890 | Testing of intra-band contiguous EN-DC is FFS | 1 | 23.33% | [5 empty] | 14 | 70% |  |  | 1 | 0% |  |  | 1 | 0%
295 | Y | 38.521-3 | 7.5B.3_1.4 | Adjacent Channel Selectivity for EN-DC within FR1 (5 NR CCs) |  | CMCC | Opt 3: RAN5#93 (Nov-21) Opt 7: FFS | R5-215890 | Testing of intra-band contiguous EN-DC is FFS | 1 | 30% | [5 empty] | 14 | 60% | [6 empty] | 1 | 0%
296 | Y | 38.521-3 | 7.5B.3A | Adjacent Channel Selectivity for inter-band NE-DC within FR1 (2 CCs) |  | CMCC | Opt 4: RAN5#93 (Nov-21) Opt 7: FFS | R5-215892 |  | 1 | 50% | [9 empty] | 1 | 100% |  |  | 1 | 0%
297 | Y | 38.521-3 | 7.5B.4 | Adjacent Channel Selectivity for inter-band EN-DC including FR2 (1 NR CC) |  | CMCC | Opt 3: RAN5#93 (Nov-21) MU: RAN5#93 (Aug-21) TT: RAN5#93 (Aug-21) Opt 4: RAN5#93 (Nov-21) Opt 7: FFS | R5-192424 R5-193317 | Testability issue due to high PSD interferer has been identified | 1 | 70% | [5 empty] | 14MT3 |  | 70% |  | 1 |  | 70% |  | 1 | 70%
|  | 38.521-3 | 7.5B.4_1 | Adjacent Channel Selectivity for inter-band EN-DC including FR2 (>1 NR CC) | [5 empty] | 0
298 | Y | 38.521-3 | 7.5B.4_1.1 | Adjacent Channel Selectivity for inter-band EN-DC including FR2 (2 NR CCs) |  | CMCC | Opt 3: RAN5#93 (Nov-21) MU: RAN5#93 (Aug-21) TT: RAN5#93 (Aug-21) Opt 4: RAN5#93 (Nov-21) Opt 7: FFS | R5-193467 |  | 1 | 50% | [5 empty] | 14MT3 |  | 50% |  | 1 |  | 50% |  | 1 | 50%
299 | Y | 38.521-3 | 7.5B.4_1.2 | Adjacent Channel Selectivity for inter-band EN-DC including FR2 (3 NR CCs) |  | CMCC | Opt 3: RAN5#93 (Nov-21) MU: RAN5#93 (Aug-21) TT: RAN5#93 (Aug-21) Opt 4: RAN5#93 (Nov-21) Opt 7: FFS | R5-193468 |  | 1 | 50% | [5 empty] | 14MT3 |  | 50% |  | 1 |  | 50% |  | 1 | 50%
300 | Y | 38.521-3 | 7.5B.4_1.3 | Adjacent Channel Selectivity for inter-band EN-DC including FR2 (4 NR CCs) |  | CMCC | Opt 3: RAN5#93 (Nov-21) MU: RAN5#93 (Aug-21) TT: RAN5#93 (Aug-21) Opt 4: RAN5#93 (Nov-21) Opt 7: FFS | R5-193469 |  | 1 | 50% | [5 empty] | 14MT3 |  | 50% |  | 1 |  | 50% |  | 1 | 50%
301 | Y | 38.521-3 | 7.5B.4_1.4 | Adjacent Channel Selectivity for inter-band EN-DC including FR2 (5 NR CCs) |  | CMCC | Opt 3: RAN5#93 (Nov-21) MU: RAN5#93 (Aug-21) TT: RAN5#93 (Aug-21) Opt 4: RAN5#93 (Nov-21) Opt 7: FFS | R5-193470 |  | 1 | 50% | [5 empty] | 14MT3 |  | 50% |  | 1 |  | 50% |  | 1 | 50%
302 |  | 38.521-3 | 7.5B.4D | Adjacent Channel Selectivity for inter-band EN-DC including FR2 for UL MIMO |  | CMCC | Opt 3: RAN5#93 (Nov-21) MU: RAN5#93 (Aug-21) TT: RAN5#93 (Aug-21) |  | Refers back to SA UL-MIMO test. Anchor-agnostic. | 1 | 80% | [5 empty] | 14MT3 |  | 80%
303 |  | 38.521-3 | 7.5B.5 | Adjacent Channel Selectivity for inter-band EN-DC including both FR1 and FR2 |  | CMCC | Opt 3: RAN5#83 (May-19) MU: RAN5#84 (Aug-19) TT: RAN5#84 (Aug-19) Opt 4: RAN5#93 (Nov-21) Opt 7: FFS | R5-193463 | FR1+FR2 Testability. No TC details added | 0.4 | 100% | [5 empty] | 4MT3 |  |  | 100% | 1 |  |  | 100% | 1 | 100%
304 |  | 38.521-3 | 7.5B.5D | Adjacent Channel Selectivity for inter-band EN-DC including FR1 and FR2 for UL MIMO |  | CMCC | Opt 3: RAN5#93 (Nov-21) MU: RAN5#93 (Aug-21) TT: RAN5#93 (Aug-21) |  | FR1+FR2 Testability. Basic text to add..No TC details needed. | 0.4 | 80% | [5 empty] | 14MT3 |  |  | 80%
|  | 38.521-3 | 7.6 | Void
305 |  | 38.521-3 | 7.6A | Blocking Characteristics for CA |  | CAICT | Opt 2: RAN5#84 (Aug-19) |  | No test case details. Add snippet per agreed template | 0.4 | 100% | 4 |  |  | 100% | 1
|  | 38.521-3 | 7.6B | Blocking Characteristics for DC
|  | 38.521-3 | 7.6B.1 | General
|  | 38.521-3 | 7.6B.2 | Inband blocking for DC
306 |  |  | 7.6B.2.0 | Minimum Conformance Requirements |  | CAICT | Opt 3: RAN5#82 (Feb-19) Opt 4: RAN5#93 (Nov-21) Opt 7: FFS | R5-192427 R5-192888 |  | 0.5 | 100% | [5 empty] | 3 | 100% |  |  | 1 | 100% |  |  | 1 | 100%
307 | Y | 38.521-3 | 7.6B.2.1 | Inband blocking for intra-band contiguous EN-DC in FR1 (2 CCs) |  | CAICT | Opt 3: RAN5#87 (May-20) Opt 4: RAN5#93 (Nov-21) Opt 7: FFS | R5-190845 R5-192427 R5-194953 |  | 1 | 100% | [5 empty] | 8 | 100% |  |  | 1 | 100% |  |  | 1 | 100%
308 | Y | 38.521-3 | 7.6B.2.2 | Inband blocking for intra-band non-contiguous EN-DC in FR1 (2 CCs) |  | CAICT | Opt 3: RAN5#87 (May-20) Opt 4: RAN5#93 (Nov-21) Opt 7: FFS | R5-190846 R5-192619 R5-193896 |  | 1 | 100% | [5 empty] | 8 | 100% |  |  | 1 | 100% |  |  | 1 | 100%
309 | Y | 38.521-3 | 7.6B.2.3 | Inband blocking for inter-band EN-DC within FR1 (1 NR CC) |  | CAICT | Opt 3: RAN5#82 (Feb-19) | R5-190847 R5-192428 |  | 1 | 100% | [5 empty] | 3 | 100%
|  | 38.521-3 | 7.6B.2.3_1 | Inband blocking for EN-DC within FR1 (>2 CCs) |  | CAICT |  | R5-190847 R5-192428
310 | Y | 38.521-3 | 7.6B.2.3_1.1 | Inband blocking for EN-DC within FR1 (3 CCs) |  | CAICT | Opt 3: RAN5#89 (Nov-20) Opt 4: RAN5#93 (Nov-21) Opt 7: FFS |  | SA reqs apply;Update Title in spec | 1 | 100% | [5 empty] | 10 | 100% |  |  | 1 | 100% |  |  | 1 | 100%
311 | Y | 38.521-3 | 7.6B.2.3_1.2 | Inband blocking for EN-DC within FR1 (4 CCs) |  | CAICT | Opt 3: RAN5#89 (Nov-20) Opt 4: RAN5#93 (Nov-21) Opt 7: FFS |  | SA reqs apply;Update Title in spec | 1 | 100% | [5 empty] | 10 | 100% |  |  | 1 | 100% |  |  | 1 | 100%
312 | Y | 38.521-3 | 7.6B.2.3_1.3 | Inband blocking for EN-DC within FR1 (5 CCs) |  | CAICT | Opt 3: RAN5#90 (Feb-21) Opt 4: RAN5#93 (Nov-21) Opt 7: FFS | R5-210501 | SA reqs apply;Update Title in spec Complete | 1 | 100% | [5 empty] | 11 | 100% |  |  | 1 | 100% |  |  | 1 | 100%
313 | Y | 38.521-3 | 7.6B.2.3_1.4 | Inband blocking for EN-DC within FR1 (6 CCs) |  | CAICT | <Autofilled> |  | Reserved. | 0 | 0% | [11 empty] | 0%
314 | Y | 38.521-3 | 7.6B.2.3A | Inband blocking for inter-band NE-DC within FR1 (2 CCs) |  | CMCC | Opt 4: RAN5#93 (Nov-21) Opt 7: FFS | R5-215893 |  | 1 | 50% | [9 empty] | 1 | 100% |  |  | 1 | 0%
315 | Y | 38.521-3 | 7.6B.2.4 | Inband blocking for inter-band EN-DC including FR2 (2 CCs) |  | CAICT | Opt 3: RAN5#92 (Aug-21) MU: RAN5#92 (Aug-21) TT: RAN5#92 (Aug-21) Opt 4: RAN5#93 (Nov-21) Opt 7: FFS | R5-193886 |  | 1 | 80% | [5 empty] | 13MT3 |  | 100% |  | 1 |  | 70% |  | 1 | 70%
|  | 38.521-3 | 7.6B.2.4_1 | Inband blocking for inter-band EN-DC including FR2 (>1 NR CC) | [5 empty] | 0
316 | Y | 38.521-3 | 7.6B.2.4_1.1 | Inband blocking for inter-band EN-DC including FR2 (2 NR CCs) |  | CAICT | Opt 3: RAN5#93 (Nov-21) MU: RAN5#93 (Aug-21) TT: RAN5#93 (Aug-21) Opt 4: RAN5#93 (Nov-21) Opt 7: FFS |  | The referred test case 7.6A.2.1 in TS 38.521-2 is incomplete | 1 | 60% | [5 empty] | 14MT3 |  | 60% |  | 1 |  | 60% |  | 1 | 60%
317 | Y | 38.521-3 | 7.6B.2.4_1.2 | Inband blocking for inter-band EN-DC including FR2 (3 NR CCs) |  | CAICT | Opt 3: RAN5#93 (Nov-21) MU: RAN5#93 (Aug-21) TT: RAN5#93 (Aug-21) Opt 4: RAN5#93 (Nov-21) Opt 7: FFS |  | The referred test case 7.6A.2.2 in TS 38.521-2 is incomplete | 1 | 60% | [5 empty] | 14MT3 |  | 60% |  | 1 |  | 60% |  | 1 | 60%
318 | Y | 38.521-3 | 7.6B.2.4_1.3 | Inband blocking for inter-band EN-DC including FR2 (4 NR CCs) |  | CAICT | Opt 3: RAN5#93 (Nov-21) MU: RAN5#93 (Aug-21) TT: RAN5#93 (Aug-21) Opt 4: RAN5#93 (Nov-21) Opt 7: FFS |  | The referred test case 7.6A.2.3 in TS 38.521-2 is incomplete | 1 | 60% | [5 empty] | 14MT3 |  | 60% |  | 1 |  | 60% |  | 1 | 60%
319 | Y | 38.521-3 | 7.6B.2.4_1.4 | Inband blocking for inter-band EN-DC including FR2 (5 NR CCs) |  | CAICT | Opt 3: RAN5#93 (Nov-21) MU: RAN5#93 (Aug-21) TT: RAN5#93 (Aug-21) Opt 4: RAN5#93 (Nov-21) Opt 7: FFS |  | The referred test case 7.6A.2.4 in TS 38.521-2 is incomplete | 1 | 60% | [5 empty] | 14MT3 |  | 60% |  | 1 |  | 60% |  | 1 | 60%
320 | Y | 38.521-3 | 7.6B.2.4D | Inband blocking for inter-band EN-DC including FR2 for UL MIMO |  | CMCC | Opt 3: RAN5#93 (Nov-21) MU: RAN5#93 (Aug-21) TT: RAN5#93 (Aug-21) |  | Refers back to SA UL-MIMO test. Anchor-agnostic. | 1 | 80% | [5 empty] | 14MT3 |  | 80%
321 |  | 38.521-3 | 7.6B.2.5 | Inband blocking for inter-band EN-DC including both FR1 and FR2 |  | CAICT | Opt 3: RAN5#83 (May-19) MU: RAN5#84 (Aug-19) TT: RAN5#84 (Aug-19) Opt 4: RAN5#93 (Nov-21) Opt 7: FFS | R5-194952 | FR1+FR2 Testability. No TC details added | 0.4 | 100% | [5 empty] | 4MT3 |  |  | 100% | 1 |  |  | 100% | 1 | 100%
322 |  | 38.521-3 | 7.6B.2.5D | Inband blocking for inter-band EN-DC including FR1 and FR2 for UL MIMO |  | CMCC | Opt 3: RAN5#93 (Nov-21) MU: RAN5#93 (Aug-21) TT: RAN5#93 (Aug-21) |  | FR1+FR2 Testability. Basic text to add..No TC details needed. | 0.4 | 80% | [5 empty] | 14MT3 |  |  | 80%
|  | 38.521-3 | 7.6B.3 | Out-of-band blocking for DC | [5 empty] | 0
323 |  | 38.521-3 | 7.6B.3.0 | Minimum Conformance Requirements |  | CAICT | Opt 3: RAN5#90 (Feb-21) Opt 4: RAN5#93 (Nov-21) Opt 7: FFS | R5-195165 |  | 0.5 | 100% | [5 empty] | 11 | 100% |  |  | 1 | 100% |  |  | 1 | 100%
324 | Y | 38.521-3 | 7.6B.3.1 | Out-of-band blocking for intra-band contiguous EN-DC in FR1 (2 CCs) |  | CAICT | Opt 3: RAN5#86 (Feb-20) Opt 4: RAN5#93 (Nov-21) Opt 7: FFS | R5-190848 R5-192429 R5-193899 |  | 1 | 100% | [5 empty] | 7 | 100% |  |  | 1 | 100% |  |  | 1 | 100%
325 | Y | 38.521-3 | 7.6B.3.2 | Out-of-band blocking for intra-band non-contiguous EN-DC in FR1 (2 CCs) |  | CAICT | Opt 3: RAN5#86 (Feb-20) Opt 4: RAN5#93 (Nov-21) Opt 7: FFS | R5-190848 R5-192430 R5-193900 |  | 1 | 100% | [5 empty] | 7 | 100% |  |  | 1 | 100% |  |  | 1 | 100%
326 | Y | 38.521-3 | 7.6B.3.3 | Out-of-band blocking for inter-band EN-DC within FR1 (2 CCs) |  | CAICT | Opt 3: RAN5#83 (May-19) Opt 4: RAN5#93 (Nov-21) Opt 7: FFS | R5-190850 R5-192431 R5-194349 R5-210502 |  | 1 | 100% | [5 empty] | 4 | 100% |  |  | 1 | 100% |  |  | 1 | 100%
|  | 38.521-3 | 7.6B.3.3_1 | Out-of-band blocking for EN-DC within FR1 (>2 CCs) | [5 empty] | 0
327 | Y | 38.521-3 | 7.6B.3.3_1.1 | Out-of-band blocking for EN-DC within FR1 (3 CCs) |  | CAICT | Opt 3: RAN5#86 (Feb-20) Opt 4: RAN5#93 (Nov-21) Opt 7: FFS |  |  | 1 | 100% | [5 empty] | 7 | 100% |  |  | 1 | 100% |  |  | 1 | 100%
328 | Y | 38.521-3 | 7.6B.3.3_1.2 | Out-of-band blocking for EN-DC within FR1 (4 CCs) |  | CAICT | Opt 3: RAN5#86 (Feb-20) Opt 4: RAN5#93 (Nov-21) Opt 7: FFS |  |  | 1 | 100% | [5 empty] | 7 | 100% |  |  | 1 | 100% |  |  | 1 | 100%
329 |  | 38.521-3 | 7.6B.3.3_1.3 | Out-of-band blocking for EN-DC within FR1 (5 CCs) |  | CAICT |  |  | Deleted to Align with Core spec | 0
330 |  | 38.521-3 | 7.6B.3.3_1.4 | Out-of-band blocking for EN-DC within FR1 (6 CCs) |  | CAICT |  |  | Deleted to Align with Core spec | 0
331 | Y | 38.521-3 | 7.6B.3.3A | Out-of-band blocking for inter-band NE-DC within FR1 (2 CCs) |  |  | Opt 4: RAN5#93 (Nov-21) Opt 7: FFS |  |  | 1 | 0% | [9 empty] | 1 | 0% |  |  | 1 | 0%
296 |  | 38.521-3 | 7.6B.3.4 | Void |  | CAICT | <Autofilled> |  | SA FR2 requirements are void for Out of band blocking. No updates in 38.521-3 needed. | 0 | 0% | [11 empty] | 0
|  | 38.521-3 | 7.6B.3.4_1 | Void
297 |  | 38.521-3 | 7.6B.3.4_1.1 | Void |  | CAICT |  |  | SA FR2 requirements are void for Out of band blocking. No updates in 38.521-3 needed. | 0
298 |  | 38.521-3 | 7.6B.3.4_1.2 | Void |  | CAICT |  |  | SA FR2 requirements are void for Out of band blocking. No updates in 38.521-3 needed. | 0
299 |  | 38.521-3 | 7.6B.3.4_1.3 | Void |  | CAICT |  |  | SA FR2 requirements are void for Out of band blocking. No updates in 38.521-3 needed. | 0
300 |  | 38.521-3 | 7.6B.3.4_1.4 | Void |  | CAICT |  |  | SA FR2 requirements are void for Out of band blocking. No updates in 38.521-3 needed. | 0
301 |  | 38.521-3 | 7.6B.3.5 | Void |  | CAICT |  |  | SA FR2 requirements are void for Out of band blocking. No updates in 38.521-3 needed. | 0
|  | 38.521-3 | 7.6B.4 | Narrow band blocking for DC
332 |  | 38.521-3 | 7.6B.4.0 | Minimum Conformance Requirements |  | CAICT | Opt 3: RAN5#90 (Feb-21) Opt 4: RAN5#93 (Nov-21) Opt 7: FFS | R5-193901 |  | 0.5 | 100% | [5 empty] | 11 | 100% |  |  | 1 | 100% |  |  | 1 | 100%
333 | Y | 38.521-3 | 7.6B.4.1 | Narrow band blocking for intra-band contiguous EN-DC in FR1 (2 CCs) |  | CAICT | Opt 3: RAN5#86 (Feb-20) Opt 4: RAN5#93 (Nov-21) Opt 7: FFS | R5-190851 R5-192432 R5-193902 |  | 1 | 100% | [5 empty] | 7 | 100% |  |  | 1 | 100% |  |  | 1 | 100%
334 | Y | 38.521-3 | 7.6B.4.2 | Narrow band blocking for intra-band non-contiguous EN-DC in FR1 (2 CCs) |  | CAICT | Opt 3: RAN5#86 (Feb-20) Opt 4: RAN5#93 (Nov-21) Opt 7: FFS | R5-190852 R5-192433 R5-193903 |  | 1 | 100% | [5 empty] | 7 | 100% |  |  | 1 | 100% |  |  | 1 | 100%
335 | Y | 38.521-3 | 7.6B.4.3 | Narrow band blocking for inter-band EN-DC within FR1 (1 NR CC) |  | CAICT | Opt 3: RAN5#82 (Feb-19) | R5-190853 R5-192434 |  | 1 | 100% | [5 empty] | 3 | 100%
|  | 38.521-3 | 7.6B.4.3_1 | Narrow band blocking for EN-DC including FR1 (> 2 CCs) | [5 empty] | 0
336 | Y | 38.521-3 | 7.6B.4.3_1.1 | Narrow band blocking for EN-DC within FR1 (3 CCs) |  | CAICT | Opt 3: RAN5#89 (Nov-20) Opt 4: RAN5#93 (Nov-21) Opt 7: FFS | R5-211713 |  | 1 | 100% | [5 empty] | 10 | 100% |  |  | 1 | 100% |  |  | 1 | 100%
337 | Y | 38.521-3 | 7.6B.4.3_1.2 | Narrow band blocking for EN-DC within FR1 (4 CCs) |  | CAICT | Opt 3: RAN5#89 (Nov-20) Opt 4: RAN5#93 (Nov-21) Opt 7: FFS |  |  | 1 | 100% | [5 empty] | 10 | 100% |  |  | 1 | 100% |  |  | 1 | 100%
338 | Y | 38.521-3 | 7.6B.4.3_1.3 | Narrow band blocking for EN-DC within FR1 (5 CCs) |  | CAICT | Opt 3: RAN5#89 (Nov-20) Opt 4: RAN5#93 (Nov-21) Opt 7: FFS |  |  | 1 | 100% | [5 empty] | 10 | 100% |  |  | 1 | 100% |  |  | 1 | 100%
339 |  | 38.521-3 | 7.6B.4.3_1.4 | Void |  | CAICT |  |  | Reserved. | 0
340 | Y | 38.521-3 | 7.6B.4.3A | Narrow band blocking for inter-band NE-DC within FR1 (2 CCs) |  | CMCC | Opt 4: RAN5#93 (Nov-21) Opt 7: FFS | R5-215894 |  | 1 | 50% | [9 empty] | 1 | 100% |  |  | 1 | 0%
|  | 38.521-3 | 7.6B.4.4 | Void |  | CAICT |  |  | SA FR2 requirements are void for Narrow-band blocking. No updates in 38.521-3 needed. | 0
|  | 38.521-3 | 7.6B.4.4_1 | Void |  | CAICT |  |  |  | 0
|  | 38.521-3 | 7.6B.4.4_1.1 | Void |  | CAICT |  |  | SA FR2 requirements are void for Narrow-band blocking. No updates in 38.521-3 needed. | 0
|  | 38.521-3 | 7.6B.4.4_1.2 | Void |  | CAICT |  |  | SA FR2 requirements are void for Narrow-band blocking. No updates in 38.521-3 needed. | 0
|  | 38.521-3 | 7.6B.4.4_1.3 | Void |  | CAICT |  |  | SA FR2 requirements are void for Narrow-band blocking. No updates in 38.521-3 needed. | 0
|  | 38.521-3 | 7.6B.4.4_1.4 | Void |  | CAICT |  |  | SA FR2 requirements are void for Narrow-band blocking. No updates in 38.521-3 needed. | 0
|  | 38.521-3 | 7.6B.4.5 | Void |  | CAICT |  |  | SA FR2 requirements are void for Narrow-band blocking. No updates in 38.521-3 needed. | 0
|  | 38.521-3 | 7.7 | Void
|  | 38.521-3 | 7.7A | Spurious response for CA
|  | 38.521-3 | 7.7B | Spurious Response for DC in FR1
341 |  |  | 7.7B.0 | Minimum Conformance Requirements |  | CAICT | Opt 3: RAN5#90 (Feb-21) Opt 4: RAN5#93 (Nov-21) Opt 7: FFS | R5-193904 |  | 0.5 | 100% | [5 empty] | 11 | 100% |  |  | 1 | 100% |  |  | 1 | 100%
342 | Y | 38.521-3 | 7.7B.1 | Spurious Response for intra-band contiguous EN-DC in FR1 (2 CCs) |  | CAICT | Opt 3: RAN5#86 (Feb-20) Opt 4: RAN5#93 (Nov-21) Opt 7: FFS | R5-190854 R5-192435 R5-193905 |  | 1 | 100% | [5 empty] | 7 | 100% |  |  | 1 | 100% |  |  | 1 | 100%
343 | Y | 38.521-3 | 7.7B.2 | Spurious Response for intra-band non-contiguous EN-DC in FR1 (2 CCs) |  | CAICT | Opt 3: RAN5#86 (Feb-20) Opt 4: RAN5#93 (Nov-21) Opt 7: FFS | R5-190855 R5-192436 R5-193906 |  | 1 | 100% | [5 empty] | 7 | 100% |  |  | 1 | 100% |  |  | 1 | 100%
344 | Y | 38.521-3 | 7.7B.3 | Spurious Response for inter-band EN-DC within FR1 (2 CCs) |  | CAICT | Opt 3: RAN5#83 (May-19) | R5-190856 R5-192437 R5-194349 |  | 1 | 100% | [5 empty] | 4 | 100%
|  | 38.521-3 | 7.7B.3_1 | Spurious Response for EN-DC within FR1 (>2 CCs) |  |  |  |  | Deleted to Align with Core spec
345 | Y | 38.521-3 | 7.7B.3_1.1 | Spurious Response for EN-DC within FR1 (3 CCs) |  | CAICT | Opt 3: RAN5#89 (Nov-20) Opt 4: RAN5#93 (Nov-21) Opt 7: FFS |  |  | 1 | 100% | [5 empty] | 10 | 100% |  |  | 1 | 100% |  |  | 1 | 100%
346 | Y | 38.521-3 | 7.7B.3_1.2 | Spurious Response for EN-DC within FR1 (4 CCs) |  | CAICT | Opt 3: RAN5#89 (Nov-20) Opt 4: RAN5#93 (Nov-21) Opt 7: FFS |  |  | 1 | 100% | [5 empty] | 10 | 100% |  |  | 1 | 100% |  |  | 1 | 100%
347 |  | 38.521-3 | 7.7B.3_1.3 | Spurious Response for EN-DC within FR1 (5 CCs) |  | CAICT |  |  | Deleted to Align with Core spec | 0
348 |  | 38.521-3 | 7.7B.3_1.4 | Spurious Response for EN-DC within FR1 (6 CCs) |  | CAICT |  |  | Deleted to Align with Core spec | 0
349 | Y | 38.521-3 | 7.7B.3A | Spurious Response for inter-band NE-DC within FR1 (2 CCs) |  |  | Opt 4: RAN5#93 (Nov-21) Opt 7: FFS |  |  | 1 | 0% | [9 empty] | 1 | 0% |  |  | 1 | 0%
|  | 38.521-3 | 7.7B.4 | Void |  | CAICT |  |  | SA FR2 requirements are void for Spurious Response. No updates in 38.521-3 needed. | 0
|  | 38.521-3 | 7.7B.4 | Void |  | CAICT |  |  | SA FR2 requirements are void for Spurious Response. No updates in 38.521-3 needed. | 0
|  | 38.521-3 | 7.7B.4_1 | Void |  | CAICT |  |  | SA FR2 requirements are void for Spurious Response. No updates in 38.521-3 needed. | 0
|  | 38.521-3 | 7.7B.4_1.1 | Void |  | CAICT |  |  | SA FR2 requirements are void for Spurious Response. No updates in 38.521-3 needed. | 0
|  | 38.521-3 | 7.7B.4_1.2 | Void |  | CAICT |  |  | SA FR2 requirements are void for Spurious Response. No updates in 38.521-3 needed. | 0
|  | 38.521-3 | 7.7B.4_1.3 | Void |  | CAICT |  |  | SA FR2 requirements are void for Spurious Response. No updates in 38.521-3 needed. | 0
|  | 38.521-3 | 7.7B.4_1.4 | Void |  | CAICT |  |  | SA FR2 requirements are void for Spurious Response. No updates in 38.521-3 needed. | 0
|  | 38.521-3 | 7.7B.5 | Void |  | CAICT |  |  | SA FR2 requirements are void for Spurious Response. No updates in 38.521-3 needed. | 0
|  | 38.521-3 | 7.8 | Void
|  | 38.521-3 | 7.8B | Intermodulation Characteristics for DC in FR1
|  | 38.521-3 | 7.8B.1 | General
|  | 38.521-3 | 7.8B.2 | Wide band Intermodulation
350 |  | 38.521-3 | 7.8B.2.0 | Minimum Conformance Requirements |  | Anritsu | Opt 3: RAN5#82 (Feb-19) Opt 4: RAN5#93 (Nov-21) Opt 7: FFS | R5-192617 |  | 0.5 | 100% | [5 empty] | 3 | 100% |  |  | 1 | 100% |  |  | 1 | 100%
351 | Y | 38.521-3 | 7.8B.2.1 | Wideband Intermodulation for intra-band contiguous EN-DC in FR1 |  | Anritsu | Opt 3: RAN5#93 (Nov-21) Opt 4: RAN5#93 (Nov-21) Opt 7: FFS | R5-192617 R5-211854 | UL Power configuration is TBD | 1 | 80% | [5 empty] | 14 | 80% |  |  | 1 | 80% |  |  | 1 | 80%
352 | Y | 38.521-3 | 7.8B.2.2 | Wideband Intermodulation for intra-band non-contiguous EN-DC in FR1 |  | Anritsu | Opt 3: RAN5#83 (May-19) Opt 4: RAN5#93 (Nov-21) Opt 7: FFS | R5-192617 R5-193314 R5-211854 |  | 1 | 100% | [5 empty] | 4 | 100% |  |  | 1 | 100% |  |  | 1 | 100%
353 | Y | 38.521-3 | 7.8B.2.3 | Wideband Intermodulation for inter-band EN-DC within FR1 (2 CCs) |  | Anritsu | Opt 3: RAN5#83 (May-19) | R5-187279r1 R5-192617 R5-193314 |  | 1 | 100% | [5 empty] | 4 | 100%
|  | 38.521-3 | 7.8B.2.3_1 | Wideband Intermodulation for EN-DC within FR1 (>2 CCs) |  |  | Opt 4: RAN5#93 (Nov-21) Opt 7: FFS |  |  |  | 60% | [9 empty] | 1 | 60% |  |  | 1 | 60%
354 | Y | 38.521-3 | 7.8B.2.3_1.1 | Wideband Intermodulation for EN-DC within FR1 (3 CCs) |  | Anritsu | Opt 3: RAN5#93 (Nov-21) Opt 4: RAN5#93 (Nov-21) Opt 7: FFS | R5-193474 R5-211854 |  | 1 | 80% | [5 empty] | 14 | 100% |  |  | 1 | 70% |  |  | 1 | 70%
355 | Y | 38.521-3 | 7.8B.2.3_1.2 | Wideband Intermodulation for EN-DC within FR1 (4 CCs) |  | Anritsu | Opt 3: RAN5#93 (Nov-21) Opt 4: RAN5#93 (Nov-21) Opt 7: FFS |  |  | 1 | 33.33% | [5 empty] | 14 | 100% |  |  | 1 | 0% |  |  | 1 | 0%
356 | Y | 38.521-3 | 7.8B.2.3_1.3 | Wideband Intermodulation for EN-DC within FR1 (5 CCs) |  | Anritsu | Opt 3: RAN5#93 (Nov-21) Opt 4: RAN5#93 (Nov-21) Opt 7: FFS |  | SA reqs apply; Test can be completed at RAN5#87 | 1 | 0% | [5 empty] | 14 | 0% |  |  | 1 | 0% |  |  | 1 | 0%
357 |  | 38.521-3 | 7.8B.2.3_1.4 | Wideband Intermodulation for EN-DC within FR1 (6 CCs) |  | Anritsu |  |  |  | 0
358 | Y | 38.521-3 | 7.8B.2.3A | Wideband Intermodulation for inter-band NE-DC within FR1 (2 CCs) |  | CMCC | Opt 4: RAN5#93 (Nov-21) | R5-215895 |  | 1 | 100% | [9 empty] | 1 | 100%
|  | 38.521-3 | 7.8B.2.4 | Void |  | Anritsu |  |  |  | 0
|  | 38.521-3 | 7.8B.2.4 | Void |  | Anritsu |  |  |  | 0
|  | 38.521-3 | 7.8B.2.4_1 | Void | [5 empty] | 0
|  | 38.521-3 | 7.8B.2.4_1.1 | Void |  | Anritsu |  |  |  | 0
|  | 38.521-3 | 7.8B.2.4_1.2 | Void |  | Anritsu |  |  |  | 0
|  | 38.521-3 | 7.8B.2.4_1.3 | Void |  | Anritsu |  |  |  | 0
|  | 38.521-3 | 7.8B.2.4_1.4 | Void |  | Anritsu |  |  |  | 0
|  | 38.521-3 | 7.8B.2.5 | Void |  | Anritsu |  |  |  | 0
|  | 38.521-3 | 7.9 | Void
|  | 38.521-3 | 7.9B | Spurious Emissions for DC in FR1
|  | 38.521-3 | 7.9B.0 | Minimum Conformance Requirements |  | Anritsu | Opt 3: RAN5#82 (Feb-19) Opt 4: RAN5#93 (Nov-21) Opt 7: FFS | R5-192618 |  | 0.5 | 100% | [5 empty] | 3 | 100% |  |  | 1 | 100% |  |  | 1 | 100%
359 | Y | 38.521-3 | 7.9B.1 | Spurious Emissions for intra-band contiguous EN-DC in FR1 (2 CCs) |  | Anritsu | Opt 3: RAN5#82 (Feb-19) Opt 4: RAN5#93 (Nov-21) Opt 7: FFS | R5-192618 |  | 1 | 100% | [5 empty] | 3 | 100% |  |  | 1 | 100% |  |  | 1 | 100%
360 | Y | 38.521-3 | 7.9B.2 | Spurious Emissions for intra-band non-contiguous EN-DC in FR1 (2 CCs) |  | Anritsu | Opt 3: RAN5#82 (Feb-19) Opt 4: RAN5#93 (Nov-21) Opt 7: FFS | R5-192618 |  | 1 | 100% | [5 empty] | 3 | 100% |  |  | 1 | 100% |  |  | 1 | 100%
361 | Y | 38.521-3 | 7.9B.3 | Spurious Emissions for inter-band EN-DC within FR1 (1 NR CC) |  | Anritsu | Opt 3: RAN5#81 (Nov-18) Opt 4: RAN5#93 (Nov-21) Opt 7: FFS | R5-187277r1 R5-192618 |  | 1 | 100% | [5 empty] | 2 | 100% |  |  | 1 | 100% |  |  | 1 | 100%
|  | 38.521-3 | 7.9B.3_1 | Spurious Emissions for EN-DC within FR1 (>2 CCs) |  | Anritsu |  |  |  | 0
362 | Y | 38.521-3 | 7.9B.3_1.1 | Spurious Emissions for EN-DC within FR1 (3 CCs) |  | Anritsu | Opt 3: RAN5#91 (May-21) Opt 4: RAN5#93 (Nov-21) Opt 7: FFS | R5-212867 | Test can be completed at RAN5#87 | 1 | 33.33% | [5 empty] | 12 | 100% |  |  | 1 | 0% |  |  | 1 | 0%
363 | Y | 38.521-3 | 7.9B.3_1.2 | Spurious Emissions for EN-DC within FR1 (4 CCs) |  | Anritsu | Opt 3: RAN5#93 (Nov-21) Opt 4: RAN5#93 (Nov-21) Opt 7: FFS |  | Test can be completed at RAN5#87 | 1 | 0% | [5 empty] | 14 | 0% |  |  | 1 | 0% |  |  | 1 | 0%
364 | Y | 38.521-3 | 7.9B.3_1.3 | Spurious Emissions for EN-DC within FR1 (5 CCs) |  | Anritsu | Opt 3: RAN5#93 (Nov-21) Opt 4: RAN5#93 (Nov-21) Opt 7: FFS |  | Test can be completed at RAN5#87 | 1 | 0% | [5 empty] | 14 | 0% |  |  | 1 | 0% |  |  | 1 | 0%
365 |  | 38.521-3 | 7.9B.3_1.4 | Spurious Emissions for EN-DC within FR1 (6 CCs) |  | Anritsu |  |  |  | 0
366 | Y | 38.521-3 | 7.9B.3A | Spurious Emissions for inter-band NE-DC within FR1 (2 CCs) |  | CMCC | Opt 4: RAN5#93 (Nov-21) | R5-215896 |  | 1 | 100% | [9 empty] | 1 | 100%
367 | Y | 38.521-3 | 7.9B.4 | Spurious Emissions for inter-band EN-DC including FR2 (1 NR CC) |  | Anritsu | Opt 3: RAN5#88 (Aug-20) MU: RAN5#88 (Aug-20) TT: RAN5#88 (Aug-20) Opt 4: RAN5#93 (Nov-21) Opt 7: FFS | R5-202905 R5-211928 |  | 1 | 100% | [5 empty] | 9MT2 |  | 100% |  | 1 | 100% |  |  | 1 | 100%
|  | 38.521-3 | 7.9B.4_1 | Spurious Emissions for inter-band EN-DC including FR2 (>2 CCs) |  |  |  |  | Deleted based on R5-214850 | 0
368 | Y | 38.521-3 | 7.9B.4_1.1 | Spurious Emissions for inter-band EN-DC including FR2 (3 CCs) |  | Anritsu | Opt 3: RAN5#93 (Nov-21) MU: RAN5#93 (Aug-21) TT: RAN5#93 (Aug-21) Opt 4: RAN5#93 (Nov-21) Opt 7: FFS |  | Deleted based on R5-214850 | 1 | 0% | [5 empty] | 14MT2 |  | 0% |  | 1 |  | 0% |  | 1 | 0%
369 | Y | 38.521-3 | 7.9B.4_1.2 | Spurious Emissions for inter-band EN-DC including FR2 (4 CCs) |  | Anritsu | Opt 3: RAN5#93 (Nov-21) MU: RAN5#93 (Aug-21) TT: RAN5#93 (Aug-21) Opt 4: RAN5#93 (Nov-21) Opt 7: FFS |  | Deleted based on R5-214850 | 1 | 0% | [5 empty] | 14MT2 |  | 0% |  | 1 |  | 0% |  | 1 | 0%
370 |  | 38.521-3 | 7.9B.4_1.3 | Spurious Emissions for inter-band EN-DC including FR2 (5 CCs) |  | Anritsu |  |  | Deleted based on R5-214850 | 0
371 |  | 38.521-3 | 7.9B.4_1.4 | Spurious Emissions for inter-band EN-DC including FR2 (6 CCs) |  | Anritsu |  |  | Deleted based on R5-214850 | 0
372 |  | 38.521-3 | 7.9B.5 | Spurious Emissions for inter-band EN-DC including both FR1 and FR2 |  | Anritsu |  |  |  | 0.4 | [6 empty] | 9MT2
Annex
373 |  | 38.521-3 | Annex A | Measurement Channels |  | Qualcomm | Opt 3: RAN5#87 (May-20) Opt 4: RAN5#93 (Nov-21) Opt 7: FFS | R5-187041 |  | 0.5 | 100% | [5 empty] | 8 | 100% | 100% | 100% | 1 | 100% | 100% | 100% | 1 | 100%
374 |  |  | Annex B | Propagation Conditions |  | Qualcomm | Opt 3: RAN5#87 (May-20) Opt 4: RAN5#93 (Nov-21) Opt 7: FFS |  |  | 0.5 | 100% | [5 empty] | 8 | 100% | 100% | 100% | 1 | 100% | 100% | 100% | 1 | 100%
375 |  | 38.521-3 | Annex C | Downlink Physical Channels |  | Qualcomm | Opt 3: RAN5#85 (Nov-19) Opt 4: RAN5#93 (Nov-21) Opt 7: FFS |  |  | 0.5 | 100% | [5 empty] | 6 | 100% | 100% | 100% | 1 | 100% | 100% | 100% | 1 | 100%
376 |  | 38.521-3 | Annex D | Characteristics of the Interfering Signal |  | Qualcomm | Opt 3: RAN5#82 (Feb-19) Opt 4: RAN5#93 (Nov-21) Opt 7: FFS |  |  | 0.5 | 100% | [5 empty] | 3 | 100% | 100% | 100% | 1 | 100% | 100% | 100% | 1 | 100%
377 |  | 38.521-3 | Annex E | Global In-Channel Tx Test |  | Qualcomm | Opt 3: RAN5#87 (May-20) Opt 4: RAN5#93 (Nov-21) Opt 7: FFS |  |  | 0.5 | 100% | [5 empty] | 8 | 100% | 100% | 100% | 1 | 100% | 100% | 100% | 1 | 100%
378 |  | 38.521-3 | Annex F | Measurements Uncertainties and Tolerances |  | Docomo | Opt 3: RAN5#93 (Nov-21) Opt 4: RAN5#93 (Nov-21) Opt 7: FFS | R5-185520 R5-186340 R5-188028 R5-188029 R5-211926 R5-211927 R5-211928 |  | 0.5 | 88.57% | [5 empty] | 14 | 90% | 90% | 90% | 1 | 90% | 90% | 90% | 1 | 80%
379 |  | 38.521-3 | Annex G | Uplink Physical Channels |  | Qualcomm | Opt 3: RAN5#89 (Nov-20) Opt 4: RAN5#93 (Nov-21) Opt 7: FFS |  |  | 0.5 | 100% | [5 empty] | 10 | 100% | 100% | 100% | 1 | 100% | 100% | 100% | 1 | 100%
380 |  | 38.521-3 | Annex H | Statistical Testing |  | Qualcomm | Opt 2: RAN5#90 (Feb-21) Opt 3: RAN5#87 (May-20) Opt 4: RAN5#93 (Nov-21) Opt 7: FFS | R5-183949 |  | 0.5 | 100% | 10 |  |  | 100% |  | 8 | 100% | 100% | 100% | 1 | 100% | 100% | 100% | 1 | 100%
381 |  | 38.521-3 | Annex I | Void |  | Qualcomm | Opt 2: RAN5#90 (Feb-21) Opt 3: RAN5#89 (Nov-20) Opt 4: RAN5#93 (Nov-21) Opt 7: FFS | R5-183949 |  | 0.5 | 100% | 10 |  |  | 100% |  | 10 | 100% | 100% | 100% | 1 | 100% | 100% | 100% | 1 | 100%
382 |  | 38.521-3 | Annex J | Test applicability per permitted test method |  | Qualcomm | Opt 2: RAN5#90 (Feb-21) Opt 3: RAN5#89 (Nov-20) Opt 4: RAN5#93 (Nov-21) Opt 7: FFS | R5-183949 |  | 0.5 | 100% | 10 |  |  | 100% |  | 10 | 100% | 100% | 100% | 1 | 100% | 100% | 100% | 1 | 100%
383 |  | 38.521-3 | Annex K | EIRP, TRP, and EIS measurement procedures |  | Qualcomm, Keysight | Opt 2: RAN5#90 (Feb-21) Opt 3: RAN5#89 (Nov-20) Opt 4: RAN5#93 (Nov-21) Opt 7: FFS | R5-182035 R5-182995 |  | 0.5 | 100% | 10 |  |  | 100% |  | 10 | 100% | 100% | 100% | 1 | 100% | 100% | 100% | 1 | 100%
384 |  | 38.521-3 | Annex L | Void |  | Qualcomm, Keysight | Opt 2: RAN5#90 (Feb-21) Opt 3: RAN5#89 (Nov-20) Opt 4: RAN5#93 (Nov-21) Opt 7: FFS | R5-182035 R5-182995 |  | 0.5 | 100% | 10 |  |  | 100% |  | 10 | 100% | 100% | 100% | 1 | 100% | 100% | 100% | 1 | 100%
385 |  | 38.521-3 | Annex M | Dual Uplink Interferer |  | Bureau Veritas | Opt 3: RAN5#89 (Nov-20) Opt 4: RAN5#93 (Nov-21) Opt 7: FFS | R5-181509 R5-184737 R5-192177 |  | 0.5 | 100% | [5 empty] | 10 | 100% | 100% | 100% | 1 | 100% | 100% | 100% | 1 | 100%
386 |  | 38.521-3 | Annex N | Modified MPR behavior |  | Ericsson | Opt 3: RAN5#86 (Feb-20) Opt 4: RAN5#93 (Nov-21) Opt 7: FFS | R5-201198 |  | 0.5 | 100% | [5 empty] | 7 | 100% | 100% | 100% | 1 | 100% | 100% | 100% | 1 | 100%
386 |  | 38.521-3 | Annex O | Change history |  |  | Opt 3: RAN5#86 (Feb-20) Opt 4: RAN5#93 (Nov-21) Opt 7: FFS | R5-201198 |  | 0.5 | 100% | [5 empty] | 7 | 100% | 100% | 100% | 1 | 100% | 100% | 100% | 1 | 100%
End of work plan items. Note! Do not remove this row. Introduce new work plan rows/items above this row.
Note on A7: Unique ID for WP items (unique within the sub-area work plan) Note! As WP item numbers may be referenced from outside of this WP that means: - Do not change number for WP items that have been published. - Do not re-use WP item numbers if a WP item is deleted
Note on B7: Y = the WP Pitem is a test case.