## UE Test Functions
WP Title: | 5GS UE test functions (TS 38.509 and TS 36.509) | [9 empty] | WP item applicability | [9 empty] | End of work plan columns. Note! Do not remove this column.
RAN-CN interface options dependency
WP Scope: | This work plan section covers UE test functions for all SA and NSA options. | [9 empty] | 5GC/NR |  | 5GC/LTE |  | EPC/LTE |  | 5GC/NR master |  | 5GC / LTE master
WP Resp: | Ramakrishnan Thiruvathirai, Rohde & Schwarz |  |  | Ramakrishnan.Thiruvathirai@rohde-schwarz.com
TS Resp: | Ramakrishnan Thiruvathirai, Rohde & Schwarz |  |  | Ramakrishnan.Thiruvathirai@rohde-schwarz.com | [6 empty] | SA |  |  |  | NSA
WP Item ID | TS | Clause | Title | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | WP item compl. | Opt. 2 |  | Opt. 5 |  | Opt. 3 |  | Opt. 4 |  | Opt. 7
[10 empty] | Overall | 100% |  | 100% |  | 100% |  | 85.71% |  | 100%
[10 empty] | Phase 1 | 100% |  | 100% |  | 100% |  | 100%
[10 empty] | Phase 2 |  |  | 100% |  | 100% |  | 0% |  | 100%
[10 empty] | Phase 3 | 100%
[10 empty] | Phase 4 | 100% |  |  |  | 100%
Phase 5
Phase 6
Phase 7
Phase 8
Phase 9
Phase 10
Phase 11
Phase 12
Phase 13
Phase 14
Phase 15
[6 empty] | Overall# WP items: Phase 1 # WP items: Phase 2# WP items: Phase 3# WP items: Phase 4# WP items: Phase 5# WP items: Phase 6# WP items: Phase 7# WP items: Phase 8# WP items: Phase 9# WP items: Phase 10# WP items: Phase 11# WP items: Phase 12# WP items: Phase 13# WP items: Phase 14# WP items: Phase 15# WP items: |  |  |  |  | 7 5 0 1 1 0 0 0 0 0 0 0 0 0 0 0 |  | 5 3 2 0 0 0 0 0 0 0 0 0 0 0 0 0 |  | 6 3 2 0 1 0 0 0 0 0 0 0 0 0 0 0 |  | 7 6 1 0 0 0 0 0 0 0 0 0 0 0 0 0 |  | 7 0 7 0 0 0 0 0 0 0 0 0 0 0 0 0
Start of work plan items. Note! Do not remove this row. Introduce new work plan rows/items below this row.
TS 38.509 work tasks
1 | 38.509 | General | General sections | Specify content for General sections providing auxiliary information in regard to the diferent test functions specified. |  | Opt 2: RAN5#81 (Nov-18) Opt 5: FFS Opt 3: RAN5#79 (May-18) Opt 4: RAN5#94 (Feb-22) Opt 7: FFS | R5-174100, R5-182070, R5-182423, R5-187113, R5-190664, R5-191196 | Remains for NE-DC: Block diagram for NE-DC and UE test loop mode A and B need to be added in clause 5.3.4.1 and 5.3.4.2. | 1 | 80% | 1 | 100% | 1 | 100% | 1 | 100% | 2 | 0% | 2 | 100%
2 | 38.509 | 5.3.4.1, 6.3 | Specific Test Mode functionality: Test Loop Mode A | Specific Test Mode functionality: Test Loop Mode A (loopback of PDCP SDUs for bi-directional NR data radio bearers) | Samsung | Opt 2: RAN5#81 (Nov-18) Opt 5: FFS Opt 3: RAN5#79 (May-18) Opt 4: RAN5#93 (Nov-21) Opt 7: FFS | R5-183081, R5-187113 |  | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 2 | 100%
3 | 38.509 | 5.3.4.2, 6.3 | Specific Test Mode functionality: Test Loop Mode B | Specific Test Mode functionality: Test Loop Mode B (loopback of PDCP SDUs for bi-directional EPS/5GC bearers) | Samsung | Opt 2: RAN5#81 (Nov-18) Opt 5: FFS Opt 3: RAN5#79 (May-18) Opt 4: RAN5#93 (Nov-21) Opt 7: FFS | R5-183081, R5-187684 | HAndling of SDAP was originally considered as a separate Test Mode but at RAN5#81 was added as part of Loop Mode B | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 2 | 100%
4 | 38.509 | 5.4, 6.4 | Specific Test Mode functionality: UE beamlock function for NR FR2 testing | Specific Test Mode functionality: UE beamlock function | Keysight | Opt 2: RAN5#81 (Nov-18) Opt 3: RAN5#81 (Nov-18) Opt 4: RAN5#93 (Nov-21) Opt 7: FFS | R5-176997, R5-182354, R5-183701, R5-185523, R5-186863, R5-199307 | RF part for Option 3 completed. Usage for SIG under investigation. For Other Options RF and SIG relevant input is expected | 1 | 100% | 1 | 100% | 1 |  | 2 | 100% | 1 | 100% | 2 | 100%
5 | 38.509 | 5.5, 6.5 | Specific Test Mode functionality: UE SS-RSRPB per receiver branch reporting function forNR FR2 testing | Specific Test Mode functionality: UE SS-RSRPB per receiver branch reporting | Qualcomm | Opt 2: RAN5#81 (Nov-18) Opt 3: RAN5#81 (Nov-18) Opt 4: RAN5#93 (Nov-21) Opt 7: FFS | R5-182037, R5-182354, R5-187891, R5-197306 |  | 1 | 100% | 1 | 100% | 1 |  | 2 | 100% | 1 | 100% | 2 | 100%
11 | 38.509 | 5.3.4 | SDP test loop for 5GS and NG-RAN | Specific Test Mode functionality for SDP test loop for 5GS and NG-RAN | Motorola Mobility, Ericsson |  |  | Not pursued. CR with first ideas was submitted to RAN5#80 (R5-185058) but withdrawn because more considerations were needed. At RAN5#81 it was agreed to be added as part of Test Loop Mode B (R5-187684) | 0 |  | 1 |  | 1 |  | 2 |  | 1 |  | 1
12 | 38.509 | 5 | Specific Test Mode functionality: ETC Reset command | Specific Test Mode functionality: Rest UE Possitioning Stored Information | Rohde & Schwarz | Opt 2: RAN5#83 (May-19) Opt 5: FFS Opt 3: RAN5#83 (May-19) Opt 4: RAN5#93 (Nov-21) Opt 7: FFS | R5-191128 | For Option 3 (EN-DC) reference to 36.509 needs to be added as the command will be used over the LTE interface. | 1 | 100% | 3 | 100% | 2 | 100% | 4 | 100% | 1 | 100% | 2 | 100%
13 | 38.509 | 5 | Specific Test Mode functionality: Update UE Location Information | Specific Test Mode functionality: Update UE Location Information and UTC time reset | Rohde & Schwarz |  |  | Not used for minimum performance testing; used for signalling. Not pursued. Present assumption: No need for 5GC - legacy functions in 36.508 | 0 |  | 2 |  | 1 |  | 3 |  | 1 |  | 1
15 | 38.509 | 5.7, 6.7 | NSSAI delete test function | Specific Test Mode functionality: The SS use the NSSAI delete test procedure to delete NSSAI information in the UE such as Default configured NSSAI, Configured NSSAI or Allowed NSSAI information | Qualcomm | Opt 2: RAN5#84 (Aug-19) Opt 5: FFS Opt 4: RAN5#93 (Nov-21) Opt 7: FFS | R5-195334, R5-197184 |  | 1 | 100% | 4 | 100% | 2 | 100% | 1 |  | 1 | 100% | 2 | 100%
TS 36.509 work tasks
10 | 36.509 | General | General sections | Specify content for General sections providing auxiliary information in regard to the diferent test functions specified | Samsung |  | R5-176914 | R5-176914 Withdrawn as RAN5 agreed to specify all 5GS UE test functions in 38.509. | 1
End of work plan items. Note! Do not remove this row. Introduce new work plan rows/items above this row. | End of work plan items. Note! Do not remove this row. Introduce new work plan rows/items above this row.
Note on A6: Unique ID for WP items (unique within the sub-area work plan) Note! As WP item numbers may be referenced from outside of this WP that means: - Do not change number for WP items that have been published. - Do not re-use WP item numbers if a WP item is deleted
Note on J6: The WP item's weight number is used to set the reletive weights between WP items used in the overall calculation of completeness. Setting it to 0 fpr a WP item means that it will not be included at all in the calculation.