## Guideline
| 3GPP RAN5#93-e |  |  | R5-216631
Electronic Meeting, 8- 19 November 2021
| Agenda Item: |  | 4.2.1
| Source: |  | Ericsson
| Title: |  | Checklist - Adding new NR band or channel bandwidth to existing bands
| Work item code: |  | -
| Document for: |  | Information
Check List for adding new NR bands and for new channel bandwidth to existing NR bands
The purpose of this document is to provide a check list for actions needed to introduced new NR bands or new channel bandwidths to existing NR bands into 3GPP RAN5 test specifications for 5G / NR. The document also calculates the overall completion status per TS that is to be included in the overall work plan. How to use it: - Use applicable work sheet to identify what need to be added to 3GPP RAN5 TSs to introduce the configuration (You can remove the non-applicable work sheets). - Initially all action items are set to 0% in the status column. - For NOT applicable action items clear the cell in the status column (delete the 0% value). - For Applicable action items indicate use the drop down box in the status column to indicate current completion (values of 0% to 100% in steps of 10%). - The overall completion per TS is shown on rows 1 and 2 (columns I to Q). Note1: If the new band also introduces a new channel bandwidth then need also the check list for New CBW be considered. Note2: This checklist does not cover Rx aspects for new SUL bands. Please refer to the NR CA/DC configuration checklist for the Rx aspects of new SUL bands with its relevant CA configurations. On request You need to provide the overall completion values for the configuration in the format for inclusion in the relevant overall work plan (5GS_NR_LTE-UEConTest, NR_bands_BW_R16-UEConTest, NR_bands_BW_R17-UEConTest).
If You have questions please contact:
Leif Mattisson, Ericsson |  | leif.mattisson@ericsson.com

## New NR band
NR band: | nXX | [5 empty] | 38.508-1 | 38.508-2 | 38.521-x: Common | 38.521-x: Tx test cases | 38.521-x: Rx test cases | 38.523-3: Protocol | 38.533: RRM & 37.571-1: LCS | 38.903: MU and TT | 38.905: Test point analysis
Note! If the new band also introduces a new channel bandwidth then need also the check list for New CBW be considered. | [6 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
TS/TR | Check item | Clause / Test case | Area | Action | Status | Comments
Action for TS 38.508-1 - Common test environment
38.508-1 | 1 | FR1: 4.3.1.1 FR2: 4.3.1.2 | Test frequencies | Add test frequencies for the new band. | 0%
38.508-1 | 2 | 6.2.3.1 | Test frequencies | Add test frequencies for protocol testing and the new band for the chosen default channel bandwidth. | 0%
38.508-1 | 3 | FR1: Table 4.3.1-1 FR2: Table 4.3.1-2 | Test channel bandwidth | Add the RF Mid Test Channel bandwidths for the NR band | 0%
38.508-1 | 4 | FR1: Table 4.3.1.0B-1 FR2: Table 4.3.1.0B-2 | Test channel bandwidth | Add the RF Low Test Channel bandwidths for the NR band | 0%
38.508-1 | 5 | FR1: Table 4.3.1.0C-1 FR2: Table 4.3.1.0C-2 | Test channel bandwidth | Add the RF High Test Channel bandwidths for the NR band | 0%
Action for TS 38.508-2 - Implementation Conformance Statements
38.508-2 | 1 | FR1 FDD: Table A.4.3.1-1 FR1 TDD: Table A.4.3.1-2 FR2 TDD: Table A.4.3.1-3 FR1 SUL: Table A.4.3.1-5 FR1 SDL: Table A.4.3.1-6 | Band ICS | Add Baseline Implementation Capabilities for the new band to the relevant table in clause A.4.3.1. | 0%
38.508-2 | 2 | PC1, PC2, PC4: A.4.3.1-4 to A.4.3.1-4x | Power class capability | If power classes PC1, PC2 or PC4 covered by the band addition work item then add the applicable NR power class Baseline Implementation Capabilities to the relevant table in clause A.4.3.1. | 0%
38.508-2 | 3 | FR1: Table A.4.3.9-4 FR2: Table A.4.3.9-2, Table A.4.3.9-3 | Additional capabilities for UE declared capability | Add the additional applicable capabilities for the NR band to the relevant table in clause A.4.3.9. | 0%
Action for TS 38.521-x - Common clauses
38.521-x | 1 | 5.2 | Operating band | Add the operating band | 0%
38.521-x | 2 | 5.3.5 | Channel bandwidth | Add the channel bandwidths for the band | 0%
38.521-x | 3 | 5.3.6 | Asymmetric Channel bandwidth | Add the asymmetric channel bandwidths for the band if applicable. If not applicable for the band then clear the status column | 0%
38.521-x | 4 | 5.4.2.3 | NR-ARFCN | Add the applicable NR-ARFCN for the band | 0%
38.521-x | 5 | 5.4.3.3 | SS raster | Add the applicable SS raster for the band | 0%
38.521-x | 6 | FDD: 5.4.4 TDD: N/A | FDD TX-RX frequency seperation | FDD band: Add the default UE TX-RX frequency separation for the band TDD band: Clear the status column | 0%
Action for TS 38.521-x - RF Transmitter test cases
38.521-x | 1 | 6.2.1 | UE maximum output power | Add minimum requirement and test requirement for the band | 0%
38.521-x | 2 | 6.2.2 | UE maximum output power reduction | Add test requirement vs appliable power classes for the band. | 0%
38.521-x | 3 | 6.2.3 | UE additional maximum output power reduction | Add minimum requirement and test requirement for the band. If new NS value introduced by the band: Add test points and test configuration for the new NS value as per test points analysis (see check item for TR 38.905). | 0%
38.521-x | 4 | 6.2C.3 | UE maximum output power for SUL | For SUL bands: Add test requirement for the SUL band. For other bands: Clear the status column | 0%
38.521-x | 5 | 6.2C.4 | UE maximum output power reduction for SUL | For SUL bands: Add test requirement for the SUL band. For other bands: Clear the status column | 0%
38.521-x | 6 | 6.2C.5 | UE additional maximum output power reduction for SUL | For SUL bands: 1. Add minimum requirement and test requirement for the SUL band. 2. If new NS value introduced by the band: Add test points and test configuration for the new NS value as per test points analysis (see check item for TR 38.905). For other bands: Clear the status column | 0%
38.521-x | 7 | 6.2D.1 | UE maximum output power for UL MIMO | For bands supporting UL MIMO: Add minimum requirement and test requirement for the band. For other bands: Clear the status column. | 0%
38.521-x | 8 | 6.2D.2 | UE maximum output power reduction for UL MIMO | For bands supporting UL MIMO: Add test requirement for the band. For other bands: Clear the status column. | 0%
38.521-x | 9 | 6.2D.3 | UE additional maximum output power reduction for UL MIMO | For bands supporting UL MIMO: 1. Add minimum requirement and test requirement for the band. 2. If new NS value introduced by the band: Add test points and test configuration for the new NS value as per test points analysis (see check item for TR 38.905). For other bands: Clear the status column | 0%
38.521-x | 10 | 6.3C.1 | Minimum output power for SUL | For SUL bands: If the CBW of SUL band is not included in table 6.3C.1.5-1, adding test requirements for the missing CBW for SUL band. For other bands: Clear the status column | 0%
38.521-x | 11 | 6.3C.2 | Transmit OFF power for SUL | For SUL bands: If the CBW of SUL band is not included in table 6.3C.2.5-1 and 6.3C.2.5-2, adding test requirements for the missing CBW for SUL band. For other bands: Clear the status column | 0%
38.521-x | 12 | 6.3C.3 | Transmit ON/OFF time mask for SUL | For SUL bands: If the CBW of SUL band is not included in tables in 6.3C.1.5, adding test requirements for the missing CBW for SUL band in 6.3C.3.1.5. For other bands: Clear the status column | 0%
38.522-x | 13 | 6.3C.4.1 | Absolute power tolerance for SUL | For SUL bands: If the CBW of SUL band is not included in tables in 6.3C.4.1.5, adding test requirements for the missing CBW for SUL band in 6.3C.4.1.5. For other bands: Clear the status column | 0%
38.523-x | 14 | 6.3C.4.2 | Relative power tolerance for SUL | For SUL bands: If the CBW of SUL band is not included in table 6.3C.4.2.4-1, adding test parameters for the missing CBW for SUL band in6.3C.4.2.4-1 For other bands: Clear the status column | 0%
38.521-x | 15 | 6.5.2.3 | Additional spectrum emission mask | If new NS value introduced by the band then add requirements for the new NS value as needed. If not then clear the status column. | 0%
38.521-x | 16 | 6.5.3.2 | Spurious emissions for UE co-existence | Add protection requirements for the new bands and existing bands against the new band | 0%
38.521-x | 17 | 6.5.3.3 | Additional spurious emissions | If new NS value introduced by the band and additional requirement is specified for the NS value then add requirements for the new NS value as needed. If not then clear the status column. | 0%
38.521-x | 18 | 6.5C.2.3 | Additional spectrum emission mask for SUL | For SUL bands: If new NS value introduced by the band and additional requirement is specified for the NS value then add requirements for the new NS value as needed. If not then clear the status column. For other bands: clear the status column | 0%
38.521-x | 19 | 6.5C.2.4.2 | UTRA ACLR for SUL | For SUL bands: If new NS value introduced by the band: add the NS value for SUL band in table 6.5C.2.4.2.4-2. For other bands: clear the status column | 0%
38.521-x | 20 | 6.5C.3.3 | Additional spurious emissions for SUL | For SUL bands: If new NS value introduced by the band: add test configuration for the NS value for SUL band in table 6.5C.3.3.4.as per test points analysis (see check item for TR 38.905) For other bands: clear the status column | 0%
38.521-x | 21 | 6.5D.1 | Occupied bandwidth for UL MIMO | For bands supporting UL MIMO: 1. Check if band need to be added to Table 6.5D.1.4.1-2: Test frequency exceptions for Occupied Bandwidth. For other bands: Clear the status column | 0%
38.521-x | 22 | 6.5D.2.3 | Additional spectrum emission mask for UL MIMO | For bands supporting UL MIMO: 1. Add minimum requirement and test requirement for the band. 2. If new NS value introduced by the band: Add test points and test configuration for the new NS value as per test points analysis (see check item for TR 38.905). For other bands: Clear the status column | 0%
38.521-x | 23 | 6.5D.2.4.2 | UTRA ACLR for UL MIMO | For bands supporting UL MIMO: 1. Add minimum requirement and test requirement for the band. 2. If new NS value introduced by the band: Add test points and test configuration for the new NS value as per test points analysis (see check item for TR 38.905). For other bands: Clear the status column | 0%
38.521-x | 21 | 6.5D.3.3 | Additional spurious emissions for UL MIMO | For bands supporting UL MIMO: 1. Add minimum requirement and test requirement for the band. 2. If new NS value introduced by the band: Add test points and test configuration for the new NS value as per test points analysis (see check item for TR 38.905). For other bands: Clear the status column | 0%
Action for TS 38.521-x - RF Receiver test cases
38.521-x | 1 | 7.3.2 | Reference sensitivity power level | Add minimum requirement, test configuration, and test requirement for the band | 0%
38.521-x | 2 | 7.6.2 | In-band blocking | Add minimum requirement and test requirement for the band | 0%
38.521-x | 3 | 7.6.3 | Out-of-band blocking | Add minimum requirement and test requirement for the band | 0%
38.521-x | 4 | 7.6.4 | Narrow band blocking | FR1: Add minimum requirement and test requirement for the band FR2: Clear status column. | 0%
Action for TS 38.523-3 - Protocol / TTCN
38.523-3 | 1 | 11 | Protocol test execution | If the band's overall bandwidth is less than 4*default CBW then add protocol test execution guideline (some protocol test cases use up to 4 inter-frequency cells). If the band's overall bandwidth is larger than 4*default CBWnot then there is no impact on 38.523-3. | 0%
Action for TS 38.533 - RRM & TS 37.571-1 Location Services
38.533 | 1 | FR1: 3A.4.1 FR2: 3A.4.2 | NR band group RRM | 1. Add band to NR band groups in clause 3A.4. 2. If the NR bands introduces a new NR Band group, an analysis of the impact should be provided | 0%
37.571-1 | 2 | 4.12.3 | NR band group LS | No need to add NR band groups in TS 37.571-1 for location services test cases as clause 4.12.2 refers to TS 38.533 clause 3A.4 for the NR band groups. |  | No changes needed
Action for TS 38.903 MU/TT for impacted transmitter and receiver test cases
38.903 | 1 |  | MU/TT FR1 | No specific new MU/TT analysis needed for new FR1 bands. |  | No changes needed
38.903 | 2 |  | MU/TT FR2 | Check if MU/TT analysis is needed for the new band. | 0%
Action for TR 38.905 Test Points analysis for impacted transmitter and receiver test cases
38.905 | 1 | FR1: 4.1.1.1 FR2: 4.2.1.1 | TP analysis A-MPR | If new NS value document test point analysis A-MPR and single carrier. If not then clear the status column. | 0%
End of check list
Note on B3: Check item number within the TS, 1,2,3 etc.
Note on C3: Impacted clause in the TS: or list of clauses if the applicable configurations and action is the same.
Note on D3: The type of configuration(s) the action applies to, could be “All” if all are impacted.
Note on E3: Action on the responsible for the configuration to check/update etc.
Note on F3: Status of the analysis: Check: The action need to be checked (not started yet) Not Applicable: Item not applicable for the configuration Ongoing: Action on-going Completed: Action completed

## New CBW
NR band: | nXX | New channel bandwidth(s): | xx MHz, yy MHz.... |  |  |  | 38.508-1 | 38.508-2 | 38.521-x: Common | 38.521-x: Tx test cases | 38.521-x: Rx test cases | 38.523-3: Protocol | 38.533: RRM & 38.571-1: LCS | 38.903: MU and TT | 38.905: Test point analysis
TS/TR | Check item | Clause / Test case | Area | Action | Status | Comments | 0% |  | 0% | 0% | 0% |  |  |  | 0%
Action for TS 38.508-1 - Common test environment
38.508-1 | 1 | FR1: 4.3.1.1 FR2: 4.3.1.2 | Test frequencies | Add test frequencies for the new channel bandwidth for the band. | 0%
38.508-1 | 2 | FR1: Table 4.3.1-1, Table 4.3.1.0B-1, Table 4.3.1.0C-1 FR2: Table 4.3.1-1, Table 4.3.1.0B-2, Table 4.3.1.0C-2 | Test channel bandwidth | Check if the new channel bandwidth impacts Low, Mid or High Test channel bandwidth for the NR band | 0%
Action for TS 38.508-2 - Implementation Conformance Statements
38.508-2 | 1 |  | ICS | None |  | No changes needed
Action for TS 38.521-x - Common clauses
38.521-x | 1 | 5.3.2 | Maximum transmission bandwidth | Add the channel bandwidth | 0%
38.521-x | 2 | 5.3.3 | Minimum guard band | Add the channel bandwidth | 0%
38.521-x | 3 | 5.3.5 | Channel bandwidth | Add the channel bandwidth for the bands | 0%
38.521-x | 4 | Annex A | Measurement channels | Check if need to add new channel bandwidth to UL or DL RMC. | 0%
38.521-x | 5 | Annex C | Downlink physical channels | Check if need to add new channel bandwidth to default downlink power levels | 0%
38.521-x | 6 | Annex D | Characteristics of the Interfering Signal | Check if need to add new channel bandwidth to description of interference signals | 0%
Action for TS 38.521-x - RF Transmitter test cases
38.521-x | 1 | 6.1 | General | Check if need to add new channel bandwidth to common uplink configuration. | 0%
38.521-x | 2 | 6.2.2 | UE maximum output power reduction | Check if need to add new channel bandwidth to uplink configuration for almost contiguous allocation. | 0%
38.521-x | 3 | 6.2.3 | UE additional maximum output power reduction | 1. Check if need to add new channel bandwidth to minimum requirement, test configuration and test requirement. 2. Add relevant test points (TPs) based on the TP analysis if the new channle bandwidth has impact to an NS value and corresponding emission requirements | 0%
38.521-x | 4 | 6.3.1 | Minimum output power | Check if need to add new channel bandwidth to minimum requirement and test requirement. | 0%
38.521-x | 5 | 6.3.2 | Transmit OFF power | Check if need to add new channel bandwidth to minimum requirement and test requirement. | 0%
38.521-x | 6 | 6.3.3.2 | General ON/OFF time mask | Check if need to add new channel bandwidth to test requirement. | 0%
38.521-x | 7 | 6.3.3.6 | SRS time mask | Check if need to add new channel bandwidth to test configuration and test requirement. | 0%
38.521-x | 8 | 6.3.4.2 | Absolute power tolerance | Check if need to add new channel bandwidth to test requirement. | 0%
38.521-x | 9 | 6.3.4.3 | Power Control Relative power tolerance | Check if need to add new channel bandwidth to test configuration and test requirement. | 0%
38.521-x | 10 | 6.3D.1 | Minimum output power for UL MIMO | For bands supporting UL MIMO: Check if need to add new channel bandwidth to minimum requirement and test requirement. For other bands: Clear the status column | 0%
38.521-x | 11 | 6.3D.2 | Transmit OFF power for UL MIMO | For bands supporting UL MIMO: Check if need to add new channel bandwidth to minimum requirement and test requirement. For other bands: Clear the status column | 0%
38.521-x | 12 | 6.3D.3 | Transmit ON/OFF time mask for UL MIMO | For bands supporting UL MIMO: Check if need to add new channel bandwidth to test requirement. For other bands: Clear the status column | 0%
38.521-x | 13 | 6.3.D.4.1 | Absolute power tolerance for UL MIMO | For bands supporting UL MIMO: Check if need to add new channel bandwidth to test requirement. For other bands: Clear the status column | 0%
38.521-x | 14 | 6.3.D.4.2 | Power Control Relative power tolerance for UL MIMO | For bands supporting UL MIMO: Check if need to add new channel bandwidth to test requirement. For other bands: Clear the status column | 0%
38.521-x | 15 | 6.5.1 | Occupied bandwidth | Check if need to add new channel bandwidth to minimum requirement and test requirement. | 0%
38.521-x | 16 | 6.5.2.2 | Spectrum Emission Mask | Check if need to add new channel bandwidth to minimum requirement and test requirement. | 0%
38.521-x | 17 | 6.5.2.3 | Additional Spectrum Emission Mask | Check if need to add new channel bandwidth to minimum requirement and test requirement. | 0%
38.521-x | 18 | 6.5.2.4.1 | NR ACLR | Check if need to add new channel bandwidth to minimum requirement and test requirement. | 0%
38.521-x | 19 | 6.5.2.4.2 | UTRA ACLR | Check if need to add new channel bandwidth to test requirement. | 0%
38.521-x | 20 | 6.5.3.3 | Additional spurious emissions | Check if need to add new channel bandwidth to minimum requirement and test requirement. | 0%
38.521-x | 21 | 6.5C.1 | Occupied bandwidth for SUL | For bands supporting SUL Band: Check if need to add new channel bandwidth to test requirement. For other bands: Clear the status column. | 0%
38.521-x | 22 | 6.5C.2.2 | Spectrum Emission Mask for SUL | For bands supporting SUL Band: Check if need to add new channel bandwidth to test requirement. For other bands: Clear the status column. | 0%
38.521-x | 23 | 6.5C.2.3 | Additional Spectrum Emission Mask for SUL | For bands supporting SUL Band: Check if need to add new channel bandwidth to test requirement. For other bands: Clear the status column. | 0%
38.521-x | 24 | 6.5C.2.4.1 | NR ACLR for SUL | For bands supporting SUL Band: Check if need to add new channel bandwidth to test requirement. For other bands: Clear the status column. | 0%
38.521-x | 25 | 6.5C.2.4.2 | UTRA ACLR for SUL | For bands supporting SUL Band: Check if need to add new channel bandwidth to test requirement. For other bands: Clear the status column. | 0%
38.521-x | 26 | 6.5D.1 | Occupied bandwidth for UL MIMO | For bands supporting UL MIMO: Check if need to add new channel bandwidth to test requirement. For other bands: Clear the status column | 0%
38.521-x | 27 | 6.5D.2.2 | Spectrum Emission Mask for UL MIMO | For bands supporting UL MIMO: Check if need to add new channel bandwidth to test requirement. For other bands: Clear the status column | 0%
38.521-x | 28 | 6.5D.2.3 | Additional Spectrum Emission Mask for UL MIMO | For bands supporting UL MIMO: Check if need to add new channel bandwidth to minimum requirement and test requirement. For other bands: Clear the status column | 0%
38.521-x | 29 | 6.5D.2.4.1 | NR ACLR for UL MIMO | For bands supporting UL MIMO: Check if need to add new channel bandwidth to test requirement. For other bands: Clear the status column | 0%
38.521-x | 30 | 6.5D.2.4.2 | UTRA ACLR for UL MIMO | For bands supporting UL MIMO: Check if need to add new channel bandwidth to test requirement. For other bands: Clear the status column | 0%
38.521-x | 33 | 6.5D.3.3 | Additional spurious emissions for UL MIMO | For bands supporting UL MIMO: Check if need to add new channel bandwidth to test requirement. For other bands: Clear the status column | 0%
Action for TS 38.521-x - RF Receiver test cases
38.521-x | 1 | 7.3.2 | Reference sensitivity power level | Check if need to add new channel bandwidth to minimum requirement and test requirement. | 0%
38.521-x | 2 | 7.4 | Maximum input level | Check if need to add new channel bandwidth to minimum requirement and test requirement. | 0%
38.521-x | 3 | 7.4D | Maximum input level for UL MIMO | For bands supporting UL MIMO: Check if need to add new channel bandwidth to test requirement. For other bands: Clear the status column. | 0%
38.521-x | 4 | 7.5 | Adjacent channel selectivity | Check if need to add new channel bandwidth to minimum requirement and test requirement. | 0%
38.521-x | 5 | 7.6.2 | Inband Blocking | Check if need to add new channel bandwidth to minimum requirement and test requirement. | 0%
38.521-x | 6 | 7.6.3 | Out-of-band blocking | Check if need to add new channel bandwidth to minimum requirement and test requirement. | 0%
38.521-x | 7 | 7.6.4 | Narrow band blocking | Check if need to add new channel bandwidth to minimum requirement and test requirement. | 0%
38.521-x | 8 | 7.7 | Spurious response | Check if need to add new channel bandwidth to minimum requirement and test requirement. | 0%
38.521-x | 9 | 7.7D | Spurious response for UL MIMO | For bands supporting UL MIMO: Check if need to add new channel bandwidth to test requirement. For other bands: Clear the status column. | 0%
38.521-x | 10 | 7.8 | Intermodulation characteristics | Check if need to add new channel bandwidth to minimum requirement and test requirement. | 0%
Action for TS 38.523-3 - Protocol / TTCN
38.523-3 | 1 | 11 | Protocol test execution | None |  | No changes needed
Action for TS 38.533 - RRM & TS 37.571-1 Location Services
38.533 | 1 | FR1: 3A.4.1 FR2: 3A.4.2 | NR band group RRM | None |  | No changes needed
38.571-1 | 1 | 4.12.3 | NR band group LS | None |  | No changes needed
Action for TS 38.903 MU/TT for impacted transmitter and receiver test cases
38.903 | 1 |  | MU/TT FR1 | No specific new MU/TT analysis needed for new channel bandwidth to FR1 bands |  | No changes needed
38.903 | 1 |  | MU/TT FR2 | No specific new MU/TT analysis needed for new channel bandwidth to FR2 bands |  | No changes needed
Action for TR 38.905 Test Points analysis for impacted transmitter and receiver test cases
38.905 | 1 | FR1: 4.1.1.1 FR2: 4.2.1.1 | TP analysis A-MPR | Check if need to updated the test point analysis for A-MPR and single carrier case due to the addition of the new channel bandwidth | 0%
End of check list
Note on B2: Check item number within the TS, 1,2,3 etc.
Note on C2: Impacted clause in the TS: or list of clauses if the applicable configurations and action is the same.
Note on D2: The type of configuration(s) the action applies to, could be “All” if all are impacted.
Note on E2: Action on the responsible for the configuration to check/update etc.
Note on F2: Status of the analysis: Check: The action need to be checked (not started yet) Not Applicable: Item not applicable for the configuration Ongoing: Action on-going Completed: Action completed