## Cover sheet
3GPP TSG-RAN WG5 Meeting #93-e | [10 empty] | R5-217020
Electronic Meeting, 08th Nov– 19th Nov 2021
Agenda Item: | 7.4.2
Source: | Huawei, Hisilicon
Title: | WP UE Conformance Test Aspects - Rel-16 NR Mobility Enhancement
Work item code: | NR_Mob_enh-UEConTest
Release: | Rel-16
Document for: | Information
RAN5 WP template v2.0
1. Introduction
The objective of the work item is to define the UE conformance requirements corresponding to WID on NR R16 Mobility Enhancement with Unique identifier 800087. The RAN5 areas of RRM and Protocol conformance test specifications with NR R16 Mobility Enhancement operation will be covered. At the RAN#88 meeting in June 2020 the Rel-16 RAN5 work item for UE Conformance Test Aspects for NR Mobility Enhancement was approved [1]. The purpose of present document is to provide a workplan for the RAN5 work item on the conformance test cases for the core requirement introduced by the core and performance work items. The workplan is updated after each RAN5 meeting to give the status of the work item.
2. Work item status
Estimation of WI overall completion:
Area |  | Completion | Number of new completed test cases (Note 1) | Number of new test cases | Comments
Overall completion |  | 88% (+26%) | 12 (+9) | 25
Completion Compensation |  | -
| Note 1: | Only test cases completed for all applicable WP areas and sub-areas are counted. For completed test cases per WP areas and WP sub-areas see below.
Estimation WI completion per area and sub-area:
|  | Completion | Number of new completed test cases | Number of new test cases | Comments
SA Option 2 (SA NR) |  | 91.9% (+24.6%) | 12 (+9) | 22
FR1 |  | 96% (+28.4%) | 16 (+10) | 18
FR2 |  | 87.7% (+15.8%) | 0 | 6
FR1 + FR2 |  | 68.3% (+17.7%) | 0 | 2
NSA Option 3 (EN-DC) |  | 70.7% (+30%) | 0 | 3
FR1 |  | 73.2% (+32.5%) | 2 (+2) | 3
FR2 |  | 68.2% (+27.5%) | 0 | 3
FR1 + FR2
Estimation of completion per TS (area):
|  | TS/TR overall completion |  |  | SA Option 2 (SA NR) | [8 empty] | NSA Option 3 (EN-DC)
TS/TR Scope | TS/TR | Completion | Number of new completed test cases | Number of new test cases | FR1 |  |  | FR2 |  |  | FR1 + FR2 |  |  | FR1 |  |  | FR2 |  |  | FR1 + FR2
[5 empty] | Completion | Number of new completed test cases | Number of new test cases | Completion | Number of new completed test cases | Number of new test cases | Completion | Number of new completed test cases | Number of new test cases | Completion | Number of new completed test cases | Number of new test cases | Completion | Number of new completed test cases | Number of new test cases | Completion | Number of new completed test cases | Number of new test cases
5GS
5GS Common
Common test environment | 38.508-1 | 94.4% (+34.4%) |  |  | 95% (+35%) |  |  | 95% (+35%) | [5 empty] | 90% (+30%) |  |  | 90% (+30%)
Common ICS | 38.508-2 | 94.4% (+4.4%) |  |  | 95% (+5%) |  |  | 95% (+5%) | [5 empty] | 90% |  |  | 90%
NR RF/RRM
RRM test cases | 38.533 | 86.9% (+18.1%) | 6 (+6) | 12 | 91.5% (+24.9%) | 6 (+6) | 8 | 80.6% (+6.4%) | 0 | 2 | 70% (+10%) | 0 | 2
Applicability RF, Demod/QSI and RRM test cases | 38.522 | 100% |  |  | 100% |  |  | 100%
Test Tolerances analysis RRM and RF Rx test cases | 38.903 | 73.8% (+73.8%) |  |  | 80% (+80%) | [5 empty] | 0%
5GS RAN and CN protocols
Protocol test cases | 38.523-1 | 92.5% (+29.4%) | 6 (+3) | 13 | 100% (+32%) | 10 (+4) | 10 | 90% (+22.5%) | 0 | 4 |  |  |  | 66.7% (+36.7%) | 2 (+2) | 3 | 60% (+30%) | 0 | 3
Applicability Protocol test cases | 38.523-2 | 99.4% (+29.4%) |  |  | 100% (+30%) |  |  | 100% (+30%) | [5 empty] | 95% (+25%) |  |  | 95% (+25%)
Test suites (TTCN) | 38.523-3
5 References
[1] RP-200893 | New WID on UE conformance test aspects for NR mobility enhancements; Huawei, Hisilicon
Note on B21: Overall completion of the work item reported at an earlier meeting will not be decreased if additional tasks are added or if corrections are made to the work plan. Instead the earlier reported completion status will be kept until necessary progress have been achieved such that completion exceeds the earlier reported completion level. The value of the Completion Compensation value represents the difference in the decrease caused by late additions or corrections to the work plan and the current estimated overall completion. '-' indicates that no compensation is applied.

## WP
WP Title: |  | UE Conformance Test Aspects - Rel-16 NR Mobility Enhancement | [11 empty] | Start of workplan status columns. Note! Do not remove this column. | WP item status | [5 empty] | End of workplan columns. Note! Do not remove this column.
WI code |  | NR_Mob_enh-UEConTest
WP Scope: |  | Conformance test specifications for the core requirements of NR R16 Mobility Enhancement. The RAN5 areas of RRM and Protocol conformance test specifications are to be covered | [13 empty] | vs Area
WP Resp: |  | Wu, Yuchun (Huawei) |  |  | wuyuchun@huawei.com | [5 empty] | WP item completion |  |  |  | SA Option 2 (SA NR) |  |  | NSA Option 3 (EN-DC)
TS Resp: |  | n/a |  |  | n/a
WP Item ID | Is new test case? | TS/area | Clause | Title | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | Overall | SA Option 2 (SA NR) | NSA Option 3 (EN-DC) |  | FR1 | FR2 | FR1 + FR2 | FR1 | FR2 | FR1 + FR2
[15 empty] | 96% (+28.4%) | 87.7% (+15.8%) | 68.3% (+17.7%) | 73.2% (+32.5%) | 68.2% (+27.5%)
[15 empty] | 36 (+1) | 19 (+1) | 3 | 8 | 8 | 0
[15 empty] | 20.7 (-0.3) | 8.1 (+0.1) | 2.1 (-0.4) | 3.8 | 3.8 | 0
5%
Start of work plan items. Note! Do not remove this row. Introduce new work plan rows/items below this row.
5GS
5GS Common
TS 38.508-1: Common test environment
|  | 38.508-1 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | 0
1 |  | 38.508-1 | 4.6 | Default NG-RAN RRC message and information elements contents | Update to RRC messages and IEs | Huawei, Hisilicon | RAN5#93 (Nov-21) | R5-206403 R5-210687 R5-210688 R5-210689 R5-211456 |  | 0.5 | 92.5% (+32.5%) | 95% (+35%) | 90% (+30%) |  | 95% | 95% |  | 90% | 90%
TS 38.508-2: Common ICS
|  | 38.508-2 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | 0
2 |  | 38.508-2 | A.4.3.8 | Mobility Capabilities | Add UE capability | Huawei, Hisilicon | RAN5#93 (Nov-21) | R5-206404 R5-211457 R5-213552 R5-215930 R5-217009 |  | 0.1 | 92.5% (+2.5%) | 95% (+5%) | 90% |  | 95% | 95% |  | 90% | 90%
NR RF/RRM
TS 38.522: Applicability for RRM test cases
38 |  | 38.522 | 4 | RRM test cases applicability | Add applicability for NR MobEnc RRM TCs | Huawei, Hisilicon | RAN5#93 (Nov-21) | R5-215931 R5-216870 |  | 0.1 | 100% | 100% |  |  | 100% | 100%
TS 38.533: Minimum requirements, cell configurations and measurement uncertainty for RRM test cases
39 |  | 38.533 | 6.3.1.0.4 | Minimum conformance requirements for NR FR1- NR FR1 DAPS handover | Add minimum conformance requirements for DAPS handover in SA for FR1 | China Telecommunications | RAN5#93 (Nov-21) | R5-214711 |  | 0.5 | 100% | 100% |  |  | 100%
40 |  | 38.533 | 6.3.3 | Conditional handover | Sub-clause heading | Huawei, Hisilicon | RAN5#93 (Nov-21) | R5-215005 |  | 0 | 100% | 100% |  |  | 100%
41 |  | 38.533 | 6.3.3.0 | Minimum conformance requirements | Sub-clause heading | Huawei, Hisilicon | RAN5#93 (Nov-21) | R5-215005 |  | 0 | 100% | 100% |  |  | 100%
42 |  | 38.533 | 6.3.3.0.1 | Minimum conformance requirements for NR FR1 intra-frequency conditional handover | Add minimum conformance requirements for NR FR1 intra-frequency conditional handover | Huawei, Hisilicon | RAN5#93 (Nov-21) | R5-215005 |  | 0.5 | 100% | 100% |  |  | 100%
43 |  | 38.533 | 6.3.3.0.2 | Minimum conformance requirements for NR FR1 inter-frequency conditional handover | Add minimum conformance requirements fo rNR FR1 inter-frequency conditional handover | Huawei, Hisilicon | RAN5#93 (Nov-21) | R5-215005 |  | 0.5 | 100% | 100% |  |  | 100%
44 |  | 38.533 | 7.3.3 | Conditional handover | Sub-clause heading | Huawei, Hisilicon | RAN5#93 (Nov-21) | R5-215006 |  | 0 | 100% | 100% |  |  |  | 100%
45 |  | 38.533 | 7.3.3.0 | Minimum conformance requirements | Sub-clause heading | Huawei, Hisilicon | RAN5#93 (Nov-21) | R5-215006 |  | 0 | 100% | 100% |  |  |  | 100%
46 |  | 38.533 | 7.3.3.0.1 | Minimum conformance requirements for NR FR2 intra-frequency conditional handover | Add minimum conformance requirements for NR FR2 intra-frequency conditional handover | Huawei, Hisilicon | RAN5#93 (Nov-21) | R5-215006 |  | 0.5 | 100% | 100% |  |  |  | 100%
47 |  | 38.533 | 7.3.3.0.2 | Minimum conformance requirements for NR FR2 inter-frequency conditional handover | Add minimum conformance requirements for NR FR2 inter-frequency conditional handover | Huawei, Hisilicon | RAN5#93 (Nov-21) | R5-215006 |  | 0.5 | 100% | 100% |  |  |  | 100%
48 |  | 38.533 | E.4 | Cell configuration mapping for SA FR1 test cases in Chapter 6 | Add cell configuration mapping for NR FR1 Mob_Enh RRM TCs | Huawei, Hisilicon | RAN5#93 (Nov-21) | R5-215932 |  | 0.1 | 100% | 100% |  |  | 100%
49 |  | 38.533 | E.5 | Cell configuration mapping for SA FR2 test cases in Chapter 7 | Add cell configuration mapping for NR FR2 Mob_Enh RRM TCs | Huawei, Hisilicon | RAN5#93 (Nov-21) | R5-215932 |  | 0.1 | 100% | 100% |  |  |  | 100%
50 |  | 38.533 | F.1 | Measurement uncertainties for FR1 and FR2 | Add maximum allowed measurement uncertainty for NR Mob_Enh RRM TCs | Huawei, Hisilicon | RAN5#93 (Nov-21) | R5-218216 |  | 0.1 | 80% (+80%) | 80% (+80%) |  |  | 80% | 80%
TS 38.533: RRM test cases
|  | 38.533 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | 0
21 | Y | 38.533 | 6.3.1.7 | NR SA FR1 synchronous DAPS handover | Test in A.6.3.1.7 in TS 38.133 | Huawei, Hisilicon | RAN5#93 (Nov-21) | R5-215007 R5-218296 |  | 1 | 100% (+40%) | 100% (+40%) |  |  | 100%
22 | Y | 38.533 | 6.3.1.8 | NR SA FR1 asynchronous DAPS handover | Test in A.6.3.1.8 in TS 38.133 | Huawei, Hisilicon | RAN5#93 (Nov-21) | R5-215008 R5-218297 |  | 1 | 100% (+40%) | 100% (+40%) |  |  | 100%
23 | Y | 38.533 | 6.3.1.9 | NR SA FR1-FR1 synchronous DAPS handover | Test in A.6.3.1.9 in TS 38.133 | China Telecommunications | RAN5#93 (Nov-21) | R5-214395 R5-218215 |  | 1 | 100% (+40%) | 100% (+40%) |  |  | 100%
24 | Y | 38.533 | 6.3.1.10 | NR SA FR1-FR1 asynchronous DAPS handover | Test in A.6.3.1.10 in TS 38.133 | China Telecommunications | RAN5#93 (Nov-21) | R5-214519 R5-218217 |  | 1 | 100% (+40%) | 100% (+40%) |  |  | 100%
25 | Y | 38.533 | 6.3.1.11 | NR SA FR1-FR1 inter-band synchronous DAPS handover | Test in A.6.3.1.11 in TS 38.133 | China Telecommunications | RAN5#93 (Nov-21) | R5-214520 |  | 1 | 60% | 60% |  |  | 60%
26 | Y | 38.533 | 6.3.1.12 | NR SA FR1-FR1 inter-band asynchronous DAPS handover | Test in A.6.3.1.12 in TS 38.133 | China Telecommunications | RAN5#93 (Nov-21) | R5-214521 |  | 1 | 60% | 60% |  |  | 60%
30 | Y | 38.533 | 6.3.3.1 | NR SA FR1 conditional handover | Test in A.6.3.3.1 in TS 38.133 | Huawei, Hisilicon | RAN5#93 (Nov-21) | R5-215009 R5-216873 |  | 1 | 100% (+40%) | 100% (+40%) |  |  | 100%
31 | Y | 38.533 | 6.3.3.2 | NR SA FR1-FR1 conditional handover | Test in A.6.3.3.2 in TS 38.133 | Huawei, Hisilicon | RAN5#93 (Nov-21) | R5-215010 R5-216874 |  | 1 | 100% (+40%) | 100% (+40%) |  |  | 100%
27 | Y | 38.533 | 7.3.1.4 | NR SA FR1-FR2 synchronous DAPS handover | Test in A.7.3.1.4 in TS 38.133 | Huawei, Hisilicon | RAN5#93 (Nov-21) | R5-215011 R5-218298 |  | 1 | 70% (+10%) | 70% (+10%) |  |  |  |  | 70%
28 | Y | 38.533 | 7.3.1.5 | NR SA FR1-FR2 asynchronous DAPS handover | Test in A.7.3.1.5 in TS 38.133 | Huawei, Hisilicon | RAN5#93 (Nov-21) | R5-215012 R5-216876 |  | 1 | 70% (+10%) | 70% (+10%) |  |  |  |  | 70%
32 | Y | 38.533 | 7.3.3.1 | NR SA FR2 conditional handover | Test in A.7.3.3.1 in TS 38.133 | Huawei, Hisilicon | RAN5#93 (Nov-21) | R5-215013 R5-218461 |  | 1 | 70% (+10%) | 70% (+10%) |  |  |  | 70%
33 | Y | 38.533 | 7.3.3.2 | NR SA FR2-FR2 conditional handover | Test in A.7.3.3.2 in TS 38.133 | Huawei, Hisilicon | RAN5#93 (Nov-21) | R5-215014 R5-218299 |  | 1 | 70% (+10%) | 70% (+10%) |  |  |  | 70%
TR 38.903: Test Tolerances analysis RRM and RF Rx test cases
|  | 38.903 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | 0
29 |  | 38.903 | 8 | Grouping of test cases defined in TS 38.533 |  |  | RAN5#93 (Nov-21) | R5-218394 R5-218395 R5-218396 R5-218242 |  | 0.1 | 40% (+40%) | 40% (+40%) |  |  | 80% |  | 0%
RAN and CN protocol
TS 38.523-1: Protocol test cases
|  | 38.523-1 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | 0
Layer 2
3 | Y | 38.523-1 | 7.1.3.4.3 | PDCP handover / DAPS handover / Status reporting / Intra-frequency | **** TP1: [Ref: 38.323, cl.4.2.2, 5.8 and 5.9] WITH: UE in NR RRC_CONNECTED state and supporting Intra-frequency DAPS handover WHEN: UE receives an RRCReconfiguration message including a reconfigurationWithSync for Intra-frequency DAPS handover THEN: PDCP entity associated with a DAPS bearer shall keep DL/UL reception/transmission with the source gNB **** TP2: [Ref: 38.323, cl.5.13] WITH: UE in NR RRC_CONNECTED state and supporting Intra-frequency DAPS handover and receiving an RRCReconfiguration message including a reconfigurationWithSync for Intra-frequency DAPS handover with key change WHEN: UE has performed random access procedure to the target cell successfully THEN: UE shall perform uplink data switching **** TP3: [Ref: 38.323, cl.5.4.1] WITH: UE in NR RRC_CONNECTED state and supporting Intra-frequency DAPS handover and receiving an RRCReconfiguration message including a reconfigurationWithSync for Intra-frequency DAPS handover with key change WHEN: upper layer requests a uplink data switching THEN: UE shall send a PDCP status report for the DAPS bearer **** TP4: [Ref: 38.323, cl.5.4.1] WITH: UE in NR RRC_CONNECTED state and supporting Intra-frequency DAPS handover and receiving an RRCReconfiguration message including a reconfigurationWithSync for Intra-frequency DAPS handover with key change WHEN: upper layer requests a PDCP entity reconfiguration and the associated RLC entity is released for a radio bearer THEN: UE shall send a PDCP status report for the DAPS bearer | Huawei, Hisilicon | RAN5#93 (Nov-21) | R5-213555 R5-216259 |  | 1 | 100% | 100% |  |  | 100%
34 | Y | 38.523-1 | 7.1.3.4.4 | PDCP handover / DAPS handover / Status reporting / Inter-frequency | **** TP1: [Ref: 38.323, cl.4.2.2, 5.8 and 5.9] WITH: UE in NR RRC_CONNECTED state and supporting Inter-frequency DAPS handover WHEN: UE receives an RRCReconfiguration message including a reconfigurationWithSync for Inter-frequency DAPS handover THEN: PDCP entity associated with a DAPS bearer shall keep DL/UL reception/transmission with the source gNB **** TP2: [Ref: 38.323, cl.5.13] WITH: UE in NR RRC_CONNECTED state and supporting Inter-frequency DAPS handover and receiving an RRCReconfiguration message including a reconfigurationWithSync for Inter-frequency DAPS handover with key change WHEN: UE has performed random access procedure to the target cell successfully THEN: UE shall perform uplink data switching **** TP3: [Ref: 38.323, cl.5.4.1] WITH: UE in NR RRC_CONNECTED state and supporting Inter-frequency DAPS handover and receiving an RRCReconfiguration message including a reconfigurationWithSync for Inter-frequency DAPS handover with key change WHEN: upper layer requests a uplink data switching THEN: UE shall send a PDCP status report for the DAPS bearer **** TP4: [Ref: 38.323, cl.5.4.1] WITH: UE in NR RRC_CONNECTED state and supporting Inter-frequency DAPS handover and receiving an RRCReconfiguration message including a reconfigurationWithSync for Inter-frequency DAPS handover with key change WHEN: upper layer requests a PDCP entity reconfiguration and the associated RLC entity is released for a radio bearer THEN: UE shall send a PDCP status report for the DAPS bearer | China Telecommunications | RAN5#93 (Nov-21) | R5-216508 |  | 1 | 100% (+100%) | 100% (+100%) |  |  | 100%
RRC
4 |  | 38.523-1 | 8.1.4.3 | DAPS handover | Sub-clause heading | Huawei, Hisilicon | RAN5#91-e (May-21) | R5-206405 |  | 0 | 100% | 100% |  |  | 100%
5 | Y | 38.523-1 | 8.1.4.3.1 | DAPS handover / Success / Intra-frequency | **** TP1: [TS 38.300 clause 9.2.3.1 and 9.2.3.2.1 and TS 38.331 clause 5.3.5.5.2] WITH: UE in NR RRC_CONNECTED state and supporting Intra-frequency DAPS handover WHEN: UE receives an RRCReconfiguration message including a reconfigurationWithSync for handover and dapsConfig is configured for a DRB THEN: UE performs DAPS handover to the target cell and keeps DL/UL reception/transmission with the source gNB for the DRB configured with dapsConfig **** TP2: [TS 38.300 clause 9.2.3.1] WITH: UE in NR RRC_CONNECTED state and supporting Intra-frequency DAPS handover and having received an RRCReconfiguration message including a reconfigurationWithSync for handover to the neighbour cell and a dapsConfig configured for any DRB WHEN: UE has performed random access procedure to the target cell successfully THEN: UE transmits an RRCReconfigurationComplete message to the target gNB **** TP3: [TS 38.331 clause 5.3.5.3] WITH: UE in NR RRC_CONNECTED state and supporting Intra-frequency DAPS handover and having received an RRCReconfiguration message including a reconfigurationWithSync for handover to the neighbour cell and a dapsConfig configured for any DRB WHEN: UE receives an RRCReconfiguration message including a daps-SourceRelease THEN: UE releases the radio link with the source cell **** TP4: [TS 38.300 clause 9.2.3.1] WITH: UE in NR RRC_CONNECTED state and supporting Intra-frequency DAPS handover and having received an RRCReconfiguration message including a reconfigurationWithSync for handover to the neighbour cell and a dapsConfig configured for any DRB WHEN: UE has performed random access procedure to the target cell successfully THEN: UE continues the downlink user data reception from the source gNB until releasing the source cell | Huawei, Hisilicon | RAN5#91-e (May-21) | R5-206405 R5-213554 R5-216260 |  | 1 | 100% | 100% |  |  | 100%
6 | Y | 38.523-1 | 8.1.4.3.2 | DAPS handover / HO Failure and source link available / HO Success and RLF in source / Intra-frequency | **** TP1: [ TS 38.300 9.2.3.1 and 9.2.3.2.1, TS 38.331 clause 5.3.5.8.3, 5.7.5.3 ] WITH: UE in NR RRC_CONNECTED state and having received an RRCReconfiguration message including a reconfigurationWithSync for handover to the neighbour cell and a dapsConfig configured for a DRB WHEN: T304 of the MCG expires and the source link has not been released THEN: UE falls back to source cell configuration, resumes the connection with source cell, and reports DAPS HO failure via the source without triggering RRC connection re-establishment **** TP2: [ TS 38.300 9.2.3.1 and 9.2.3.2.1, TS 38.331 clause 5.3.5.5.2, 5.3.5.3.] WITH: UE in NR RRC_CONNECTED state and having received an RRCReconfiguration message including a reconfigurationWithSync for handover to the neighbour cell and a dapsConfig configured for a DRB WHEN: Radio link failure is detected for the source MCG THEN: UE suspends all DRBs in the source and releases the source connection and continue the handover procedure to target | Huawei, Hisilicon | RAN5#93 (Nov-21) | R5-216261 R5-217874 |  | 1 | 100% (+20%) | 100% (+20%) |  |  | 100%
7 |  | 38.523-1 | 8.1.4.3.3 | void | void | Huawei, Hisilicon | RAN5#93 (Nov-21) |  | Merge the TP of 8.1.4.3.3 into TC 8.1.4.3.2 and remove the unverifiable TPs | 0 | 100% (+100%) | 100% (+100%) |  |  | 100%
35 | Y | 38.523-1 | 8.1.4.3.4 | DAPS handover / Success / Inter-frequency | **** TP1: [TS 38.300 9.2.3.1 and 9.2.3.2.1 and TS 38.331 clause 5.3.5.5.2] WITH: UE in NR RRC_CONNECTED state and supporting Inter-frequency DAPS handover WHEN: UE receives an RRCReconfiguration message including a reconfigurationWithSync for handover and dapsConfig is configured for a DRB THEN: UE performs DAPS handover to the target cell and keeps DL/UL reception/transmission with the source gNB for the DRB configured with dapsConfig **** TP2: [TS 38.300 9.2.3.1] WITH: UE in NR RRC_CONNECTED state and supporting Inter-frequency DAPS handover and having received an RRCReconfiguration message including a reconfigurationWithSync for handover to the neighbour cell and a dapsConfig configured for any DRB WHEN: UE has performed random access procedure to the target cell successfully THEN: UE transmits an RRCReconfigurationComplete message to the target gNB **** TP3: [TS 38.331 clause 5.3.5.3] WITH: UE in NR RRC_CONNECTED state and supporting Inter-frequency DAPS handover and having received an RRCReconfiguration message including a reconfigurationWithSync for handover to the neighbour cell and a dapsConfig configured for any DRB WHEN: UE receives an RRCReconfiguration message including a daps-SourceRelease THEN: UE releases the radio link with the source cell | China Telecommunications | RAN5#91-e (May-21) | R5-213553 |  | 1 | 100% | 100% |  |  | 100%
36 | Y | 38.523-1 | 8.1.4.3.5 | DAPS handover / HO Failure and source link available / HO Success and RLF in source / Inter-frequency | **** TP1: [ TS 38.300 9.2.3.1 and 9.2.3.2.1, TS 38.331 clause 5.3.5.8.3, 5.7.5.3 ] WITH: UE in NR RRC_CONNECTED state and having received an RRCReconfiguration message including a reconfigurationWithSync for handover to the neighbour cell and a dapsConfig configured for a DRB WHEN: T304 of the MCG expires and the source link has not been released THEN: UE falls back to source cell configuration, resumes the connection with source cell, and reports DAPS HO failure via the source without triggering RRC connection re-establishment **** TP2: [ TS 38.300 9.2.3.1 and 9.2.3.2.1, TS 38.331 clause 5.3.5.5.2, 5.3.5.3.] WITH: UE in NR RRC_CONNECTED state and having received an RRCReconfiguration message including a reconfigurationWithSync for handover to the neighbour cell and a dapsConfig configured for a DRB WHEN: Radio link failure is detected for the source MCG THEN: UE suspends all DRBs in the source and releases the source connection and continue the handover procedure to target | China Telecommunications | RAN5#93 (Nov-21) | R5-216509 |  | 1 | 100% (+100%) | 100% (+100%) |  |  | 100%
37 |  | 38.523-1 | 8.1.4.3.6 | void | void | China Telecommunications | RAN5#93 (Nov-21) |  | Merge the TP of 8.1.4.3.6 into TC 8.1.4.3.5 and remove the unverifiable TPs | 0 | 100% (+100%) | 100% (+100%) |  |  | 100%
8 |  | 38.523-1 | 8.1.4.4 | Conditional handover | Sub-clause heading | Huawei, Hisilicon | RAN5#91-e (May-21) | R5-211458 |  | 0 | 100% | 100% |  |  | 100% | 100%
9 | Y | 38.523-1 | 8.1.4.4.1 | Conditional handover / Success / A3 / A5 / A3+A5 | **** TP1: [ TS 38.300 clause 9.2.3.4 and TS 38.331 clause 5.3.5.1] WITH: UE in NR RRC_CONNECTED state and supporting conditional handover and receiving an RRCReconfiguration message including ConditionalReconfiguration WHEN: any CHO execution condition is not satisfied THEN: UE maintains connection with source gNB and starts evaluating the CHO execution conditions for the candidate cell(s) **** TP2: [ TS 38.300 clause 9.2.3.4 and TS 38.331 clause 5.3.5.1, 5.3.5.13.1, 5.3.5.13.4 ] WITH: UE in NR RRC_CONNECTED state and supporting conditional handover WHEN: UE receives an RRCReconfiguration message including ConditionalReconfiguration and only event A3 is configured as conditional handover trigger event THEN: UE starts evaluating the CHO execution condition A3 and perform conditional handover to the neighbor cell triggered in conditional configuration execution **** TP3: [ TS 38.300 clause 9.2.3.4 and TS 38.331 clause 5.3.5.1, 5.3.5.13.1, 5.3.5.13.4 ] WITH: UE in NR RRC_CONNECTED state and supporting conditional handover WHEN: UE receives an RRCReconfiguration message including ConditionalReconfiguration and only event A5 is configured as conditional handover trigger event THEN: UE starts evaluating the CHO execution condition A5 and perform conditional handover to the neighbor cell triggered in conditional configuration execution **** TP4: [ TS 38.300 clause 9.2.3.4 and TS 38.331 clause 5.3.5.1, 5.3.5.13.1, 5.3.5.13.4 ] WITH: UE in NR RRC_CONNECTED state and supporting conditional handover WHEN: UE receives an RRCReconfiguration message including ConditionalReconfiguration and both event A3 and event A5 are configured as conditional handover trigger events THEN: UE starts evaluating the CHO execution condition A3 and A5 and perform conditional handover to the neighbor cell triggered in conditional configuration execution **** TP5: [ TS 38.300 clause 9.2.3.4, 9.2.3.4.2 ] WITH: UE in NR RRC_CONNECTED state and supporting conditional handover WHEN: UE perform conditional handover procedure successfully THEN: UE releases stored CHO configurations | Huawei, Hisilicon | RAN5#91-e (May-21) | R5-211458 R5-217011 |  | 1 | 95% | 95% |  |  | 100% | 90%
10 | Y | 38.523-1 | 8.1.4.4.2 | Conditional handover / modify conditional handover configuration | **** TP1: [ TS 38.300 clause 9.2.3.4 and TS 38.331 clause 5.3.5.1, 5.3.5.3, 5.3.5.13.3 ] WITH: UE in NR RRC_CONNECTED state and supporting conditional handover and receiving an RRCReconfiguration message including a ConditionalReconfiguration WHEN: UE received another RRCReconfiguration message with adding a new entry in the CondReconfigToAddModList before any CHO execution condition is satisfied THEN: UE add the new entry within the VarConditionalReconfig and apply the latest conditional handover configurations **** TP2: [ TS 38.300 clause 9.2.3.4 and TS 38.331 clause 5.3.5.1, 5.3.5.3, 5.3.5.13.4 ] WITH: UE in NR RRC_CONNECTED state and supporting conditional handover and receiving an RRCReconfiguration message including a ConditionalReconfiguration WHEN: UE received another RRCReconfiguration message with modifying an exsisting entry in the CondReconfigToAddModList before any CHO execution condition is satisfied THEN: UE replace the exsisting entry with the value received and apply the latest conditional handover configurations **** TP3: [ TS 38.300 clause 9.2.3.4 and TS 38.331 clause 5.3.5.1, 5.3.5.3, 5.3.5.13.2 ] WITH: UE in NR RRC_CONNECTED state and supporting conditional handover and receiving an RRCReconfiguration message including a ConditionalReconfiguration WHEN: UE received another RRCReconfiguration message with condConfigToRemoveList before any CHO execution condition is satisfied THEN: UE removes the entry with the matching condConfigId included in the condConfigToRemoveList and apply the latest conditional handover configurations | Huawei, Hisilicon | RAN5#91-e (May-21) | R5-211459 R5-217012 |  | 1 | 95% | 95% |  |  | 100% | 90%
11 | Y | 38.523-1 | 8.1.4.4.3 | Conditional handover / Failure | **** TP1: [ TS 38.300 clause 9.2.3.4 and TS 38.331 clause 5.3.7.3 ] WITH: UE in NR RRC_CONNECTED state and supporting conditional handover and receiving a RRCReconfiguration message including ConditionalReconfiguration WHEN: UE detects conditional handover failure and finds a selectable cell which is the candidate cell included in ConditionalReconfiguration before T311 expires THEN: UE applies the stored condRRCReconfig associated to the selected cell and perform conditional handover to the selected cell **** TP2: [ TS 38.300 clause 9.2.3.4 and TS 38.331 clause 5.3.7.6, 5.3.11 ] WITH: UE in NR RRC_CONNECTED state and supporting conditional handover and receiving a RRCReconfiguration message including ConditionalReconfiguration WHEN: UE detects conditional handover failure and can not find any selectable cell before T311 expires THEN: UE goes to RRC_IDLE and release the stored conditional handover configurations | Huawei, Hisilicon | RAN5#91-e (May-21) | R5-211460 R5-217013 |  | 1 | 95% | 95% |  |  | 100% | 90%
12 | Y | 38.523-1 | 8.1.4.4.4 | Conditional handover / legacy Handover / legacy Handover Failure | **** TP1: [ TS 38.300 9.2.3.4.1 ] WITH: UE in NR RRC_CONNECTED state and supporting conditional handover and having received an RRCReconfiguration message including a ConditionalReconfiguration WHEN: UE receives an RRCReconfiguration message including a reconfigurationWithSync for legacy handover to a neighbour cell THEN: UE performs handover procedure **** TP2: [ TS 38.300 9.2.3.1 and TS 38.331 clause 5.3.7.3] WITH: UE having stored ConditionalReconfiguration and having received another RRCReconfiguration message including a reconfigurationWithSync for legacy handover to a neighbour cell WHEN: UE detects handover failure and find a selectable cell which is the candidate cell included in ConditionalReconfiguration before T311 expires THEN: UE applies the stored condRRCReconfig associated to the selected cell and performs conditional handover to the selected cell **** TP3: [ TS 38.300 9.2.3.1, TS 38.331 clause 5.3.11 ] WITH: UE having stored ConditionalReconfiguration and having received another RRCReconfiguration message including a reconfigurationWithSync for handover to a neighbour cell WHEN: UE detects handover failure and can not find any selectable cell before T311 expires THEN: UE goes to RRC_IDLE and releases the stored conditional handover configurations | Huawei, Hisilicon | RAN5#93 (Nov-21) | R5-217875 |  | 1 | 95% (+95%) | 95% (+95%) |  |  | 100% | 90%
13 |  | 38.523-1 | 8.1.5.6.6 | Void | Void | Huawei, Hisilicon | RAN5#93 (Nov-21) |  |  | 0 | 100% (+100%) | 100% (+100%) |  |  | 100% | 100%
14 |  | 38.523-1 | 8.2.3.18 | Conditional PSCell change | Sub-clause heading |  | RAN5#93 (Nov-21) |  |  | 0 | 100% |  | 100% |  |  |  |  | 100% | 100%
15 | Y | 38.523-1 | 8.2.3.18.1 | Conditional PSCell change / Success / EN-DC | **** TP1: [ TS 37.340 clause 10.6 ] WITH: UE in RRC_CONNECTED state with EN-DC and receiving an RRCReconfiguration message for conditional PScell change WHEN: Any CPC execution condition is not satisfied THEN: UE maintains connection with source PScell and continue to evaluate the CPC execution conditions **** TP2: [ TS 37.340 clause 10.6 ] WITH: UE in NR RRC_CONNECTED state with EN-DC and receiving an RRCReconfiguration message for conditional PScell change WHEN: Any CPC execution condition is satisfied THEN: UE performs conditional PScell change to the candidate target cell **** TP3: [ TS 37.340 clause 10.6 ] WITH: UE in NR RRC_CONNECTED state with EN-DC and receiving an RRCReconfiguration message for conditional PScell change WHEN: UE perform conditional PSCell change successfully THEN: UE releases stored CPC configurations | Huawei, Hisilicon | RAN5#93 (Nov-21) | R5-215677 R5-217014 |  | 1 | 95% (+5%) |  | 95% (+5%) |  |  |  |  | 100% | 90%
16 | Y | 38.523-1 | 8.2.3.18.2 | Conditional PSCell change / Failure / EN-DC | **** TP1: [ TS 37.340 clause 7.7 ] WITH: UE in RRC_CONNECTED state with EN-DC and receiving an RRCReconfiguration message for conditional PSCell change WHEN: CPC execution failure happens THEN: UE suspends SCG transmissions for all radio bearers and reports the SCG Failure Information to the MN **** TP2: [ TS 37.340 clause 7.7 ] WITH: UE in RRC_CONNECTED state with EN-DC and receiving an RRCReconfiguration message for conditional PSCell change WHEN: radio link failure is detected for MCG during the execution of CPC THEN: the UE initiates the RRC connection re-establishment procedure | Huawei, Hisilicon | RAN5#93 (Nov-21) | R5-217876 |  | 1 | 95% (+95%) |  | 95% (+95%) |  |  |  |  | 100% | 90%
17 | Y | 38.523-1 | 8.2.3.18.3 | Conditional PSCell change / PCell change / PSCell change / EN-DC | **** TP1: [ TS 37.340 clause 10.6 ] WITH: UE in RRC_CONNECTED state with EN-DC and receiving an RRCReconfiguration message for conditional PScell change WHEN: UE receives PCell change command THEN: UE executes the PCell change procedure, regardless of any previously received CPC configuration **** TP2: [ TS 37.340 clause 10.6 ] WITH: UE in RRC_CONNECTED state with EN-DC and receiving an RRCReconfiguration message for conditional PScell change WHEN: UE receives PSCell change command THEN: UE executes the SPCell change procedure, regardless of any previously received CPC configuration | CATT | RAN5#93 (Nov-21) |  |  | 1 | 0% |  | 0% |  |  |  |  | 0% | 0%
TS 38.523-2: Applicability for Protocol test cases
19 |  | 38.523-2 | 4.1 | Protocol conformance test cases applicability | Add applicability for NR MobEnh Layer 2 TCs | Huawei, Hisilicon | RAN5#91-e (May-21) | R5-206406 R5-211461 R5-213556 R5-216262 R5-217774 |  | 0.1 | 100% (+30%) | 100% (+30%) | 100% (+30%) |  | 100% | 100% |  | 100% | 100%
20 |  | 38.523-2 | 4.2 | Protocol conformance test cases Applicability Condition | Add applicability for NR MobEnh RRC TCs | Huawei, Hisilicon | RAN5#91-e (May-21) | R5-206406 R5-211461 R5-213556 R5-216262 R5-217774 R5-217018 |  | 0.1 | 95% (+25%) | 100% (+30%) | 90% (+20%) |  | 100% | 100% |  | 90% | 90%
End of workplan items. Note! Do not remove this row. Introduce new work plan rows/items above this row.
Note on A6: Unique ID for WP items (unique within the sub-area work plan) Note! As WP item numbers may be referenced from outside of this WP that means: - Do not change number for WP items that have been published. - Do not re-use WP item numbers if a WP item is deleted
Note on B6: Set to Y if the WP item represents a new test case that will be specified in RAN5 test specifications as an executable test case else leave blank.
Note on K6: The WP item's weight number is used to set the reletive weights between WP items used in the overall calculation of completeness. Setting it to 0 for a WP item means that it will not be included at all in the calculation.