## Cover sheet
RAN5 meeting #95e | [10 empty] | R5-222255
Electronic Meeting, 9th May 2022 – 20th May 2022
Agenda Item: | 7.4.2
Source: | Qualcomm
Title: | WP UE Conformance Test Aspects - Rel-16 Private Network Support for NG-RAN
Work item code: | NG_RAN_PRN_Vertical_LAN-UEConTest
Release: | Rel-16
Document for: | Information
RAN5 WP template v2.0
1. Introduction
<Description of work item and its scope>
2. Work item status
Estimation of WI overall completion:
Area |  | Completion | Number of new completed test cases (Note 1) | Number of new test cases | Comments
Overall completion |  | 89% (+89%) | 5 (+5) | 14 (+14)
Completion Compensation |  | -
| Note 1: | Only test cases completed for all applicable WP areas and sub-areas are counted. For completed test cases per WP areas and WP sub-areas see below.
Estimation WI completion per area and sub-area:
|  | Completion | Number of new completed test cases | Number of new test cases | Comments
SA Option 2 (SA NR) |  | 88.8% (+88.8%) | 5 (+5) | 14 (+14)
FR1 |  | 90.5% (+90.5%) | 13 (+13) | 14 (+14)
FR2 |  | 87.1% (+87.1%) | 5 (+5) | 14 (+14)
Estimation of completion per TS (area):
|  | TS/TR overall completion |  |  | SA Option 2 (SA NR)
TS/TR Scope | TS/TR | Completion | Number of new completed test cases | Number of new test cases | FR1 |  |  | FR2
[5 empty] | Completion | Number of new completed test cases | Number of new test cases | Completion | Number of new completed test cases | Number of new test cases
5GS
5GS Common
Common test environment | 38.508-1 | 100% (+100%) |  |  | 100% (+100%) |  |  | 100% (+100%)
Common ICS | 38.508-2 | 100% (+100%) |  |  | 100% (+100%) |  |  | 100% (+100%)
5GS RAN and CN protocols
Protocol test cases | 38.523-1 | 85.6% (+85.6%) | 5 (+5) | 14 (+14) | 88.1% (+88.1%) | 13 (+13) | 14 (+14) | 83.1% (+83.1%) | 5 (+5) | 14 (+14)
Applicability Protocol test cases | 38.523-2 | 80% (+80%) |  |  | 80% (+80%) |  |  | 80% (+80%)
Test suites (TTCN) | 38.523-3 | 100% (+100%) |  |  | 100% (+100%) |  |  | 100% (+100%)
5 References
[1] RP-201152 | UE Conformance Test Aspects - Private Network Support for NG-RAN
Note on B21: Overall completion of the work item reported at an earlier meeting will not be decreased if additional tasks are added or if corrections are made to the work plan. Instead the earlier reported completion status will be kept until necessary progress have been achieved such that completion exceeds the earlier reported completion level. The value of the Completion Compensation value represents the difference in the decrease caused by late additions or corrections to the work plan and the current estimated overall completion. '-' indicates that no compensation is applied.

## WP
WP Title: |  | Private Network Support for NG-RAN | [10 empty] | Start of workplan status columns. Note! Do not remove this column. | WP item status |  | End of workplan columns. Note! Do not remove this column.
WI code |  | NG_RAN_PRN_Vertical_LAN-UEConTest
WP Scope: |  | <WP Scope description> | [12 empty] | vs Area
WP Resp: |  | Yogesh Tugnawat |  |  | Yogesht@qti.qualcomm.com | [5 empty] | WP item completion |  |  | SA Option 2 (SA NR)
TS Resp: |  | <TS responsible if a new TS is involved> |  |  | <Email to TS responsible>
WP Item ID | Is new test case? | TS/area | Clause | Title | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | Overall | SA Option 2 (SA NR) |  | FR1 | FR2
[14 empty] | 90.5% (+90.5%) | 87.1% (+87.1%)
[14 empty] | 23 (+23) | 23 (+23)
[14 empty] | 22.4 (+22.4) | 22.4 (+22.4)
5%
Start of work plan items. Note! Do not remove this row. Introduce new work plan rows/items below this row.
5GS
5GS Common
TS 38.508-1: Common test environment
1 |  | 38.508-1 | 4, 6 | Introduction of General and Signaling Test Environment for Rel-16 Private Network Tests | SNPN, PNI-NPN cell definitions, ASN.1 updates (SIB1, SIB10, other messages), USIM updates Cell Definitions - SNPN, CAG Generic Procedure SI Combinations | Qualcomm | RAN5#92 (Aug-21) | R5-211465 R5-211548 R5-211466 R5-213573 R5-213574 R5-214900 |  | 2 | 100% (+100%) | 100% (+100%) |  | 100% | 100%
TS 38.508-2: Common ICS
2 |  | 38.508-2 | A.4.3.7 | Introduction of common implementation conformance statements for Rel-16 Private Network Tests T. | CAG PICS Resolve Applicability for SNPN | Qualcomm | RAN5#91-e (May-21) | R5-213575 R5-217715 |  | 1 | 100% (+100%) | 100% (+100%) |  | 100% | 100%
RAN and CN protocol
TS 38.523-1: Protocol test cases
Idle Mode
29 |  | 38.523-1 | 6.5 | SNPN and CAG Selection | New sub-clause header
30 |  | 38.523-1 | 6.5.1 | SNPN Only Selection | New sub-clause header |  |  |  |  | 0
5 | Y | 38.523-1 | 6.5.1.1 | SNPN Selection in Manual Mode | 23.122 cl 4.9.3 (1) with { UE in Manual network/SNPN selection mode and an SNPN cell is available for which an entry does not exist in the "list of subscriber data" } ensure that { when { UE is switched on or return to coverage } then { UE does not indicate to the user any available SNPNs } } (2) with { UE in Manual network/SNPN selection mode } ensure that { when { an SNPN cell is available for which an entry exists in the "list of subscriber data" } then { UE indicates to the user that an SNPN is available and user selects the SNPN } } (3) with { UE in Manual network/SNPN selection mode and has registered on an SNPN selected by the user } ensure that { when { an SNPN cell is available for which an entry exists in the "list of subscriber data" } then { UE does not automatically register on the SNPN cell until the user selects automatic SNPN selection mode } } | Qualcomm | RAN5#94 (Feb-22) | R5-213578 R5-214894 R5-221533 |  | 1 | 95% (+95%) | 95% (+95%) |  | 100% | 90%
6 | Y | 38.523-1 | 6.5.1.2 | SNPN Selection in Automatic Mode | 23.122 cl 4.9.3 (1) with { UE in Automatic SNPN selection mode and SNPN cell is available for which an entry does not exist in the "list of subscriber data" } ensure that { when { UE is switched on or return to coverage } then { UE does not only select the SNPN cell and continues searching for an allowable SNPN Cell } } (2) with { UE in Automatic SNPN selection mode and a Registered SNPN cell along with another better ranked allowable SNPN cell becomes available } ensure that { when { UE is switched on or return to coverage } then { UE selects the Registered SNPN cell and UE attempts a Registration on the selected cell } } (3) with { UE in Automatic SNPN selection mode and Registration on a SNPN cell is unsuccessful} ensure that { when { UE continues searching for a allowable SNPN Cell and a new allowable SNPN cell becomes available } then { the UE registers on the new SNPN cell } } | Qualcomm | RAN5#94 (Feb-22) | R5-213576 R5-214895 R5-217288 R5-220682 |  | 1 | 95% (+95%) | 95% (+95%) |  | 100% | 90%
7 | Y | 38.523-1 | 6.5.1.3 | SNPN / User Reselection in Automatic Mode | 23.122 cl 4.9.3 (1) with { UE in Automatic SNPN selection mode and registered on an SNPN cell for which an entry exists in the "list of subscriber data" and another SNPN cell is made available for which an entry exists in the "list of subscriber data" } ensure that { when { UE is requested to initiate reselection and registration onto an available SNPN } then { UE reselects to the SNPN cell } } | Qualcomm | RAN5#94 (Feb-22) | R5-217897 R5-221532 |  | 1 | 95% (+95%) | 95% (+95%) |  | 100% | 90%
|  | 38.523-1 | 6.5.2 | CAG (Closed Acccess Group) | New sub-clause header |  |  |  |  | 0
9 | Y | 38.523-1 | 6.5.2.1 | CAG Selection in Manual Mode | 23.122 cl 4.4.3 (1) with { UE in Manual network selection mode and provided with CAG information list } ensure that { when { there exists an entry with the PLMN ID of the PLMN in the "CAG information list" and the CAG-ID is included in the "Allowed CAG list" } then { UE manually selects the CAG cell } } (2) with { UE in Manual network selection mode and PLMN ID of the PLMN in the "CAG information list" and the CAG-ID are not included in the "Allowed CAG list" } ensure that { when { the available CAG cell broadcasts that the PLMN allows a user to manually select the CAG-ID } then { UE manually selects the CAG cell that is outside the UE's Allowed CAG list} } (3) with { UE in Manual network selection mode } ensure that { when { there exists an entry for the presented PLMN in the "CAG information list" and the entry includes an "indication that the MS is only allowed to access 5GS via CAG cells" } then { UE manually selects the CAG cell } | Qualcomm | RAN5#94 (Feb-22) | R5-213579 R5-214747 R5-221531 R5-223381 |  | 1 | 95% (+95%) | 95% (+95%) |  | 100% | 90%
10 | Y | 38.523-1 | 6.5.2.2 | CAG Selection in Automatic Mode | 23.122 cl 4.4.3 (1) with { UE in Automatic network selection mode and provisioned with an empty "CAG information list” } ensure that { when { UE is switched on or returned to coverage, and a cell which is not a CAG cell becomes available} then { UE selects the cell } } (2) with { UE in Automatic network selection mode provisioned with a "CAG information list” } ensure that { when { UE is switched on or returned to coverage, and a CAG cell with a CAG-ID present in the "Allowed CAG list" becomes available} then { UE selects the CAG cell } } (3) with { UE in Automatic network selection mode provisioned with a "CAG information list” } ensure that { when { UE is switched on and a cell which is not a CAG cell becomes available, and there is an entry with the PLMN ID of the PLMN in the "CAG information list" but the "indication that the MS is only allowed to access 5GS via CAG cells" is not included in the entry} then { UE selects the cell } } | Qualcomm | RAN5#94 (Feb-22) | R5-213577 R5-214746 R5-217413 R5-220531 R5-223382 |  | 1 | 95% (+95%) | 95% (+95%) |  | 100% | 90%
11 | Y | 38.523-1 | 6.5.2.3 | CAG / Limited Service / No Suitable cell | TS 23.122 cl 3.5 (1) with { UE in Automatic network selection mode provisioned with a "CAG information list” } ensure that { when { UE is switched on or returned to coverage, and a CAG cell with a CAG-ID not present in the "Allowed CAG list" becomes available } then { UE does not select the CAG cell } } (2) with { UE in Automatic network selection mode configured with "indication that the MS is only allowed to access 5GS via CAG cells" } ensure that { when { UE is switched on and a cell which is not a CAG cell becomes available, and there is an entry with the PLMN ID of the PLMN in the "CAG information list" but the "indication that the MS is only allowed to access 5GS via CAG cells" is included in the entry } then { UE does not select the CAG cell } } (3) with { UE in Automatic network selection mode provisioned with an empty "CAG information list” } ensure that { when { UE is switched on or returned to coverage, and a CAG cell with a PLMN ID becomes available } then { UE does not select the CAG cell } } | Qualcomm | RAN5#95 (May-22) | R5-223379 |  | 1 | 95% (+95%) | 95% (+95%) |  | 100% | 90%
12 | Y | 38.523-1 | 6.5.2.4 | CAG / cell reselection / Within allowed CAG/ non-CAG cell to CAG cell | (1) with { UE in NR RRC_IDLE state on a non-CAG cell and UE’s Allowed CAG list is not empty } ensure that { when { UE detects an allowed CAG cell which becomes highest ranked cell } then { UE reselects to the CAG cell } } (2) with { UE in NR RRC_IDLE state } ensure that { when { UE detects the cell re-selection criteria are met for the CAG cell which belongs to the higher priority frequency } then { UE reselects the cell which belongs to the higher priority frequency } } | Qualcomm | RAN5#94 (Feb-22) | R5-217898 R5-220532 R5-223382 |  | 1 | 95% (+95%) | 95% (+95%) |  | 100% | 90%
13 | Y | 38.523-1 | 6.5.2.5 | CAG/ cell selection/reselection / allowed CAG list empty | 38.304 cl 5.2.4.4, 5.2.4.10 |  | RAN5#95 (May-22) |  | Test case to be voided as conformance requirements are not testable. | 1 | 0% | 0% |  | 0% | 0%
14 | Y | 38.523-1 | 6.5.2.6 | CAG/ Cell Reservation | TS 38.304: clauses 5.2.4.4, 5.2.4.6 and 5.3.1 (1) with { UE in Automatic network selection mode and provisioned with an empty "CAG information list } ensure that { when { UE is switched on or returns to coverage, and a cell which is not a CAG cell with cell status “true” for other use becomes available } then { UE does not attempt to reselect to the higher ranked cell } } (2) with { UE camped normally in state NR RRC_IDLE on a CAG cell and UE’s Allowed CAG list is not empty } ensure that { when { a higher ranked CAG cell is found with cell status as “not barred” and “not reserved” for operator use and “true” for other use, and not “true” for future use } then { UE does reselect to the higher ranked cell } } | Rohde and Schwarz | RAN5#95 (May-22) | R5-223380 |  | 1 | 95% (+95%) | 95% (+95%) |  | 100% | 90%
TBD |  | 38.523-1 | 6.5.x | SNPN only cell Selection, RRC_INACTIVE | New sub-clause header |  | RAN5#94 (Feb-22) |  | Tracked via WP Item ID -31 below. Sub tasks to be identified: All Relevant test cases fron NG RAN 6.1.2 and 6.4 replace the cells with SNPN cells | 0 | 0% | 0% |  | 0% | 0%
RRC
17 |  | 38.523-1 | 8.1.7 | Non-public networks | New sub-clause header |  |  |  |  | 0
19 |  | 38.523-1 | 8.1.7.1 | Measurement for self-optimized networks | New sub-clause header |  |  |  |  | 0
20 | Y | 38.523-1 | 8.1.7.1.1 | Measurement configuration control and reporting / CGI reporting of NR NPN cell | TS 38.331, cl 5.5.5.1 (1) with { UE in NR RRC_CONNECTED state } ensure that { when { UE is configured to report the global cell identity of the neighbour NR NPN cell } then { UE determines the global cell identity of the cell included in the associated measurement object by acquiring the relevant system information from the concerned cell and reports the global cell identity in the MeasurementReport } } | Qualcomm | RAN5#93 (Nov-21) | R5-217899 |  | 1 | 100% (+100%) | 100% (+100%) |  | 100% | 100%
NAS
27 |  | 38.523-1 | 9.1.11 | SNPN / Mobility management aspects | New sub-clause header |  |  |  |  | 0
21 | Y | 38.523-1 | 9.1.11.1 | SNPN / Initial registration / Rejected / Temporarily not authorized for this SNPN | TS 24.501 clauses 5.5.1.2.5, 5.1.3.2.1, 5.1.3.2.2, TS 23.122 clause 4.9.3.0 (1) with { UE in Automatic SNPN selection mode and a SNPN cell is available for which an entry exists in the "list of subscriber data" and the UE in 5GMM-REGISTERED-INITIATED state } ensure that { when { the SS sends a REGISTRATION REJECT message to the UE including an appropriate 5GMM cause value #74 (Temporarily not authorized for this SNPN) } then { the UE deletes any 5G-GUTI, last visited registered TAI and ngKSI, and stores the SNPN identity in the "temporarily forbidden SNPNs" } } (2) with { the initial registration request cannot be accepted by the network } ensure that { when { the SS sends a REGISTRATION REJECT message to the UE including an appropriate 5GMM cause value #74 (Temporarily not authorized for this SNPN) } then { The UE stores the SNPN identity in the "temporarily forbidden SNPNs" and does not remove it atleast until 60 minutes or the UE is switched off } } (3) with { the UE is in 5GMM-DEREGISTERED.PLMN-SEARCH state and the SNPN identity of the current cell belongs to the list of "temporarily forbidden SNPNs" } ensure that { when { the UE enters a cell belonging to a SNPN cell for which an entry exists in the "list of subscriber data" } then { the UE attempts registration on the SNPN cell } } | Qualcomm | RAN5#92 (Aug-21) | R5-216273 |  | 1 | 100% (+100%) | 100% (+100%) |  | 100% | 100%
22 | Y | 38.523-1 | 9.1.11.2 | SNPN / Initial registration / Rejected / Permanently not authorized for this SNPN | TS 24.501 clauses 5.5.1.2.5, 5.1.3.2.1, 5.1.3.2.2, TS 23.122 clause 4.9.3.0 (1) with { UE in Automatic SNPN selection mode and a and SNPN cell is available for which an entry exists in the "list of subscriber data" and the UE in 5GMM-REGISTERED-INITIATED state } ensure that { when { the SS sends a REGISTRATION REJECT message to the UE including an appropriate 5GMM cause value #75 (Permanently not authorized for this SNPN) } then { the UE deletes any 5G-GUTI, last visited registered TAI and ngKSI, and store the SNPN identity in the "permanently forbidden SNPNs" } } (2) with { the UE is in 5GMM-DEREGISTERED.PLMN-SEARCH state } ensure that { when { User manually selects the SNPN cell which belongs to the "permanently forbidden SNPNs" list } then { the UE attempts registration on the SNPN cell } } | Qualcomm | RAN5#92 (Aug-21) | R5-215671 |  | 1 | 100% (+100%) | 100% (+100%) |  | 100% | 100%
26 | Y | 38.523-1 | 9.1.11.3 | SNPN / EAP based primary authentication and key agreement / EAP-AKA' related procedures | TS 24.501 cl 5.4.1.2.2.3, 5.4.1.2.2.8, 5.4.1.2.2.11 , 9.12.1 (1) with { the UE in 5GMM-REGISTERED-INITIATED state } ensure that { when { the SS sends an EAP-request/AKA'-challenge message within AUTHENTICATION REQUEST } then { the UE sends an EAP-response/AKA'-challenge message within AUTHENTICATION RESPONSE } } (2) with { the UE in 5GMM-REGISTERED-INITIATED state and SS initiates an EAP based primary authentication and key agreement procedure } ensure that { when { the SS sends an EAP-success message within AUTHENTICATION RESULT } then { the UE considers the procedure complete and authentication procedure succeed } } (3) with { the UE in 5GMM-REGISTERED-INITIATED state and SS initiates an EAP based primary authentication and key agreement procedure} ensure that { when { the SS sends an EAP-failure message within AUTHENTICATION REJECT } then { the UE shall consider the entry of the "list of subscriber data" with/without the SNPN identity of the current SNPN as invalid for 3GPP access until the UE is switched off or the entry is updated, and the USIM is considered invalid until switching off the UE } } | Motorola Mobility | RAN5#94 (Feb-22) | R5-221534 |  | 1 | 100% (+100%) | 100% (+100%) |  | 100% | 100%
28 |  | 38.523-1 | 10.1.7 | SNPN / Session management aspects | New sub-clause header |  |  |  |  | 0 | 0% | 0% |  | 0% | 0%
24 | Y | 38.523-1 | 10.1.7.1 | SNPN / Network-requested PDU session release / Accepted / Insufficient resources / T3396, Accepted / Insufficient resources for specific slice and DNN / T3584 | TS 24.501, clause 6.2.7, 6.4.3.3 and 6.4.3.5 (1) with { UE is in PDU SESSION ACTIVE state } ensure that { when { UE receives a PDU SESSION RELEASE COMMAND message including 5GSM cause #26 "insufficient resources" and the Back-off timer value that indicates deactivated } then { UE does not send a PDU SESSION ESTABLISHMENT REQUEST message until the UE is switched off, the USIM is removed, the entry in the "list of subscriber data" for the current SNPN is updated } } (2) with { UE is in PDU SESSION ACTIVE state } ensure that { when { UE receives a PDU SESSION RELEASE COMMAND message including 5GSM cause #67 "insufficient resources for specific slice and DNN" and the Back-off timer value that indicates deactivated } then { UE does not send a PDU SESSION ESTABLISHMENT REQUEST message for the same [S-NSSAI, DNN] combination until the UE is switched off, the USIM is removed, the entry in the "list of subscriber data" for the current SNPN is updated } } | Motorola Mobility | RAN5#95 (May-22) | R5-223495 |  | 1 | 100% (+100%) | 100% (+100%) |  | 100% | 100%
32 |  | 38.523-1 | 11.3 | Unified Access Control (UAC) | Existing sub-clause header |  |  |  | Sub tasks to be identified | 0 | 0% | 0% |  | 0% | 0%
15 |  | 38.523-2 | 4.1, 4.2 | Add test case applicability statements for the new test cases introduced in 38.523-1 | Add test case applicability statements for the new test cases introduced in 38.523-1 | Qualcomm | RAN5#94 (Feb-22) | R5-212808 R5-216274 R5-217900 R5-223383 |  | 1.4 | 80% (+80%) | 80% (+80%) |  | 80% | 80%
TS 38.523-3: Protocol test suites (TTCN)
3 |  | 38.523-3 | NA | Introduction of General and Signaling Test Environment for SNPN and PNI-NPN | <Describe task> | MCC TF160 | RAN5#93 (Nov-21) |  |  | 1 | 100% (+100%) | 100% (+100%) |  | 100% | 100%
Overall WP completion
16 |  |  |  | Overall Definition and scope of WI |  |  | RAN5#93 (Nov-21) |  |  | 1 | 95% (+95%) | 95% (+95%) |  | 95% | 95%
31 |  | 38.523-1 | TBD | Solution and Scoping of NR option 2 Rel-15 applicable TCs for SNPN Only UE |  |  | RAN5#93 (Nov-21) | R5-213408 R5-214736 R5-223351 |  | 2 | 55% (+55%) | 55% (+55%) |  | 55% | 55%
End of workplan items. Note! Do not remove this row. Introduce new work plan rows/items above this row.
Note on A6: Unique ID for WP items (unique within the sub-area work plan) Note! As WP item numbers may be referenced from outside of this WP that means: - Do not change number for WP items that have been published. - Do not re-use WP item numbers if a WP item is deleted
Note on B6: Set to Y if the WP item represents a new test case that will be specified in RAN5 test specifications as an executable test case else leave blank.
Note on K6: The WP item's weight number is used to set the reletive weights between WP items used in the overall calculation of completeness. Setting it to 0 for a WP item means that it will not be included at all in the calculation.