## Slide 1: MCC TF160 Status Report
Olivier Genoud
Task Force 160 Leader, 3GPP MCC

## Slide 2
TTCN workflow Simplified view
Note: Each step above has a feedback loop to any previous step(s) (e.g. prose/TTCN bug report).
Who:
RAN5_SIG
TF160 +
SS Vendors
TF160
SS Vendor(s) +
UE Vendor(s) +
TF160
Where:
RAN5 meeting
TTCN Workshop
ETSI
SS/UE Vendor
lab
scope of this report
Notes: SS: System Simulator
UE: User Equipment

## Slide 3
Test Models – 5G:
  Rel-15:
    NE-DC: endorsed NE-DC L3 test model updates.
    Endorsed handling of PDCP duplication in the 5G Layer3 Test Models.
    Intra-NR inter-cell CA handover procedure: endorsed TTCN test sequence updates.
  Rel-16:
    NR IIoT: endorsed new NR PDCP test model for NR CA (3CC) PDCP duplication testing.
    5G V2X: endorsed updated test model & ASPs.
  Prose CRs to TS 38.523-3 proposed at RAN5#95-e for the above.
Test Models – POS:
  Rel-16 NR positioning: endorsed NR test model & ASP updates for posSIBs broadcast support.
  Prose CR to TS 38.523-3 proposed at RAN5#95-e for the above.
Test models & ASPs design Progress at TTCN Workshop #57 (29th Apr’22)
Notes: ASP: Abstract Service Primitive

## Slide 4
Test Models – NB-IoT:
  Endorsed test model update for NB-IoT in-band with different PCI.
  Prose CR to TS 36.523-3 proposed at RAN5#95-e for the above.
Test Models – MCX:
  MCPTT:
    Discussed potential MCX core specs issues related to Session Id for Call Establishment. Relevant 3GPP WG(s) to be contacted.
  MCVideo:
    Discussed various potential MCX core specs & test specs issues related to MCVideo. Relevant 3GPP WG(s) to be contacted.
  Prose CRs to TS 36.579-x proposed at RAN5#95-e for the above.
Test models & ASPs design Progress at TTCN Workshop #57 (29th Apr’22)

## Slide 5: TTCN development Progress for period: March to May’22
Completed:
  5GS Rel-16:
    NR mobility enhancements
    Network slicing enhancements
  LTE Rel-14:
    IMS eCall over LTE
  Mission Critical over LTE:
    MCPTT on-NW group & private calls
Progressed:
  5GS Rel-15:
    NR/5GC single carrier
    NR/5GC NR-DC
  5GS Rel-16:
    NR RACS
    NR SON/MDT
    NR UE power saving
  IMS over NR/5GC:
    Supplementary services
    IMS emergency
  POS:
    Rel-16 NR positioning
Started:
  5GS Rel-15:
    NR/5GC NE-DC
  5GS Rel-16:
    NR URLLC phy layer enh.
    NR IIoT
  Mission Critical over LTE:
    MCData
    MCVideo
Notes: Completed: The TTCN of all test cases is ready for verification.
Progressed: TTCN development ongoing, not yet completed.
Started: TTCN development has started since last report.
Suspended: TTCN development on hold due to external blocker.

## Slide 6: TTCN verification Progress for period: 15th Feb --> 3rd May’22
Completed:
Feature | 3GPP Release | Priority (GCF/PTCRB) | Verified TC # | Progress | Comments
NR/5GC Inter-RAT | Rel-15 | WI-513 | 38 / 38 | +2 | Prio1: 16/16 ; Prio2: 22/22
Notes: Completed: Since last report, the TTCN of all remaining test cases has been verified and agreed.

## Slide 7: TTCN verification Progress for period: 15th Feb --> 3rd May’22
Progressed – 5G (EN-DC, NR/5GC):
Feature | 3GPP Release | Priority (GCF/PTCRB) | Verified TC # | Progress | Comments
EN-DC AS | Rel-15 | WI-503 | 89 / 102 | +2 | 
NR/5GC AS | Rel-15 | WI-503 | 144 / 158 | +2 | Prio1: 88/96 ; Prio2: 56/62
NR/5GC NR-DC | Rel-15 | WI-503 | 9 / 13 | +2 | Prio1: 8/11 ; Prio2: 1/2
NR/5GC NAS | Rel-15 | WI-504 | 69 / 72 | +1 | Prio1: 32/32 ; Prio2: 37/40
NR/5GC NR CA | Rel-15 | WI-510 | 27 / 31 | +3 | Prio1: 14/15 ; Prio2: 13/16 +2 under verification
EN-DC NR CA | Rel-15 | WI-512 | 9 / 17 | +2 | Prio1: 9/13 ; Prio2: 0/4
Intra-NR SON/MDT | Rel-16 | WI-517_A | 26 / 30 | +14 | Prio1: 21/24 ; Prio2: 5/6 +1 under verification
5G network slicing enhancements | Rel-16 | None | 3 / 5 | +2 | +1 under verification
NR RACS | Rel-16 | None | 4 / 8 | +2 | 
Notes: Progressed: Evolution of TTCN test case verification compared to the last report. Not completed yet.

## Slide 8: TTCN verification Progress for period: 15th Feb --> 3rd May’22
Progressed – IMS, Positioning, MCPTT:
Feature | 3GPP Release | Priority (GCF/PTCRB) | Verified TC # | Progress | Comments
VoLTE (GSMA IR.92) | Rel-8 | WI-103 | 45 / 51 | = | 
SMS over IMS | Rel-8 | WI-128 | 2 / 5 | = | 
IMS emergency over LTE | Rel-9 | WI-154 | 31 / 35 | = | 
LTE positioning | Rel-9+ | WI-166 | 14 / 27 | = | 
VoWiFi (GSMA IR.51) | Rel-11 | WI-267 | 18 / 22 | = | Prio1: 5/9 ; Prio2: 13/13
VoLTE over CAT-M1 (GSMA NG.108) | Rel-13 | WI-283 | 10 / 11 | = | Left: TC J.15.5(TIR)
SMS over CAT-M1 (GSMA NG.108) | Rel-13 | WI-128M | 1 / 2 | = | Left: TC J.18.1(MO SMS)
MCPTT over LTE | Rel-14 | WI-288, RFT-153 | 35 / 49 | = | Prio1: 35/46 ; Prio2: 0/3
IMS eCall over LTE | Rel-14 | WI-298 | 5 / 12 | = | 
IMS over NR/5GC | Rel-15 | WI-505 | 58 / 96 | +4 | Prio1: 21/21 ; Prio2: 37/75 +22 under verification
5G Positioning | Rel-15 | WI-506 | 9 / 10 | = | Left: TC 9.3.3.1B
Notes: Progressed: Evolution of TTCN test case verification compared to the last report. Not completed yet.

## Slide 9: TTCN verification Progress for period: 15th Feb --> 3rd May’22
Progressed – 4G (LTE, eMTC, NB-IoT):
Feature | 3GPP Release | Priority (GCF/PTCRB) | Verified TC # | Progress | Comments
LTE/C2K Inter-RAT | Rel-8 | WI-088 | 13 / 14 | = | Left: TC 8.4.5.4(LTE to HRPD HO)
LTE/UMTS Inter-RAT | Rel-9 | WI-167 | 11 / 12 | = | Left: TC 13.1.21(emergency call)
LTE/GERAN Inter-RAT | Rel-9 | WI-168 | 3 / 4 | = | Left: TC 13.1.21(emergency call)
LTE/C2K Inter-RAT | Rel-10 | WI-180 | 1 / 2 | = | Left: TC 8.6.5.3(MDT RLF logging)
LTE/GERAN Inter-RAT | Rel-10 | WI-182/184 | 1 / 2 | = | Left: TC 8.6.5.2(MDT RLF logging)
CA intra-band contiguous | Rel-11 | WI-162 | 20 / 21 | = | Left: TC 7.1.2.11.1(multiple TA)
SCE-PHY | Rel-12 | WI-245 | 6 / 9 | = | 
eDRX | Rel-13 | WI-253 | 4 / 5 | = | Left: TC 9.2.4.1.3(emergency call)
eMTC (CAT-M1) | Rel-13 | WI-254-A | 14 / 15 | = | Left: TC 7.1.4.3a(Lch prioritization)
eMTC (CIoT) | Rel-13 | WI-254-C | 2 / 5 | = | 
NB-IoT (CAT-NB1) | Rel-13 | WI-257 | 71 / 73 | = | Left: TCs 22.1.1.M2, 22.4.26
LAA | Rel-13 | WI-272 | 1 / 2 | = | Left: TC 8.3.1.32(RSSI measurement)
eNB-IoT | Rel-14 | WI-295 | 11 / 14 | = | Left: SC-PTM (in iWD-003), IRAT with E-UTRA
L2 latency reduction | Rel-14 | WI-306 | 1 / 4 | = | 
Notes: Progress: Evolution of TTCN test case verification compared to the last report. Not completed yet.

## Slide 10: TTCN verification Progress for period: 15th Feb --> 3rd May’22
Started:
Starting:
Feature | 3GPP Release | Priority (GCF / PTCRB) | Verified TC # | Progress | Comments
NR mobility enhancements | Rel-16 | None | 2 / 10 | +2 | +2 under verification
Feature | 3GPP Release | Priority (GCF / PTCRB) | Verified TC # | Progress | Comments
5G private network | Rel-16 | None | 0 / 14 |  | +1 under verification
Notes: Started: lists the features for which at least one (first) test case has been submitted and agreed since the last report.
Starting: lists the feature for which no test case has yet been verified, but at least one submission has been made, which is under review (consultation period still running).

## Slide 11
2021 Tasks (carried over) | Rel- | RAT | Prose Target | SIG TC # | TTCN Develpmt | 2022 WkLoad | TTCN Status (as of May’22) / Comments
MCX: PTT, Video, Data | Rel-14 | L | Q3’20 | 106 | Q3’17-Q2’22 | 4 | 73% (@iwd-22wk12)
LTE CA band combinations | R15to16 | L | Q4’22 | n/a | Q1’19-Q4’22 | 0.1 | 41% (@iwd-22wk12)
MTC (even) further enhanced | R14to15 | L | Q4’21 | 18 | Q1’18-Q2’22 | 1 | 11% (@iwd-21wk49)
NB-IoT further enhanced | Rel-15 | L | Q3’21 | 8 | Q2’20-Q2’22 | 0.5 | 60% (@iwd-21wk49)
MCX enhancements | Rel-15 | L | Q2’22 | 70 | Q3’21-Q4’22 | 6 | 34% (@iwd-22wk12)
LTE mobility even further enhancements | Rel-16 | L | Q2’22 | 11 | Q4’20-Q2’22 | 1 | Not started
5GS: NR/5GC (option 2) | Rel-15 | N,L | Q2’22 | 449 | Q3’18-Q2’22 | 1 | 98% (@iwd-22wk12)
UE RACS optimisations | Rel-16 | N,L | Q1’22 | 17 | Q4’20-Q2’22 | 1 | 76% (@iwd-22wk12)
NR UE power saving | Rel-16 | N | Q2’22 | 9 | Q4’20-Q3’22 | 0.5 | 33% (@iwd-22wk12)
NR industrial IoT | Rel-16 | N,L | Q1’22 | 7 | Q4’20-Q3’22 | 1 | 10% (@iwd-22wk12)
5G V2X with NR sidelink | Rel-16 | N,L | Q2’22 | 74 | Q4’20-Q3’22 | 6 | 8% ; Test Model work
5G private network | Rel-16 | N | Q2’22 | 14 | Q4’20-Q3’22 | 0.8 | 64% (@iwd-21wk49)
NR mobility enhancements | Rel-16 | N | Q2’22 | 13 | Q4’20-Q1’22 | 0.5 | 100% (@iwd-22wk12)
NR SON & MDT | Rel-16 | NLWB | Q2’22 | 47 | Q1’21-Q3’22 | 1 | 90% (@iwd-22wk12)
NR URLLC phy layer enhancements | Rel-16 | N | Q2’22 | 10 | Q2’21-Q2’22 | 1 | 40% (@iwd-22wk12)
NW slicing enhancements | Rel-16 | N | Q4’21 | 5 | Q3’21-Q1’22 | 0.1 | 100% (@iwd-22wk12)
IMS eCall over NR | Rel-16 | N | Q3’22 | 19 | Q3’21-Q3’22 | 2 | Not started
NR positioning | Rel-16 | N | Q4’22 | 14 | Q2’21-Q4’22 | 0.5 | 50% (@iwd-22wk12)
NR MIMO enhancements | Rel-16 | N | Q2’22 | 2 | Q4’20-Q2’22 | 0.5 | Not started
NR new/extended bands | R16to17 | N | Q2’22 | n/a | Q1’21-Q2’22 | 0.2 | 49% (@iwd-22wk12)
5G CA/DC band combinations | R16to17 | N,L | Q2’22 | n/a | Q1’21-Q2’22 | 0.2 | 8% (@iwd-22wk12)
Total: |  |  |  | 894 |  | 28.9 | person-months
TTCN workplan 2022 Status of 2021 tasks carried over
Notes: Note: TTCN of some features initially started in 2021 will only be completed in 2022 due to availability of prose late in CY2021, especially those which impacts the Test Models.
Legend:
Blue: changes from last MCC TF160 report.
Red: Important information.
Italics: Estimation based on limited information available.

## Slide 12
2022 Tasks & Maintenance | Rel- | RAT | Prose Target | SIG TC # | TTCN Develpmt | 2022 WkLoad | TTCN Status (as of May’22) / Comments
5GS: NE-DC (option 4) | Rel-15 | N,L | Q4’22 | 35 | Q1’22-Q4’22 | 6 | 10% (@iwd-22wk12)
NR 2-step RACH | Rel-16 | N | Q2’22 | 8 | Q1’22-Q3’22 | 1 | Not started
MR-DC & NR CA enhancements | Rel-16 | N,L | Q4’22 | 29 | Q1’22-Q4’22 | 3 | Not started
NR in unlicensed spectrum (NR-U) | Rel-16 | N | Q4’22 | 13 | Q1’22-Q4’22 | 3 | Not started ; no prose
NR FR1 RF requirements | Rel-16 | N | Q4’22 | 6 | Q3’22-Q4’22 | 1 | Not started ; no prose
LTE/NR multi-SIM UE | Rel-17 | N,L | Q3’23 | 16 | Q4’22-Q4’23 | 0.5 | Not started ; no prose
NR & MR-DC SON/MDT enhancements | Rel-17 | N,L | Q2’23 | >11 | Q4’22-Q4’23 | 0.5 | Not started ; no prose
Reduced capability NR UE (RedCap) | Rel-17 | N | Q2’23 | 9 | Q4’22-Q4’23 | 1 | Not started ; no prose
NR multi/broadcast services (MBS) | Rel-17 | N | Q2’23 | 7 | Q4’22-Q4’23 | 0.5 | Not started ; no prose
NW slicing enhancements - Phase2 | Rel-17 | N | Q4’22 | 13 | Q4’22-Q4’23 | 0.5 | Not started ; no prose
NR UE power saving enhancements | Rel-17 | N | Q3’23 | FFS | Q4’22-Q4’23 | 0.5 | New Test Work Item @RAN5#95-e
NR RAN slicing enhancements | Rel-17 | N | Q3’23 | FFS | Q4’22-Q4’23 | 0.5 | New Test Work Item @RAN5#95-e
NR sidelink enhancements | Rel-17 | N | Q3’23 | FFS | Q4’22-Q4’23 | 0.5 | New Test Work Item @RAN5#95-e
NR sidelink relay | Rel-17 | N | Q3’23 | FFS | Q4’22-Q4’23 | 0.5 | New Test Work Item @RAN5#95-e
NB-IoT new band 103 | Rel-17 | L | Q4’22 | n/a | Q3’22-Q4’22 | 0.1 | New Test Work Item @RAN5#95-e
TEIx_Test (new TC coverage) | Rel-8+ | All | n/a | 20 | Q1’22-Q4’22 | 2 | 2022 total after RAN5#95-e: 3 TCs
TTCN maintenance & deliveries |  |  |  |  | Q1’22-Q4’22 | 45 | 
Release & configuration management |  |  |  |  | Q1’22-Q4’22 | 6 | 
Total: |  |  |  | >167 |  | 72.1 | person-months
TTCN workplan 2022 Status of new 2022 tasks and maintenance tasks
Notes: Legend:
Blue: changes from last MCC TF160 report.
Red: Important information.
Italics: Estimation based on limited information available.

## Slide 13
2022 workload is estimated at 101 person-months, see previous slides.
PCG#47/OP#46 approved the 3GPP funding of 58 person-months for 2022 TTCN tasks.
CTIA/PTCRB and GCF have agreed to continue TF160 financial support in 2022.
Current commitments for 2022 are as follows:
3GPP companies / 3GPP MRPs committed to provide 17 person-months as voluntary contributions for 2022 TTCN development.
Total resources of 101 person-months  no estimated funding gap.
Funding |  | 
Entity | Person-months | Comments
3GPP | 58 | PCG#47/OP#46 approved (decision OP46/08)
CTIA/PTCRB | 12 | 5GS, MCX
GCF | 12 | 5GS, MCX
Qualcomm | 2 | RACS, NPN, IMSoNR eCall
Total: | 84 | person-months
TTCN experts free-of-charge |  | 
Entity | Person-months | Comments
TDIA (CAICT, CATT, HiSilicon, Starpoint) | 14 | 5GS, V2X, NB-IoT, LCR TDD
Anritsu | 1 | 5GS
Keysight | 1 | 5GS
Rohde&Schwarz | 1 | 5GS
Total: | 17 | person-months
TTCN funding 2022 Status

## Slide 14: Annexes

## Slide 15: TTCN deliveries and baseline 2022 schedule
One TTCN-2 full delivery (FDD & LCR TDD) and five TTCN-3 full deliveries.
  Q4 dates tentative: dependent on RAN5#97 meeting being physical or electronic (TBC).
Type definitions baseline upgrade to 3GPP Release 17 required in 2022:
  Rel-17 Stage3 freeze achieved by 3GPP in March 2022.
  Rel-17 ASN.1 freeze scheduled by 3GPP in June 2022.
Week number | iWD delivery date | TTCN CR cut-off date | TTCN agreement status report | Type of delivery | Comment
wk04 |  |  | 21-Jan |  | 
wk12 | 25-Mar | 21-Mar | 25-Mar | TTCN-3 | 
wk16 |  |  | 14-Apr |  | GCF CAG#70 (19-22 Apr)
wk19 |  |  | 06-May |  | PTCRB PVG#97 (10-12 May)
wk23 | 10-Jun | 06-Jun | 10-Jun | TTCN-3 | 
wk30 |  |  | 22-Jul |  | GCF CAG#71 (26-29 Jul)
wk33 |  |  | 12-Aug |  | PTCRB PVG#98 (16-18 Aug)
wk37 | 16-Sep | 12-Sep | 16-Sep | TTCN-3 | 
wk42 |  |  | 14-Oct |  | GCF CAG#72 (18-21 Oct)
wk43 | 28-Oct | 19-Oct | 28-Oct | TTCN-3 Rel-17 Baseline upgrade | Move to Rel-17 Sep'22 baseline
wk45 |  |  | 04-Nov |  | PTCRB PVG#99 (8-10 Nov)
wk48 | 01-Dec | 28-Nov |  | TTCN2 (FDD) | 
wk48 | 02-Dec | 28-Nov |  | TTCN2 (LCR TDD) | 
wk49 | 09-Dec | 05-Dec | 09-Dec | TTCN-3 | 

## Slide 16: 5GS Rel-15 – Protocol test case numbers Before RAN5#95-e
5GS Rel-15 | TCs # | Details
NR/5GC (5G option 2) | Total: 449 | IdleMode: 60, NR L2: 81, NR RRC: 107, 5GC: 57, Multilayer: 33, IMS: 101, POS: 10.
EN-DC (5G option 3) | Total: 125 | NR L2: 71, RRC: 51, EPC: 3, IMS, POS: none.
NE-DC (5G option 4) | Total: 35 | NR L2: 2, NR RRC: 33, IdleMode, 5GC, Multilayer, IMS, POS: none.
TOTAL: | 609 | 
Notes: Legend:
Blue: changes from last MCC TF160 report.

## Slide 17
2023 Potential Candidate | Rel- | RAT | Prose Target | SIG TC # | TTCN Develpmt | 2023 WkLoad | Work Item Code / Status
NR coverage enhancements | Rel-17 | N | Q2’23 | FFS | FFS | FFS | NR_cov_enh-UEConTest
NR UL Data Compression (UDC) | Rel-17 | N | Q2’23 | FFS | FFS | FFS | NR_UDC-UEConTest / New
NR industrial IoT and URLLC enhancements | Rel-17 | N | Q2’23 | FFS | FFS | FFS | NR_IIoT_URLLC_enh-UEConTest / New
NR small data transmissions in INACTIVE state | Rel-17 | N | Q3’23 | FFS | FFS | FFS | NR_SmallData_INACTIVE-UEConTest / New
NB-IoT/eMTC support for non-terrestrial networks (NTN) | Rel-17 | L | Q3’23 | n/a | FFS | FFS | LTE_NBIOT_eMTC_NTN_plus_EPS-UEConTest / New
NR support for non-terrestrial networks (NTN) | Rel-17 | N | Q4’23 | FFS | FFS | FFS | NR_NTN_Solutions-UEConTest / New
5G private network support enhancements | Rel-17 | N | Q4’23 | FFS | FFS | FFS | NG_RAN_PRN_enh-UEConTest / New
NR MIMO further enhancements | Rel-17 | N | Q4’23 | FFS | FFS | FFS | NR_feMIMO-UEConTest / New
TTCN workplan: 2023 early candidates WIs with no 2022 budget, candidate for 2023 budgeting
Notes: Legend:
Blue: changes from last MCC TF160 report.
Red: Important information.
Italics: Estimation based on limited information available.

## Slide 18: Minutes of TTCN Sidebar
Friday 13th May @11AM CEST.
Agenda and minutes:
  See RAN5#95-e_TTCN_Sidebar-v2.zip