## Cover sheet
3GPP TSG-RAN5 Meeting # 98 | [10 empty] | R5-230083
Athens, Greece, Feb 27th – March 3rd 2023
Agenda Item: | 7.4.2
Source: | China Telecom
Title: | WP UE Conformance Test NR coverage enhancements RAN5#98
Work item code: | NR_cov_enh-UEConTest
Release: | Rel-17
Document for: | Information
RAN5 WP template v2.0-7
1. Introduction
The Rel-17 study item “Study on NR coverage enhancements” studied the enhancements of coverage for PUSCH, PUCCH and other channels/signals. In the follow-up WI on NR coverage enhancements, the enhancements for PUSCH, PUCCH and Msg3 PUSCH have been specified. The overall completion level for the core part of NR_cov_enh WI is already 85% at the RAN #94e in December 2021, and the WI core part is expected to be 100% completed at March 2022. The corresponding UE conformance specifications are now required to be implemented in RAN5.
2. Work item status
Estimation of WI overall completion:
Area |  | Completion | Number of new completed test cases (Note 1) | Number of new test cases | Comments
Overall completion |  | 13% (+2%) | 0 | 7
Completion Compensation |  | -
| Note 1: | Only test cases completed for all applicable WP areas and sub-areas are counted. For completed test cases per WP areas and WP sub-areas see below.
Estimation WI completion per area and sub-area:
|  | Completion | Number of new completed test cases | Number of new test cases | Comments
SA Option 2 (SA NR) |  | 13.3% (+2.5%) | 0 | 7
FR1 |  | 8.6% | 0 | 6
FR2 |  | 18% (+5%) | 0 | 6
Estimation of completion per TS (area):
|  | TS/TR overall completion |  |  | SA Option 2 (SA NR)
TS/TR Scope | TS/TR | Completion | Number of new completed test cases | Number of new test cases | FR1 |  |  | FR2
[5 empty] | Completion | Number of new completed test cases | Number of new test cases | Completion | Number of new completed test cases | Number of new test cases
5GS
5GS Common
Common test environment | 38.508-1 | 0% |  |  | 0% |  |  | 0%
Common ICS | 38.508-2 | 20% |  |  | 20% |  |  | 20%
NR RF/RRM
FR1 RF | 38.521-1 Tx
FR2 RF | 38.521-2 | 72.7% (+36.4%) | 0 | 1 |  |  |  | 72.7% (+36.4%) | 0 | 1
Applicability RF, Demod/QSI and RRM test cases | 38.522 | 25% (+25%) |  |  | 0% |  |  | 50% (+50%)
Test Tolerances analysis RRM and RF Rx test cases | 38.903
Test Point analysis receiver and transmitter test cases | 38.905 | 0% |  |  | 0% |  |  | 0%
5GS RAN and CN protocols
Protocol test cases | 38.523-1 | 4.3% | 0 | 5 | 4.3% | 0 | 5 | 4.3% | 0 | 5
Applicability Protocol test cases | 38.523-2 | 10% |  |  | 10% |  |  | 10%
Test suites (TTCN) | 38.523-3
5 References
[1] RP-yyxxxx | <WID document title>
Note on B21: Overall completion of the work item reported at an earlier meeting will not be decreased if additional tasks are added or if corrections are made to the work plan. Instead the earlier reported completion status will be kept until necessary progress have been achieved such that completion exceeds the earlier reported completion level. The value of the Completion Compensation value represents the difference in the decrease caused by late additions or corrections to the work plan and the current estimated overall completion. '-' indicates that no compensation is applied.

## WP
WP Title: |  | WP UE Conformance Test NR coverage enhancements | [10 empty] | Start of workplan status columns. Note! Do not remove this column. | WP item status |  | End of workplan columns. Note! Do not remove this column.
WI code |  | NR_cov_enh-UEConTest
WP Scope: |  | The objective of this work item is to define the UE conformance requirements corresponding to the WID on NR coverage enhancements. This work item will cover RF and Protocol conformance test specifications. | [12 empty] | vs Area
WP Resp: |  | Wu Jingzhou |  |  | wujingzhou@chinatelecom.cn | [5 empty] | WP item completion |  |  | SA Option 2 (SA NR)
TS Resp:
WP Item ID | Is new test case? | TS/area | Clause | Title | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | Overall | SA Option 2 (SA NR) |  | FR1 | FR2
[14 empty] | 8.6% | 18% (+5%)
[14 empty] | 14 | 14
[14 empty] | 8.6 | 8.6
5%
Start of work plan items. Note! Do not remove this row. Introduce new work plan rows/items below this row.
5GS
5GS Common
TS 38.508-1: Common test environment
|  | 38.508-1 | 4.6 | Adding default RRC message and information elements contents related to coverage enhancements |  | Huawei,Hisilicon | RAN5#98 (March-23) |  |  | 0.1 | 0% | 0% |  | 0% | 0%
TS 38.508-2: Common ICS
1 |  | 38.508-2 |  | Adding ICS for Rel-17 coverage enhancement. |  |  |  | R5-224267 |  | 0.1 | 20% | 20% |  | 20% | 20%
NR RF/RRM
TS 38.521-1: FR1 RF test cases
2 |  | 38.521-1 | F.9.1 | Phase offset measurement for DMRS bundling | Introduction of the measurement point for phase offset measurement. |  | RAN5#98 (March-23) |  |  | 0.1 | 0% | 0% |  | 0%
3 | Y | 38.521-1 Tx | 6.4.2.6 | Phase continuity requirements for DMRS bundling | Introduction of phase continuty test for DMRS bundling |  | RAN5#98 (March-23) |  |  | 1 | 0% | 0% |  | 0%
TS 38.521-2: FR2 RF test cases
4 |  | 38.521-2 | F.8.1 | Phase offset measurement for DMRS bundling | Introduction of the measurement point for phase offset measurement. | Apple | RAN5#98 (March-23) | R5-227773 |  | 0.1 | 100% | 100% |  |  | 100%
5 | Y | 38.521-2 | 6.4.2.6 | Phase continuity requirements for DMRS bundling | Introduction of phase continuty test for DMRS bundling | Apple | RAN5#98 (March-23) | R5-227773 R5-231371 | Test procedure and message content is FFS. Test Requirements and MU/TT analysis is pending | 1 | 70% (+40%) | 70% (+40%) |  |  | 70%
TS 38.522: Applicability for RF test cases
6 |  | 38.522 | 4.0 4.1.1 4.1.2 | Adding test applicability for the new test cases defined in 38.521-1 and 38.521-2. |  | All companies. | RAN5#98 (March-23) | R5-221810 | Test condition is FFS. | 0.1 | 25% (+25%) | 25% (+25%) |  | 0% | 50%
TR 38.903: Test Tolerances analysis RF Rx test cases
|  | 38.903 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
TR 38.905: Test Point analysis receiver and transmitter test cases
7 |  | 38.905 |  | Test point analysis for the new test cases defined in 38.521-1 and 38.521-2. |  | All companies | RAN5#98 (March-23) |  |  | 0.1 | 0% | 0% |  | 0% | 0%
RAN and CN protocol
TS 38.523-1: Protocol test cases
8 | Y | 38.523-1 | 7.1.1.1.18 | Random access procedure / Msg3 repetition indication / Random access resources selection | **** TP1: [TS 38.321, 5.1.1b TS38.300 19] WITH: UE in RRC_IDLE state and supporting MSG3 repetition WHEN: UE is configured both set(s) of Random Access resources with and without MSG3 repetition indication AND the the RSRP of the downlink pathloss reference is less than the configured threshold THEN: UE requests MSG3 repetition via separate RACH resources ------------------ **** TP2: [TS 38.321, 5.1.1b TS38.300 19] WITH: UE in RRC_IDLE state and supporting MSG3 repetition WHEN: UE is only configured Random Access resources with MSG3 repetition indication THEN: UE requests MSG3 repetition via separate RACH resources | China Telecom | RAN5#98-e (March-23) | R5-224269 |  | 1 | 30% | 30% |  | 30% | 30%
9 | Y | 38.523-1 | 7.1.1.2.6 | Correct HARQ process handling / dynamic PUCCH repetition indication | TP1: WITH: UE in RRC_CONNECTED state and supporting dynamic PUCCH repetition indication. UE is configured with a set of PUCCH resources and resource-specific PUCCH repetition numbers. WHEN: UE receives a DCI scheduling PDSCH reception. THEN: UE transmits HARQ feedback on PUCCH with the repetition number associated with the PUCCH resource indicated by DCI scheduling PDSCH. | Huawei,Hisilicon | RAN5#98-e (March-23) |  |  | 1 | 0% | 0% |  | 0% | 0%
10 | Y | 38.523-1 | 7.1.1.3.14 | Correct Handling of UL HARQ process / PUSCH Repetition Type A enhancement | TP1: WITH: UE in RRC_CONNECTED state and supporting PUSCH repetition type A enhancement. UE is configured with a repetition factor of 32 for PUSCH repetition Type A. WHEN: UE receives an UL Grant with toggled NDI and has data available for transmission THEN: UE transmits a new MAC PDU and repeats the MAC PDU in 31 times after first transmission and selects the redundancy version correctly. TP2: WITH: UE in RRC_CONNECTED state and supporting PUSCH repetition type A enhancement. UE is configured with availableSlotCounting. WHEN: UE receives an UL Grant with toggled NDI and has data available for transmission THEN: UE transmits repetitions of PUSCH on available UL slots and selects the redundancy version correctly. | Huawei,Hisilicon | RAN5#98-e (March-23) |  |  | 1 | 0% | 0% |  | 0% | 0%
11 | Y | 38.523-1 | 7.1.1.3.15 | Correct Handling of UL HARQ process / TBoMS procedure | TP1: WITH: UE in RRC_CONNECTED state and supporting TBoMS. WHEN: UE receives an UL Grant with toggled NDI which indicates TBoMS transmission and has data available for transmission THEN: UE transmits a new MAC PDU in numberOfSlotsTBoMS available slots and selects the redundancy version correctly. TP2: WITH: UE in RRC_CONNECTED state and supporting TBoMS. UE is configured with numberOfRepetitions WHEN: UE receives an UL Grant with toggled NDI which indicates TBoMS transmission and has data available for transmission THEN: UE transmits a new MAC PDU in numberOfSlotsTBoMS available slots, and then repeats the MAC PDU in numberOfRepetitions-1 times after first transmission and selects the redundancy version correctly. each transmission uses numberOfSlotsTBoMS available slots. | Huawei,Hisilicon | RAN5#98-e (March-23) |  |  | 1 | 0% | 0% |  | 0% | 0%
12 | Y | 38.523-1 | 7.1.1.4.2.7 | UL-SCH Transport Block Size selection / TBoMS procedure | TP1: WITH: UE in RRC_CONNECTED state and supporting TBoMS. WHEN: UE has pending data for transmission and receives on PDCCH DCI format 0_2 indicating a resource block assignment correspondent to physical resource blocks , Time domain resource assignment and modulation and coding THEN: UE transmits MAC PDU on PUSCH as per Modulation Coding scheme, time domain resource allocation and PRB's. | Huawei,Hisilicon | RAN5#98-e (March-23) |  |  | 1 | 0% | 0% |  | 0% | 0%
13 |  | 38.523-1 | 8.1.5.1.1 | Adding UE capability check related to coverage enhancement |  | Huawei,Hisilicon | RAN5#98-e (March-23) |  |  | 1 | 0% | 0% |  | 0% | 0%
|  | 38.523-1 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | 1 | 0% | 0% |  | 0% | 0%
TS 38.523-2: Applicability for Protocol test cases
14 |  | 38.523-2 | 4.1 4.2 |  | Add test case applicability and ICS statements for the new test cases introduced in 38.523-1 |  | RAN5#98-e (March-23) | R5-225332 |  | 0.1 | 10% | 10% |  | 10% | 10%
TS 38.523-3: Protocol test suites (TTCN)
|  | 38.523-3 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
End of workplan items. Note! Do not remove this row. Introduce new work plan rows/items above this row.
Note on A6: Unique ID for WP items (unique within the sub-area work plan) Note! As WP item numbers may be referenced from outside of this WP that means: - Do not change number for WP items that have been published. - Do not re-use WP item numbers if a WP item is deleted
Note on B6: Set to Y if the WP item represents a new test case that will be specified in RAN5 test specifications as an executable test case else leave blank.
Note on K6: The WP item's weight number is used to set the reletive weights between WP items used in the overall calculation of completeness. Setting it to 0 for a WP item means that it will not be included at all in the calculation.