## Cover sheet
3GPP TSG-RAN5 Meeting #99 | [7 empty] | R5-232327
Incheon, Korea (Republic Of) 22nd May, 2023 - 26th May, 2023
Agenda Item: | 7.4.2
Source: | Ligado Networks
Title: | WP for LTE_TDD_1670_1675MHz-UEConTest
Work item code: | LTE_TDD_1670_1675MHz-UEConTest
Release: | Rel-18
Document for: | Information
RAN5 WP template v3.0.0
1. Introduction
At RAM#99, a RAN5 work item for conformance test aspects was approved to update the test cases for a new LTD TDD band 54 in 1670 - 1675 MHz range [1]. The purpose of the present document is to provide a work plan and status for RAN5 work related to specification of conformance testing for the new LTE TDD band 54. The work plan will be updated after each RAN5 meeting to give the status of the work item until the work is fully completed
2. Work item status
Estimation of WI overall completion:
Area |  | Completion | Number of new completed test cases (Note 1) | Number of new test cases | Comments
Overall completion |  | 83% (+83%)
Completion Compensation |  | -
| Note 1: | Only test cases completed for all applicable WP areas and sub-areas are counted. For completed test cases per WP areas and WP sub-areas see below.
Estimation WI completion per area and sub-area:
|  | Completion | Number of new completed test cases | Number of new test cases | Comments
LTE |  | 82.6% (+82.6%)
82.6% (+82.6%)
Estimation of completion per TS (area):
|  | TS/TR overall completion |  |  | LTE
TS/TR Scope | TS/TR | Completion | Number of new completed test cases | Number of new test cases
[5 empty] | Completion | Number of new completed test cases | Number of new test cases
LTE
LTE Common
Common test environment | 36.508 | 100% (+100%) |  |  | 100% (+100%)
LTE RF/RRM
RF common parts | 36.521-1 | 100% (+100%) |  |  | 100% (+100%)
RF Rx test cases | 36.521-1 Rx | 100% (+100%) |  |  | 100% (+100%)
RF Tx test cases | 36.521-1 Tx | 93.9% (+93.9%) |  |  | 93.9% (+93.9%)
Applicability RF. Demod/QSI and RRM test cases | 36.521-2 | 100% (+100%) |  |  | 100% (+100%)
RRM test cases | 36.521-3 | 100% (+100%) |  |  | 100% (+100%)
LTE RAN and CN protocols
Applicability Protocol test cases | 36.523-2 | 100% (+100%) |  |  | 100% (+100%)
Test suites (TTCN) | 36.523-3 | 100% (+100%) |  |  | 100% (+100%)
5GS
NR RF/RRM
FR1 RF Tx test cases | 38.521-1 Tx | 0% |  |  | 0%
FR1 and FR2 Interworking operation with other radios RF Tx test cases | 38.521-3 Tx | 0% |  |  | 0%
NTN RF Tx test cases | 38.521-5 Tx | 0% |  |  | 0%
Test Point analysis receiver and transmitter test cases | 38.905 | 0% |  |  | 0%
5 References
[1] RP-230063 | UE Conformance – Introduction of LTE TDD band in 1670 – 1675 MHz
Note on B21: Overall completion of the work item reported at an earlier meeting will not be decreased if additional tasks are added or if corrections are made to the work plan. Instead the earlier reported completion status will be kept until necessary progress have been achieved such that completion exceeds the earlier reported completion level. The value of the Completion Compensation value represents the difference in the decrease caused by late additions or corrections to the work plan and the current estimated overall completion. '-' indicates that no compensation is applied.

## WP
WP Title: |  | Work plan for Introduction of LTE TDD Band in 1670 - 1675 MHz | [10 empty] | Start of workplan status columns. Note! Do not remove this column. | WP item status | End of workplan columns. Note! Do not remove this column.
WI code |  | LTE_TDD_1670_1675MHz-UEConTest
WP Scope: |  | Introduce new LTE TDD band 54 to the conformance testing specifications
WP Resp: |  | Ojas Choksi |  |  | ojas.choksi@ligado.com | [5 empty] | WP item completion |  |  | LTE
TS Resp: |  | <TS responsible if a new TS is involved> |  |  | <Email to TS responsible>
WP Item ID | Is new test case? | TS/area | Clause | Title | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | Overall | LTE
82.6% (+82.6%)
53 (+53)
1.9 (+1.9)
5%
Start of work plan items. Note! Do not remove this row. Introduce new work plan rows/items below this row.
LTE
LTE Common
TS 36.508: Common test environment
1 |  | 36.508 | 4.3.1.2 | Test frequencies | Addition of test frequencies for B54 |  | RAN5#100 (Aug-23) | R5-2323694 revof R5-232311 |  | 0.02 | 100% (+100%) | 100% (+100%) |  | 100%
2 |  | 36.508 | 6.2.31 | Test frequencies for signalling test | Addition of signaling frequencies for B54 |  | RAN5#100 (Aug-23) | R5-232312 |  | 0.01 | 100% (+100%) | 100% (+100%) |  | 100%
LTE RF/RRM
TS 36.521-1: RF test cases - Common parts (general clauses, Annexes)
3 |  | 36.521-1 | 5.2 | Operating bands | Addition of LTE TDD band 54 |  | RAN5#100 (Aug-23) | R5-232313 |  | 0.01 | 100% (+100%) | 100% (+100%) |  | 100%
4 |  | 36.521-1 | 5.4.2.1 | Channel bandwidths per operating band | Addition of channel BWs for TDD B54 |  | RAN5#100 (Aug-23) | R5-232313 |  | 0.01 | 100% (+100%) | 100% (+100%) |  | 100%
5 |  | 36.521-1 | 5.4.4 | Carrier frequency and EARFCN | Addition of EARFCNs for TDD B54 |  | RAN5#100 (Aug-23) | R5-232313 |  | 0.01 | 100% (+100%) | 100% (+100%) |  | 100%
TS 36.521-1: RF test cases - Tx
6 |  | 36.521-1 Tx | 6.2.2 | UE Maximum Output Power | Update conformance and test requirements to introduce B54 |  | RAN5#100 (Aug-23) | R5-232314 |  | 0.02 | 100% (+100%) | 100% (+100%) |  | 100%
7 |  | 36.521-1 Tx | 6.2.2B | UE Maximum Output Power for UL-MIMO | Update conformance and test requirements to introduce B54 |  | RAN5#100 (Aug-23) | R5-232314 |  | 0.02 | 100% (+100%) | 100% (+100%) |  | 100%
8 |  | 36.521-1 Tx | 6.2.2_s | UE Maximum Output Power for subslot/slot TTI | Update test requirements to introduce B54 |  | RAN5#100 (Aug-23) | R5-232314 |  | 0.02 | 100% (+100%) | 100% (+100%) |  | 100%
9 |  | 36.521-1 Tx | 6.2.3 | Maximum Power Reduction (MPR) | Update test requirements to introduce B54 |  | RAN5#100 (Aug-23) | R5-232314 |  | 0.02 | 100% (+100%) | 100% (+100%) |  | 100%
10 |  | 36.521-1 Tx | 6.2.3_2 | Maximum Power Reduction (MPR) for Multi-Cluster PUSCH | Update test requirements to introduce B54 |  | RAN5#100 (Aug-23) | R5-232314 |  | 0.02 | 100% (+100%) | 100% (+100%) |  | 100%
11 |  | 36.521-1 Tx | 6.2.3_3 | Maximum Power Reduction (MPR) for UL 64QAM | Update test requirements to introduce B54 |  | RAN5#100 (Aug-23) | R5-232314 |  | 0.02 | 100% (+100%) | 100% (+100%) |  | 100%
12 |  | 36.521-1 Tx | 6.2.3_4 | Maximum Power Reduction (MPR) for Multi-Cluster PUSCH with UL 64QAM | Update test requirements to introduce B54 |  | RAN5#100 (Aug-23) | R5-232314 |  | 0.02 | 100% (+100%) | 100% (+100%) |  | 100%
13 |  | 36.521-1 Tx | 6.2.3_5 | Maximum Power Reduction (MPR) for UL 256QAM | Update test requirements to introduce B54 |  | RAN5#100 (Aug-23) | R5-232314 |  | 0.02 | 100% (+100%) | 100% (+100%) |  | 100%
14 |  | 36.521-1 Tx | 6.2.3_6 | Maximum Power Reduction (MPR) for Multi-Cluster PUSCH with UL 256QAM | Update test requirements to introduce B54 |  | RAN5#100 (Aug-23) | R5-232314 |  | 0.02 | 100% (+100%) | 100% (+100%) |  | 100%
15 |  | 36.521-1 Tx | 6.2.3B | Maximum Power Reduction (MPR) for UL-MIMO | Update test applicability, test description and test requirement to introduce B54 |  | RAN5#100 (Aug-23) | R5-232314 |  | 0.02 | 100% (+100%) | 100% (+100%) |  | 100%
16 |  | 36.521-1 Tx | 6.2.4 | Additional Maximum Power Reduction (A-MPR) | Update test applicability, test description and test requirement for NS_62 to introduce B54 |  | RAN5#100 (Aug-23) | R5-232315 |  | 0.1 | 100% (+100%) | 100% (+100%) |  | 100%
17 |  | 36.521-1 Tx | 6.2.4_2 | Additional Maximum Power Reduction (A-MPR) for UL 64QAM | Update test applicability, test description and test requirement for NS_62 to introduce B54 |  | RAN5#100 (Aug-23) | R5-232315 |  | 0.1 | 100% (+100%) | 100% (+100%) |  | 100%
18 |  | 36.521-1 Tx | 6.2.4_4 | Additional Maximum Power Reduction (A-MPR) for UL 256QAM | Update test applicability, test description and test requirement for NS_62 to introduce B54 |  | RAN5#100 (Aug-23) | R5-232315 |  | 0.1 | 100% (+100%) | 100% (+100%) |  | 100%
19 |  | 36.521-1 Tx | 6.2.4B | Additional Maximum Power Reduction (A-MPR) for UL-MIMO | Update test applicability, test description and test requirement for NS_62 to introduce B54 |  | RAN5#100 (Aug-23) | R5-232315 |  | 0.1 | 100% (+100%) | 100% (+100%) |  | 100%
20 |  | 36.521-1 Tx | 6.2.4_s | Additional Maximum Power Reduction (A-MPR) for subslot/slot TTI | Update test applicability, test description and test requirement for NS_62 to introduce B54 |  | RAN5#100 (Aug-23) | R5-232315 |  | 0.1 | 100% (+100%) | 100% (+100%) |  | 100%
21 |  | 36.521-1 Tx | 6.6.3.2 | Spurious emission band UE co-existence | Update conformance and test requirements to protect B54 from spurious emissions of other applicable regional bands |  | RAN5#100 (Aug-23) | R5-233704 revof R5-232316 |  | 0.1 | 100% (+100%) | 100% (+100%) |  | 100%
22 |  | 36.521-1 Tx | 6.6.3..2A | Spurious emission band UE co-existence for CA | Update conformance and test requirements to protect B54 from spurious emissions of CA band combinations of other applicable regional bands |  | RAN5#100 (Aug-23) | R5-233704 revof R5-232316 |  | 0.1 | 100% (+100%) | 100% (+100%) |  | 100%
23 |  | 36.521-1 Tx | 6.6.3.3 | Additional spurious emissions | Update conformance requirements, test description and requirements for the new NS_56 to introduce B54 |  | RAN5#100 (Aug-23) | R5-233704 revof R5-232316 |  | 0.1 | 100% (+100%) | 100% (+100%) |  | 100%
24 |  | 36.521-1 Tx | 6.6.3.3_1 | Additional spurious emission for UL 64QAM | Update conformance requirements, test description and requirements for the new NS_56 to introduce B54 |  | RAN5#100 (Aug-23) | R5-233704 revof R5-232316 |  | 0.1 | 100% (+100%) | 100% (+100%) |  | 100%
25 |  | 36.521-1 Tx | 6.6.3.3_2 | Additional spurious emission for UL 256QAM | Update conformance requirements, test description and requirements for the new NS_56 to introduce B54 |  | RAN5#100 (Aug-23) | R5-233704 revof R5-232316 |  | 0.1 | 100% (+100%) | 100% (+100%) |  | 100%
26 |  | 36.521-1 Tx | 6.6.3B.2 | Spurious emission band UE co-existence for UL-MIMO | Update conformance requirements, test description and requirements for the new NS_56 to introduce B54 |  | RAN5#100 (Aug-23) | R5-233704 revof R5-232316 |  | 0.02 | 100% (+100%) | 100% (+100%) |  | 100%
27 |  | 36.521-1 Tx | 6.6.3B.3 | Additional spurious emssiions for UL-MIMO | Update conformance requirements,, test description and requirements for the new NS_56 to introduce B54 |  | RAN5#100 (Aug-23) | R5-233704 revof R5-232316 |  | 0.02 | 100% (+100%) | 100% (+100%) |  | 100%
28 |  | 36.521-1 Tx | 6.6.3E.2 | Spurious emission band UE co-existence for UE Category 0 | Update conformance and test requirements for the new NS_56 to introduce B54 |  | RAN5#100 (Aug-23) |  |  | 0.02 | 0% | 0% |  | 0%
29 |  | 36.521-1 Tx | 6.6.3EA.2 | Spurious emission band UE co-existence for UE Category M1 | Update conformance and test requirements for the new NS_56 to introduce B54 |  | RAN5#100 (Aug-23) |  |  | 0.02 | 0% | 0% |  | 0%
30 |  | 36.521-1 Tx | 6.6.3EC.2 | Spurious emission band UE co-existence for UE Category M2 | Update conformance and test requirements for the new NS_56 to introduce B54 |  | RAN5#100 (Aug-23) |  |  | 0.02 | 0% | 0% |  | 0%
31 |  | 36.521-1 Tx | 6.6.3F.2.3 | Spurious emission band UE co-existence for UE Category NB1 and NB2 | Update conformance and test requirements for the new NS_56 to introduce B54 |  | RAN5#100 (Aug-23) |  |  | 0.02 | 0% | 0% |  | 0%
32 |  | 36.521.-1 Tx | F.3.2 | Measurement of transmitter | Map formula for test configuration id for 6.2.4 test cases |  | RAN5#100 (Aug-23) |  |  | 0.02 | 0% | 0% |  | 0%
TS 36.521-1: RF test cases - Rx
33 |  | 36.521-1 Rx | 7.3 | Reference sensitivity level | Update conformance requirements,, test description and requirements 6 to introduce B54 |  | RAN5#100 (Aug-23) | R5-232321 |  | 0.02 | 100% (+100%) | 100% (+100%) |  | 100%
34 |  | 36.521-1 Rx | 7.3B | Reference sensitivity level for UL-MIMO | Update conformance requirements,, test description and requirements 6 to introduce B54 |  | RAN5#100 (Aug-23) | R5-232321 |  | 0.02 | 100% (+100%) | 100% (+100%) |  | 100%
35 |  | 36.521-1 Rx | 7.6.1 | In-band blocking | Update conformance and test requirements to introduce B54 |  | RAN5#100 (Aug-23) | R5-232322 |  | 0.02 | 100% (+100%) | 100% (+100%) |  | 100%
36 |  | 36.521-1 Rx | 7.6.1B | In-band blocking for UL-MIMO | Update test requirements to introduce B54 |  | RAN5#100 (Aug-23) | R5-232322 |  | 0.02 | 100% (+100%) | 100% (+100%) |  | 100%
37 |  | 36.521-1 Rx | 7.6.2 | Out-of-band blocking | Update conformance and test requirements to introduce B54 |  | RAN5#100 (Aug-23) | R5-232322 |  | 0.02 | 100% (+100%) | 100% (+100%) |  | 100%
38 |  | 36.521-1 Rx | 7.6.2B | Out-of-band blocking for UL-MIMO | Update test requirements to introduce B54 |  | RAN5#100 (Aug-23) | R5-232322 |  | 0.02 | 100% (+100%) | 100% (+100%) |  | 100%
TS 36.521-2: Applicability for RF, Demod/CSI reporting and RRM test cases
39 |  | 36.521-2 | A.4.3 | Baseline Implementation Capabilities | Add test case applicability statements for B54 introduced for 36.521-1 and 38.521-3 |  | RAN5#100 (Aug-23) | R5-232323 |  | 0.02 | 100% (+100%) | 100% (+100%) |  | 100%
40 |  | 36.521-2 | A.4.5 | Additional information | Add UL-MIMO applicability statement for B54 introduced for 36.521-1 and 38.521-3 |  | RAN5#100 (Aug-23) | R5-232323 |  | 0.02 | 100% (+100%) | 100% (+100%) |  | 100%
TS 36.521-3: RRM test cases
41 |  | 36.521-3 | 3.5.1 | Group of bands | Specify band group for B54 introduced for 36.521-1 |  | RAN5#100 (Aug-23) | R5-232324 |  | 0.01 | 100% (+100%) | 100% (+100%) |  | 100%
LTE RAN and CN protocols
TS 36.523-2: Applicability for Protocol test cases
42 |  | 36.523-2 | A.4.3.1 | RF Baseline Implementation Capabilities | Add test case applicability statements for the new test cases introduced in 36.523-1 |  |  | R5-232325 |  | 0.02 | 100% (+100%) | 100% (+100%) |  | 100%
TS 36.523-3: Protocol test suites (TTCN)
43 |  | 36.523-3 | 11.1 | E-UTRA single technology | Add guidelines for test execution for B54 |  | RAN5#100 (Aug-23) | R5-233414 rev of R5-232326 |  | 0.01 | 100% (+100%) | 100% (+100%) |  | 100%
44 |  | 36.523-3 | 11.2 | E-UTRA - UTRA - GERAN | Add guidelines for test execution for B54 |  | RAN5#100 (Aug-23) | R5-233414 rev of R5-232326 |  | 0.01 | 100% (+100%) | 100% (+100%) |  | 100%
45 |  | 36.523-3 | 11.3 |  | Add guidelines for test execution for B54 |  | RAN5#100 (Aug-23) | R5-233414 rev of R5-232326 |  | 0.01 | 100% (+100%) | 100% (+100%) |  | 100%
5GS
TS 38.521-1: FR1 RF test cases - Tx
46 |  | 38.521-1 Tx | 6.5.3.2 | Spurious emission for UE co-existence | Update conformance and test requirements to protect B54 from spurious emissions of other applicable regional bands |  | RAN5#100 (Aug-23) |  |  | 0.02 | 0% | 0% |  | 0%
47 |  | 38.521-1 Tx | 6.5A.3.2 | Spurious emission for UE co-existence (CA) | Update conformance requirements, inter band CA test configuration and test requirements to protect B54 from spurious emissions of CA band combinations of other applicable regional bands |  | RAN5#100 (Aug-23) |  |  | 0.02 | 0% | 0% |  | 0%
48 |  | 38.521-1 Tx | 6.5C.3.2 | Spurious emissions for UE co-existence for SUL | Update test requirements to protect B54 from spurious emissions of other applicable regional SUL bands |  | RAN5#100 (Aug-23) |  |  | 0.02 | 0% | 0% |  | 0%
TS 38.521-3: FR1 and FR2 Interworking operation with other radios RF test cases - Tx
49 |  | 38.521-3 Tx | 6.5B.3.1.2 | Spurious emission band UE co-existence for intra-band contiguous EN-DC | Update conformance and test requirements to protect B54 from spurious emissions of other applicable regional bands |  | RAN5#100 (Aug-23) |  |  | 0.02 | 0% | 0% |  | 0%
50 |  | 38.521-3 Tx | 6.5B.3.2.2 | Spurious emission band UE co-existence for intra-band non-contiguous EN-DC | Update conformance and test requirements to protect B54 from spurious emissions of other applicable regional bands |  | RAN5#100 (Aug-23) |  |  | 0.02 | 0% | 0% |  | 0%
51 |  | 38.521-3 Tx | 6.5B.3.3.3 | Spurious emission band UE co-existence for inter-band within FR1 | Update conformance requirements, inter band CA test configuration and test requirements to protect B54 from spurious emissions of CA band combinations of other applicable regional bands |  | RAN5#100 (Aug-23) |  |  | 0.02 | 0% | 0% |  | 0%
TS 38.521-5: NTN RF test cases - Tx
52 |  | 38.521-5 Tx | 6.5.3.2 | Spurious emissions for UE co-existence | Update conformance and test requirements to protect B54 from spurious emissions of other applicable regional bands |  | RAN5#101 (Nov-23) |  |  | 0.02 | 0% | 0% |  | 0%
TR 38.905: Test Point analysis receiver and transmitter test cases
53 |  | 38.905 | 4.1.3.2 | Spurious emissions test cases for FR1 UL CA | Add TPs based onspurious emissions co-existence analysis for applicable inter-band regional FR1 CA band combinations for protection of B54 |  | RAN5#100 (Aug-23) |  |  | 0.1 | 0% | 0% |  | 0%
End of workplan items. Note! Do not remove this row. Introduce new work plan rows/items above this row.
Note on A6: Unique ID for WP items (unique within the sub-area work plan) Note! As WP item numbers may be referenced from outside of this WP that means: - Do not change number for WP items that have been published. - Do not re-use WP item numbers if a WP item is deleted
Note on B6: Set to Y if the WP item represents a new test case that will be specified in RAN5 test specifications as an executable test case else leave blank.
Note on K6: The WP item's weight number is used to set the reletive weights between WP items used in the overall calculation of completeness. Setting it to 0 for a WP item means that it will not be included at all in the calculation.