## Summary
Work plan summary:
Rel-15 5GS EN-DC and SA NR Maintenance Workplan for protocol testing
Completion
|  |  | Overall | FR1 | FR2 | FR1+FR2
| Rel-15 5GS EN-DC and SA NR Maintenance Workplan for protocol testing | SA Option 2 (SA NR) | 92.01% | 100% | 82.29% | 91.43%
|  | NSA Option 3 (EN-DC) | 96.46% | 100% | 90.43% | 100%
Test case statistics
|  |  | Overall number of test cases |  | Number of test cases applicable for FR1 |  | Number of test cases applicable for FR2 |  | Number of FR1+FR2 specific test cases
|  |  | Overall | Completed for at least one of FR1, FR2 or FR1+FR2 | Overall | Completed | Overall | Completed | Overall | Completed
| Rel-15 5GS EN-DC and SA NR Maintenance Workplan for protocol testing | SA Option 2 (SA NR) | 55 | 55 | 55 | 55 | 46 | 3 | 6 | 1
|  | NSA Option 3 (EN-DC) | 12 | 12 | 12 | 12 | 9 | 4 | 4 | 4

## WP
WP Title: | Rel-15 5GS EN-DC and SA NR Maintenance Workplan for protocol testing | [20 empty] | End of work plan columns. Note! Do not remove this column.
WP Scope: | This work plan section covers the Layer 2, Idle Mode, RRC, 5GC and Multilayer and Services protocol test cases to be completed under maintenace and WI codes: TEI15_Test, 5GS_NR_LTE-UEConTest.
WP Resp: | Yogesh Tugnawat (Qualcomm) |  |  |  | yogesht@qti.qualcomm.com | [7 empty] | SA NR |  |  | EN-DC |  |  | NE-DC
WP Item ID | Is test case | TS | Clause | Title | Test purpose / Task | Company | Target | TDOC(s) | Comments | Outstanding issues | Weight | WP item compl. | FR1 | FR2 | FR1+FR2 | FR1 | FR2 | FR1+FR2 | FR1 | FR2 | FR1+FR2
[12 empty] | Overall | 92.01% |  |  | 96.46%
[13 empty] | 100% | 82.29% | 91.43% | 100% | 90.43% | 100%
Start of work plan items. Note! Do not remove this row. Introduce new work plan rows/items below this row.
Layer 2 | [5 empty] | Responsible: Abdul Rasheed, Mohammed, Motorola Mobility
MAC
84 | Y | 38.523-1 | 7.1.1.3.8.2 | UE power headroom reporting / SCell activation / DL pathloss change reporting / Inter-band CA | **** TP1: [TS 38.321:5.4.6, 6.1.3.9] WITH: UE in RRC_Connected state with Power headroom reporting with phr-Type2SpCell and phr-Type2OtherCell and an SCell with uplink is configured WHEN: UE receives an Activation MAC Control Element activating the SCell THEN: UE transmits a MAC PDU containing Power Headroom Report MAC Control Element including PH type2 for SpCell and Scell **** TP2: [TS 38.321:5.4.6, 6.1.3.9] WITH: UE in RRC_Connected state with Power headroom reporting for phr-dl-PathlossChange, phr-Type2spCell and phr-Type2OtherCell configured WHEN: the DL Pathloss changes and phr-ProhibitTimer is running THEN: UE does not transmit a MAC PDU containing Power Headroom Report MAC Control Element including PH type2 for SpCell and Scell **** TP3: [TS 38.321:5.4.6, 6.1.3.9] WITH: UE in RRC_Connected state with Power headroom reporting for phr-dl-PathlossChange, phr-Type2SpCell and phr-Type2OtherCell configured WHEN: phr-ProhibitTimer expires and extended power headroom report is triggered due to DL Pathloss change THEN: UE transmits a MAC PDU containing Power Headroom Report MAC Control Element including PH type2 for SpCell and Scell | Motorola Mobility | Opt 2: Post WI close Opt 3: Post WI close | R5-185152, R5-194819, R5-198891, R5-202611, R5-206324, R5-206324, R5-211385, R5-215675, R5-220287 | The FR1-FR2 interband status is set to 90% @ RAN5#94 as it will not be possible to run in an OTA environment since there is power level changes on both the cells |  | 1 | 96.67% | 100% | 100% | 90% | 100% | 100% | 90%
86 | Y | 38.523-1 | 7.1.1.8.1 | Bandwidth Part (BWP) operation UL/DL | (1) with { UE in RRC_CONNECTED state } ensure that { when { UE receives BandwidthPart-Config IE included in RRC Message received on SpCell (i.e. PSCell in case of EN-DC or PCell in case of SA) } then { UE starts normal MAC operation in the FirstActive UL and DL Bandwidth part } } (2) with { UE in RRC_CONNECTED state } ensure that { when { UE receives a DL DCI format 1_1 assigning a BWP different than the previously configured BWP } then { UE starts normal MAC operation in the received new BWP } } (3) with { UE in RRC_CONNECTED } ensure that { when { UE receives a UL DCI format 0_1 assigning a BWP different than the previously configured BWP } then { UE starts normal MAC operation in the received new BWP } } (4) with { UE in RRC_CONNECTED state } ensure that { when { UE determines that a RACH Procedure is triggered in SpCell (i.e. PSCell in case of EN-DC or PCell in case of SA) and PRACH occasions are not configured } then { UE initiates the PRACH procedure in the initial BWP } } (5) with { UE in RRC_Connected State with defaultDownlinkBWP configured } ensure that { when { UE bwp-InactivityTimer expires } then { UE performs BWP switching to a BWP indicated by the defaultDownlinkBWP } } (6) with { UE in RRC_Connected State with defaultDownlinkBWP configured and Active BWP is different than defaultDownlinkBWP and bwp-InactivityTimer is running } ensure that { when { UE receives UL assignment or DL grant addressed to its C-RNTI } then { UE restarts the bwp-InactivityTimer } } | Qualcomm | Opt 2: Post WI close Opt 3: Post WI close | R5-231578 |  | prose is only 100% complete for FR1 TDD, and incomplete (90%) for FR1 FDD & FR2 | 1 | 95% | 100% | 90% |  | 100% | 90%
Idle Mode | [5 empty] | Responsible: Yogesh Tugnawat, Qualcomm
NG-RAN Only PLMN Selection
|  | 38.523-1 | 6.1.1 | NG-RAN Only PLMN Selection
1 | Y | 38.523-1 | 6.1.1.1 | PLMN selection of RPLMN, HPLMN/EHPLMN, UPLMN and OPLMN / Automatic mode | Editor's note: 1 **** TP: [] Editor's note: UE in Automatic network selection mode and RPLMN, HPLMN, UPLMN and OPLMN NR cells available and UE is fitted with a USIM indicating RPLMN should be selected WITH: UE is switched on or return to coverage WHEN: UE selects a cell of the RPLMN and UE attempts Registration on the selected cell THEN: **** TP2: [TS 23,122:4.4.3.1, 4.4.3.1.1 and 4.4.3.3] WITH: UE camped on an NG-RAN VPLMN cell and cells of a higher priority NG-RAN PLMN available WHEN: higher priority PLMN search timer T expires THEN: UE selects and camps on a cell of the highest priority PLMN and UE attempts Registration with mobility on the selected cell **** TP3: [TS 23,122:4.4.3.1, 4.4.3.1.1 and 4.4.3.3] WITH: UE in Automatic network selection mode and HPLMN, UPLMN and OPLMN NG-RAN cells available and UE is fitted with a USIM with Access Technology data files for each PLMN and there are no equivalent HPLMNs defined WHEN: UE is switched on or return to coverage THEN: UE selects a cell of the highest priority PLMN and UE attempts Registration with mobility on the selected cell **** TP4: [TS 23,122:4.4.3.1, 4.4.3.1.1 and 4.4.3.3] WITH: UE camped on an NG-RAN VPLMN cell and cells of a NG-RAN HPLMN available WHEN: Higher priority PLMN search timer T expires THEN: UE selects and camps on a cell of HPLMN and UE attempts Registration on the selected cell | Qualcomm | Opt 2: Post WI close | R5-190751 R5-191663 R5-201206 R5-202593 R5-203363 R5-225374 R5-233445 |  |  | 1 | 100% | 100% | 100% | [5 empty] | 1
3 | Y | 38.523-1 | 6.1.1.3 | Cell reselection of ePLMN in manual mode | **** TP1: [TS 23,122:4.4.3.1.2] WITH: UE camped normally on a cell and network has downloaded a list of equivalent PLMNs during the Registration procedure WHEN: Higher ranked cell is a cell of a PLMN in the downloaded equivalent PLMN list THEN: UE reselects to the equivalent PLMN cell **** TP2: [TS 23,122:4.4.3.1.2] WITH: UE camped normally on a cell and network has downloaded a list of equivalent PLMNs during Registration procedure for mobility WHEN: Highest ranked cell is a cell of a PLMN not in the downloaded equivalent PLMN list THEN: UE does not reselect to the cell | Huawei,Hisilicon | Opt 2: Post WI close | R5-190737 R5-192758 R5-196598 R5-200338 R5-201477 R5-211329 R5-230297 R5-233445 |  |  | 1 | 100% | 100% | 100% | [5 empty] | 1
3a | Y | 38.523-1 | 6.1.1.4a | PLMN selection in shared network environment / Automatic mode / Cells broadcasting multiple PLMN IDs with unique TAC's, RAN areas, and cell identities |  | Qualcomm |  | R5-227412 |  | New TC defined in RAN5#97 | 1 | 100% | 100% | 100%
5 | Y | 38.523-1 | 6.1.1.5 | PLMN selection of RPLMN, HPLMN/EHPLMN, UPLMN and OPLMN / Automatic mode / User reselection | **** TP1: [TS 23,122:4.4.3.2 and 4.4.3.2.1] WITH: UE in Automatic network selection mode registered to UPLMN and RPLMN, UPLMN and OPLMN NG-RAN cells available WHEN: UE is requested to initiate reselection and registration onto an available PLMN THEN: UE reselects to the cell which belongs to higher priority OPLMN **** TP2: [TS 23,122:4.4.3.2 and 4.4.3.2.1] WITH: UE in Automatic network selection mode registered to OPLMN and only RPLMN NG-RAN cells available WHEN: UE is requested to initiate reselection and registration onto an available PLMN THEN: UE remains on the current cell which belongs to RPLMN. **** TP3: [TS 23,122:4.4.3.2 and 4.4.3.2.1] WITH: UE in Automatic network selection mode registered to OPLMN and RPLMN, UPLMN and OPLMN NG-RAN cells available WHEN: UE is requested to initiate reselection and registration onto an available PLMN THEN: UE reselects to the cell which belongs to UPLMN **** TP4: [TS 23,122:4.4.3.2 and 4.4.3.2.1] WITH: UE in Automatic network selection mode registered to UPLMN and RPLMN, UPLMN, OPLMN and HPLMN NG-RAN cells available WHEN: UE is requested to initiate reselection and registration onto an available PLMN THEN: UE reselects to the cell which belongs to HPLMN | Huawei,Hisilicon | Opt 2: Post WI close | R5-190739 R5-192759 R5-201127 R5-202594 R5-203367 R5-233445 |  |  | 1 | 100% | 100% | 100% | [5 empty] | 1
62 |  | 38.523-1 | 6.1.1.1 to 6.1.1.8 |  | Define FR2 power levels for test cases 6.1.1.1 to 6.1.1.8 | See above | Opt 2: Post WI close | R5-187778 R5-190755 R5-192751 |  |  | 0.4 | 0% |  | 0%
NG-RAN Only Cell Selection & Cell Reselection
|  | 38.523-1 | 6.1.2 | NG-RAN Only Cell Selection
10 | Y | 38.523-1 | 6.1.2.2 | Cell Selection / Qqualmin/Intra NR / Serving cell becomes non-suitable (Srxlev > 0, Squal < 0) | **** TP1: [TS 38,3:9.2.1.1; TS 38,304:4.1 , 4.5 , 5.2.1,5.2.3.1 , 5.2.3.2] WITH: UE in NR RRC_IDLE state WHEN: a cell fulfils all requirements for a suitable cell except the cell selection criteria which are not fulfilled (Srxlev>0 AND Squal<0) THEN: the UE does not consider the cell suitable and no camping on this cell can take place **** TP2: [TS 38,3:9.2.1.1; TS 38,304:4.1 ,4.5 , 5.2.1,5.2.3.1 , 5.2.3.2] WITH: UE in NR RRC_IDLE state WHEN: a cell fulfils all requirements for a suitable cell including the cell selection criteria for a cell which are also fulfilled (Srxlev>0 AND Squal>0) THEN: the UE considers the cell suitable and camps on it **** TP3: [TS 38,304:5.3.1 , 5.2.4.6] WITH: UE in NR RRC_IDLE state WHEN: the serving cell becomes non-suitable (Srxlev > 0 and Squal < 0)and there is a suitable neighbour cell (Srxlev > 0 and Squal > 0) THEN: UE selects the suitable neighbour cell | Huawei,Hisilicon | Opt 2: Post WI close | R5-190741 R5-192749 R5-196217 R5-201440 R5-206318 R5-212411 R5-216163 R5-225372 |  | FR2 not applicable | 1 | 100% | 100%
11 | Y | 38.523-1 | 6.1.2.3 | Cell selection / Intra NR/ Serving cell becomes non-suitable (S<0, MIB Indicated barred) | **** TP1: [TS 38,304:4.1 , 4.5 , 5.2.1, 5.2.3.1 , 5.3.1 , 5.2.4.6; TS 38,3:9.2.1.1] WITH: UE in NR RRC_IDLE state WHEN: the serving cell becomes non-suitable (S<0)and there is a suitable neighbour cell (S>0) THEN: UE selects the suitable neighbour cell **** TP2: [TS 38,304:5.2.4.6 , cl 5.3.1] WITH: UE in NR RRC_IDLE state WHEN: the serving cell becomes barred and there is a suitable neighbour cell THEN: UE selects the suitable neighbour cell | Huawei,Hisilicon | Opt 2: Post WI close | R5-190742 R5-192756 R5-201228 R5-233445 |  |  | 1 | 100% | 100% | 100%
| Y | 38.523-1 | 6.1.2.3a | Intra frequency reselection not allowed | with { UE in NR RRC_IDLE state } ensure that { when { the serving cell becomes barred and broadcasting intraFreqReselection to "not allowed" and UE detects both intra-frequency and equal priority inter-frequency neighbour cells and the intra-frequency cell is the highest ranked cell } then { UE reselects the inter-frequency cell } | Qualcomm |  | R5-233463 |  |  |  | 95% | 100% | 90%
12 | Y | 38.523-1 | 6.1.2.4 | Cell Reselection for interband operation | **** TP1: [TS 38,304:5.2.4.1 , 52.4.2 , 5.2.4.6] WITH: UE in NR RRC_IDLE state WHEN: UE detects the cell re-selection criteria are met for the cell on the different frequency band THEN: UE reselects the new cell | Huawei,Hisilicon | Opt 2: Post WI close | R5-190743 R5-191426 R5-201113 R5-217076 R5-221433 R5-233445 |  |  | 1 | 100% | 100% | 100%
13 | Y | 38.523-1 | 6.1.2.5 | Cell reselection for interband operation using Pcompensation / Between FDD and TDD | **** TP1: [TS 38,304:5.2.3.1 , 5.2.4.1 , 5.2.4.2 , 5.2.4.6] WITH: UE in NR RRC_IDLE state on a FDD Band WHEN: UE detects the re-selection criteria using Pcompensation is met for the cell on a TDD band THEN: UE reselects to the new cell | Huawei,Hisilicon | Opt 2: Post WI close | R5-190744 R5-191427 R5-201114 R5-201499 R5-211377 R5-217076 R5-221433 R5-233445 |  |  | 1 | 100% | 100% | 100%
15 | Y | 38.523-1 | 6.1.2.7 | Cell reselection / Equivalent PLMN | **** TP1: [TS 23,122:4.4.3; TS 38,304:5.2.4.1] WITH: UE camped normally on a cell and network has downloaded a list of equivalent PLMNs during the Registration procedure WHEN: a suitable neighbour cell on an equivalent PLMN becomes better ranked than the suitable Serving cell THEN: UE reselects to this equivalent PLMN cell **** TP2: [TS 23,122:4.4.3; TS 38,304:5.2.4.1] WITH: UE camped normally on a cell and network has downloaded a list of equivalent PLMNs during the Registration procedure WHEN: the Serving cell becomes unsuitable due to S<0 and a suitable cell exists on an equivalent PLMN THEN: UE reselects to this equivalent PLMN cell **** TP3: [TS 23,122:4.4.3; TS 38,304:5.2.4.1] WITH: UE camped normally on a cell and network has downloaded a list of equivalent PLMNs during the Registration procedure WHEN: the UE evaluates cells for reselection THEN: UE ignores suitable cells for which the UE has no reselection priority provided | Qualcomm | Opt 2: Post WI close | R5-190750 R5-192285 R5-201793 R5-233445 |  |  | 1 | 100% | 100% | 100%
16 | Y | 38.523-1 | 6.1.2.8 | Cell reselection / Equivalent PLMN / Single Frequency operation | **** TP1: [TS 23,122:4.4.3; TS 38,304:5.2.4.1] WITH: UE camped normally on a cell and network has downloaded a list of equivalent PLMNs during the Registration procedure WHEN: a suitable neighbour cell on an equivalent PLMN becomes better ranked than the suitable Serving cell THEN: UE reselects to this equivalent PLMN cell **** TP2: [TS 23,122:4.4.3; TS 38,304:5.2.4.1] WITH: UE camped normally on a cell and network has downloaded a list of equivalent PLMNs during the Registration procedure WHEN: the Serving cell becomes unsuitable due to S<0 and a suitable cell exists on an equivalent PLMN THEN: UE reselects to this equivalent PLMN cell | Keysight | Opt 2: Post WI close | R5-192767 R5-196610 R5-201793 R5-211330 R5-233445 |  |  | 1 | 100% | 100% | 100%
19 | Y | 38.523-1 | 6.1.2.11 | Area Specific SIBs using systemInformationAreaID | **** TP1: [TS 38,331:5.2.2.1] WITH: UE is in NR RRC_IDLE state WHEN: SIB1 does not include si-RequestConfig and si-BroadcastStatus set to notBroadcasting THEN: UE sends RRCSystemInfoRequest message and acquires the necessary SIBs **** TP2: [TS 38,331:5.2.2.1] WITH: UE in NR_RRC Idle State WHEN: UE reselects to neighbor cell with same systemInformationAreaID and SIB1 does not include si-RequestConfig and si-BroadcastStatus set to notBroadcasting THEN: UE applies system information parameters of previous cell for reselection purposes | Huawei,Hisilicon | Opt 2: Post WI close | R5-198874 R5-201006 R5-202603 R5-203648 R5-225373 |  | FR2 Power level to be defined. | 1 | 95% | 100% | 90%
20 | Y | 38.523-1 | 6.1.2.12 | Cell reselection using cell status and cell reservations / cellReservedForOtherUse | **** TP1: [TS 38,304:R2-1813084] WITH: UE camped normally in state NR RRC_IDLE WHEN: A higher ranked cell is found with cell status "true" for other use THEN: UE does not attempt to reselect to the higher ranked cell | Huawei,Hisilicon | Opt 2: Post WI close | R5-194823 |  | FR2 Power level to be defined. | 1 | 95% | 100% | 90%
21 | Y | 38.523-1 | 6.1.2.13 | Cell reselection using cell status and cell reservations / Access Identity 0, 1, 2 and 12 to 14 – cellReservedForOperatorUse | **** TP1: [TS 38,304:5.3.1] WITH: UE camped normally in state NR RRC_IDLE and UE fitted with a USIM with at least one of the following Access Identities set: 0,1,2,12,13,14 WHEN: a higher ranked cell is found "reserved" for Operator use THEN: UE does not attempt to reselect to the higher ranked cell | Huawei,Hisilicon | Opt 2: Post WI close | R5-195244 R5-197020 R5-204416 R5-205366 |  | FR2 Power level to be defined. | 1 | 95% | 100% | 90%
22 | Y | 38.523-1 | 6.1.2.14 | Cell reselection using cell status and cell reservations / Access Identity 11 or 15 - cellReservedForOperatorUse | **** TP1: [TS 38,304:5.3.1] WITH: UE camped normally in state NR RRC_IDLE operating in their HPLMN/EHPLMN and fitted with a USIM with Access Identity 11 or 15 WHEN: a higher ranked cell is found "reserved" for Operator use THEN: UE re-selects to the higher ranked cell | Huawei,Hisilicon | Opt 2: Post WI close | R5-195245 R5-197839 R5-211173 |  | FR2 Power level to be defined. | 1 | 95% | 100% | 90%
22a | Y | 38.523-1 | 6.1.2.15a | Cell reselection in shared network environment / Cells broadcasting multiple PLMN IDs with unique TAC's, RAN areas, and cell identities |  | Qualcomm |  | R5-227413 |  | New TC defined in RAN5#97 | 1 | 100% | 100% | 100%
24 | Y | 38.523-1 | 6.1.2.16 | Inter-frequency cell reselection (equal priority) | **** TP1: [TS 38,304:5.2.4.6] WITH: UE in NR RRC_IDLE state WHEN: UE detects both intra-frequency and equal priority inter-frequency neigbour cells and the inter-frequency cell is the highest ranked cell THEN: UE reselects the inter-frequency cell | Keysight | Opt 2: Post WI close | R5-199028 |  | FR2 Power level to be defined. | 1 | 95% | 100% | 90%
26 | Y | 38.523-1 | 6.1.2.18 | Cell reselection, Sintrasearch, Snonintrasearch | **** TP1: [TS 38,304:5.2.4.1 , 5.2.4.5 , 5.2.4.6; TS <TS#2>:FFS; TS <TS#n>:FFS] WITH: UE in NR RRC_IDLE state, and the UE is not in high mobility state WHEN: Sintrasearch is non-zero in system information THEN: UE perform measurement and reselects the highest ranked cell upon Srxlev < Sintrasearch **** TP2: [TS 38,304:5.2.4.1 , 5.2.4.5 , 5.2.4.6; TS <TS#2>:FFS; TS <TS#n>:FFS] WITH: UE in NR RRC_IDLE state, and the UE is not in high mobility state WHEN: Snonintrasearch is non-zero in system information THEN: UE perform measurement and reselects the cell which belong to the equal priority frequency cell upon Srxlev < Snonintrasearch **** TP3: [TS 38,304:5.2.4.1 , 5.2.4.5 , 5.2.4.6; TS <TS#2>:FFS; TS <TS#n>:FFS] WITH: UE in E-UTRA RRC_IDLE state, and the UE is not in high mobility state WHEN: Snonintrasearch is non-zero in system information THEN: UE perform measurement and reselects the cell which belong to the high priority frequency cell upon Srxlev > Snonintrasearch | Qualcomm | Opt 2: Post WI close | R5-197203 R5-201115 R5-201340 R5-206312 R5-217076 R5-221431 |  | FR2 Power level to be defined. | 1 | 95% | 100% | 90%
27 | Y | 38.523-1 | 6.1.2.19 | Speed-dependent cell reselection | **** TP1: [TS 38,304:5.2.4.3] WITH: UE in NR RRC_IDLE state and in high mobility state WHEN: UE detects the cell ranked as the best cell taking into account scaling factor THEN: UE reselects to the new cell **** TP2: [TS 38,304:5.2.4.3] WITH: UE in NR RRC_IDLE state and in medium mobility state WHEN: UE detects the cell ranked as the best cell taking into account scaling factor THEN: UE reselects to the new cell | Qualcomm | Opt 2: Post WI close | R5-190672 R5-192282 R5-200622 R5-201341 R5-204405 R5-211377 |  | FR2 Power level to be defined. | 1 | 95% | 100% | 90%
29 | Y | 38.523-1 | 6.1.2.21 | Cell reselection, SIntra SearchQ and SnonIntraSearchQ | **** TP1: [TS 38,304:5.2.4.1 , 5.2.4.2 , 5.2.4.5, 5.2.4.6 ,5.2.4.7] WITH: UE in NR RRC_IDLE state, and the UE is not in high mobility state WHEN: UE receives non-zero SIntraSearchQ in system information THEN: UE perform measurement and reselects the highest ranked cell upon Squal < SIntraSearchQ **** TP2: [TS 38,304:5.2.4.1 , 5.2.4.2 , 5.2.4.5, 5.2.4.6 ,5.2.4.7] WITH: UE in NR RRC_IDLE state, and the UE is not in high mobility state WHEN: UE receives non-zero SnonIntraSearchQ in system information THEN: UE perform measurement and reselects the cell which belong to the equal priority frequency cell upon Squal < SnonIntraSearchQ **** TP3: [TS 38,304:5.2.4.1 , 5.2.4.2 , 5.2.4.5, 5.2.4.6 ,5.2.4.7] WITH: UE in E-UTRA RRC_IDLE state, and the UE is not in high mobility state WHEN: UE receives non-zero SnonIntraSearchQ in system information THEN: UE perform measurement and reselects the cell which belong to the high priority frequency cell upon Squal > SnonIntraSearchQ | Huawei,Hisilicon | Opt 2: Post WI close | R5-190747 R5-191430 R5-196218 R5-201112 R5-203372 R5-206313 R5-211377 R5-217076 R5-225372 |  | FR2 not applicable | 1 | 100% | 100%
30 | Y | 38.523-1 | 6.1.2.22 | Inter-frequency cell reselection based on common priority information with parameters ThreshX,HighQ, ThreshX,LowQ and ThreshServing,LowQ | **** TP1: [TS 38,304:5.2.4.5 and 5.2.4.7] WITH: UE in NR RRC_IDLE state WHEN: UE detects the cell re-selection criteria are met for the cell which belongs to the higher priority frequency THEN: UE reselects the cell which belongs to the higher priority frequency **** TP2: [TS 38,304:5.2.4.5 and 5.2.4.7] WITH: UE in NR RRC_IDLE state WHEN: UE detects the cell re-selection criteria are met for the cell which belongs to the lower priority frequency THEN: UE reselects the cell which belongs to the lower priority frequency | Huawei,Hisilicon | Opt 2: Post WI close | R5-190748 R5-191431 R5-197193 R5-201128 R5-211377 R5-217076 |  | FR2 Power level to be defined. | 1 | 95% | 100% | 90%
63 |  | 38.523-1 | 6.1.2.1 to 6.1.2.22 |  | Define FR2 power levels for test cases 6.1.2.1 to 6.1.2.22 | See above | Opt 2: Post WI close |  |  |  | 1.5 | 0% |  | 0%
Inter-RAT PLMN Selection (E-UTRAN , NG-RAN)
|  | 38.523-1 | 6.2.1 | Inter-RAT PLMN Selection
64 |  | 38.523-1 | 6.2.1.1 to 6.2.1.5 |  | Define FR2 power levels for test cases 6.2.1.1 to 6.1.1.5 | See above | Opt 2: Post WI close |  |  |  | 0 | 0% |  | 0%
Inter-RAT Cell Selection
37 | Y | 38.523-1 | 6.2.2.1 | Inter-RAT cell selection / From NR RRC_IDLE to EUTRA_Idle / Serving cell becomes non-suitable | **** TP1: [TS 38,304:5.2.1 , 5.2.3.1 , 5.2.3.2; TS 36,304:5.2.1,5.2.3.1 , 5.2.3.2; TS <TS#n>:FFS] WITH: UE in NR RRC_IDLE state WHEN: the serving cell becomes non-suitable and there is a suitable E-UTRA neighbour cell THEN: UE selects the suitable E-UTRA neighbour cell **** TP2: [TS 38,304:4.5 , 5.3.1; TS 36,304:5.2.1,5.2.3.1 , 5.2.3.2] WITH: UE in NR RRC_IDLE state WHEN: the serving cell becomes barred and there is a suitable E-UTRA neighbour cell THEN: UE selects the suitable E-UTRA neighbour cell | Huawei,Hisilicon | Opt 2: Post WI close | R5-201471 R5-204412 R5-204015 R5-221433 R5-225372 |  | FR2 not applicable | 1 | 100% | 100%
38 | Y | 38.523-1 | 6.2.2.2 | Inter-RAT cell selection / From E-UTRA_Idle to NR RRC_IDLE / Serving cell becomes non-suitable | **** TP1: [TS 38,304:5.2.1 , 5.2.3.1 , 5.2.3.2; TS 36,304:5.2.1,5.2.3.1 , 5.2.3.2] WITH: UE in E-UTRA RRC_IDLE state WHEN: the serving cell becomes non-suitable and there is a suitable NR neighbour cell THEN: UE selects the suitable NR neighbour cell **** TP2: [TS 38,304:4.5 , 5.3.1; TS 36,304:5.2.1,5.2.3.1 , 5.2.3.2] WITH: UE in E-UTRA RRC_IDLE state WHEN: the serving cell becomes barred and there is a suitable NR neighbour cell THEN: UE selects the suitable NR neighbour cell | Huawei,Hisilicon | Opt 2: Post WI close | R5-202602 R5-204413 R5-204018 R5-221433 R5-225372 |  | FR2 not applicable | 1 | 100% | 100%
65 |  | 38.523-1 | 6.2.2.1 to 6.2.2.2 |  | Define FR2 power levels for test cases 6.2.2.1 to 6.2.2.2 | See above | Opt 2: Post WI close |  |  |  | 0.2 | 0% |  | 0%
Inter-RAT Cell Reselection
|  | 38.523-1 | 6.2.3 | Inter-RAT Cell Reselection
39 | Y | 38.523-1 | 6.2.3.1 | Inter-RAT cell reselection / From E-UTRA_Idle to NR RRC_IDLE (lower priority & higher priority, Srxlev based) | **** TP1: [TS 36,304:5.2.4.1. , 5.2.4.2 and 5.2.4.5] WITH: UE in E-UTRA_Idle state WHEN: UE detects the cell re-selection criteria are met for the cell which belongs to the lower priority inter-RAT NR cell THEN: UE reselects the cell which belongs to the lower priority inter-RAT NR cell **** TP2: [TS 36,304:5.2.4.1. , 5.2.4.2 and 5.2.4.5] WITH: UE in E-UTRA_Idle state WHEN: UE detects the cell re-selection criteria are met for the cell which belongs to the higher priority inter-RAT NR cell THEN: UE reselects the cell which belongs to the higher priority inter-RAT NR cell | Huawei,Hisilicon | Opt 2: Post WI close | R5-197185 R5-201171 R5-201791 R5-204417 R5-221431 R5-221433 R5-225372 |  | FR2 not applicable | 1 | 100% | 100%
40 | Y | 38.523-1 | 6.2.3.2 | Inter-RAT cell reselection / From E-UTRA_Idle to NR RRC_IDLE (lower priority & higher priority, Squal based) | **** TP1: [TS 36,304:5.2.4.1 , 5.2.4.2 and 5.2.4.5] WITH: UE in E-UTRA RRC_IDLE state WHEN: UE detects the cell re-selection criteria are met for the cell which belongs to the lower priority inter-RAT NR cell THEN: UE reselects the cell which belongs to the lower priority inter-RAT NR cell **** TP2: [TS 36,304:5.2.4.1 , 5.2.4.2 and 5.2.4.5] WITH: UE in E-UTRA_Idle state WHEN: UE detects the cell re-selection criteria are met for the cell which belongs to the higher priority inter-RAT NR cell THEN: UE reselects the cell which belongs to the higher priority inter-RAT NR cell | Huawei,Hisilicon | Opt 2: Post WI close | R5-197186 R5-197840 R5-201129 R5-204417 R5-206265 R5-210631 R5-221433 R5-225372 |  | FR2 not applicable | 1 | 100% | 100%
41 | Y | 38.523-1 | 6.2.3.3 | Inter-RAT cell reselection / From NR RRC_IDLE to E-UTRA_IDLE (lower priority & higher priority, Srxlev based) | **** TP1: [TS 38,304:5.2.4.1 , 5.2.4.2 , 5.2.4.5] WITH: UE in NR RRC_IDLE state WHEN: UE detects the cell re-selection criteria are met for the neighbour cell which belongs to the higher priority E-UTRA frequency THEN: UE reselects to the E-UTRA cell **** TP2: [TS 38,304:5.2.4.1 , 5.2.4.2 , 5.2.4.5] WITH: UE in NR RRC_IDLE state WHEN: UE detects the cell re-selection criteria are met for the neighbour cell which belongs to the lower priority E-UTRA frequency THEN: UE reselects to the E-UTRA cell | Huawei,Hisilicon | Opt 2: Post WI close | R5-195243 R5-202595 R5-217188 R5-221431 R5-221433 R5-225372 |  | FR2 not applicable | 1 | 100% | 100%
42 | Y | 38.523-1 | 6.2.3.4 | Inter-RAT cell reselection / From NR RRC_Idle to E-UTRA_IDLE (lower priority & higher priority, Squal based) | **** TP1: [TS 38,304:5.2.4.1 , 5.2.4.2 , 5.2.4.5] WITH: UE in NR RRC_Idle state WHEN: UE detects the cell re-selection criteria are met for the cell which belongs to the lower priority inter-RAT E-UTRA cell THEN: UE reselects the cell which belongs to the lower priority inter-RAT E-UTRA cell **** TP2: [TS 38,304:5.2.4.1 , 5.2.4.2 , 5.2.4.5] WITH: UE in NR RRC_Idle state WHEN: UE detects the cell re-selection criteria are met for the cell which belongs to the higher priority inter-RAT E-UTRA cell THEN: UE reselects the cell which belongs to the higher priority inter-RAT E-UTRA cell | Huawei,Hisilicon | Opt 2: Post WI close | R5-197187 R5-197841 R5-201943 R5-204417 R5-210632 R5-213455 R5-217188 R5-221433 R5-225372 |  | FR2 not applicable | 1 | 100% | 100%
43 | Y | 38.523-1 | 6.2.3.5 | Inter-RAT cell reselection/From NR RRC_IDLE to E-UTRA_Idle according to RAT priority provided by dedicated signalling (RRCRelease) | **** TP1: [TS 38,304:5.2.4.1 , 5.2.4.5; TS 38,331:5.3.8.3 , 5.3.8.4] WITH: UE in NR RRC_IDLE state having received an RRCRelease message including cellReselectionPriorities WHEN: UE detects the cell re-selection criteria are met for the cell which belongs to the higher priority RAT THEN: UE reselects the cell which belongs to the higher priority RAT **** TP2: [TS 38,304:5.2.4.1 , 5.2.4.5; TS 38,331:5.3.8.3 , 5.3.8.4] WITH: UE in NR RRC_IDLE state having received an RRCRelease message including a cellReselectionPriorities WHEN: UE detects the cell re-selection criteria are met for the cell which belongs to the lower priority RAT THEN: UE reselects the cell which belongs to the lower priority RAT **** TP3: [TS 38,304:5.2.4.1 , 5.2.4.5; TS 38,331:5.3.8.3 , 5.3.8.4] WITH: UE in NR RRC_IDLE state having received an RRCRelease message including a cellReselectionPriorities WHEN: T320 expires THEN: UE reselects a cell by applying the cellReselectionPriority broadcast in the system information **** TP4: [TS 38,304:5.2.4.1 , 5.2.4.5; TS 38,331:5.3.8.3 , 5.3.8.4] WITH: UE in NR RRC_IDLE state and reselection priorities have been provided in dedicated signalling WHEN: T320 has not expired THEN: The UE shall ignore all the priorities provided in system information, and not perform cell reselection evaluation for NR frequencies and E-UTRA frequencies for which the UE doesn’t have a priority provided | Huawei,Hisilicon | Opt 2: Post WI close | R5-195247 R5-197842 R5-201130 R5-204417 R5-221433 R5-225372 |  | FR2 not applicable | 1 | 100% | 100%
44 | Y | 38.523-1 | 6.2.3.6 | Inter-RAT cell reselection / From E-UTRA_Idle to NR RRC_IDLE according to RAT priority provided by dedicated signalling (RRConnRelease) | **** TP1: [TS 36,304:5.2.4.1; TS 38,304:5.2.4.1] WITH: UE in E-UTRA RRC_Idle state having received RRCConnectionRelease including IdleModeMobilityControlInfo containing cellReselectionPriority for NR cell WHEN: UE detects the cell re-selection criteria are met for the cell which belongs to the lower priority inter-RAT NR cell based on the configured RAT priority provided by dedicated signaling THEN: UE reselects the cell which belongs to the lower priority inter-RAT NR cell **** TP2: [TS 36,304:5.2.4.1; TS 38,304:5.2.4.1] WITH: UE in NR RRC_IDLE state having inherit RAT priority provided by dedicated signaling with the remaining validity time WHEN: UE discard the inherit RAT priority upon connection establishment THEN: UE reselects a cell by applying the cellReselectionPriority broadcast in the system information | Huawei,Hisilicon | Opt 2: Post WI close | R5-197188 R5-197843 R5-201131 R5-221433 R5-225372 R5-231174 |  | FR2 not applicable | 1 | 100% | 100%
45 | Y | 38.523-1 | 6.2.3.7 | Inter-RAT cell reselection/From NR RRC_IDLE to E-UTRA RRC_IDLE, Snonintrasearch | **** TP1: [TS 38,304:5.2.4.1, 5.2.4.2, 5.2.4.5] WITH: UE in NR RRC_IDLE state, and the UE is not in high mobility state WHEN: Snonintrasearch is non-zero in system information THEN: UE perform measurement and reselects the cell which belong to the high priority E-UTRA cell even if Srxlev > Snonintrasearch | Huawei,Hisilicon | Opt 2: Post WI close | R5-195249 R5-198875 R5-221433 R5-225372 | Fr2 Power levels to be defined | FR2 not applicable | 1 | 100% | 100%
61 | Y | 38.523-1 | 6.2.3.8 | Inter-RAT cell reselection/From E-UTRA RRC_IDLE to NR RRC_Idle, Snonintrasearch | **** TP1: [TS 36,304:5.2.4.1 , 5.2.4.2 , 5.2.4.5] WITH: UE in E-UTRA RRC_IDLE state, and the UE is not in high mobility state WHEN: Snonintrasearch is non-zero in system information THEN: UE perform measurement and reselects to cell which belongs to the high priority NR cell even if Srxlev > Snonintrasearch | Huawei,Hisilicon | Opt 2: Post WI close | R5-197189 R5-201132 R5-221433 R5-225372 |  | FR2 not applicable | 1 | 100% | 100%
61a | Y | 38.523-1 | 6.2.3.10 | Inter-RAT cell reselection / From E-UTRA_Idle to NR RRC_IDLE / schedulingInfoList-v12j0 | **** TP1: [TS 36.331:5.2.3, 5.2.3a; TS 36.304:5.2.4.1, 5.2.4.2, 5.2.4.5] WITH: the UE is in E-UTRA IDLE state and SystemInformationBlockType24 scheduled by optional extended field schedulingInfoList-v12j0 in SystemInformationBlockType1 is broadcasted WHEN: UE detects the cell re-selection criteria is met for a lower priority NR cell THEN: UE reselects to the NR cell | Huawei,Hisilicon | Opt 2: Post WI close | R5-206315 R5-216164 R5-216166 R5-221433 |  | FR2 not applicable | 1 | 100% | 100%
61b | Y | 38.523-1 | 6.2.3.11 | Inter-RAT cell reselection / From E-UTRA_Idle to NR RRC_IDLE / schedulingInfoListExt-r12 | **** TP1: [TS 36.331:5.2.3, 5.2.3a; TS 36.304:5.2.4.1, 5.2.4.2, 5.2.4.5] WITH: the UE is in E-UTRA IDLE state and SystemInformationBlockType24 scheduled by optional extended field schedulingInfoListExt-r12 in SystemInformationBlockType1 is broadcasted WHEN: UE detects the cell re-selection criteria is met for a lower priority NR cell THEN: UE reselects to the NR cell | Huawei,Hisilicon | Opt 2: Post WI close | R5-206316 R5-216166 R5-221433 |  | FR2 not applicable | 1 | 100% | 100%
66 |  | 38.523-1 | 6.2.3.1 to 6.2.3.11 |  | Define FR2 power levels for test cases 6.2.3.1 to 6.2.3.9 | See above | Opt 2: Post WI close |  |  |  | 0.9 | 0% |  | 0%
Steering of Roaming
|  | 38.523-1 | 6.3.1 | Steering of Roaming
67 |  | 38.523-1 | 6.3.1.1 to 6.3.1.9 |  | Define FR2 power levels for test cases 6.3.1.1 to 6.3.1.9 | See above | Opt 2: Post WI close |  |  |  | 0 | 0% |  | 0%
RRC_INACTIVE
|  | 38.523-1 | 6.4 | UE Procedures in RRC_INACTIVE state
|  | 38.523-1 | 6.4.1 | NG-RAN Only PLMN Selection in RRC_INACTIVE state
56 | Y | 38.523-1 | 6.4.1.1 | PLMN Selection/Higher priority/HPLMN in Automatic PLMN Selection Mode | **** TP1: [TS 38,304:4.1 , 4.2; TS 23,122:4.4.3.3] WITH: UE in NR RRC_INACTIVE state on an NG-RAN VPLMN cell WHEN: UE performs PLMN Selection to a PLMN that is equivalent PLMN of the registered PLMN THEN: UE remains in RRC_INACTIVE state after moving to the Equivalent PLMN cell **** TP2: [TS 38,304:4.1 , 4.2; TS 23,122:4.4.3.3] WITH: UE in NR RRC_INACTIVE state on an NG-RAN VPLMN cell and cells of a higher priority NG-RAN PLMN available WHEN: Higher priority PLMN search timer T expires THEN: UE selects the higher priority PLMN cell , moves to RRC_IDLE and attempts Registration with mobility on the selected cell | Huawei,Hisilicon | Opt 2: Post WI close | R5-195649 R5-197838 R5-201349 R5-203382 R5-204415 R5-210062 R5-216995 R5-220543 R5-224571 R5-233462 |  |  | 1 | 100% | 100% | 100%
57 | Y | 38.523-1 | 6.4.1.2 | Cell reselection of ePLMN in manual mode | **** TP1: [TS 23,122:4.4.3.1.2; TS 38,304:4.1 , 4.2] WITH: UE in NR RRC_INACTIVE state on a NR cell in manual PLMN Selection mode and network has downloaded a list of equivalent PLMNs during the Registration procedure WHEN: Higher ranked cell is a cell of a PLMN in the downloaded equivalent PLMN list THEN: UE reselects to the equivalent PLMN cell and remains in NR RRC_INACTIVE state on the new cell **** TP2: [TS 23,122:4.4.3.1.2; TS 38,304:4.1 , 4.2] WITH: UE in NR RRC_INACTIVE state on a cell and network has downloaded a list of equivalent PLMNs during Registration procedure for mobility WHEN: Highest ranked cell is a cell of a PLMN not in the downloaded equivalent PLMN list THEN: UE does not reselect to the cell | Huawei,Hisilicon | Opt 2: Post WI close | R5-200339 R5-201477 R5-204379 R5-211331 R5-213163 R5-215699 R5-224572 R5-233462 |  |  | 1 | 100% | 100% | 100%
|  | 38.523-1 | 6.4.2 | NG-RAN Only Cell Selection in RRC_INACTIVE State
58 | Y | 38.523-1 | 6.4.2.1 | Cell Selection/Qrxlevmin & Cell Reselection (Intra NR in RRC_INACTIVE state) | **** TP1: [TS 38.300:9.2.1.1; TS 38,304:4.1 , 4.2 , 4.5 , 5.2.1, 5.2.3.1 , 5.2.3.2] WITH: UE in NR RRC_INACTIVE state WHEN: serving cell fulfils all requirements for a suitable cell except the cell selection criteria which are not fulfilled (Srxlev<0) THEN: UE does not consider the cell as suitable , leaves NR RRC_INACTIVE state and does not remain camped on that cell **** TP2: [TS 38.300:9.2.1.1; TS 38,304:4.1 , 4.2 , 4.5 , 5.2.1, 5.2.3.1 , 5.2.3.2] WITH: UE in NR RRC_INACTIVE state WHEN: UE detects a cell ranked as the best cell THEN: UE reselects to the new cell and continues to remain in NR RRC_INACTIVE state | Huawei,Hisilicon | Opt 2: Post WI close | R5-195252 R5-201133 R5-201790 R5-205600 R5-212084 R5-224573 R5-233462 |  |  | 1 | 100% | 100% | 100%
59 | Y | 38.523-1 | 6.4.2.2 | Inter-frequency cell reselection according to cell reselection priority provided by SIBs in RRC_INACTIVE state | **** TP1: [TS 38,304:4.1 , 4.2 , 5.2.4.1 , 5.2.4.2 , 5.2.4.5] WITH: UE in NR RRC_INACTIVE state WHEN: UE detects the cell re-selection criteria are met for the cell which belongs to the equal priority frequency THEN: UE reselects to the cell which belongs to the equal priority frequency and remains in NR RRC_INACTIVE state **** TP2: [TS 38,304:4.1 , 4.2 , 5.2.4.1 , 5.2.4.2 , 5.2.4.5] WITH: UE in NR RRC_INACTIVE state WHEN: UE detects the cell re-selection criteria are met for the cell which belongs to the higher priority frequency THEN: UE reselects to the cell which belongs to the higher priority frequency and remains in NR RRC_INACTIVE state **** TP3: [TS 38,304:4.1 , 4.2 , 5.2.4.1 , 5.2.4.2 , 5.2.4.5] WITH: UE in NR RRC_INACTIVE state WHEN: UE detects the cell re-selection criteria are met for the cell which belongs to the lower priority frequency THEN: UE reselects to the cell which belongs to the lower priority frequency and remains in NR RRC_INACTIVE state | Huawei,Hisilicon | Opt 2: Post WI close | R5-195650 R5-201500 R5-203502 R5-224574 R5-233462 |  |  | 1 | 100% | 100% | 100%
|  | 38.523-1 | 6.4.3 | Inter-RAT Cell Reselection
60 | Y | 38.523-1 | 6.4.3.1 | Inter-RAT cell reselection From NR RRC_INACTIVE to E-UTRA RRC_IDLE (lower priority & higher priority, Srxlev based) | **** TP1: [TS 38,304:4.1 , 4.2 , 5.2.4.1 , 5.2.4.2 , 5.2.4.5] WITH: UE in NR RRC_INACTIVE state WHEN: UE detects the cell re-selection criteria are met for the neighbour cell which belongs to the higher priority E-UTRA frequency THEN: UE reselects to the E-UTRA cell and transitions to E-UTRA RRC_IDLE State **** TP2: [TS 38,304:4.1 , 4.2 , 5.2.4.1 , 5.2.4.2 , 5.2.4.5] WITH: UE in NR RRC_INACTIVE state WHEN: UE detects the cell re-selection criteria are met for the neighbour cell which belongs to the lower priority E-UTRA frequency THEN: UE reselects to the E-UTRA cell and transitions to E-UTRA RRC_IDLE State | Huawei,Hisilicon | Opt 2: Post WI close | R5-197191 R5-200366 R5-203745 R5-204417 R5-210610 R5-211022 R5-212368 R5-221433 R5-225372 | Fr2 Power levels to be defined | FR2 not applicable | 1 | 100% | 100%
RRC | [5 empty] | Responsible: Yogesh Tugnawat, Qualcomm
RRC connection management procedures
102 | Y | 38.523-1 | 8.1.1.3.4 | RRC connection release / Success / With priority information / T320 expiry / E-UTRA | **** TP1: [TS 38,331:5.3.8.3 and 5.3.8.4; TS 38,304:5.2.4.1, 5.2.4.2, 5.2.4.5 and 5.2.4.6] WITH: UE in NR RRC_IDLE state having received an RRCRelease message with the freqPriorityListEUTRA with higher priority frequency WHEN: UE detects the cell re-selection criteria are met for the cell which belongs to the higher priority E-UTRA frequency THEN: UE reselects the cell which belongs to the higher priority E-UTRA frequency **** TP2: [TS 38,331:5.3.8.3 and 5.3.8.4; TS 38,304:5.2.4.1, 5.2.4.2, 5.2.4.5 and 5.2.4.6] WITH: UE in NR RRC_IDLE state having received an RRCRelease message with the freqPriorityListEUTRA with higher priority frequency and timer T320 WHEN: T320 timer expires THEN: UE discards the cell reselection priority information provided by the cellReselectionPriorities and apply the cell reselection priority information broadcast in the system information to perform reselection to an E-UTRA cell | Huawei, Hisilicon | Opt 2: Post WI close | R5-192298, R5-197052, R5-201137 R5-202623 R5-204434 R5-206332, R5-213464 R5-225372 | Since UE needs to perform cell reselection measurements, E-UTRA OTA calibration needed | FR2 not applicable | 1 | 100% | 100%
105 | Y | 38.523-1 | 8.1.1.3.7 | RRC connection release / Success / Deprioritisation / Frequency / T325 expiry | **** TP1: [TS 38,331:5.3.8.3; TS 38,304:5.2.4.1] WITH: UE in NR RRC_CONNECTED state WHEN: UE receives an RRCRelease message including IE deprioritisationReq with deprioritisationType indicating ‘frequency’ and a deprioritisationTimer THEN: UE considers the current frequency to be the lowest priority frequency (i.e. lower than any of the network configured values) while T325 is running | Qualcomm | Opt 2: Post WI close | R5-212791 R5-216174 R5-214767, R5-220545 | FR2 Power levels are FFS | FR2 Power level to be defined. | 1 | 95% | 100% | 90%
236 | Y | 38.523-1 | 8.1.1.3.7a | RRC connection release / Success / Deprioritisation / NR / T325 expiry | **** TP1: [TS 38,331:5.3.8.3; TS 38,304:5.2.4.1] WITH: UE in NR RRC_CONNECTED state WHEN: UE receives an RRCRelease message including IE deprioritisationReq with deprioritisationType indicating ‘nr’ and a deprioritisationTimer THEN: UE considers all frequencies of NR to be the lowest priority frequency (i.e. lower than any of the network configured values) while T325 is running | Qualcomm | Opt 2: Post WI close | R5-216176, R5-221436 | FR2 Power levels are FFS | FR2 Power level to be defined. | 1 | 95% | 100% | 90%
239 | Y | 38.523-1 | 8.1.1.3.7b | RRC connection release / Success / Deprioritisation / Deletion of Stored deprioritisation request | **** TP1: [TS 38,331:5.3.8.3; TS 38,304:5.2.4.1] WITH: UE in NR RRC_CONNECTED state and T325 is running WHEN: UE is requested to perform manual PLMN selection THEN: UE deletes the stored deprioritisation request(s) and proceeds with the PLMN selection | Qualcomm | Opt 2: Post WI close | R5-217810 | FR2 Power levels are FFS |  | 1 | 95% | 100% | 90%
196 |  | 38.523-1 | 8.1.1.3.3, 8.1.1.3.4 | See above | Define FR2 power levels for test cases 8.1.1.3.3, 8.1.1.3.4 | See above | Opt 2: Post WI close | See above |  |  | 0.2 | 0% |  | 0%
RRC reconfiguration
Measurement configuration control and reporting
83 | Y | 38.523-1 | 8.1.3.1.1 | Measurement configuration control and reporting / Intra NR measurements / Event A1 / Event A2 | **** TP1: [TS 38,331:5.3.5.3, 5.5.2, 5.5.4.1, 5.5.4.2, 5.5.4.3 and 5.5.6] WITH: UE in NR RRC_CONNECTED and measurement configured for event A1 and event A2 with event based periodical reporting WHEN: Serving cell becomes better than absolute threshold plus hysteresis and entering condition for event A1 is met THEN: UE sends MeasurementReport message at regular intervals while entering condition for event A1 is satisfied **** TP2: [TS 38,331:5.3.5.3, 5.5.2, 5.5.4.1, 5.5.4.2, 5.5.4.3 and 5.5.6] WITH: UE in NR RRC_CONNECTED and periodical measurement reporting triggered by event A1 ongoing WHEN: Serving cell becomes worse than absolute threshold minus hysteresis THEN: UE stops sending MeasurementReport message **** TP3: [TS 38,331:5.3.5.3, 5.5.2, 5.5.4.1, 5.5.4.2, 5.5.4.3 and 5.5.6] WITH: UE in NR RRC_CONNECTED and measurement configured for event A1 and event A2 with event based periodical reporting WHEN: Serving cell becomes worse than absolute threshold minus hysteresis and entering condition for event A2 is met THEN: UE sends MeasurementReport message at regular intervals while entering condition for event A2 is satisfied **** TP4: [TS 38,331:5.3.5.3, 5.5.2, 5.5.4.1, 5.5.4.2, 5.5.4.3 and 5.5.6] WITH: UE in NR RRC_CONNECTED and periodical measurement reporting triggered by event A2 ongoing WHEN: Serving cell becomes better than absolute threshold plus hysteresis THEN: UE stops sending MeasurementReport message **** TP5: [TS 38,331:5.3.5.3, 5.5.2, 5.5.4.1, 5.5.4.2, 5.5.4.3 and 5.5.6] WITH: UE in NR RRC_CONNECTED and measurements are re-configured for event A1 with event based reporting to report on leaving condition WHEN: Serving cell becomes worse than absolute threshold minus hysteresis THEN: UE sends MeasurementReport message when leaving condition for event A1 is satisfied | Huawei, Hisilicon | Opt 2: Post WI close | R5-188149, R5-191403, R5-201229, R5-202635 | eventA1 rsrp is FFS for FR2 | FR2 Power level to be defined. FFS in Table 8.1.3.1.1.3.3-4 and Table 8.1.3.1.1.3.3-10 needs to be addressed once FR2 Power levels are defined | 1 | 95% | 100% | 90%
115 | Y | 38.523-1 | 8.1.3.1.2 | Measurement configuration control and reporting / Event A3 / Measurement of Neighbor NR cell / Intra-frequency measurements | **** TP1: [TS 38,331:5.3.5.3, 5.5.2, 5.5.4.1, 5.5.4.4 and 5.5.5] WITH: UE in NR RRC_CONNECTED state and intra-frequency measurements configured for event A3 WHEN: Entry condition for event A3 is not met for neighbor cell THEN: UE does not send MeasurementReport **** TP2: [TS 38,331:5.3.5.3, 5.5.2, 5.5.4.1, 5.5.4.4 and 5.5.5] WITH: UE in NR RRC_CONNECTED state and intra-frequency measurements configured for event A3 WHEN: Neighbour cell becomes offset better than serving cell THEN: UE sends MeasurementReport with correct measId for event A3 | Rohde-Schwarz | Opt 2: Post WI close | R5-195277, R5-198754, R5-199038, R5-201214, R5-202635, R5-202183, R5-204437, R5-206334, R5-206335, R5-211389, R5-216799, R5-221439 | eventA3 rsrp is FFS for FR2 | FR2 Power level to be defined. FFS in Table 8.1.3.1.2.3.3-4 needs to be addressed once FR2 Power levels are defined | 1 | 95% | 100% | 90%
184 | Y | 38.523-1 | 8.1.3.1.3 | Measurement configuration control and reporting / Event A3 / Measurement of Neighbour NR cell / Inter-frequency measurements | **** TP1: [TS 38,331:5.3.5.3, 5.5.2, 5.5.4.1, 5.5.4.4 and 5.5.5] WITH: UE in NR RRC_CONNECTED state and inter-frequency measurements configured for event A3 using measurement gaps configured as gapUE WHEN: Entry condition for event A3 is not met for neighbor cell THEN: UE does not send MeasurementReport **** TP2: [TS 38,331:5.3.5.3, 5.5.2, 5.5.4.1, 5.5.4.4 and 5.5.5] WITH: UE in NR RRC_CONNECTED state and inter-frequency measurements configured for event A3 using measurement gaps configured as gapUE WHEN: Neighbour cell becomes offset better than serving cell THEN: UE sends MeasurementReport with correct measId for event A3 | Rohde-Schwarz | Opt 2: Post WI close | R5-195278, R5-202635, R5-206335, R5-206334, R5-216799, R5-221439 |  | FR2 Power level to be defined. | 1 | 95% | 100% | 90%
191 | Y | 38.523-1 | 8.1.3.1.4 | Measurement configuration control and reporting / Event A3 / Measurement of Neighbour NR cell / Inter-band measurements | **** TP1: [TS 38,331:5.3.5.3, 5.5.2, 5.5.4.1, 5.5.4.4 and 5.5.5] WITH: UE in NR RRC_CONNECTED state and inter-band measurements configured for event A3 using measurement gaps configured as gapUE WHEN: Entry condition for event A3 is not met for neighbor cell THEN: UE does not send MeasurementReport **** TP2: [TS 38,331:5.3.5.3, 5.5.2, 5.5.4.1, 5.5.4.4 and 5.5.5] WITH: UE in NR RRC_CONNECTED state and inter-band measurements configured for event A3 using measurement gaps configured as gapUE WHEN: Neighbour cell becomes offset better than serving cell THEN: UE sends MeasurementReport with correct measId for event A3 | Rohde-Schwarz | Opt 2: Post WI close | R5-195279, R5-202635, R5-206335, R5-206334, R5-216799, R5-221439 |  | FR2 Power level to be defined. | 1 | 95% | 100% | 90%
116 | Y | 38.523-1 | 8.1.3.1.5 | Measurement configuration control and reporting / Event A4 / Measurement of Neighbour NR cell / Intra-frequency measurements | **** TP1: [TS 38,331:5.3.5.3, 5.5.2.1, 5.5.2.9, 5.5.4.1, 5.5.4.5 and 5.5.5] WITH: UE in NR RRC_CONNECTED state and intra-frequency measurements configured for event A4 with event based periodical reporting WHEN: Neighbour cell becomes better than absolute threshold THEN: UE sends MeasurementReport message at regular intervals while entering condition for event A4 is satisfied **** TP2: [TS 38,331:5.3.5.3, 5.5.2.1, 5.5.2.9, 5.5.4.1, 5.5.4.5 and 5.5.5] WITH: UE in NR RRC_CONNECTED state and periodical measurement reporting triggered by event A4 ongoing WHEN: Neighbour cell becomes worse than absolute threshold THEN: UE stops sending MeasurementReport message | Huawei, Hisilicon | Opt 2: Post WI close | R5-192779, R5-198917, R5-201097, R5-202635, R5-203709, R5-204437, R5-211389, R5-221439 | eventA4 rsrp is FFS for Fr2 | FR2 Power level to be defined. FFS in Table 8.1.3.1.5.3.3-3 needs to be addressed once FR2 Power levels are defined | 1 | 95% | 100% | 90%
185 | Y | 38.523-1 | 8.1.3.1.6 | Measurement configuration control and reporting / Event A4 / Measurement of Neighbour NR cell / Inter-frequency measurements | **** TP1: [TS 38,331:5.3.5.3, 5.5.2.1, 5.5.2.9, 5.5.4.1, 5.5.4.5, 5.5.2 and 5.5.5] WITH: UE in NR RRC_CONNECTED state WHEN: UE receives RRCReconfiguration message containing MeasConfig to setup gapUE and event A4 with event based periodical reporting for neighbor cell THEN: UE successfully apllies MeasConfig and sends RRCReconfigurationComplete message **** TP2: [TS 38,331:5.3.5.3, 5.5.2.1, 5.5.2.9, 5.5.4.1, 5.5.4.5, 5.5.2 and 5.5.5] WITH: UE in NR RRC_CONNECTED state and inter-frequency measurements configured for event A4 with event based periodical reporting WHEN: Neighbour cell becomes better than absolute threshold THEN: UE sends MeasurementReport message at regular intervals while entering condition for event A4 is satisfied **** TP3: [TS 38,331:5.3.5.3, 5.5.2.1, 5.5.2.9, 5.5.4.1, 5.5.4.5, 5.5.2 and 5.5.5] WITH: UE in NR RRC_CONNECTED state and periodical measurement reporting triggered by event A4 ongoing WHEN: Neighbour cell becomes worse than absolute threshold THEN: UE stops sending MeasurementReport message | Huawei, Hisilicon | Opt 2: Post WI close | R5-195259, R5-202635, R5-221439 |  | FR2 Power level to be defined. | 1 | 95% | 100% | 90%
192 | Y | 38.523-1 | 8.1.3.1.7 | Measurement configuration control and reporting / Event A4 / Measurement of Neighbour NR cell / Inter-band measurements | **** TP1: [TS 38,331:5.3.5.3, 5.5.2.1, 5.5.2.9, 5.5.4.1, 5.5.4.5 and 5.5.5] WITH: UE in NR RRC_CONNECTED state and inter-band measurements configured for event A4 with event based periodical reporting WHEN: Neighbour cell becomes better than absolute threshold THEN: UE sends MeasurementReport message at regular intervals while entering condition for event A4 is satisfied **** TP2: [TS 38,331:5.3.5.3, 5.5.2.1, 5.5.2.9, 5.5.4.1, 5.5.4.5 and 5.5.5] WITH: UE in NR RRC_CONNECTED state and periodical measurement reporting triggered by event A4 ongoing WHEN: Neighbour cell becomes worse than absolute threshold THEN: UE stops sending MeasurementReport message | Huawei, Hisilicon | Opt 2: Post WI close | R5-195260, R5-202635, R5-221439 |  | FR2 Power level to be defined. | 1 | 95% | 100% | 90%
117 | Y | 38.523-1 | 8.1.3.1.8 | Measurement configuration control and reporting / Event A5 / Measurement of Neighbour NR cell / Intra-frequency measurements | **** TP1: [TS 38,331:5.3.5.3, 5.5.2.1, 5.5.2.9, 5.5.4.1, 5.5.4.6 and 5.5.5] WITH: UE in NR RRC_CONNECTED state and intra-frequency measurements configured for event A5 with event based periodical reporting WHEN: Serving cell becomes worse than absolute threshold1 and neighbour cell becomes better than absolute threshold2 THEN: UE sends MeasurementReport message at regular intervals while entering conditions for event A5 are satisfied **** TP2: [TS 38,331:5.3.5.3, 5.5.2.1, 5.5.2.9, 5.5.4.1, 5.5.4.6 and 5.5.5] WITH: UE in NR RRC_CONNECTED state and periodical measurement reporting triggered by event A5 ongoing WHEN: Serving cell becomes better than absolute threshold1 or neighbour cell becomes worse than absolute threshold2 THEN: UE stops sending MeasurementReport message | Huawei, Hisilicon | Opt 2: Post WI close | R5-192781, R5-197856, R5-201097, R5-202635, R5-203710, R5-204437, R5-211389, R5-221439 | eventA5 rsrp is FFS for FR2 | FR2 Power level to be defined. FFS in Table 8.1.3.1.8.3.3-3 needs to be addressed once FR2 Power levels are defined | 1 | 95% | 100% | 90%
186 | Y | 38.523-1 | 8.1.3.1.9 | Measurement configuration control and reporting / Event A5 / Measurement of Neighbour NR cell / Inter-frequency measurements | **** TP1: [TS 38,331:5.3.5.3, 5.5.2.1, 5.5.2.9, 5.5.4.1, 5.5.4.6 and 5.5.5] WITH: UE in NR RRC_CONNECTED state and inter-frequency measurements configured for event A5 with event based periodical reporting WHEN: Serving cell becomes worse than absolute threshold1 and neighbour cell becomes better than absolute threshold2 THEN: UE sends MeasurementReport message at regular intervals while entering conditions for event A5 are satisfied **** TP2: [TS 38,331:5.3.5.3, 5.5.2.1, 5.5.2.9, 5.5.4.1, 5.5.4.6 and 5.5.5] WITH: UE in NR RRC_CONNECTED state and periodical measurement reporting triggered by event A5 ongoing WHEN: Serving cell becomes better than absolute threshold1 or neighbour cell becomes worse than absolute threshold2 THEN: UE stops sending MeasurementReport message | Huawei, Hisilicon | Opt 2: Post WI close | R5-195261, R5-202635, R5-221439 |  | FR2 Power level to be defined. | 1 | 95% | 100% | 90%
193 | Y | 38.523-1 | 8.1.3.1.10 | Measurement configuration control and reporting / Event A5 / Measurement of Neighbour NR cell / Inter-band measurements | **** TP1: [TS 38,331:5.3.5.3, 5.5.2.1, 5.5.2.9, 5.5.4.1, 5.5.4.6 and 5.5.5] WITH: UE in NR RRC_CONNECTED state and inter-band measurements configured for event A5 with event based periodical reporting WHEN: Serving cell becomes worse than absolute threshold1 and neighbour cell becomes better than absolute threshold2 THEN: UE sends MeasurementReport message at regular intervals while entering conditions for event A5 are satisfied **** TP2: [TS 38,331:5.3.5.3, 5.5.2.1, 5.5.2.9, 5.5.4.1, 5.5.4.6 and 5.5.5] WITH: UE in NR RRC_CONNECTED state and periodical measurement reporting triggered by event A5 ongoing WHEN: Serving cell becomes better than absolute threshold1 or neighbour cell becomes worse than absolute threshold2 THEN: UE stops sending MeasurementReport message | Huawei, Hisilicon | Opt 2: Post WI close | R5-195262, R5-202635, R5-221439 |  | FR2 Power level to be defined. | 1 | 95% | 100% | 90%
118 | Y | 38.523-1 | 8.1.3.1.11 | Measurement configuration control and reporting / Intra NR measurements / Two simultaneous events A3 (intra and inter-frequency measurements) / RSRQ based measurements | **** TP1: [TS 38,331:5.3.5.3, 5.5.2, 5.5.4.1, 5.5.4.4 and 5.5.5] WITH: UE in NR RRC_CONNECTED state, measurements configured for two event A3 at the same time and triggerQuantity set to rsrq WHEN: Entry condition for event A3 is not met THEN: UE does not send MeasurementReport **** TP2: [TS 38,331:5.3.5.3, 5.5.2, 5.5.4.1, 5.5.4.4 and 5.5.5] WITH: UE in NR RRC_CONNECTED state, measurements configured for two event A3 at the same time and triggerQuantity set to rsrq WHEN: Neighbour becomes offset better than serving THEN: UE sends MeasurementReport with correct measId for event A3 | Huawei, Hisilicon | Opt 2: Post WI close | R5-191447, R5-197058, R5-195949, R5-197064, R5-201097, R5-202630, R5-202635, R5-204443, R5-205373, R5-205718, R5-216179, R5-216637 R5-225383 |  | FR2 not applicable | 1 | 100% | 100%
119 | Y | 38.523-1 | 8.1.3.1.12 | Measurement configuration control and reporting / Intra NR measurements / Two simultaneous events A5 (intra and inter-frequency measurements) / SINR based measurements | **** TP1: [TS 38,331:5.3.5.3, 5.5.2, 5.5.4.1, 5.5.4.6 and 5.5.5] WITH: UE in NR RRC_CONNECTED state, measurements configured for two event A5 at the same time and triggerQuantity set to sinr WHEN: Entry condition for event A5 is not met THEN: UE does not send MeasurementReport **** TP2: [TS 38,331:5.3.5.3, 5.5.2, 5.5.4.1, 5.5.4.6 and 5.5.5] WITH: UE in NR RRC_CONNECTED state, measurements configured for two event A5 at the same time and triggerQuantity set to sinr WHEN: Neighbour becomes offset better than serving THEN: UE sends MeasurementReport with correct measId for event A5 | Huawei, Hisilicon | Opt 2: Post WI close | R5-191448, R5-197059, R5-195949, R5-197064, R5-202635, R5-204444, R5-204341,R5-205718, R5-216179, R5-216637 R5-225383 |  | FR2 not applicable | 1 | 100% | 100%
200 | Y | 38.523-1 | 8.1.3.1.15A | Measurement configuration control and reporting / Intra NR measurements / Blacklisting | **** TP1: [TS 38,331:5.3.5.3, 5.5.2.5,5.5.4.1 and 5.5.5] WITH: UE in NR RRC_CONNECTED state and measurement configured for event A3 reporting WHEN: Blacklisted neighbour cell satisfies entry condition for event A3 THEN: It is not considered in event evaluation and UE does not send MeasurementReport message **** TP2: [TS 38,331:5.3.5.3, 5.5.2.5,5.5.4.1 and 5.5.5] WITH: UE in NR RRC_CONNECTED state and measurement reporting triggered by event A3 is ongoing and no neighbour cells are blacklisted WHEN: Neighbour cells satisfies entry condition for event A3 THEN: Neighbour cells are considered in measurement reporting | Rohde-Schwarz | Opt 2: Post WI close | R5-195280, R5-195949, R5-196779, R5-201097, R5-202635, R5-202636, R5-202637, R5-203394, R5-203539, R5-210643, R5-216637 |  | FR2 Power level to be defined. | 1 | 95% | 100% | 90%
123 | Y | 38.523-1 | 8.1.3.1.16 | Measurement configuration control and reporting / Intra NR measurements / Whitelisting | **** TP1: [TS 38,331:5.3.5.3, 5.5.2.5,5.5.4.1 and 5.5.5] WITH: UE in NR RRC_CONNECTED state and measurement configured for event A3 reporting WHEN: Neighbour cell not listed as a white cell satisfies entry condition for event A3 THEN: It is not considered in event evaluation and UE does not send MeasurementReport message **** TP2: [TS 38,331:5.3.5.3, 5.5.2.5,5.5.4.1 and 5.5.5] WITH: UE in NR RRC_CONNECTED state and measurement reporting triggered by event A3 is ongoing and all of the neighbour cells are whitelisted WHEN: Neighbour cells satisfies entry condition for event A3 THEN: Neighbour cells are considered in measurement reporting | Huawei, Hisilicon | Opt 2: Post WI close | R5-197209, R5-200150, R5-201097, R5-202631, R5-202635, R5-203657, R5-203728, R5-204437, R5-211389 | eventA3 rsrp is FFS for FR2 | FR2 Power level to be defined. FFS in Table 8.1.3.1.16.3.3-5 needs to be addressed once FR2 Power levels are defined | 1 | 95% | 100% | 90%
124 | Y | 38.523-1 | 8.1.3.1.17.1 | NR CA / Measurement configuration control and reporting / Intra NR measurements / Event A6 / Intra-band Contiguous CA | **** TP1: [TS 38,331:5.3.5.3, 5.3.5.5.9, 5.5.2.1, 5.5.4.1, 5.5.4.7 and 5.5.5] WITH: UE in NR RRC_CONNECTED state and measurements configured for event A6 WHEN: Entry condition for event A6 is not met THEN: UE does not send MeasurementReport **** TP2: [TS 38,331:5.3.5.3, 5.3.5.5.9, 5.5.2.1, 5.5.4.1, 5.5.4.7 and 5.5.5] WITH: UE in NR RRC_CONNECTED state and measurements configured for event A6 WHEN: Intra-frequency neighbour becomes offset better than Scell THEN: UE sends MeasurementReport with correct measId for event A6 **** TP3: [TS 38,331:5.3.5.3, 5.3.5.5.9, 5.5.2.1, 5.5.4.1, 5.5.4.7 and 5.5.5] WITH: UE in NR RRC_CONNECTED state and measurements configured for event A6 WHEN: UE receives a RRCReconfiguration message containing sCellToReleaseList with a sCellIndex equal to one of the current UE SCell configuration THEN: UE stops sending MeasurementReport message | Huawei, Hisilicon | Opt 2: Post WI close | R5-192782, R5-195271, R5-198914, R5-200341, R5-201097, R5-202635, R5-203811, R5-204437, R5-211389, R5-221439 |  | FR2 Power level to be defined. | 1 | 95% | 100% | 90%
125 | Y | 38.523-1 | 8.1.3.1.17.2 | NR CA / Measurement configuration control and reporting / Intra NR measurements / Event A6 / Inter-band CA | Editor's note: Same as TC 8.1.3.11.1 but applied to Inter-band CA. **** TP1: [TS 38,331:] WITH: WHEN: THEN: | Huawei, Hisilicon | Opt 2: Post WI close | R5-192783, R5-195272, R5-201097, R5-202635, R5-203811, R5-204437, R5-211389, R5-221439 |  | FR2 Power level to be defined. | 1 | 93.33% | 100% | 90% | 90%
126 | Y | 38.523-1 | 8.1.3.1.17.3 | NR CA / Measurement configuration control and reporting / Intra NR measurements / Event A6 / Intra-band non Contiguous CA | Editor's note: Same as TC 8.1.3.11.1 but applied to Intra-band non-Contiguous CA. **** TP1: [TS 38,331:] WITH: WHEN: THEN: | Huawei, Hisilicon | Opt 2: Post WI close | R5-192784, R5-195273, R5-197060, R5-201097, R5-202635, R5-203811, R5-204437, R5-211389, R5-221439 |  | FR2 Power level to be defined. | 1 | 85% | 100% | 70%
127 | Y | 38.523-1 | 8.1.3.1.18.1 | NR CA / Measurement configuration control and reporting / Intra NR measurements / Additional measurement reporting / Intra-band Contiguous CA | **** TP1: [TS 38,331:5.3.5.3, 5.3.5.5.9, 5.5.2.1, 5.5.4.1, 5.5.4.7 and 5.5.5.1] WITH: UE in NR RRC_CONNECTED state and measurements configured for event A2 reporting include reportAddNeighMeas WHEN: Entry condition for event A2 of the concerned frequency that triggered measurement reporting is met THEN: UE sends MeasurementReport that does not include the best non-serving cell of the concerned frequency in the measResultBestNeighCell **** TP2: [TS 38,331:5.3.5.3, 5.3.5.5.9, 5.5.2.1, 5.5.4.1, 5.5.4.7 and 5.5.5.1] WITH: UE in NR RRC_CONNECTED state and measurements configured for event A2 reporting include reportAddNeighMeas WHEN: Entry condition for event A2 of other than the concerned frequency that triggered measurement reporting is met THEN: UE sends MeasurementReport that includes the best non-serving cell of the concerned frequency in the measResultBestNeighCell | Huawei, Hisilicon | Opt 2: Post WI close | R5-192785, R5-195274, R5-197744, R5-198918, R5-201097, R5-202635, R5-202530, R5-203503, R5-203811, R5-204437, R5-211389, R5-212089, R5-213473, R5-214614 R5-216637, R5-221439 | eventA2 rsrp is FFS for FR2 | FR2 Power level to be defined. FFS in System Simulator and Table 8.1.3.1.18.1.3.3-6 needs to be addressed once FR2 Power levels are defined | 1 | 90% | 100% | 80%
128 | Y | 38.523-1 | 8.1.3.1.18.2 | NR CA / Measurement configuration control and reporting / Intra NR measurements / Additional measurement reporting / Inter-band CA | Editor's note: Same as TC 8.1.3.12.1 but applied to Inter-band CA. **** TP1: [TS 38,331:] WITH: WHEN: THEN: | Huawei, Hisilicon | Opt 2: Post WI close | R5-192786, R5-195275, R5-201097, R5-202530, R5-202635, R5-203503, R5-203811, R5-204437, R5-211389, R5-212089, R5-213473, R5-214614, R5-216637, R5-221439 |  | FR2 Power level to be defined. | 1 | 93.33% | 100% | 90% | 90%
129 | Y | 38.523-1 | 8.1.3.1.18.3 | NR CA / Measurement configuration control and reporting / Intra NR measurements / Additional measurement reporting / Intra-band non Contiguous CA | Editor's note: Same as TC 8.1.3.12.1 but applied to Intra-band non-Contiguous CA. **** TP1: [TS 38,331:] WITH: WHEN: THEN: | Huawei, Hisilicon | Opt 2: Post WI close | R5-192787, R5-195276, R5-197061, R5-201097, R5-202530, R5-202635, R5-203503, R5-203811, R5-204437, R5-211389, R5-212089, R5-213473, R5-214614, R5-216637, R5-221439 |  | FR2 Power level to be defined. | 1 | 85% | 100% | 70%
134 | Y | 38.523-1 | 8.1.3.1.23 | Measurement configuration control and reporting / Intra NR measurements / Periodic reporting / Continuation of the measurements after RRC Resume | **** TP1: [TS 38,331:5.3.13.4, 5.5.2, 5.5.4.1] WITH: UE in NR RRC_CONNECTED state WHEN: UE receives RRCReconfiguration including measConfig to setup periodical measurement reporting THEN: UE sends RRCReconfigurationComplete and starts sending periodic measurement reports **** TP2: [TS 38,331:5.3.13.4, 5.5.2, 5.5.4.1] WITH: UE in NR RRC_INACTIVE state and measurement configured for periodical reporting WHEN: UE receives RRCResume message without including the measconfig THEN: UE resumes RRC connection and performs periodic measurements as per the measurement configuration **** TP3: [TS 38,331:5.3.13.4, 5.5.2, 5.5.4.1] WITH: UE in NR RRC_INACTIVE state and measurement configured for periodical reporting WHEN: UE receives RRCResume message including the measconfig THEN: UE resumes RRC connection and performs periodic measurements as per the received measconfig in RRCResume message | Tech Mahindra | Opt 2: Post WI close | R5-197214, R5-200803, R5-201356, R5-202635, R5-204441, R5-215149 |  | FR2 Power level to be defined. | 1 | 95% | 100% | 90%
84 | Y | 38.523-1 | 8.1.3.2.1 | Measurement configuration control and reporting / Inter-RAT measurements / Event B1 / Measurement of E-UTRA cells | **** TP1: [TS 38,331:5.3.5.3, 5.5.2, 5.5.4.1, 5.5.4.8 and 5.5.5] WITH: UE is NR RRC_CONNECTED state and inter-RAT measurement event B1 to measure neighbor E-UTRA cell is configured WHEN: Entering condition for the event B1 is not met THEN: UE does not transmit any MeasurementReport **** TP2: [TS 38,331:5.3.5.3, 5.5.2, 5.5.4.1, 5.5.4.8 and 5.5.5] WITH: UE is NR RRC_CONNECTED state and inter-RAT measurement event B1 to measure neighbor E-UTRA cell is configured WHEN: Entering condition for the event B1 is met THEN: UE transmits a MeasurementReport | Huawei, Hisilicon | Opt 2: Post WI close | R5-192776, R5-195345, R5-198920, R5-201213, R5-202635, R5-204437, R5-205374, R5-211389, R5-221439 R5-225383 |  | FR2 not applicable | 1 | 100% | 100%
135 | Y | 38.523-1 | 8.1.3.2.2 | Measurement configuration control and reporting / Inter-RAT measurements / Event B2 / Measurement of E-UTRA cells | **** TP1: [TS 38,331:5.3.5.3, 5.5.2, 5.5.4.1, 5.5.4.9 and 5.5.5] WITH: UE is NR RRC_CONNECTED state and inter-RAT measurement event B2 to measure neighbor E-UTRA cell is configured WHEN: Entering condition 1 for event B2 is not met but Entering condition 2 is met THEN: UE does not transmit any MeasurementReport **** TP2: [TS 38,331:5.3.5.3, 5.5.2, 5.5.4.1, 5.5.4.9 and 5.5.5] WITH: UE is NR RRC_CONNECTED state and inter-RAT measurement event B2 to measure neighbor E-UTRA cell is configured WHEN: Entering condition 1 and 2 for event B2 is met THEN: UE transmits a MeasurementReport | Huawei, Hisilicon | Opt 2: Post WI close | R5-192777, R5-195346, R5-198920, R5-201118, R5-201097, R5-202635, R5-204382, R5-204437, R5-205374, R5-211389, R5-210644, R5-221439 R5-225383 |  | FR2 not applicable | 1 | 100% | 100%
136 | Y | 38.523-1 | 8.1.3.2.3 | Measurement configuration control and reporting / Inter-RAT measurements / Event B2 / Measurement of E-UTRA cells / RSRQ based measurements | **** TP1: [TS 38,331:5.3.5.3, 5.5.2, 5.5.4.1, 5.5.4.9 and 5.5.5] WITH: UE is NR RRC_CONNECTED state and inter-RAT measurement event B2 to measure neighbor E-UTRA cell is configured and triggerQuantity set to rsrq WHEN: Entering condition 1 and 2 for event B2 is not met THEN: UE does not transmit any MeasurementReport **** TP2: [TS 38,331:5.3.5.3, 5.5.2, 5.5.4.1, 5.5.4.9 and 5.5.5] WITH: UE is NR RRC_CONNECTED state and inter-RAT measurement event B2 to measure neighbor E-UTRA cell is configured and triggerQuantity set to rsrq WHEN: Entering condition 1 and 2 for event B2 is met THEN: UE transmits a MeasurementReport | Huawei, Hisilicon | Opt 2: Post WI close | R5-191415, R5-195347, R5-195949, R5-197064, R5-201097, R5-202632, R5-202635, R5-203504, R5-204437, R5-211389, R5-221439 R5-225383 |  | FR2 not applicable | 1 | 100% | 100%
137 | Y | 38.523-1 | 8.1.3.2.4 | Measurement configuration control and reporting / Inter-RAT measurements / Event B2 / Measurement of E-UTRA cells / SINR based measurements | **** TP1: [TS 38,331:5.3.5.3, 5.5.2, 5.5.4.1, 5.5.4.9 and 5.5.5] WITH: UE is NR RRC_CONNECTED state and inter-RAT measurement event B2 to measure neighbor E-UTRA cell is configured and triggerQuantity set to sinr WHEN: Entering condition 1 and 2 for event B2 is not met THEN: UE does not transmit any MeasurementReport **** TP2: [TS 38,331:5.3.5.3, 5.5.2, 5.5.4.1, 5.5.4.9 and 5.5.5] WITH: UE is NR RRC_CONNECTED state and inter-RAT measurement event B2 to measure neighbor E-UTRA cell is configured and triggerQuantity set to sinr WHEN: Entering condition 1 and 2 for event B2 is met THEN: UE transmits a MeasurementReport | Huawei, Hisilicon | Opt 2: Post WI close | R5-197213, R5-198921, R5-202635, R5-202638, R5-203504, R5-221439 R5-225383 |  | FR2 not applicable | 1 | 100% | 100%
85 | Y | 38.523-1 | 8.1.3.3.1 | Measurement configuration control and reporting / CGI reporting of NR cell | **** TP1: [TS 38,331:5.3.5.3, 5.5.2.3, 5.5.3.1, 5.5.4.1, 5.5.4.4 and 5.5.5.1] WITH: UE in NR RRC_CONNECTED state WHEN: Neighbour NR cell becomes offset better than serving THEN: UE sends MeasurementReport for event A3 **** TP2: [TS 38,331:5.3.5.3, 5.5.2.3, 5.5.3.1, 5.5.4.1, 5.5.4.4 and 5.5.5.1] WITH: UE in NR RRC_CONNECTED state WHEN: UE is commanded to report the global cell identity of the neighbour NR cell THEN: UE determines the global cell identity of the cell included in the associated measurement object by acquiring the relevant system information from the concerned cell and reports the global cell identity in the MeasurementReport | Huawei, Hisilicon | Opt 2: Post WI close | R5-198915, R5-201138, R5-201097, R5-202633, R5-202635, R5-212091 |  | FR2 Power level to be defined. | 1 | 95% | 100% | 90%
140 | Y | 38.523-1 | 8.1.3.3.2 | Measurement configuration control and reporting / CGI reporting of E-UTRA cell | **** TP1: [TS 38,331:5.3.5.3, 5.5.2.3, 5.5.3.1, 5.5.4.1, 5.5.4.9 and 5.5.5.1] WITH: UE in NR RRC_CONNECTED state WHEN: UE detects that entering condition 1 and 2 for event B2 is met THEN: UE transmits a MeasurementReport for event B2 **** TP2: [TS 38,331:5.3.5.3, 5.5.2.3, 5.5.3.1, 5.5.4.1, 5.5.4.9 and 5.5.5.1] WITH: UE in NR RRC_CONNECTED state WHEN: UE is commanded to report the global cell identity of the neighbour E-UTRA cell THEN: UE determines the global cell identity of the cell included in the associated measurement object by acquiring the relevant system information from the concerned cell and reports the global cell identity in the MeasurementReport | Huawei, Hisilicon | Opt 2: Post WI close | R5-198916, R5-201139, R5-201097, R5-202634, R5-202635, R5-204437, R5-211389, R5-212091, R5-221439 R5-225383 |  | FR2 not applicable | 1 | 100% | 100%
197 |  | 38.523-1 | 8.1.3.1.1 to 8.1.3.3.2 | See above | Define FR2 power levels for test cases 8.1.3.1.1 to 8.1.3.3.2 | See above | Opt 2: Post WI close | See above |  |  | 2.7 | 0% |  | 0%
Handover
187 | Y | 38.523-1 | 8.1.4.1.2 | Intra NR handover / Success / Inter-frequency | **** TP1: [TS 38,331:5.2.2.4.2, 5.3.5.5.2, 5.3.5.3 and 5.3.5.7] WITH: UE in NR RRC_CONNECTED state and having performed the inter-frequency measurements for the neighbour cell WHEN: UE receives an RRCReconfiguration message including a reconfigurationWithSync with rach-ConfigDedicated THEN: UE performs handover to the target cell and transmits an RRCReconfigurationComplete message **** TP2: [TS 38,331:5.2.2.4.2, 5.3.5.5.2, 5.3.5.3 and 5.3.5.7] WITH: UE in NR RRC_CONNECTED state and having performed the inter-frequency measurements for the neighbour cell WHEN: UE receives an RRCReconfiguration message including a reconfigurationWithSync without rach-ConfigDedicated THEN: UE performs handover to the target cell and transmits an RRCReconfigurationComplete message **** TP3: [TS 38,331:5.2.2.4.2, 5.3.5.5.2, 5.3.5.3 and 5.3.5.7] WITH: UE in NR RRC_CONNECTED state WHEN: UE receives an RRCReconfiguration message including dedicatedSIB1-Delivery containing SIB1 information with a change of trackingAreaCode THEN: UE reads the updated SIB1 information and sends an RRCReconfigurationComplete message followed by registration on the new tracking area **** TP4: [TS 38,331:5.2.2.4.2, 5.3.5.5.2, 5.3.5.3 and 5.3.5.7] WITH: UE in NR RRC_CONNECTED state WHEN: UE receives an RRCReconfiguration message including a reconfigurationWithSync and keySetChangeIndicator set to 'true' in MasterKeyUpdate for handover to the target cell THEN: UE performs handover to the target cell with security key update and transmits an RRCReconfigurationComplete message | Tech Mahindra | Opt 2: Post WI close | R5-195291, R5-197256, R5-202641, R5-204450, R5-204237, R5-205244, R5-211389, R5-221440 | eventA3 rsrp is FFS for FR2 | FR2 Power level to be defined. FFS in Table 8.1.4.1.2.3.3-3 needs to be addressed once FR2 Power levels are defined | 1 | 95% | 100% | 90%
159 | Y | 38.523-1 | 8.1.4.1.5 | Intra NR handover / Failure / Re-establishment successful | **** TP1: [TS 38,331:5.3.5.5.2, 5.3.5.7, 5.3.5.8.3, 5.3.7.5] WITH: UE in NR RRC_CONNECTED state and having received an RRCReconfiguration message including a reconfigurationWithSync for handover to the target cell WHEN: UE detects handover failure and the initial cell is selectable THEN: UE performs an RRCReestablishment procedure on the source cell **** TP2: [TS 38,331:5.3.5.5.2, 5.3.5.7, 5.3.5.8.3, 5.3.7.5] WITH: UE detects handover failure and having transmitted an RRCReestablishmentRequest message WHEN: UE receives an RRCReestablishment message with a nextHopChainingCount which is different from the NCC associated with the currently active KgNB THEN: UE derives new KgNB from the nextHopChainingCount and completes RRCReestablishment procedure on the source cell **** TP3: [TS 38,331:5.3.5.5.2, 5.3.5.7, 5.3.5.8.3, 5.3.7.5] WITH: UE detects handover failure and having transmitted an RRCReestablishmentRequest message WHEN: UE receives an RRCReestablishment message with a nextHopChainingCount which is same as the NCC associated with the currently active KgNB THEN: UE derives new KgNB from the currently active KgNB and completes RRCReestablishment procedure on the source cell | Qualcomm | Opt 2: Post WI close | R5-195288, R5-198924, R5-206336, R5-211332 R5-215356 |  | FR2 Power level to be defined. | 1 | 95% | 100% | 90%
160 | Y | 38.523-1 | 8.1.4.1.6 | Intra NR handover / Failure / Re-establishment failure | **** TP1: [TS 38,331:5.3.5.5.2, 5.3.5.8.3, 5.3.7.5] WITH: UE in NR RRC_CONNECTED state and having received an RRCReconfiguration message including a reconfigurationWithSync for handover to the target cell WHEN: UE detects handover failure and fails an RRCReestablishment procedure THEN: UE enters NR RRC_IDLE state | Qualcomm | Opt 2: Post WI close | R5-195289, R5-200185, R5-204359 |  | FR2 Power level to be defined. | 1 | 95% | 100% | 90%
161 | Y | 38.523-1 | 8.1.4.1.7.1 | NR CA / Intra NR handover / Success / PCell Change and SCell addition / SCell release / Intra-band Contiguous CA | **** TP1: [TS 38,331:5.3.5.5.2, 5.3.5.5.9, 5.3.5.5.8] WITH: UE in NR RRC_CONNECTED state and configured an SCell WHEN: UE receives an RRCReconfiguration message including a reconfigurationWithSync for handover to one of the SCell and sCellToAddModList for an SCell addition THEN: UE transmits an RRCReconfigurationComplete message **** TP2: [TS 38,331:5.3.5.5.2, 5.3.5.5.9, 5.3.5.5.8] WITH: UE in NR RRC_CONNECTED state WHEN: UE receives an RRCReconfiguration message including a reconfigurationWithSync for PCell change and including sCellToReleaseList with an sCellIndex set to the configured Scell THEN: UE sends an RRCReconfigurationComplete message | Huawei, Hisilicon | Opt 2: Post WI close | R5-197215, R5-201140, R5-204446, R5-203665, R5-210131, R5-217771, R5-220188, R5-221441, R5-221442 |  | FR2 Power level to be defined. | 1 | 95% | 100% | 90%
162 | Y | 38.523-1 | 8.1.4.1.7.2 | NR CA / Intra NR handover / Success / PCell Change and SCell addition / SCell release / Inter-band CA | Editor's note: Same as TC 8.1.4.1.6.1 but applied to Inter-band CA. **** TP1: [TS 38,331:] WITH: WHEN: THEN: | Huawei, Hisilicon | Opt 2: Post WI close | R5-195663, R5-204446, R5-203665, R5-210131, R5-217771, R5-220188, R5-221441, R5-221442 |  | FR2 Power level to be defined. | 1 | 93.33% | 100% | 90% | 90%
163 | Y | 38.523-1 | 8.1.4.1.7.3 | NR CA / Intra NR handover / Success / PCell Change and SCell addition / SCell release/ Intra-band non-contiguous CA | Editor's note: Same as TC 8.1.4.1.6.1 but applied to Intra-band non-Contiguous CA. **** TP1: [TS 38,331:] WITH: WHEN: THEN: | Huawei, Hisilicon | Opt 2: Post WI close | R5-195664, R5-204446, R5-203665, R5-210131, R5-217771, R5-220188, R5-221441, R5-221442 |  | FR2 Power level to be defined. | 1 | 90% | 100% | 80%
164 | Y | 38.523-1 | 8.1.4.1.8.1 | NR CA / Intra NR handover / Success / PCell Change / SCell no Change / Intra-band Contiguous CA | **** TP1: [TS 38,331:5.3.5.5.2, 5.3.5.5.9] WITH: UE in NR RRC_CONNECTED state and configured an SCell WHEN: UE receives an RRCReconfiguration message including a reconfigurationWithSync for PCell change and sCellToAddModList with an SCell same from configured Scell THEN: UE transmits an RRCReconfigurationComplete message | Huawei, Hisilicon | Opt 2: Post WI close | R5-197216, R5-200187, R5-204016, R5-203665, R5-214615, R5-217771, R5-220188, R5-221441 |  | FR2 Power level to be defined. | 1 | 95% | 100% | 90%
165 | Y | 38.523-1 | 8.1.4.1.8.2 | NR CA / Intra NR handover / Success / PCell Change / SCell no Change / Inter-band CA | Editor's note: Same as TC 8.1.4.1.7.1 but applied to Inter-band CA. **** TP1: [TS 38,331:] WITH: WHEN: THEN: | Huawei, Hisilicon | Opt 2: Post WI close | R5-195666, R5-204016, R5-203665, R5-214615, R5-217771, R5-220188, R5-221441 |  | FR2 Power level to be defined. | 1 | 93.33% | 100% | 90% | 90%
166 | Y | 38.523-1 | 8.1.4.1.8.3 | NR CA / Intra NR handover / Success / PCell Change / SCell no Change / Intra-band non-contiguous CA | Editor's note: Same as TC 8.1.4.1.7.1 but applied to Intra-band non-Contiguous CA. **** TP1: [TS 38,331:] WITH: WHEN: THEN: | Huawei, Hisilicon | Opt 2: Post WI close | R5-195667, R5-204016, R5-203665, R5-214615, R5-217771, R5-220188, R5-221441 |  | FR2 Power level to be defined. | 1 | 90% | 100% | 80%
167 | Y | 38.523-1 | 8.1.4.1.9.1 | NR CA / Intra NR handover / Failure / Re-establishment successful / Intra-band Contiguous CA | **** TP1: [TS 38,331:5.3.5.5.2, 5.3.5.5.9, 5.3.5.5.8, 5.3.7.5] WITH: UE in NR RRC_CONNECTED state and having received an RRCReconfiguration message including a reconfigurationWithSync for PCell change and including sCellToReleaseList with an sCellIndex set to the configured Scell WHEN: UE detects handover failure and the source PCell is selectable THEN: UE successfully performs an RRCReestablishment procedure on source Pcell **** TP2: [TS 38,331:5.3.5.5.2, 5.3.5.5.9, 5.3.5.5.8, 5.3.7.5] WITH: UE in NR RRC_CONNECTED state and having received an RRCReconfiguration message including a reconfigurationWithSync for PCell change and including sCellToReleaseList with an sCellIndex set to the configured SCell WHEN: UE detects handover failure and the initial SCell is selectable THEN: UE successfully performs an RRCReestablishment procedure on original SCell and the original SCell becomes the PCell | TEOCO | Opt 2: Post WI close | R5-195285, R5-197064, R5-204437, R5-205342, R5-211391, R5-212092, R5-213475, R5-216180, R5-217771, R5-217997, R5-221441, R5-221392 | Event A3 RSRP is FFS for FR2 | FR2 power level to be defined ; (FFS in Table 8.1.4.1.9.1.3.3-9 needs to be addressed once FR2 power level defined) | 1 | 90% | 100% | 80%
168 | Y | 38.523-1 | 8.1.4.1.9.2 | NR CA / Intra NR handover / Failure / Re-establishment successful / Inter-band CA | Editor's note: Same as TC 8.1.4.1.9.1 but applied to Inter-band CA. **** TP1: [TS 38,331:] WITH: WHEN: THEN: | TEOCO | Opt 2: Post WI close | R5-195286, R5-204437, R5-205342, R5-211391, R5-212092, R5-213475, R5-217771, R5-217997, R5-221441, R5-221392 | Event A3 RSRP is FFS for FR2 in Table 8.1.4.1.9.1.3.3-9 | FR2 power level to be defined ; (FFS in Table 8.1.4.1.9.1.3.3-9 needs to be addressed once FR2 power level defined) | 1 | 93.33% | 100% | 90% | 90%
169 | Y | 38.523-1 | 8.1.4.1.9.3 | NR CA / Intra NR handover / Failure / Re-establishment successful / Intra-band non-contiguous CA | Editor's note: Same as TC 8.1.4.1.9.1 but applied to Intra-band non-Contiguous CA. **** TP1: [TS 38,331:] WITH: WHEN: THEN: | TEOCO | Opt 2: Post WI close | R5-195287, R5-204437, R5-205342, R5-211391, R5-212092, R5-213475, R5-217771, R5-217997, R5-221441, R5-221392 | Event A3 RSRP is FFS for FR2 | FR2 power level to be defined ; (FFS in Table 8.1.4.1.9.1.3.3-9 needs to be addressed once FR2 power level defined) | 1 | 90% | 100% | 80%
198 |  | 38.523-1 | 8.1.4.1.1 to 8.1.4.2.2.3.3 | See above | Define FR2 power levels for test cases 8.1.4.1.1 to 8.1.4.2.2.3.3 | See above | Opt 2: Post WI close | See above |  |  | 0.9 | 0% |  | 0%
RRC others
201 | Y | 38.523-1 | 8.1.5.8.1 | Processing delay / RRC_Idle to RRC_Connected / RRC_Inactive to RRC_Connected / Success / Latency check | **** TP1: [TS 38,331:12] WITH: UE in NR RRC_IDLE state and has sent an RRCSetupRequest message WHEN: UE receives RRCSetup message and after 10ms receives an UL grant THEN: UE successfully transmits RRCSetupComplete message **** TP2: [TS 38,331:12] WITH: UE in NR RRC_CONNECTED state WHEN: UE receive a SecurityModeCommand message and after 5ms receives an UL grant THEN: UE successfully transmits SecurityModeComplete **** TP3: [TS 38,331:12] WITH: UE in NR RRC_CONNECTED state WHEN: UE receive a RRCReconfiguration message to establish DRB that is not part of the current UE configuration and after 10ms receives an UL grant THEN: UE successfully transmits RRCReconfigurationComplete message **** TP4: [TS 38,331:12] WITH: UE in NR RRC_CONNECTED state WHEN: UE receives an UECapabilityEnquiry message and after 80ms receives an UL grant THEN: UE successfully transmits an UECapabilityInformation message **** TP5: [TS 38,331:12] WITH: UE in NR RRC_INACTIVE state and has sent an RRCResumeRequest message WHEN: UE receives RRCResume message and after 6 or 10ms receives an UL grant depending on UE capability THEN: UE successfully transmits RRCResumeComplete message **** TP6: [TS 38,331:12] Editor's note: Voided and moved to TC 8.1.5.8.2.x WITH: WHEN: THEN: **** TP7: [TS 38,331:12] WITH: UE in NR RRC_CONNECTED state and and has sent an RRCReestablishmentRequest message after detecting radio link failure on expiring of timer T310 WHEN: UE receives RRCReestablishment message and after 10ms receives an UL grant THEN: UE successfully transmits RRCReestablishmentComplete message **** TP8: [TS 38,331:12] Editor's note: Voided and moved to TC 8.1.5.8.2.x WITH: WHEN: THEN: **** TP9: [TS 38,331:12] WITH: UE in NR RRC_CONNECTED state WHEN: UE receives CounterCheck message and after 5ms receives an UL grant THEN: UE successfully transmists an CounterCheckResponse message | Huawei | Opt 2: Post WI close | R5-201367, R5-211392, R5-212420, R5-214769, R5-217815 |  | FR2 Power level to be defined. | 1 | 95% | 100% | 90%
233 | Y | 38.523-1 | 8.1.5.8.2.1 | Processing delay / RRC_Inactive to RRC_Connected / Success / Latency check / SCell addition / Intra-band Contiguous CA | **** TP1: [TS 38,331:12] WITH: UE in NR RRC_CONNECTED state WHEN: UE receives an RRCReconfiguration message containing sCellToAddModList with a SCell addition and after 16ms receives an UL grant THEN: UE successfully transmits RRCReconfigurationComplete message **** TP2: [TS 38,331:12] WITH: UE in NR RRC_INACTIVE state and has sent an RRCResumeRequest message WHEN: UE receives RRCResume message containing sCellToAddModList with a SCell addition and after 16ms receives an UL grant THEN: UE successfully transmits RRCResumeComplete message | Huawei | Opt 2: Post WI close | R5-211393, R5-214618 |  | FR2 Power level to be defined. | 1 | 85% | 100% | 70%
234 | Y | 38.523-1 | 8.1.5.8.2.2 | Processing delay / RRC_Inactive to RRC_Connected / Success / Latency check / SCell addition / Inter-band CA | Editor's note: Same as TC 8.1.5.8.2.1 but applied to Inter-band CA. **** TP1: [TS 38,331:12] WITH: WHEN: THEN: | Huawei | Opt 2: Post WI close | R5-210648, R5-214618 |  | FR2 Power level to be defined. | 1 | 95% | 100% | 90%
235 | Y | 38.523-1 | 8.1.5.8.2.3 | Processing delay / RRC_Inactive to RRC_Connected / Success / Latency check / SCell addition / Intra-band non-Contiguous CA | Editor's note: Same as TC 8.1.5.8.2.1 but applied to Intra-band non-Contiguous CA. **** TP1: [TS 38,331:12] WITH: WHEN: THEN: | Huawei | Opt 2: Post WI close | R5-210649, R5-214618 |  | FR2 Power level to be defined. | 1 | 85% | 100% | 70%
RRC Connection Reconfiguration / Radio Bearer Addition, Modification and Release
241 | Y | 38.523-1 | 8.2.2.2.2 | Split SRB Establishment and Release / NR-DC | **** TP1: [TS 38,331:5.3.5.3, 5.3.5.5.3, 5.3.5.6.1 and 5.3.5.6.3] with { UE in RRC_CONNECTED state with NR-DC } ensure that { when { UE receives an RRCReconfiguration message on SRB1 to configure split SRB1 and split SRB2 with PDCP duplication activated } then { UE configures the split SRBs and sends an RRCConnectionReconfigurationComplete message on split SRB1 with the PDCP PDU duplicated on the MCG and SCG path } } **** TP2: [TS 38,331:5.3.5.3, 5.3.5.5.3, 5.3.5.6.1 and 5.3.5.6.3] with { UE in RRC_CONNECTED state with NR-DC and split SRB configured } ensure that { when { UE receives an RRCReconfiguration message on split SRB1 over the SCG path to release split SRB1 and split SRB2 } then { UE releases split SRB1 and split SRB2 and sends an RRCConnectionReconfigurationComplete message on SRB1 over the MCG path} } **** TP3: [TS 38,331:5.3.5.3, 5.3.5.5.3, 5.3.5.6.1 and 5.3.5.6.3] with { UE in RRC_CONNECTED state in NR-DC mode with split SRB1 and split SRB2 configured with PDCP duplication } ensure that { when { UE receives a CounterCheck on split SRB1 over the SCG path } then { UE replies with CounterCheckResponse on split SRB1 duplicated on the MCG and SCG path} } **** TP4: [TS 38,331:5.3.5.3, 5.3.5.5.3, 5.3.5.6.1 and 5.3.5.6.3] with { UE in RRC_CONNECTED state in NR-DC mode with split SRB1 and split SRB2 configured with PDCP duplication } ensure that { when { UE receives a IDENTITY REQUEST on split SRB2 over the SCG path } then { UE replies with IDENTITY RESPONSE on split SRB2 duplicated on the MCG and SCG path} |  | Opt 2: Post WI close | R5-225393 |  |  | 1 | 100% | 100% |  | 100%
Measurement configuration control and reporting / Handovers
14 | Y | 38.523-1 | 8.2.3.2.1 | Measurement configuration control and reporting / Inter-RAT measurements / Event B1 / Measurement of NR cells / RSRQ based measurements / EN-DC | **** TP1: [TS 36,331:5.5.1, 5.5.4.1, 5.5.4.7, 5.5.5] WITH: UE in RRC_CONNECTED state with EN-DC, and, MCG(s) (E-UTRA PDCP) only having completed the radio bearer establishment and performed the inter RAT measurement for NR cell, configured b1-Threshold set to threshold-RSRQ and not detected entering condition for the event B1 is met WHEN: UE detects entering condition for the event B1 is not met THEN: UE does not transmit any MeasurementReport **** TP2: [TS 36,331:5.5.1, 5.5.4.1, 5.5.4.7, 5.5.5] WITH: UE in RRC_CONNECTED state with EN-DC, and, MCG(s) (E-UTRA PDCP) only having completed the radio bearer establishment and performed the inter RAT measurement for NR cell, configured b1-Threshold set to threshold-RSRQ and not detected entering condition for the event B1 is met WHEN: UE detects entering condition for the event B1 is met THEN: UE transmits a MeasurementReport **** TP3: [TS 36,331:5.5.1, 5.5.4.1, 5.5.4.7, 5.5.5] WITH: UE in RRC_CONNECTED state with EN-DC, and, MCG(s) (E-UTRA PDCP) only having completed the radio bearer establishment and performed the inter RAT measurement for NR cell, configured b1-Threshold set to threshold-RSRQ and detected entering condition for the event B1 is met WHEN: UE detects leaving condition for the event B1 is met THEN: UE does not transmit any MeasurementReport | Qualcomm | Opt 3: Post WI close | R5-181982, R5-183132, R5-184763, R5-185157, R5-187530, R5-192308, R5-198181, R5-200997, R5-201632, R5-202540, R5-210389, R5-213477, R5-221447, R5-225403 | Since UE needs to perform connection mode measurement, E-UTRA OTA calibration needed | FR2 not applicable | 1 | 100% |  |  |  | 100%
27 | Y | 38.523-1 | 8.2.3.12.1 | Measurement configuration control and reporting / Inter-RAT measurements / Event B2 / Measurement of NR cells / EN-DC | **** TP1: [TS 36,331:5.5.1, 5.5.4.1, 5.5.4.8, 5.5.5] WITH: UE in RRC_CONNECTED state with EN-DC, and, MCG(s) (E-UTRA PDCP) only having completed the radio bearer establishment and performed the inter RAT measurement for NR cell and not detected entering condition for the event B2 is met WHEN: UE detects entering condition for the event B2 is not met THEN: UE does not transmit any MeasurementReport **** TP2: [TS 36,331:5.5.1, 5.5.4.1, 5.5.4.8, 5.5.5] WITH: UE in RRC_CONNECTED state with EN-DC, and, MCG(s) (E-UTRA PDCP) only having completed the radio bearer establishment and performed the inter RAT measurement for NR cell and not detected entering condition for the event B2 is met WHEN: UE detects entering condition for the event B2 is met THEN: UE transmits a MeasurementReport **** TP3: [TS 36,331:5.5.1, 5.5.4.1, 5.5.4.8, 5.5.5] WITH: UE in RRC_CONNECTED state with EN-DC, and, MCG(s) (E-UTRA PDCP) only having completed the radio bearer establishment and performed the inter RAT measurement for NR cell and detected entering condition for the event B2 is met WHEN: UE detects leaving condition for the event B2 is met THEN: UE does not transmit any MeasurementReport | InterTek | Opt 3: Post WI close | R5-183129, R5-185089, R5-187701, R5-192331, R5-198181, R5-200625, R5-202651, R5-201632, R5-201802, R5-202048, R5-210378, R5-213479, R5-221447, R5-225403 | Since UE needs to perform connection mode measurement, E-UTRA OTA calibration needed | FR2 not applicable | 1 | 100% |  |  |  | 100%
29 | Y | 38.523-1 | 8.2.3.13.1 | PCell Handover with SCG change / Reconfiguration with sync / SCG DRB / EN-DC | Editor's note: L1+NR1 --> HO to L2+NR1 (Reconfiguration with sync) **** TP1: [TS 36,331:5.3.5.4; TS 38,331:5.3.5.3, 5.3.5.5.1 and 5.3.5.5.2] WITH: UE in RRC_CONNECTED state with EN-DC, and, MCG(s) (E-UTRA PDCP) and SCG DRB established WHEN: UE receives an RRCConnectionReconfiguration message containing mobilityControlInfo to handover to target E-UTRAN PCell involving SCG change with reconfigurationWithSync on the same PSCell THEN: UE sends an RRCConnectionReconfigurationComplete message | Keysight | Opt 3: Post WI close | R5-182083, R5-183120, R5-186891, R5-192330, R5-197100, R5-221447 | As per AP 91.01, FR2 power levels are to be defined By defining inter-frequency cells, this test can be made verifiable as there is no cell releseciton or connected mode measurements are needed. Note T0 applied "after preamble". | FR2 Power level to be defined. | 1 | 95% |  |  |  | 100% | 90%
156 | Y | 38.523-1 | 8.2.3.15.1 | Measurement configuration control and reporting / Two simultaneous events A2 and A3 (intra-frequency measurements) / Measurement of Neighbour NR cells / EN-DC | **** TP1: [TS 36,331:5.3.5.3; TS 38,331:5.3.5.3, 5.5.2, 5.5.4.1, 5.5.4.3, 5.5.4.4 and 5.5.5] WITH: UE in RRC_CONNECTED state with EN-DC, and, MCG(s) (E-UTRA PDCP) and SCG and measurements configured for event A2 and event A3 WHEN: Serving NR cell becomes worse than absolute threshold minus hysteresis THEN: UE sends MeasurementReport for event A2 **** TP2: [TS 36,331:5.3.5.3; TS 38,331:5.3.5.3, 5.5.2, 5.5.4.1, 5.5.4.3, 5.5.4.4 and 5.5.5] WITH: UE in RRC_CONNECTED state with EN-DC, and, MCG(s) (E-UTRA PDCP) and SCG and measurements configured for event A2 and event A3 WHEN: Neighbour NR cell becomes offset better than serving NR PSCell THEN: UE sends MeasurementReport for event A3 | NTT Docomo | Opt 3: Post WI close | R5-191764, R5-197072, R5-202651, R5-212098, R5-221447, R5-225403 | This test still not verifiable as it requires careful design of thresholds and power levels. | FR2 not applicable | 1 | 100% |  |  |  | 100%
194 |  | 38.523-1 | 8.2.3.2.1, 8.2.3.12.1, 8.2.3.13.1, 8.2.3.15.1 | See above | Define FR2 power levels for test cases 8.2.3.2.1, 8.2.3.6.1a, 8.2.3.6.1b, 8.2.3.7.1a, 8.2.3.7.1b, 8.2.3.8.1, 8.2.3.8.1a, 8.2.3.8.1b, 8.2.3.9.1, 8.2.3.10.1, 8.2.3.11.1, 8.2.3.11.2, 8.2.3.12.1, 8.2.3.13.1, 8.2.3.14.1, 8.2.3.15.1 | See above | Opt 3: Post WI close | See above |  |  | 0.4 | 0% |  |  |  |  | 0%
Carrier Aggregation
32 | Y | 38.523-1 | 8.2.4.1.1.2 | NR CA / NR SCell addition / modification / release / Success / EN-DC / Intra-band non-Contiguous CA | Editor's note: Same as for 8.2.4.1.1.1, but for Intra-band non-contiguous NR cell configuration **** TP1: [] WITH: WHEN: THEN: | Qualcomm | Opt 3: Post WI close | R5-185069, R5-185157, R5-187254, R5-191654, R5-199033, R5-201326, R5-203666, R5-205577, R5-216184, R5-217078, R5-221449 |  | EN-DC IBNC CA support for FR1 ready, so FR1 column set at 100% | 1 | 100% |  |  |  | 100% | 100%
33 | Y | 38.523-1 | 8.2.4.1.1.3 | NR CA / NR SCell addition / modification / release / Success / EN-DC / Inter-band CA | Editor's note: Same as for 8.2.4.1.1.1, but for Inter-band NR cell configuration **** TP1: [] WITH: WHEN: THEN: | Qualcomm | Opt 3: Post WI close | R5-185069, R5-185157, R5-187254, R5-191654, R5-199033, R5-201326, R5-203666, R5-205577, R5-216184, R5-217078, R5-221449 |  | ENDC with NR CA Inter-band CA with FR2 is Not Ready in 38.508-1 | 1 | 96.67% |  |  |  | 100% | 90% | 100%
35 | Y | 38.523-1 | 8.2.4.2.1.2 | NR CA / Simultaneous PSCell and SCell addition / PSCell and SCell change / CA Release / EN-DC / Intra-band non-Contiguous CA | Editor's note: Same as for 8.2.4.2.1.1, but for Intra-band non-contiguous NR cell configuration **** TP1: [] WITH: WHEN: THEN: | Huawei | Opt 3: Post WI close | R5-183225, R5-185062, R5-186995, R5-202652, R5-203666, R5-213078, R5-220397, R5-230676 |  | EN-DC IBNC CA support for FR1 ready, so FR1 column set at 100% EUTRA and FR2 cell power definition to be crosschecked | 1 | 100% |  |  |  | 100% | 100%
36 | Y | 38.523-1 | 8.2.4.2.1.3 | NR CA / Simultaneous PSCell and SCell addition / PSCell and SCell change / CA Release / EN-DC / Inter-band CA | Editor's note: Same as for 8.2.4.2.1.1, but for Inter-band NR cell configuration **** TP1: [] WITH: WHEN: THEN: | Huawei | Opt 3: Post WI close | R5-183226, R5-185148, R5-186995, R5-202652, R5-203666, R5-213078, R5-220397, R5-230676 |  | ENDC with NR CA Inter-band CA with FR2 is Not Ready in 38.508-1 EUTRA and FR2 cell power definition to be crosschecked | 1 | 96.67% |  |  |  | 100% | 90% | 100%
47 | Y | 38.523-1 | 8.2.4.3.1.2 | NR CA / SCell change / Intra-NR measurement event A6 / SRB3 / EN-DC / Intra-band non-Contiguous CA | Editor's note: Same as for 8.2.4.3.1.1, but for Intra-band non-contiguous NR cell configuration **** TP1: [] WITH: WHEN: THEN: | CATT | Opt 3: Post WI close | R5-185072, R5-185157, R5-187302, R5-202653, R5-206345, R5-210561, R5-213480, R5-216639, R5-220397 |  | EN-DC IBNC CA support for FR1 ready, so FR1 column set at 100% | 1 | 100% |  |  |  | 100% | 100%
48 | Y | 38.523-1 | 8.2.4.3.1.3 | NR CA / SCell change / Intra-NR measurement event A6 / SRB3 / EN-DC / Inter-band CA | Editor's note: Same as for 8.2.4.3.1.1, but for Inter-band NR cell configuration **** TP1: [] WITH: WHEN: THEN: | CATT | Opt 3: Post WI close | R5-184500, R5-185157, R5-187302, R5-201225, R5-202653, R5-206345, R5-210561, R5-212100, R5-213480, R5-216639, R5-220397 |  | ENDC with NR CA Inter-band CA with FR2 is Not Ready in 38.508-1 | 1 | 96.67% |  |  |  | 100% | 90% | 100%
Reconfiguration Failure / Radio link failure
MR-DC RRC others
223 | Y | 38.523-1 | 8.2.6.1.1.2 | Failure information / RLC failure / SCG / EN-DC / Inter-band CA | **** TP1: [TS 36,331:5.3.5.3; TS 38,331:5.7.5.2 and 5.7.5.3] WITH: UE in RRC_CONNECTED state with EN-DC, and, MCG(s) (E-UTRA PDCP) and SCG WHEN: an indication from SCG RLC that the maximum number of retransmissions has been reached and when CA duplication is configured and activated and for the corresponding logical channel allowedServingCells only includes SCell(s) THEN: UE sends the FailureInformation message embedded in E-UTRA RRC message ULInformationTransferMRDC to report RLC failure **** TP2: [TS 36,331:5.3.5.3; TS 38,331:5.7.5.2 and 5.7.5.3] WITH: UE in RRC_CONNECTED state with EN-DC, and, MCG(s) (E-UTRA PDCP) and SCG and SRB3 configured WHEN: an indication from SCG RLC that the maximum number of retransmissions has been reached and when CA duplication is configured and activated and for the corresponding logical channel allowedServingCells only includes SCell(s) THEN: UE initiates the failure information procedure to report RLC failure via SRB3 | Huawei | Opt 3: Post WI close | R5-202654, R5-203405, R5-206348 |  | ENDC with NR CA Inter-band CA with FR2 is Not Ready in 38.508-1 | 1 | 96.67% |  |  |  | 100% | 90% | 100%
224 | Y | 38.523-1 | 8.2.6.1.1.3 | Failure information / RLC failure / SCG / EN-DC / Intra-band non Contiguous CA | **** TP1: [TS 36,331:5.3.5.3; TS 38,331:5.7.5.2 and 5.7.5.3] WITH: UE in RRC_CONNECTED state with EN-DC, and, MCG(s) (E-UTRA PDCP) and SCG WHEN: an indication from SCG RLC that the maximum number of retransmissions has been reached and when CA duplication is configured and activated and for the corresponding logical channel allowedServingCells only includes SCell(s) THEN: UE sends the FailureInformation message embedded in E-UTRA RRC message ULInformationTransferMRDC to report RLC failure **** TP2: [TS 36,331:5.3.5.3; TS 38,331:5.7.5.2 and 5.7.5.3] WITH: UE in RRC_CONNECTED state with EN-DC, and, MCG(s) (E-UTRA PDCP) and SCG and SRB3 configured WHEN: an indication from SCG RLC that the maximum number of retransmissions has been reached and when CA duplication is configured and activated and for the corresponding logical channel allowedServingCells only includes SCell(s) THEN: UE initiates the failure information procedure to report RLC failure via SRB3 | Huawei | Opt 3: Post WI close | R5-202654, R5-203405, R5-206348 |  | EN-DC IBNC CA support for FR1 ready, so FR1 column set at 100% | 1 | 100% |  |  |  | 100% | 100%
RRC resume
5GC | [5 empty] | Responsible: Xiaozhong Chen, CATT
5GS mobility management
47 | Y | 38.523-1 | 9.1.6.1.3 | UE-initiated de-registration / Abnormal / Change of cell into a new tracking area | UE-initiated de-registration / Abnormal / Change of cell into a new tracking area **** TP1: [TS 24,501:5.5.2.2.6 f)] WITH: UE in 5GMM-DEREGISTERED-INITIATED state and de-registration request is not due to switch off WHEN: UE changes into a new tracking area that is not in the stored TAI list THEN: UE aborts the de-registration procedure and initiates a mobility registration procedure **** TP2: [TS 24,501:5.5.2.2.6 f)] WITH: UE in 5GMM-REGISTERED-INITIATED state for a mobility registration procedure due to change of cell into a new tracking area list during UE-initiated de-registration procedure WHEN: UE receives REGISTRATION ACCEPT message THEN: UE re-initiates the de-registration procedure after completing the mobility registration procedure **** TP3: [TS 24,501:5.5.2.2.6 f)] WITH: UE in 5GMM-DEREGISTERED-INITIATED state and de-registration request is due to switch off WHEN: UE changes into a new tracking area that is not in the stored TAI list THEN: UE aborts the de-registration procedure and enter the state 5GMM-DEREGISTERED | Qualcomm | Opt 2: Post WI close | R5-195210 R5-197082 R5-198185 R5-200208 R5-202660 R5-204464 R5-205385 R5-224029 | ‘Non-suitable’ cell needs to be updated for FR2 |  | 1 | 100% | 100% | 100%
Multilayer and Services | [5 empty] | Responsible: Eniko Sokondar, Mediatek
5GS/EPS fallback
48 | Y | 38.523-1 | 11.1.1a | MO MMTEL enhanced voice service call setup from NR RRC_IDLE / EPS Fallback with redirection / Single registration mode with N26 interface / Success | **** TP1:FFS Editor's note: Complimentary references: TS 23.501, subclause 5.16.3.10, TS 23.502, subclauses 4.13.6.1, 4.11.1 WITH: UE supporting both S1 mode and N1 mode and operating in single-registration mode, and, the Network has indicated "interworking without N26 interface not supported", and, the UE in NR RRC_IDLE state WHEN: User initiates a MMTEL call and the UE completes Access control and checking in 5GMM-IDLE mode THEN: UE requests the establishment of a MMTEL call by transmitting an RRCSetupRequest message with establishmentCause set to 'mo-VoiceCall', and, a SERVICE REQUEST message with Service type set to 'data' **** TP2:FFS Editor's note: Complimentary references: TS 23.501, subclause 5.16.3.10, TS 23.502, subclauses 4.13.6.1, 4.11.1 WITH: UE is NR RRC_CONNECTED state after having requested a MMTEL call establishment and the MO IMS voice session establishment has been initiated WHEN: UE receives a RRCRelease message which includes redirectedCarrierInfo indicating redirection to eutra THEN: UE selects the E-UTRA cell, performs a TAU procedure, and, successfully completes voice call setup in EPS using EVS | Ericsson | Opt 2: Post WI close | R5-220267, R5-221452, R5-222430 |  |  | 1 | 100% | 100% | 100%
48 | Y | 38.523-1 | 11.1.3a | MO MMTEL enhanced voice service call setup from NR RRC_CONNECTED / EPS Fallback with handover / Single registration mode with N26 interface / Success | **** TP1: [TS 24,501:4.8.2.2, 5.1.4.2, 6.1.4.1; TS 38,331:5.4.3.3, 5.4.3.4; TS 24,229:U.2.2.1, U.3.1.2] Editor's note: Complimentary references: TS 23.501, subclause 5.16.3.10, TS 23.502, subclauses 4.13.6.1, 4.11.1 WITH: UE supporting both S1 mode and N1 mode and operating in single-registration mode, and, the Network has indicated "interworking without N26 interface not supported", and, the UE is in NR RRC_CONNECTED state WHEN: User initiates a MMTEL call, the MO IMS voice session establishment has been initiated and the UE receives a MobilityFromNRCommand message which includes targetRAT-Type set to eutra THEN: UE performs a handover to the E-UTRA including a TAU procedure, and, while the UE continues receiving and transmitting PS data the UE successfully completes the MO MMTEL call in EPS | Ericsson | Opt 2: Post WI close | R5-223432 |  |  | 1 | 100% | 100% | 100%
Unified Access Control (UAC)
34 | Y | 38.523-1 | 11.3.4 | UAC / Access Identity 0 / Registration procedure for mobility and periodic registration update / BarringPerPLMN/Implicit AC Barring List | Editor's note: Conformance references: TS 24.501 4.5.2 , 4.5.4.1 , 4.5.6; TS 38.331 5.3.14 **** TP1: [TS <TS#1>:FFS] WITH: UE in NR RRC_IDLE not configured for special AIs (1,2,11-15) having received a SIB1 message including UAC set to 0% accessibility for Access Category 3 WHEN: UE finds a new cell (AC 3) with SIB1 containing UAC Barring Info Per PLMNwith Implicit AC Barring List THEN: UE does not move to the new cell until barring is alleviated | CATT | Opt 2: Post WI close | R5-198985, R5-200358, R5-202671, R5-206364, R5-211408 | Needs Review for the case of 2 NR FR2 cells active simultaneously. |  | 1 | 95% | 100% | 90%
35 | Y | 38.523-1 | 11.3.5 | UAC / Access Identity 1 / New cell not in the country of its HPLMN/EHPLMN 0% access probability/MPS indicator / HPLMN/0%/100% accessibility AC5/MMTEL-Video call | Editor's note: Conformance Requirements: TS 24.501 4.5.2 , 4.5.4.1 , 4.5.6; TS 38.331 5.3.14 **** TP1: [TS <TS#1>:FFS] WITH: UE configured for Access Identity 1 WHEN: UE moves to a new cell which is not in the country of its HPLMN or in an EHPLMN (if the EHPLMN list is present) having received SIB1 message including UAC set to 0% accessibility for Access Identity 1 THEN: UE does not consider Access Identity 1 as valid and continues with the REGISTRATION procedure **** TP2: [TS <TS#1>:FFS] WITH: UE configured for Access Identity 1 WHEN: UE moves to a new cell which is not in the country of its HPLMN or in an EHPLMN (if the EHPLMN list is present) but receives the MPS indicator bit of the 5GS network feature support IE in the REGISTRATION ACCEPT message being set to "Access identity 1 valid" THEN: UE does consider Access Identity 1 as valid **** TP3: [TS <TS#1>:FFS] WITH: UE configured for Access Identity 1 having received SIB1 containing UAC Barring Info indicating 0% accessibility for Access Category 5 in NR RRC_IDLE state on HPLMN WHEN: User initiates MMTEL-Video call THEN: UE does not attempt to initiate connection on the NR Cell **** TP4: [TS <TS#1>:FFS] WITH: UE configured for Access Identity 1 having received SIB1 containig UAC Info indicating 100% accessibility for Access Cateogry 5 while camped on HPLMN in NR RRC_IDLE state WHEN: User initiates MMTEL-Video call and Access Barring check indicates Barring is alleviated THEN: UE initiates RRC Connection Setup procedure with establishmentCause set to mps-PriorityAccess | Huawei | Opt 2: Post WI close | R5-201379, R5-213503, R5-216193, R5-220557, R5-223436 | FR2 Cell settings FFS |  | 1 | 85% | 100% | 70%
36 | Y | 38.523-1 | 11.3.6 | UAC / Access Identity 2 / New cell not in the country of its HPLMN/EHPLMN 0% access probability/MCS indicator / HPLMN/0%/100% accessibility AC7/RRC_INACTIVE | Editor's note: Conformance requirements: TS 24.501 4.5.2 , 4.5.4.1 , 4.5.6; TS 38.331 5.3.14 **** TP1: [TS <TS#1>:FFS] WITH: UE configured for Acces Identity 2 WHEN: UE moves to a new cell which is not in the country of its HPLMN or in an EHPLMN (if the EHPLMN list is present) having received SIB1 message including UAC set to 0% accessibility for Access Identity 2 THEN: UE does not consider Access Identity 2 as valid and continues with the REGISTRATION procedure **** TP2: [TS <TS#1>:FFS] WITH: UE configured for Acces Identity 2 WHEN: UE moves to a new cell which is not in the country of its HPLMN or in an EHPLMN (if the EHPLMN list is present) but receives the MCS indicator bit of the 5GS network feature support IE in the REGISTRATION ACCEPT message being set to "Access identity 2 valid" THEN: UE does consider Access Identity 2 as valid **** TP3: [TS <TS#1>:FFS] WITH: UE configured for Acces Identity 2 having received SIB1 containing UAC Info indicating 0% accessibility for Access Category 7 camped in NR RRC_INACTIVE state on HPLMN WHEN: UE attempts to send uplink user data packet for a PDU session with suspended user-plane resources THEN: UE does not attempt to initiate connection on the NR Cell until barring is alleviated **** TP4: [TS <TS#1>:FFS] WITH: UE configured for Acces Identity 2 having received SIB1 containig UAC Info indicating 100% accessibility for Access Category 7 while camped on HPLMN in NR RRC_INACTIVE state WHEN: UE attempts to send uplink user data packet for a PDU session with suspended user-plane resources THEN: UE initiates RRC Resume procedure with establishmentCause set to mcs-PriorityAccess | Huawei | Opt 2: Post WI close | R5-199036, R5-201227, R5-211409, R5-213506, R5-216194, R5-221457, R5-223437 | FR2 Cell settings FFS |  | 1 | 90% | 100% | 80%
38 | Y | 38.523-1 | 11.3.8 | UAC / Access Identity 0 / NR RRC_IDLE / Cell re-selection while T390 is running | Editor's note: Conformance Requirements: TS 24.501 4.5.2 , 4.5.4.1 , 4.5.6; TS 38.331 5.3.14 | Qualcomm | Opt 2: Post WI close | R5-202670, R5-204019, R5-213501, R5-212431, R5-223434 | Needs Review for the case of 2 NR FR2 cells active simultaneously. |  | 1 | 95% | 100% | 90%
Emergency Services
242 | Y | 38.523-1 | 11.4.10a | 5GMM-REGISTERED.NORMAL-SERVICE / N26 interface not supported / N1 mode to S1 mode transfer of an existing emergency PDU session | 5GMM-REGISTERED.NORMAL-SERVICE / N26 interface not supported / N1 mode to S1 mode transfer of an existing emergency PDU session **** TP1: [TS 24.501:6.1.4.2; TS 22.101: 10.1.1] WITH: UE in 5GMM-REGISTERED.NORMAL-SERVICE state and 5GMM-IDLE mode with Interworking without N26 interface supported, and, the UE has an emergency PDU session established WHEN: UE performs a inter-system change from the N1 to S1 mode THEN: UE correctly transfers the existing emergency PDU session into an emergency PDN connection | Huawei | Opt 2: Post WI close | R5-224720, R5-227577 |  |  |  | 100% | 100% | 100%
243 | Y | 38.523-1 | 11.4.13 | 5GMM-REGISTERED.NORMAL-SERVICE / 5GMM-IDLE / Emergency call / obtaining new IP address different than the IP address | TS 24.229, subclause 5.1.1.2.1, 5.1.1.5.1, 5.1.6.2A, 5.1.6.8.3, and TS 33.203 subclause 7.5 TP1 WITH: UE in 5GMM-REGISTERED.NORMAL-SERVICE state and 5GMM-IDLE mode WHEN: UE is requested to make an outgoing emergency call THEN: UE performs IMS emergency registration and sets up an IMS emergency call TP2 WITH: UE in 5GMM-REGISTERED.NORMAL-SERVICE state and 5GMM-CONNECTED mode having established an Emergency call WHEN: UE recieves an IMS BYE message to release an emergency call THEN: UE release the emergency call TP3 WITH: UE has ended and Emergency call and IMS emergency registration not having expired ensure that { when { IP address re-allocation is triggered by the network } then { UE performs a new initial IMS emergency registration } } | ZTE | Opt 2: Post WI close | R5-227445, R5-227219 |  |  |  | 100% | 100% | 100%
244 | Y | 38.523-1 | 11.4.14 | 5GMM-REGISTERED.NORMAL-SERVICE / 5GMM-IDLE / Emergency call /Deregistration upon emergency registration expiration | TS 24.229, subclause 5.1.6.4, 5.1.6.6 WITH: UE has ended Emergency call and IMS emergency registration not having expired WHEN: half of the emergency registration expiration time has passed THEN: UE does not attempt IMS emergency re-registration | ZTE | Opt 2: Post WI close | R5-227446, R5-227219 |  |  |  | 100% | 100% | 100%
End of work plan items. Note! Do not remove this row. Introduce new work plan rows/items above this row.
Note on A4: Unique ID for WP items (unique within the sub-area work plan) Note! As WP item numbers may be referenced from outside of this WP that means: - Do not change number for WP items that have been published. - Do not re-use WP item numbers if a WP item is deleted
Note on B4: Y = the WP Pitem is a test case.
Note on L4: The WP item's weight number is used to set the reletive weights between WP items used in the overall calculation of completeness. Setting it to 0 fpr a WP item means that it will not be included at all in the calculation.