## Slide 1: Proposal for update of RAN5 5G NR phases and targets
RAN5#2-5G-NR-Adhoc meeting R5-182113
Taoyuan, Taiwan, 9th-13th April 2018

## Slide 2: Introduction
RAN#79 plenary update
RAN5 Time plan for defining MU and TT for RF tests
Proposal for update of RAN5 phases and targets
Proposal for content of NSA Option 3 (EN-DC) Phases
Proposed way forward

## Slide 3
RAN#79 plenary updates (Ref:RP-180554)
Rel-15 schedule unchanged
  Architecture Option 3: ASN.1 Freeze March 2018
  Architecture Option 2: ASN.1 Freeze September 2018
  Architecture Option 5: ASN.1 Freeze September 2018 (only impacts LTE ASN.1)
Introduce Late Rel-15 Drop
  Follows Rel-15 completion by 6 months
  The late drop is to exclusively contain NR architecture options that were not completed by September ASN.1 drop
  Options 4, 7 are part of the late drop
  In case Option 5 is not completed by September ASN.1 drop, it will be part of the late drop
  NR-NR DC to be considered to be added to the late drop at RAN#80
  Band combinations which are not completed by June 2018 (other than NR-NR DC combinations) will be moved to Rel-16 band specifications, but continue to be release independent.

## Slide 4: Time line (Ref:RP-180554)

## Slide 5
RAN5#2-5G-NR-Adhoc FR2 MU/TT timeplan (Ref:R5-182092)
Proposed Time plan for FR2 MU/TT
  RF MU/TT Target 1: [MU] RAN5#NR3 (Oct-18) [TT] RAN5#NR4 (Jan-19)
  RF MU/TT Target 2: [MU] RAN5#82 (Feb-19) [TT] RAN5#83 (May-19)
  RF MU/TT Target 3: [MU] RAN5#83 (May-19) [TT] RAN5#84 (Aug-19)
RF MU/TT Target 1 test cases (regulatory):
  6.2.1 Max Output Power 7.3 Ref Sensitivity
RF MU/TT Target 2 test cases (regulatory):
  6.3.2 Transmit OFF power 6.4.1 Frequency Error
  6.5.1 Occupied bandwidth 6.5.2.1 Spectrum emission mask
  6.5.2.2 Adjacent Channel Leakage Ratio 6.5.3.1 General spurious emissions
  6.5.3.2 Spurious emissions for UE co-existence 7.7 Receiver Spurious emissions
RF MU/TT Target 3 test cases: all other test cases

## Slide 6
Proposal for update of RAN5 phases and targets
(based on RAN#79 updates and RAN5 MU/TT time plan)
RAN5#79 May-18
  NSA Option 3 (EN-DC) Phase 1 --- No change
RAN5#81 Nov-18
  NSA Option 3 (EN-DC) Phase 2 --- No change
  SA Option 2 (SA NR) Phase 1 --- No change
  SA Option 5 (SA E-UTRA) Phase 1** --- No change
RAN5#83 May-19
  NSA Option 3 (EN-DC) Phase 3 --- Added phase 3
  SA Option 2 (SA NR) Phase 2 --- Added phase 2
  SA Option 5 (SA E-UTRA) Phase 2** --- Added phase 2
  NSA Option 7 (NGEN-DC) Phase 1* --- Moved 6 Months
  NSA Option 4 (NE-DC) Phase 1* --- Target date added
  *ASN.1 late drop freeze March-19 **May be deferred 6 months if Option 5 will be moved from ASN.1 Freeze in Sept-18 to the late drop freeze March-19

## Slide 7
The RF, Demod/CSI reporting and RRM test cases can be divided into the following parts
  Test definition Test case description excluding MU (FR2) and TT (FR1 and FR2) part(s) i.e. non MU/TT parts of minimum requirements, Initial conditions, Test points, Test procedure, Specific message content etc.
  MU Measurement Uncertainty
  TT Test Tolerances
  Complete FR1 test case Test definition + MU + TT
  Complete FR2 test case Test definition + MU + TT
NOTE!
  The completion targets for EN-DC FR2 test cases are set based on the RAN5 MU/TT targets as described in R5-182092.
  Until the MU/TT becomes available it is important that the parts of test definition of the FR2 test cases that are NOT dependent on MU/TT are progressed as far as possible.
  This concerns the EN-DC specific FR2 test cases in TS 38.521-3, but also the parts of the TS 38.521-2 FR2 test cases referenced by the TS 38.521-3 FR2 test cases.
Proposal for NSA Option 3 (EN-DC) PHASE content
- GENERAL CONSIDERATIONs

## Slide 8
Included EN-DC configurations: LTE 1CC + NR FR1 1CC
INCLUDED:
  RF - TS 38.521-3, TS 38.522, TS 38.521-1 (Note 1), TS 38.521-2 (Note 1), TR 38.903, TR 38.905
    Test definition, MU for all LTE+NR FR1 Rx and Tx test cases, Note 2, Note 3
    Progress on Test definition for all LTE+NR FR2 Rx and Tx test cases, Note 2
  Protocol - TS 38.523-x
    Layer 2: NR MAC, RLC and PDCP test cases
    RRC: Basic RRC test cases (see below what is excluded)
    NAS: All test cases
  Test environment - TS 36.508, TS 38.508-1, TS 38.508-2
    Common test environment to enable LTE+NR FR1 MCG+SCG and Split bearer testing
    Common ICS as needed for test cases in TS 38.521-3 and TS 38.523-1.
  UE test functions - TS 38.509
    UE test loop mode A and UE test loop mode B.
NOT INCLUDED:
  MU/TT for any Rx and Tx LTE+NR FR2 test cases (TS 38.521-3)
  All LTE+NR FR1 and FR2 Demod/CSI reporting test cases (TS 38.521-4)
  All LTE+NR FR1 and FR2 RRM test cases (TS 38.533)
  Protocol test cases for EN-DC NR CA TC, BWP, SRB3, measurement gaps and CSI-RS, and SS\PBCH based measurements test cases
  IMS test cases (TS 34.229-x)
  Positioning test cases (TS 37.571-x)
Note 1: The TS 38.521-3 referenced clauses in TS 38.521-1 and TS 38.521-2 need to be completed as part of the TS 38.521-3 target.
Note 2: Dependency: RAN4 progress until RAN4#87 (May-18)
Note 3: TT needs one more meeting cycle
Proposal for NSA Option 3 (EN-DC) Phase 1 content
- Target RAN5#79 MAY-18

## Slide 9
Included EN-DC configurations: LTE xCC + NR FR1 1CC, where x>=1; and LTE 1CC + NR FR2 1CC
INCLUDED:
  RF - TS 38.521-3, TS 38.522, TS 38.521-1 (Note 1), TS 38.521-2 (Note 1), TR 38.903, TR 38.905
    Test definition, MU and TT for LTE+NR FR1: Rx and Tx test cases not completed in NSA Opt.3 Phase 1, Note 2
    Test definition, MU and TT for LTE+NR FR2 RF MU/TT Target 1 test cases, Note 3
    Progress on Test definition for LTE+NR FR2: Rx and Tx test cases not progressed in NSA Opt.3 Phase 1, Note 2
  Protocol - TS 38.523-x, TS 34.229-x, TS 37.571-x
    Remaining test cases not completed in NSA Opt.3 Phase 1
    LTE xCC + NR FR1 1CC test cases
    RRC EN-DC LTE xCC + NR 1CC, BWP, SRB3, measurement gaps and CSI-RS, and SS\PBCH based measurements test cases
    IMS IR.92 EN-DC test cases
    Positioning EN-DC test cases
  Test environment - TS 36.508, TS 38.508-1, TS 38.508-2
    Common test environment to enable FR2 testing (RF and protocol)
    Common ICS as needed for test cases in TS 38.521-3 and TS 38.523-1.
  UE test functions - TS 38.509
    UBF, SS-RSRPB UE reporting, UE Positioning test functions
NOT INCLUDED:
  RF MU/TT for RF MU/TT Target 2 and Target 3 test cases (TS 38.521-3)
  All LTE + NR FR1 or FR2 Demod/CSI reporting (TS 38.521-4)
  All LTE + NR FR1 or FR2 RRM (TS 38.533)
Note 1: The TS 38.521-3 referenced clauses in TS 38.521-1 and TS 38.521-2 need to be completed as part of the TS 38.521-3 target.
Note 2: Dependency: RAN4 progress until RAN4#89 (Nov-18)
Note 3: Dependency: RAN4 progress until RAN4#89 (Nov-18) + RAN5 RF MU/TT progress. For RF MU/TT target 1 test cases MU ss planned to be completed by RAN5#NR3 (Oct-18) and TT is targeted to be completed by RAN5#NR4 (Jan-19) (Ref R5-182092)
Proposal for NSA Option 3 (EN-DC) Phase 2 content
- Target RAN5#81 NOV-18

## Slide 10
Proposal for NSA Option 3 (EN-DC) Phase 3 content
- Target RAN5#83 MAY-19
Included EN-DC configurations: LTE xCC + NR FR1/FR2 yCC, where x,y>=1
INCLUDED:
  RF - TS 38.521-3, TS 38.522, TS 38.521-1 (Note 1), TS 38.521-2 (Note 1), TR 38.903, TR 38.905
    Test definition and MU/TT for LTE+NR FR2 Rx and Tx RF MU/TT target 2 test cases where MU/TT analysis completed, Note 3
    Test definition and MU part for RF MU/TT Target 3 test cases (TS 38-521-3), Note 4
    Test definition and TT for LTE+NR FR1 Demod/CSI reporting (TS 38.521-4), Note 2
    Test definition and TT for LTE+NR FR1 RRM (TS 38.533) test definition and TT, Note 2
    Test definition for LTE+NR FR2 Demod/CSI reporting (TS 38.521-4), Note 2
    Test definition for LTE+NR FR2 RRM (TS 38.533), Note 2
  Protocol - TS 38.523-x, TS 34.229-x, TS 37.571-x
    Remaining test cases not completed in NSA Opt.3 Phase 2
    LTE xCC + NR FR1 yCC test cases
  Test environment - TS 36.508, TS 38.508-1, TS 38.508-2
    Common test environment to enable to enable LTE xCC + NR FR1 yCC test cases
    Common test environment to enable to enable LTE xCC + NR FR2 yCC test cases
    Common ICS as needed for test cases in TS 38.521-3 and TS 38.523-1.
  UE test functions - TS 38.509
    TBD if any additional UE test functions needed
NOT INCLUDED:
  TT part of RF MU/TT Target 3 test cases (TS 38-521-3), Note 4
  MU/TT part of LTE+NR FR2 Demod/CSI reporting (TS 38.521-4), Note 5
  MU/TT part of LTE+NR FR2 RRM (TS 38.533), Note 5
Note 1: The TS 38.521-3 referenced clauses in TS 38.521-1 and TS 38.521-2 need to be completed as part of the TS 38.521-3 target.
Note 2: Dependency: RAN4 progress until RAN4#89 (Nov-18)
Note 3: Dependency: RAN4 progress until RAN4#89 (Nov-18) + RAN5 MU/TT progress. MU part of RF MU/TT target 2 test cases is RAN5#82 (Frb-19) and TT part is targeted to be completed by RAN5#83 (May-19) (Ref R5-182092)
Note 4: MU part of RF MU/TT target 3 test cases are planned to be completed by RAN5#83 (May 19) and TT part by RAN5#84 (Aug-19). The TT part need thus to be completed after NSA Opt.3 Phase 3. Note 5: There will be a need for a NSA Opt.3 Phase 4 to be added when MU/TT targets for Demod/CSI and RRM test cases becomes available.

## Slide 11: Proposed way forward
It is proposed that the details of the content for NSA Option 3 (EN-DC) phases and the overall target dates for SA Option 2, SA Option 5, NSA Option 7 and NSA Option 4 phases as described in this document is used as base for the update of the RAN5 5GS work plan. The time plan for the proposed targets are illustrated below.