## WP scope
Work plan for introduction of EN-DC PC3 FR2 configurations into 3GPP UE conformance test specifications
| WP template: | WP EN-DC PC3 FR2 v1.5.0
Note! A copy of this work plan shall be included in a Completion Declaration Statement (CDS) to be submitted as a TDOC to the RAN5 meeting when the configuration(s) are completed.
Workplan scope
| Workplan Name |  | WP NR CA PC3 FR1 CA_n3A-n77A | [6 empty] | <= Default workplan name is the filename. To change replace the formula with preferred text.
| Company (Contact) | [8 empty] | <= Enter Responsible Company and Contact for the configurations in the WP
| Target completion |  | TBD | [6 empty] | <= Enter target completion date here. Format RAN5#<xx>, where <xx> is the RAN5 meeting, e.g. RAN5#94-e>
Comments
| Overall completion |  | 100%
Target configurations
Note: A work plan can include multiple target configurations but it is recommended to create separate work plans for Intra-band continuous, Intra-band Non-Continuous and Inter-band configurations. Copy target configuration(s) for the WP from the "PRD21 NR bands and 5G NR CADC list" as values in the table below by: 1. Select and copy the complete rows of the target configuration(s) in the "PRD21 NR bands and 5G NR CADC list". 2. Select cell A15 in the table below and right-click. 3. Select paste option "Paste as values" (see picture). It may take a few seconds before the pasted information is shown. 4. To include additional configurations, repeat steps 1 to 3, but in step 2 select the cell in column A next below the last configuration in the list.
Marked config | Release introduced in TS 38.101-x | Type of configuration | TS and Source Table | Configuration | Uplink configuration | PC3 Status | PC2 completed? | RAN5 Completion Meeting (PC3) | Completion Reference (PC3) | Interested operator (PC3) | Responsible Company (contact) (PC3) | Assignment [RAN5 meeting] (PC3) | Applicable RAN5 WI code(s) for CRs | Comments | Introduced in PRD version | 列1 | 列2
| Rel-16 | EN-DC FR2 (4 bands) | 38.101-3:Table 5.5B.5.3-1 | DC_1A-3A-18A_n257A | DC_1A_n257A | Ongoing | PC3 |  |  | KDDI | KDDI (Keita Sekino) | <RAN5#99 | NR_CADC_NR_LTE_DC_R16-UEConTest | DC_001A_003A_018A_n257A | DC_001A_n257A |  | v1.0.0
| Rel-16 | EN-DC FR2 (4 bands) | 38.101-3:Table 5.5B.5.3-1 | DC_1A-3A-18A_n257A | DC_3A_n257A | Ongoing | PC3 |  |  | KDDI | KDDI (Keita Sekino) | <RAN5#99 | NR_CADC_NR_LTE_DC_R16-UEConTest | DC_001A_003A_018A_n257A | DC_003A_n257A |  | v1.0.0
| Rel-16 | EN-DC FR2 (4 bands) | 38.101-3:Table 5.5B.5.3-1 | DC_1A-3A-18A_n257A | DC_18A_n257A | Ongoing | PC3 |  |  | KDDI | KDDI (Keita Sekino) | <RAN5#99 | NR_CADC_NR_LTE_DC_R16-UEConTest | DC_001A_003A_018A_n257A | DC_018A_n257A |  | v1.0.0
| Rel-16 | EN-DC FR2 (4 bands) | 38.101-3:Table 5.5B.5.3-1 | DC_1A-3A-18A_n257I | DC_1A_n257I | Ongoing | PC3 |  |  | KDDI | KDDI (Keita Sekino) | RAN5#100 | NR_CADC_NR_LTE_DC_R16-UEConTest | DC_001A_003A_018A_n257I | DC_001A_n257I |  | v1.0.0
| Rel-16 | EN-DC FR2 (4 bands) | 38.101-3:Table 5.5B.5.3-1 | DC_1A-3A-18A_n257I | DC_3A_n257I | Ongoing | PC3 |  |  | KDDI | KDDI (Keita Sekino) | RAN5#100 | NR_CADC_NR_LTE_DC_R16-UEConTest | DC_001A_003A_018A_n257I | DC_003A_n257I |  | v1.0.0
| Rel-16 | EN-DC FR2 (4 bands) | 38.101-3:Table 5.5B.5.3-1 | DC_1A-3A-18A_n257I | DC_18A_n257I | Ongoing | PC3 |  |  | KDDI | KDDI (Keita Sekino) | RAN5#100 | NR_CADC_NR_LTE_DC_R16-UEConTest | DC_001A_003A_018A_n257I | DC_018A_n257I |  | v1.0.0
| Rel-16 | EN-DC FR2 (4 bands) | 38.101-3:Table 5.5B.5.3-1 | DC_1A-3A-41A_n257A | DC_1A_n257A | Ongoing | PC3 |  |  | KDDI | KDDI (Keita Sekino) | <RAN5#99 | NR_CADC_NR_LTE_DC_R16-UEConTest | DC_001A_003A_041A_n257A | DC_001A_n257A |  | v1.0.0
| Rel-16 | EN-DC FR2 (4 bands) | 38.101-3:Table 5.5B.5.3-1 | DC_1A-3A-41A_n257A | DC_3A_n257A | Ongoing | PC3 |  |  | KDDI | KDDI (Keita Sekino) | <RAN5#99 | NR_CADC_NR_LTE_DC_R16-UEConTest | DC_001A_003A_041A_n257A | DC_003A_n257A |  | v1.0.0
| Rel-16 | EN-DC FR2 (4 bands) | 38.101-3:Table 5.5B.5.3-1 | DC_1A-3A-41A_n257A | DC_41A_n257A | Ongoing | PC3 |  |  | KDDI | KDDI (Keita Sekino) | <RAN5#99 | NR_CADC_NR_LTE_DC_R16-UEConTest | DC_001A_003A_041A_n257A | DC_041A_n257A |  | v1.0.0
| Rel-16 | EN-DC FR2 (4 bands) | 38.101-3:Table 5.5B.5.3-1 | DC_1A-3A-41A_n257I | DC_1A_n257I | Ongoing | PC3 |  |  | KDDI | KDDI (Keita Sekino) | RAN5#100 | NR_CADC_NR_LTE_DC_R16-UEConTest | DC_001A_003A_041A_n257I | DC_001A_n257I |  | v1.0.0
| Rel-16 | EN-DC FR2 (4 bands) | 38.101-3:Table 5.5B.5.3-1 | DC_1A-3A-41A_n257I | DC_3A_n257I | Ongoing | PC3 |  |  | KDDI | KDDI (Keita Sekino) | RAN5#100 | NR_CADC_NR_LTE_DC_R16-UEConTest | DC_001A_003A_041A_n257I | DC_003A_n257I |  | v1.0.0
| Rel-16 | EN-DC FR2 (4 bands) | 38.101-3:Table 5.5B.5.3-1 | DC_1A-3A-41A_n257I | DC_41A_n257I | Ongoing | PC3 |  |  | KDDI | KDDI (Keita Sekino) | RAN5#100 | NR_CADC_NR_LTE_DC_R16-UEConTest | DC_001A_003A_041A_n257I | DC_041A_n257I |  | v1.0.0
| Rel-16 | EN-DC FR2 (3 bands) | 38.101-3:Table 5.5B.5.2-1 | DC_1A-18A_n257I | DC_1A_n257I | Ongoing | PC3 |  |  | KDDI | KDDI (Keita Sekino) | RAN5#100 | NR_CADC_NR_LTE_DC_R16-UEConTest | DC_001A_018A_n257I | DC_001A__n257I |  | v1.0.0
| Rel-16 | EN-DC FR2 (3 bands) | 38.101-3:Table 5.5B.5.2-1 | DC_1A-18A_n257I | DC_18A_n257I | Ongoing | PC3 |  |  | KDDI | KDDI (Keita Sekino) | RAN5#100 | NR_CADC_NR_LTE_DC_R16-UEConTest | DC_001A_018A_n257I | DC_018A_n257I |  | v1.0.0
| Rel-16 | EN-DC FR2 (3 bands) | 38.101-3:Table 5.5B.5.2-1 | DC_1A-41A_n257I | DC_1A_n257I | Ongoing | PC3 |  |  | KDDI | KDDI (Keita Sekino) | RAN5#100 | NR_CADC_NR_LTE_DC_R16-UEConTest | DC_001A_041A_n257I | DC_001A_n257I |  | v1.0.0
| Rel-16 | EN-DC FR2 (3 bands) | 38.101-3:Table 5.5B.5.2-1 | DC_1A-41A_n257I | DC_41A_n257I | Ongoing | PC3 |  |  | KDDI | KDDI (Keita Sekino) | RAN5#100 | NR_CADC_NR_LTE_DC_R16-UEConTest | DC_001A_041A_n257I | DC_041A_n257I |  | v1.0.0
| Rel-16 | EN-DC FR2 (3 bands) | 38.101-3:Table 5.5B.5.2-1 | DC_3A-18A_n257A | DC_3A_n257A | Ongoing | PC3 |  |  | KDDI | KDDI (Keita Sekino) | <RAN5#99 | NR_CADC_NR_LTE_DC_R16-UEConTest | DC_003A_018A_n257A | DC_003A_n257A |  | v1.0.0
| Rel-16 | EN-DC FR2 (3 bands) | 38.101-3:Table 5.5B.5.2-1 | DC_3A-18A_n257A | DC_18A_n257A | Ongoing | PC3 |  |  | KDDI | KDDI (Keita Sekino) | <RAN5#99 | NR_CADC_NR_LTE_DC_R16-UEConTest | DC_003A_018A_n257A | DC_018A_n257A |  | v1.0.0
| Rel-16 | EN-DC FR2 (3 bands) | 38.101-3:Table 5.5B.5.2-1 | DC_3A-18A_n257I | DC_3A_n257I | Ongoing | PC3 |  |  | KDDI | KDDI (Keita Sekino) | RAN5#100 | NR_CADC_NR_LTE_DC_R16-UEConTest | DC_003A_018A_n257I | DC_003A_n257I |  | v1.0.0
| Rel-16 | EN-DC FR2 (3 bands) | 38.101-3:Table 5.5B.5.2-1 | DC_3A-18A_n257I | DC_18A_n257I | Ongoing | PC3 |  |  | KDDI | KDDI (Keita Sekino) | RAN5#100 | NR_CADC_NR_LTE_DC_R16-UEConTest | DC_003A_018A_n257I | DC_018A_n257I |  | v1.0.0
| Rel-16 | EN-DC FR2 (3 bands) | 38.101-3:Table 5.5B.5.2-1 | DC_3A-41A_n257I | DC_3A_n257I | Ongoing | PC3 |  |  | KDDI | KDDI (Keita Sekino) | RAN5#100 | NR_CADC_NR_LTE_DC_R16-UEConTest | DC_003A_041A_n257I | DC_003A_n257I |  | v1.0.0
| Rel-16 | EN-DC FR2 (3 bands) | 38.101-3:Table 5.5B.5.2-1 | DC_3A-41A_n257I | DC_41A_n257I | Ongoing | PC3 |  |  | KDDI | KDDI (Keita Sekino) | RAN5#100 | NR_CADC_NR_LTE_DC_R16-UEConTest | DC_003A_041A_n257I | DC_041A_n257I |  | v1.0.0
| Rel-16 | EN-DC FR2 (2 bands) | 38.101-3:Table 5.5B.5.1-1 | DC_18A_n257I | DC_18A_n257I | Ongoing | PC3 |  |  | KDDI | KDDI (Keita Sekino) | RAN5#100 | NR_CADC_NR_LTE_DC_R16-UEConTest | DC_018A_n257I | DC_018A_n257I |  | v1.0.0

## WP EN-DC PC3 FR2
Work plan for introduction of EN-DC PC3 FR2 configurations into 3GPP UE conformance test specifications
Note! A copy of this work plan shall be included in a Completion Declaration Statement (CDS) to be submitted as a TDOC to the RAN5 meeting when the configuration(s) are completed. | [12 empty] | WP template: WP EN-DC PC3 FR2 v1.5.0
1. EN-DC configurations covered by the work plan
|  | Type of CA configurations |  |  |  | WP item Applicability Label | CA configurations [DL/UL]
|  | FR2 EN-DC configuration(s) without UL CA |  |  |  | DL/-
|  | FR2 EN-DC configurations with UL CA |  |  |  | DL/UL | DC_1A-3A-18A_n257A/DC_1A_n257A DC_1A-3A-18A_n257A/DC_3A_n257A DC_1A-3A-18A_n257A/DC_18A_n257A DC_1A-3A-18A_n257I/DC_1A_n257I DC_1A-3A-18A_n257I/DC_3A_n257I DC_1A-3A-18A_n257I/DC_18A_n257I DC_1A-3A-41A_n257A/DC_1A_n257A DC_1A-3A-41A_n257A/DC_3A_n257A DC_1A-3A-41A_n257A/DC_41A_n257A DC_1A-3A-41A_n257I/DC_1A_n257I DC_1A-3A-41A_n257I/DC_3A_n257I DC_1A-3A-41A_n257I/DC_41A_n257I DC_1A-18A_n257I/DC_1A_n257I DC_1A-18A_n257I/DC_18A_n257I DC_1A-41A_n257I/DC_1A_n257I DC_1A-41A_n257I/DC_41A_n257I DC_3A-18A_n257A/DC_3A_n257A DC_3A-18A_n257A/DC_18A_n257A DC_3A-18A_n257I/DC_3A_n257I DC_3A-18A_n257I/DC_18A_n257I DC_3A-41A_n257I/DC_3A_n257I DC_3A-41A_n257I/DC_41A_n257I DC_18A_n257I/DC_18A_n257I
|  | All configurations |  |  |  | All | DC_1A-3A-18A_n257A/DC_1A_n257A DC_1A-3A-18A_n257A/DC_3A_n257A DC_1A-3A-18A_n257A/DC_18A_n257A DC_1A-3A-18A_n257I/DC_1A_n257I DC_1A-3A-18A_n257I/DC_3A_n257I DC_1A-3A-18A_n257I/DC_18A_n257I DC_1A-3A-41A_n257A/DC_1A_n257A DC_1A-3A-41A_n257A/DC_3A_n257A DC_1A-3A-41A_n257A/DC_41A_n257A DC_1A-3A-41A_n257I/DC_1A_n257I DC_1A-3A-41A_n257I/DC_3A_n257I DC_1A-3A-41A_n257I/DC_41A_n257I DC_1A-18A_n257I/DC_1A_n257I DC_1A-18A_n257I/DC_18A_n257I DC_1A-41A_n257I/DC_1A_n257I DC_1A-41A_n257I/DC_41A_n257I DC_3A-18A_n257A/DC_3A_n257A DC_3A-18A_n257A/DC_18A_n257A DC_3A-18A_n257I/DC_3A_n257I DC_3A-18A_n257I/DC_18A_n257I DC_3A-41A_n257I/DC_3A_n257I DC_3A-41A_n257I/DC_41A_n257I DC_18A_n257I/DC_18A_n257I
2. Overall status vs WP steps
[7 empty] | Overall Sub-WI |  | Handling of not applicable WP item rows: - WP item rows not applicable for the target configurations are indicated as being strikethrough text. You can hide those not applicable WP items by filtering on excluding "(Blanks)" in column "Impacted config(s)". - Some WP items may still not be applicable for the target configurations based on the applicability information in the "Task" column. To NOT include those WP items in the overall status calculations You need to clear the "Detailed Completion Status" cells for the WP item row and state "N/A" in the comments field. Note: It is not recomended to completly delete not applicable WP item rows in case additional target configurations added at a later stage may require those WP Item rows.
|  | Overall completeness |  |  |  |  | 100%
|  | Step 1: Work plan pre-requisite |  |  |  |  | 100%
Step 2: Complete Test Point (TP) analysis for impacted EN-DC configurations
|  | Step 3.1: CR(s) to common test environment (TS 38.508-1) |  |  |  |  | 100%
|  | Step 3.2: CR(s) to common clauses for RF / Performance testing area (TS 38.521-3) |  |  |  |  | 100%
Step 3.3: CR(s) for RF transmitter test cases (TS 38.521-3, clause 6)
Step 3.4: CR(s) for RF receiver test cases (TS 38.521-3, clause 7)
Step 3.5: CR(s) for RF Performance test cases (TS 38.521-4)
Step 3.6: CRs to protocol test cases (TS 38.523-1, TS 38.523-2)
|  | Step 4: CR(s) for new ICS/capabilities (TS 38.508-2) |  |  |  |  | 100%
3. Details
[8 empty] | WP item columns to be filled in |  |  |  | Do not edit |  | WP item columns to be filled in
Step 1: Work plan pre-requisite
WP item applicability | WP item ID | Area | TS/PRD | TC / Clause Number | Description / Title | Impacted config(s) [DL/UL] | Task | Company | Target | TDOC(s) | Comments | Weight | Item Overall Completeness | Detailed Completion Status per area
[14 empty] | Bands completed | CA completed
[14 empty] | 1 | 1
All | 1-1 | Pre-requisite | PRD21 | NR bands worksheet | All NR bands within the WP scope are completed | DC_1A-3A-18A_n257A/DC_1A_n257A DC_1A-3A-18A_n257A/DC_3A_n257A DC_1A-3A-18A_n257A/DC_18A_n257A DC_1A-3A-18A_n257I/DC_1A_n257I DC_1A-3A-18A_n257I/DC_3A_n257I DC_1A-3A-18A_n257I/DC_18A_n257I DC_1A-3A-41A_n257A/DC_1A_n257A DC_1A-3A-41A_n257A/DC_3A_n257A DC_1A-3A-41A_n257A/DC_41A_n257A DC_1A-3A-41A_n257I/DC_1A_n257I DC_1A-3A-41A_n257I/DC_3A_n257I DC_1A-3A-41A_n257I/DC_41A_n257I DC_1A-18A_n257I/DC_1A_n257I DC_1A-18A_n257I/DC_18A_n257I DC_1A-41A_n257I/DC_1A_n257I DC_1A-41A_n257I/DC_41A_n257I DC_3A-18A_n257A/DC_3A_n257A DC_3A-18A_n257A/DC_18A_n257A DC_3A-18A_n257I/DC_3A_n257I DC_3A-18A_n257I/DC_18A_n257I DC_3A-41A_n257I/DC_3A_n257I DC_3A-41A_n257I/DC_41A_n257I DC_18A_n257I/DC_18A_n257I | Set status in column "Bands completed" to 100% when all impacted NR bands have been confirmed completed in PRD21 worksheet "NR bands". |  | TBD |  | Already existing. | 1 | 100% | 100%
All | 1-1.1 | Pre-requisite | PRD21 | 5G NR CADC Configurations | All NR CA sub-configurations included in the EN-DC configurations within the WP scope are completed | DC_1A-3A-18A_n257A/DC_1A_n257A DC_1A-3A-18A_n257A/DC_3A_n257A DC_1A-3A-18A_n257A/DC_18A_n257A DC_1A-3A-18A_n257I/DC_1A_n257I DC_1A-3A-18A_n257I/DC_3A_n257I DC_1A-3A-18A_n257I/DC_18A_n257I DC_1A-3A-41A_n257A/DC_1A_n257A DC_1A-3A-41A_n257A/DC_3A_n257A DC_1A-3A-41A_n257A/DC_41A_n257A DC_1A-3A-41A_n257I/DC_1A_n257I DC_1A-3A-41A_n257I/DC_3A_n257I DC_1A-3A-41A_n257I/DC_41A_n257I DC_1A-18A_n257I/DC_1A_n257I DC_1A-18A_n257I/DC_18A_n257I DC_1A-41A_n257I/DC_1A_n257I DC_1A-41A_n257I/DC_41A_n257I DC_3A-18A_n257A/DC_3A_n257A DC_3A-18A_n257A/DC_18A_n257A DC_3A-18A_n257I/DC_3A_n257I DC_3A-18A_n257I/DC_18A_n257I DC_3A-41A_n257I/DC_3A_n257I DC_3A-41A_n257I/DC_41A_n257I DC_18A_n257I/DC_18A_n257I | Set status in column "CA completed" to 100% when all NR CA sub-configurations included in the WP scope's EN-DC configurations are listed as completed in RAN5 PRD21 worksheet "5G NR CADC Configurations". |  | TBD |  | Already existing. | 1 | 100% |  | 100%
All | 1-2 | Pre-requisite | 36.521-2 | Annex A | All E-UTRA bands within the WP scope are completed | DC_1A-3A-18A_n257A/DC_1A_n257A DC_1A-3A-18A_n257A/DC_3A_n257A DC_1A-3A-18A_n257A/DC_18A_n257A DC_1A-3A-18A_n257I/DC_1A_n257I DC_1A-3A-18A_n257I/DC_3A_n257I DC_1A-3A-18A_n257I/DC_18A_n257I DC_1A-3A-41A_n257A/DC_1A_n257A DC_1A-3A-41A_n257A/DC_3A_n257A DC_1A-3A-41A_n257A/DC_41A_n257A DC_1A-3A-41A_n257I/DC_1A_n257I DC_1A-3A-41A_n257I/DC_3A_n257I DC_1A-3A-41A_n257I/DC_41A_n257I DC_1A-18A_n257I/DC_1A_n257I DC_1A-18A_n257I/DC_18A_n257I DC_1A-41A_n257I/DC_1A_n257I DC_1A-41A_n257I/DC_41A_n257I DC_3A-18A_n257A/DC_3A_n257A DC_3A-18A_n257A/DC_18A_n257A DC_3A-18A_n257I/DC_3A_n257I DC_3A-18A_n257I/DC_18A_n257I DC_3A-41A_n257I/DC_3A_n257I DC_3A-41A_n257I/DC_41A_n257I DC_18A_n257I/DC_18A_n257I | Set status in column "Bands completed" to 100% when all impacted E-UTRA bands have been confirmed completed in RAN5 TSs and TRs. |  | TBD |  | Already existing. | 1 | 100% | 100%
All | 1-3 | Pre-requisite | PRD20 | E-UTRA CA list work sheet | All E-UTRA CA configurations included in the EN-DC configurations within the WP scope are completed | DC_1A-3A-18A_n257A/DC_1A_n257A DC_1A-3A-18A_n257A/DC_3A_n257A DC_1A-3A-18A_n257A/DC_18A_n257A DC_1A-3A-18A_n257I/DC_1A_n257I DC_1A-3A-18A_n257I/DC_3A_n257I DC_1A-3A-18A_n257I/DC_18A_n257I DC_1A-3A-41A_n257A/DC_1A_n257A DC_1A-3A-41A_n257A/DC_3A_n257A DC_1A-3A-41A_n257A/DC_41A_n257A DC_1A-3A-41A_n257I/DC_1A_n257I DC_1A-3A-41A_n257I/DC_3A_n257I DC_1A-3A-41A_n257I/DC_41A_n257I DC_1A-18A_n257I/DC_1A_n257I DC_1A-18A_n257I/DC_18A_n257I DC_1A-41A_n257I/DC_1A_n257I DC_1A-41A_n257I/DC_41A_n257I DC_3A-18A_n257A/DC_3A_n257A DC_3A-18A_n257A/DC_18A_n257A DC_3A-18A_n257I/DC_3A_n257I DC_3A-18A_n257I/DC_18A_n257I DC_3A-41A_n257I/DC_3A_n257I DC_3A-41A_n257I/DC_41A_n257I DC_18A_n257I/DC_18A_n257I | Set status in column "E-UTRA CA completed" to 100% when all E-UTRA CA sub-configurations included in the WP EN-DC configurations are listed as completed in RAN5 PRD20. |  | TBD |  | Already existing. | 1 | 100% |  | 100%
End list sub-area WP items (insert any additional WP items for this area above this row)
Step 2: Complete Test Point (TP) analysis for impacted EN-DC configurations
WP item applicability | WP item ID | Area | TR | TC / Clause Number | Description / Title | Impacted CA config(s) [UDL/UL] | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | Item Overall Completeness | Detailed Completion Status per area
TP analysis
1
DL/UL | 2-1 | TP Analysis | 38.905 | 4.3 | Test point (TP) analysis for MOP | DC_1A-3A-18A_n257A/DC_1A_n257A DC_1A-3A-18A_n257A/DC_3A_n257A DC_1A-3A-18A_n257A/DC_18A_n257A DC_1A-3A-18A_n257I/DC_1A_n257I DC_1A-3A-18A_n257I/DC_3A_n257I DC_1A-3A-18A_n257I/DC_18A_n257I DC_1A-3A-41A_n257A/DC_1A_n257A DC_1A-3A-41A_n257A/DC_3A_n257A DC_1A-3A-41A_n257A/DC_41A_n257A DC_1A-3A-41A_n257I/DC_1A_n257I DC_1A-3A-41A_n257I/DC_3A_n257I DC_1A-3A-41A_n257I/DC_41A_n257I DC_1A-18A_n257I/DC_1A_n257I DC_1A-18A_n257I/DC_18A_n257I DC_1A-41A_n257I/DC_1A_n257I DC_1A-41A_n257I/DC_41A_n257I DC_3A-18A_n257A/DC_3A_n257A DC_3A-18A_n257A/DC_18A_n257A DC_3A-18A_n257I/DC_3A_n257I DC_3A-18A_n257I/DC_18A_n257I DC_3A-41A_n257I/DC_3A_n257I DC_3A-41A_n257I/DC_41A_n257I DC_18A_n257I/DC_18A_n257I | No TP analysis requiered for specific EN-DC FR2 configurations |  |  |  | No changes are needed. | 1
End list sub-area WP items (insert any additional WP items for this area above this row)
Step 3: CRs to impacted TSs areas
Step 3.1: CR(s) to common test environment (TS 38.508-1)
WP item applicability | WP item ID | Area | TS | TC / Clause Number | Description / Title | Impacted CA config(s) [UDL/UL] | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | Item Overall Completeness | Detailed Completion Status per area
Test Freq.
1
All | 3.1-1 | 38.508-1 - (4) Common | 38.508-1 | 4.3.1.x | NR Test frequencies | DC_1A-3A-18A_n257A/DC_1A_n257A DC_1A-3A-18A_n257A/DC_3A_n257A DC_1A-3A-18A_n257A/DC_18A_n257A DC_1A-3A-18A_n257I/DC_1A_n257I DC_1A-3A-18A_n257I/DC_3A_n257I DC_1A-3A-18A_n257I/DC_18A_n257I DC_1A-3A-41A_n257A/DC_1A_n257A DC_1A-3A-41A_n257A/DC_3A_n257A DC_1A-3A-41A_n257A/DC_41A_n257A DC_1A-3A-41A_n257I/DC_1A_n257I DC_1A-3A-41A_n257I/DC_3A_n257I DC_1A-3A-41A_n257I/DC_41A_n257I DC_1A-18A_n257I/DC_1A_n257I DC_1A-18A_n257I/DC_18A_n257I DC_1A-41A_n257I/DC_1A_n257I DC_1A-41A_n257I/DC_41A_n257I DC_3A-18A_n257A/DC_3A_n257A DC_3A-18A_n257A/DC_18A_n257A DC_3A-18A_n257I/DC_3A_n257I DC_3A-18A_n257I/DC_18A_n257I DC_3A-41A_n257I/DC_3A_n257I DC_3A-41A_n257I/DC_41A_n257I DC_18A_n257I/DC_18A_n257I | - Add the EN-DC configuration to the relevant test frequency table in clause 4.3.1.5 - Check that the involved NR bands have single carrier test frequencies specified in 4.3.1.2.1 - For EN-DC configurations including any intra-band EN-DC contiguous CCs or any intra-band EN-DC non-contiguous CCs check if existing test frequencies can be re-used or if new test frequencies need to be specified in in clause clause 4.3.1.2.x. |  | TBD | R5-232338, R5-234076 |  | 1 | 100% | 100%
All | 3.1-2 | 38.508-1 - (4) Common | 38.508-1 | 4.3.1.x | EN-DC band combination test frequencies | DC_1A-3A-18A_n257A/DC_1A_n257A DC_1A-3A-18A_n257A/DC_3A_n257A DC_1A-3A-18A_n257A/DC_18A_n257A DC_1A-3A-18A_n257I/DC_1A_n257I DC_1A-3A-18A_n257I/DC_3A_n257I DC_1A-3A-18A_n257I/DC_18A_n257I DC_1A-3A-41A_n257A/DC_1A_n257A DC_1A-3A-41A_n257A/DC_3A_n257A DC_1A-3A-41A_n257A/DC_41A_n257A DC_1A-3A-41A_n257I/DC_1A_n257I DC_1A-3A-41A_n257I/DC_3A_n257I DC_1A-3A-41A_n257I/DC_41A_n257I DC_1A-18A_n257I/DC_1A_n257I DC_1A-18A_n257I/DC_18A_n257I DC_1A-41A_n257I/DC_1A_n257I DC_1A-41A_n257I/DC_41A_n257I DC_3A-18A_n257A/DC_3A_n257A DC_3A-18A_n257A/DC_18A_n257A DC_3A-18A_n257I/DC_3A_n257I DC_3A-18A_n257I/DC_18A_n257I DC_3A-41A_n257I/DC_3A_n257I DC_3A-41A_n257I/DC_41A_n257I DC_18A_n257I/DC_18A_n257I | For EN-DC Inter-band configurations add the CA configuration to the relevant table in one of the clauses in clause 4.3.1.5. |  | TBD | R5-232338, R5-234076 |  | 1 | 100% | 100%
All | 3.1-3 | 38.508-1 - (6) Common SIG | 38.508-1 | 6.2.3.2 | Test frequencies for EN_DC signalling test | DC_1A-3A-18A_n257A/DC_1A_n257A DC_1A-3A-18A_n257A/DC_3A_n257A DC_1A-3A-18A_n257A/DC_18A_n257A DC_1A-3A-18A_n257I/DC_1A_n257I DC_1A-3A-18A_n257I/DC_3A_n257I DC_1A-3A-18A_n257I/DC_18A_n257I DC_1A-3A-41A_n257A/DC_1A_n257A DC_1A-3A-41A_n257A/DC_3A_n257A DC_1A-3A-41A_n257A/DC_41A_n257A DC_1A-3A-41A_n257I/DC_1A_n257I DC_1A-3A-41A_n257I/DC_3A_n257I DC_1A-3A-41A_n257I/DC_41A_n257I DC_1A-18A_n257I/DC_1A_n257I DC_1A-18A_n257I/DC_18A_n257I DC_1A-41A_n257I/DC_1A_n257I DC_1A-41A_n257I/DC_41A_n257I DC_3A-18A_n257A/DC_3A_n257A DC_3A-18A_n257A/DC_18A_n257A DC_3A-18A_n257I/DC_3A_n257I DC_3A-18A_n257I/DC_18A_n257I DC_3A-41A_n257I/DC_3A_n257I DC_3A-41A_n257I/DC_41A_n257I DC_18A_n257I/DC_18A_n257I | For Intra-band contiguous or intra-band non-contiguous configurations with 2CC add test frequencies in clause 6.2.3.2. |  | TBD |  | Not applicable. | 1
End list sub-area WP items (insert any additional WP items for this area above this row)
Step 3.2: CR(s) to common clauses for RF / Performance testing area (TS 38.521-3)
WP item applicability | WP item ID | Area | TS | TC / Clause Number | Description / Title | Impacted CA config(s) [UDL/UL] | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | Item Overall Completeness | Detailed Completion Status per area
Clause 5
1
All | 3.2-3 | 36.521-3 - General | 38.521-3 | 5.5B.5 | Inter-band EN-DC | DC_1A-3A-18A_n257A/DC_1A_n257A DC_1A-3A-18A_n257A/DC_3A_n257A DC_1A-3A-18A_n257A/DC_18A_n257A DC_1A-3A-18A_n257I/DC_1A_n257I DC_1A-3A-18A_n257I/DC_3A_n257I DC_1A-3A-18A_n257I/DC_18A_n257I DC_1A-3A-41A_n257A/DC_1A_n257A DC_1A-3A-41A_n257A/DC_3A_n257A DC_1A-3A-41A_n257A/DC_41A_n257A DC_1A-3A-41A_n257I/DC_1A_n257I DC_1A-3A-41A_n257I/DC_3A_n257I DC_1A-3A-41A_n257I/DC_41A_n257I DC_1A-18A_n257I/DC_1A_n257I DC_1A-18A_n257I/DC_18A_n257I DC_1A-41A_n257I/DC_1A_n257I DC_1A-41A_n257I/DC_41A_n257I DC_3A-18A_n257A/DC_3A_n257A DC_3A-18A_n257A/DC_18A_n257A DC_3A-18A_n257I/DC_3A_n257I DC_3A-18A_n257I/DC_18A_n257I DC_3A-41A_n257I/DC_3A_n257I DC_3A-41A_n257I/DC_41A_n257I DC_18A_n257I/DC_18A_n257I | Add inter-band EN-DC configurations within FR2 to the relevant table in clause 5.5B.5. Note! - Check if changes should be merged into "jumbo" CR (email sent out before meeting by responsible "jumbo" CR author). - Changes to common clauses in chapter 5 are excluded from the requirement to submit a discussion paper to justify why no changes are needed to chapter 6 and 7 (ref. PRD21 section 4.1, item 14). |  | TBD | R5-233183, R5-235675 |  | 1 | 100% | 100%
End list sub-area WP items (insert any additional WP items for this area above this row)
Step 3.3: CR(s) for RF transmitter test cases (TS 38.521-3, clause 6)
WP item applicability | WP item ID | Area | TS | TC / Clause Number | Description / Title | Impacted CA config(s) [UDL/UL] | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | Item Overall Completeness | Detailed Completion Status per area
[14 empty] | TCs available |  |  |  | Other Areas
[14 empty] | 1 |  |  |  | 2
DL/UL | 3.3-1 | 38.521-3 - RF Tx | 38.521-3 | 6.x | Tx test cases for EN_DC with NR FR2 >=1CC | DC_1A-3A-18A_n257A/DC_1A_n257A DC_1A-3A-18A_n257A/DC_3A_n257A DC_1A-3A-18A_n257A/DC_18A_n257A DC_1A-3A-18A_n257I/DC_1A_n257I DC_1A-3A-18A_n257I/DC_3A_n257I DC_1A-3A-18A_n257I/DC_18A_n257I DC_1A-3A-41A_n257A/DC_1A_n257A DC_1A-3A-41A_n257A/DC_3A_n257A DC_1A-3A-41A_n257A/DC_41A_n257A DC_1A-3A-41A_n257I/DC_1A_n257I DC_1A-3A-41A_n257I/DC_3A_n257I DC_1A-3A-41A_n257I/DC_41A_n257I DC_1A-18A_n257I/DC_1A_n257I DC_1A-18A_n257I/DC_18A_n257I DC_1A-41A_n257I/DC_1A_n257I DC_1A-41A_n257I/DC_41A_n257I DC_3A-18A_n257A/DC_3A_n257A DC_3A-18A_n257A/DC_18A_n257A DC_3A-18A_n257I/DC_3A_n257I DC_3A-18A_n257I/DC_18A_n257I DC_3A-41A_n257I/DC_3A_n257I DC_3A-41A_n257I/DC_41A_n257I DC_18A_n257I/DC_18A_n257I | For EN-DC FR2 with 1 CC NR band; Set status of "TCs available" to 100% if all the NR single carrier FR2 Tx test cases in TS 38.521-2 for the NR band, as referenced by the applicable Tx test cases for EN-DC FR2 with 1CC NR in TS 38.521-3, are completed. For EN-DC FR2 with xCC NR CA; Set status of "TCs available" to 100% if all the NR CA Tx test cases in TS 38.521-2 for the xCC NR CA, as referenced by the applicable applicable Tx test cases for EN-DC FR2 with xCC NR CA in TS 38.521-3, are completed. No specific changes are needed in the EN-DC FR2 Tx test cases for the specific EN-DC FR2 configurations in TS 38.521-3. |  | TBD |  | No changes are needed. | 1
End list sub-area WP items (insert any additional WP items for this area above this row)
Step 3.4: CR(s) for RF receiver test cases (TS 38.521-3, clause 7)
WP item applicability | WP item ID | Area | TS | TC / Clause Number | Description / Title | Impacted CA config(s) [UDL/UL] | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | Item Overall Completeness | Detailed Completion Status per area
[14 empty] | TCs available |  |  |  | Other Areas
[14 empty] | 1 |  |  |  | 2
All | 3.4-1 | 36.521-3-RF Rx | 38.521-3 | 7.x | Rx test cases for EN_DC with NR FR2 >=1CC | DC_1A-3A-18A_n257A/DC_1A_n257A DC_1A-3A-18A_n257A/DC_3A_n257A DC_1A-3A-18A_n257A/DC_18A_n257A DC_1A-3A-18A_n257I/DC_1A_n257I DC_1A-3A-18A_n257I/DC_3A_n257I DC_1A-3A-18A_n257I/DC_18A_n257I DC_1A-3A-41A_n257A/DC_1A_n257A DC_1A-3A-41A_n257A/DC_3A_n257A DC_1A-3A-41A_n257A/DC_41A_n257A DC_1A-3A-41A_n257I/DC_1A_n257I DC_1A-3A-41A_n257I/DC_3A_n257I DC_1A-3A-41A_n257I/DC_41A_n257I DC_1A-18A_n257I/DC_1A_n257I DC_1A-18A_n257I/DC_18A_n257I DC_1A-41A_n257I/DC_1A_n257I DC_1A-41A_n257I/DC_41A_n257I DC_3A-18A_n257A/DC_3A_n257A DC_3A-18A_n257A/DC_18A_n257A DC_3A-18A_n257I/DC_3A_n257I DC_3A-18A_n257I/DC_18A_n257I DC_3A-41A_n257I/DC_3A_n257I DC_3A-41A_n257I/DC_41A_n257I DC_18A_n257I/DC_18A_n257I | For EN-DC FR2 with 1 CC NR band; Set status of "TCs available" to 100% if all the NR single carrier FR2 Rx test cases in TS 38.521-2 for the NR band, as referenced by the applicable Rx test cases for EN-DC FR2 with 1CC NR in TS 38.521-3, are completed. For EN-DC FR2 with xCC NR CA; Set status of "TCs available" to 100% if all the NR CA Rx test cases in TS 38.521-2 for the xCC NR CA, as referenced by the applicable applicable Rx test cases for EN-DC FR2 with xCC NR CA in TS 38.521-3, are completed. No specific changes are needed in the EN-DC FR2 Rx test cases for the specific EN-DC FR2 configurations in TS 38.521-3. |  | TBD |  | No changes are needed. | 1
End list sub-area WP items (insert any additional WP items for this area above this row)
Step 3.5: CR(s) for RF Performance test cases (TS 38.521-4)
WP item applicability | WP item ID | Area | TS | TC / Clause Number | Description / Title | Impacted CA config(s) [UDL/UL] | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | Item Overall Completeness | Detailed Completion Status per area
[14 empty] | Min. Req. | Test proc. | Test Pts | Test Req | Other Areas
[14 empty] | 1 | 5 | 5 | 2 | 2
| 3.5-1 | [5 empty] | No changes needed |  | TBD |  |  | 1
End list sub-area WP items (insert any additional WP items for this area above this row)
Step 3.6: CRs to protocol test cases (TS 38.523-1, TS 38.523-2)
WP item applicability | WP item ID | Area | TS | TC / Clause Number | Description / Title | Impacted CA config(s) [UDL/UL] | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | Item Overall Completeness | Detailed Completion Status per area
ICS / TC appli.
1
| 3.6-1 | [5 empty] | No changes needed |  | TBD |  |  | 1
End list sub-area WP items (insert any additional WP items for this area above this row)
Step 4: CR(s) for new ICS/capabilities (TS 38.508-2)
WP item applicability | WP item ID | Area | TS | TC / Clause Number | Description / Title | Impacted CA config(s) [UDL/UL] | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | Item Overall Completeness | Detailed Completion Status per area
ICS / TC appli.
1
All | 4-1 | 38.508-2 - ICS | 38.508-2 | Annex A.4.3.2B.x | Inter-band EN-DC including FR2 | DC_1A-3A-18A_n257A/DC_1A_n257A DC_1A-3A-18A_n257A/DC_3A_n257A DC_1A-3A-18A_n257A/DC_18A_n257A DC_1A-3A-18A_n257I/DC_1A_n257I DC_1A-3A-18A_n257I/DC_3A_n257I DC_1A-3A-18A_n257I/DC_18A_n257I DC_1A-3A-41A_n257A/DC_1A_n257A DC_1A-3A-41A_n257A/DC_3A_n257A DC_1A-3A-41A_n257A/DC_41A_n257A DC_1A-3A-41A_n257I/DC_1A_n257I DC_1A-3A-41A_n257I/DC_3A_n257I DC_1A-3A-41A_n257I/DC_41A_n257I DC_1A-18A_n257I/DC_1A_n257I DC_1A-18A_n257I/DC_18A_n257I DC_1A-41A_n257I/DC_1A_n257I DC_1A-41A_n257I/DC_41A_n257I DC_3A-18A_n257A/DC_3A_n257A DC_3A-18A_n257A/DC_18A_n257A DC_3A-18A_n257I/DC_3A_n257I DC_3A-18A_n257I/DC_18A_n257I DC_3A-41A_n257I/DC_3A_n257I DC_3A-41A_n257I/DC_41A_n257I DC_18A_n257I/DC_18A_n257I | Add band combinations for inter-band EN-DC including FR2 to the relevant table in Column A.4.3.2B.2.6~A.4.3.2B.2.9 A.4.3.2B.2.11~A.4.3.2B.2.9 |  | TBD | R5-232363, R5-234077 |  | 1 | 100% | 100%
End list sub-area WP items (insert any additional WP items for this area above this row)
Note on N27: Used to calculate item's relative impact on work item's completeness. Should be set from a WI overall perspective. Default value is 1.
Note on N37: Used to calculate item's relative impact on work item's completeness. Should be set from a WI overall perspective. Default value is 1.
Note on N45: Used to calculate item's relative impact on work item's completeness. Should be set from a WI overall perspective. Default value is 1. If a more work intesive item is added set to value >1.
Note on N54: Used to calculate item's relative impact on work item's completeness. Should be set from a WI overall perspective. Default value is 1.
Note on N61: Used to calculate item's relative impact on work item's completeness. Should be set from a WI overall perspective. Default value is 1.
Note on N68: Used to calculate item's relative impact on work item's completeness. Should be set from a WI overall perspective. Default value is 1.
Note on N75: Used to calculate item's relative impact on work item's completeness. Should be set from a WI overall perspective. Default value is 1.
Note on N82: Used to calculate item's relative impact on work item's completeness. Should be set from a WI overall perspective. Default value is 1.
Note on N89: Used to calculate item's relative impact on work item's completeness. Should be set from a WI overall perspective. Default value is 1.

## Revision History WP template
Revision history for WP template only Note! Cell A3 shall always include the version of the latest version of the WP as used to set the WP template version in the WP scope worksheet.
Version | Date | Comment
v1.5.0 | RAN5#99 | 1. Editorial correction to WP item 1-2 Column E TS/PRD to "36.521-2" instead of "38.521-3"
v1.4.0 | RAN5#98 | No changes. Same as v1.3.0.
v1.3.0 | RAN5#97 | No changes. Same as v1.2.0.
v1.2.0 | RAN5#96-e | 1. Extended the number of rows in the input table to cope with the case when multiple cut and paste of configurations from PRD21 CADC list are done.
v1.1.0 | RAN5#95-e | 1. Updated WP template version in WP scope worksheet to get version number from cell A3 in the "Revision History WP template" worksheet. 2. Correcting TS reference in "area" and "TS" columns from 36.521-1 to 38.521-1. 3. Added a note to WP-item 3.2-3 to remind about merge with "jumbo" CR and that the requirement in PRD21 section 4.1 item 14 on submitting a discussion paper to allow adding configuration details to chapter 5 without changes to chapter 6 and 7 is not applciable for EN-DC inter-band configurations with NR FR2. 4. Added WP item 1-1.1 to check that sub-NR CA configurations have been completed as part of WP pre-requisite.
v1.0.0 | RAN5#94-e | Initial version