## Cover sheet
3GPP TSG-RAN5 Meeting #100 | [8 empty] | R5-234268
Toulouse, France, Aug 21-25, 2023
Agenda Item: | 7.4.2
Source: | Qualcomm
Title: | WP UE Conformance Test Aspects - Solutions for NR to support non-terrestrial networks (NTN)
Work item code: | NR_NTN_solutions_plus_CT-UEConTest
Release: | Rel-17
Document for: | Information
RAN5 WP template v2.0
1. Introduction
<Description of work item and its scope>
2. Work item status
Estimation of WI overall completion:
Area |  | Completion | Number of new completed test cases (Note 1) | Number of new test cases | Comments
Overall completion |  | 50% (+17%) | 0 | 65 (+1)
Completion Compensation |  | -
| Note 1: | Only test cases completed for all applicable WP areas and sub-areas are counted. For completed test cases per WP areas and WP sub-areas see below.
Estimation WI completion per area and sub-area:
|  | Completion | Number of new completed test cases | Number of new test cases | Comments
SA Option 2 (SA NR) (FR1) |  | 49.9% (+17.4%) | 0 | 65 (+1)
FR1 |  | 49.9% (+17.4%) | 0 | 65 (+1)
Estimation of completion per TS (area):
|  | TS/TR overall completion |  |  | SA Option 2 (SA NR)
TS/TR Scope | TS/TR | Completion | Number of new completed test cases | Number of new test cases | FR1
[5 empty] | Completion | Number of new completed test cases | Number of new test cases
5GS
5GS Common
Common test environment | 38.508-1 | 50% (+15%) |  |  | 50% (+15%)
Common ICS | 38.508-2 | 50% (+40%) |  |  | 50% (+40%)
UE specific testing functions | 38.509 | 100% (+100%) |  |  | 100% (+100%)
Conducted RF Transmitter Test cases | 38.521-5 | 70.8% (+32.7%) | 0 | 28 (-22) | 70.8% (+32.7%) | 0 | 28 (-22)
Protocol Test Cases | 38.523-1 | 5.3% (+5.3%) | 0 | 14 | 5.3% (+5.3%) | 0 | 14
5 References
[1] RP-221299 | New WID on UE Conformance - Further enhancement on NR demodulation performance
[2] R5-231336 | WP UE Conformance Test Aspects - Solutions for NR to support non-terrestrial networks (NTN)
[2] R5-232846 | WP UE Conformance Test Aspects - Solutions for NR to support non-terrestrial networks (NTN)
Note on B21: Overall completion of the work item reported at an earlier meeting will not be decreased if additional tasks are added or if corrections are made to the work plan. Instead the earlier reported completion status will be kept until necessary progress have been achieved such that completion exceeds the earlier reported completion level. The value of the Completion Compensation value represents the difference in the decrease caused by late additions or corrections to the work plan and the current estimated overall completion. '-' indicates that no compensation is applied.

## WP
WP Title: |  | UE Conformance- Solutions for NR to support non-terrestrial networks (NTN) | [10 empty] | Start of workplan status columns. Note! Do not remove this column. | WP item status | End of workplan columns. Note! Do not remove this column.
WI code |  | NR_NTN_solutions_plus_CT-UEConTest
WP Scope: |  | This part of the work plan covers all applicable test cases for Solutions for NR to support non-terrestrial networks (NTN) Work item
WP Resp: |  | Vijay Balasubramanian |  |  | vijayb@qti.qualcomm.com | [5 empty] | WP item completion |  |  | SA Option 2 (SA NR)
TS Resp: |  | Vijay Balasubramanian |  |  | vijayb@qti.qualcomm.com
WP Item ID | Is new test case? | TS/area | Clause | Title | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | Overall | SA Option 2 (SA NR) |  | FR1
49.9% (+17.4%)
121 (+30)
110.6 (+35.8)
5%
Start of work plan items. Note! Do not remove this row. Introduce new work plan rows/items below this row.
5GS
5GS Common
TS 38.508-1: Common test environment
1 |  | 38.508-1 | 4, 6 | Introduction of General and RF Demod Test Environment for Rel17 NTN solutions |  | Google, Qualcomm |  | R5-227480 R5-230882, R5-230884 R5-225352 R5-225353 R5-225354 R5-225355 R5-233434 R5-233435 R5-233436 R5-232693 R5-233369 R5-232520 R5-235336 R5-235951 |  | 1 | 50% | 50% |  | 50%
TS 38.508-2: Common ICS
2 |  | 38.508-2 | TBD | Introduction of common implementation conformance statements for Rel-17 NTN solutions |  | Qualcomm |  | R5-226551 |  | 1 | 50% | 50% |  | 50%
TS 38.509: UE specific testing functions
62 |  | 38.509 | TBD |  |  | Qualcomm |  |  | No change needed | 1 | 100% | 100% (+100%) |  | 100%
TS 38.521-5: Conducted RF Transmitter Test cases
3 |  | 38.521-5 | 4 | General |  | Qualcomm | RAN5#97 (Nov-22) | R5-226639 R5-226640 |  | 0.2 | 50% | 100% |  | 100%
4 |  | 38.521-5 | 5 | Operating bands and channel arrangement |  | Qualcomm | RAN5#97 (Nov-22) | R5-226641 |  | 0.2 | 50% | 100% |  | 100%
5 |  | 38.521-5 | 5.1 | General |  | Qualcomm | RAN5#97 (Nov-22) | R5-226641 |  | 0.2 | 50% | 100% |  | 100%
6 |  | 38.521-5 | 5.2 | Operating bands |  | Qualcomm | RAN5#97 (Nov-22) | R5-226641 |  | 0.2 | 50% | 100% |  | 100%
7 |  | 38.521-5 | 5.3 | UE Channel Bandwidth |  | Qualcomm | RAN5#97 (Nov-22) | R5-226641 |  | 0.2 | 50% | 100% |  | 100%
8 |  | 38.521-5 | 5.4 | Channel arrangment |  | Qualcomm | RAN5#97 (Nov-22) | R5-226641 |  | 0.2 | 50% | 100% |  | 100%
9 |  | 38.521-5 | 6 | Conducted Transmitter characteristics |  | Google | RAN5#97 (Nov-22) | R5-227885 |  | 0.2 | 50% | 100% |  | 100%
10 |  | 38.521-5 | 6.1 | General |  | Google, Keysight | RAN5#97 (Nov-22) | R5-227885 R5-235456 |  | 20 | 100% | 100% |  | 100%
11 |  | 38.521-5 | 6.2 | Transmitter Power |  | Google | RAN5#97 (Nov-22) | R5-227885 |  | 0.2 | 50% | 100% |  | 100%
12 | Y | 38.521-5 | 6.2.1 | UE maximum output power |  | Google | RAN5#97 (Nov-22) | R5-227885, R5-231854 R5-235186 | Editor’s Note: - Addition to applicability spec is pending - Initial condition and Test procedure to support NR satellite access is TBD - Message exceptions specific to satellite access is TBD - Annex F MU/TT is TBD | 1 | 60% | 60% |  | 60%
13 | Y | 38.521-5 | 6.2.2 | UE maximum output power reduction |  | Google | RAN5#97 (Nov-22) | R5-227886. R5-231854 R5-235186 | Editor’s Note: - Addition to applicability spec is pending - Initial condition and Test procedure to support NR satellite access is TBD - Message exceptions specific to satellite access is TBD - Annex F MU/TT is TBD | 1 | 60% | 60% |  | 60%
14 | Y | 38.521-5 | 6.2.3 | UE additional maximum output power reduction |  | Google | RAN5#98 (Feb-23) | R5-233569 R5-234627 R5-235186 | Editor’s Note: This clause is incomplete. The following aspects are either missing or not yet determined: - Addition to applicability spec is pending - Initial condition and call setup procedure to support NR satellite access are TBD - Message exceptions specific to satellite access is TBD - Annex F MU/TT is TBD | 1 | 60% | 60% (+20%) |  | 60%
15 | Y | 38.521-5 | 6.2.4 | Configured transmitted power |  | Google | RAN5#97 (Nov-22) | R5-232519 R5-234628 R5-235186 | Editor’s Note: This clause is incomplete. The following aspects are either missing or not yet determined: - Addition to applicability spec is pending - Initial condition and call setup procedure to support NR satellite access are TBD - Message exceptions specific to satellite access is TBD - Annex F MU/TT is TBD | 1 | 40% | 40% |  | 40%
16 |  | 38.521-5 | 6.3 | Output power dynamics | [9 empty] | 0%
17 | Y | 38.521-5 | 6.3.1 | Minimum output power |  | Keysight | TBD | R5-231738 R5-235824 R5-235186 | Editor’s Note: This clause is incomplete. The following aspects are either missing or not yet determined: - Addition to applicability spec is pending - Initial condition and call setup procedure to support NR satellite access are TBD - Message exceptions specific to satellite access is TBD | 1 | 70% | 70% (+55%) |  | 70%
18 | Y | 38.521-5 | 6.3.2 | Transmit off power |  | Keysight | TBD | R5-231739 R5-235824 R5-235186 | Editor’s Note: This clause is incomplete. The following aspects are either missing or not yet determined: - Addition to applicability spec is pending | 1 | 90% | 90% (+75%) |  | 90%
19 | Y | 38.521-5 | 6.3.3 | Transmit on/off time mask |  | Apple |  | R5-231367 R5-233571 R5-235186 R5-235679 | Editor’s Note: This clause is incomplete. The following aspects are either missing or not yet determined: - Addition to applicability spec is pending - Initial condition and call setup procedure to support NR satellite access is TBD - Message exceptions specific to satellite access is TBD - Annex F MU/TT is TBD | 1 | 70% | 70% (+20%) |  | 70%
20 | Y | 38.521-5 | 6.3.4 | Power control | [5 empty] | 1 | 0% | 0% |  | 0%
21 |  | 38.521-5 | 6.4 | Transmit signal quality | [9 empty] | 0%
22 | Y | 38.521-5 | 6.4.1 | Frequency error |  | Qualcomm |  |  |  | 1 | 0% | 0% |  | 0%
23 | Y | 38.521-5 | 6.4.2 | Transmit modulation quality | [5 empty] | 1 | 0% | 0% |  | 0%
24 |  | 38.521-5 | 6.5 | Output RF spectrum emissions | [9 empty] | 0%
25 | Y | 38.521-5 | 6.5.1 | Occupied Bandwidth | [5 empty] | 1 | 0% | 0% |  | 0%
26 | Y | 38.521-5 | 6.5.2 | Out of band emissions | [9 empty] | 0%
27 |  | 38.521-5 | 6.5.2.1 | General | [5 empty] | 0.2 | 0% | 0% |  | 0%
28 | Y | 38.521-5 | 6.5.2.2 | Spectrum emission mask |  | Apple |  | R5-231368 R5-233572 R5-235186 R5-235683 | Editor’s Note: This clause is incomplete. The following aspects are either missing or not yet determined: - Addition to applicability spec is pending - Initial condition and call setup procedure to support NR satellite access is TBD - Message exceptions specific to satellite access is TBD - Annex F MU/TT is TBD | 1 | 50% | 50% |  | 50%
29 | Y | 38.521-5 | 6.5.2.4 | Adjacent channel leakage ratio |  | Apple |  | R5-231369 R5-233573 R5-235186 R5-235681 | Editor’s Note: This clause is incomplete. The following aspects are either missing or not yet determined: - Addition to applicability spec is pending - Initial condition and call setup procedure to support NR satellite access is TBD - Message exceptions specific to satellite access is TBD - Test Points analysis is TBD - Test configuration is TBD - Annex F MU/TT is TBD | 1 | 70% | 70% (+20%) |  | 70%
30 |  | 38.521-5 | 6.5.3 | Spurious emission |  | Qualcomm | [7 empty] | 0%
31 | Y | 38.521-5 | 6.5.3.1 | General spurious emission |  | Qualcomm |  | R5-230877 R5-233158 R5-235186 | Editor’s Note: This clause is incomplete. The following aspects are either missing or not yet determined: - Addition to applicability spec is pending - Initial condition and call setup procedure to support NR satellite access are TBD - Message exceptions specific to satellite access is TBD - Test Points analysis is TBD - Test configuration is TBD - Annex F MU/TT is TBD | 1 | 60% | 60% |  | 60%
32 | Y | 38.521-5 | 6.5.3.2 | Spurious emissions for UE co-existence |  | Qualcomm |  | R5-230879 R5-235827 R5-235186 | Editor’s Note: This clause is incomplete. The following aspects are either missing or not yet determined: - Addition to applicability spec is pending - Initial condition and call setup procedure to support NR satellite access are TBD - Message exceptions specific to satellite access is TBD - Annex F MU/TT is TBD | 2 | 70% | 70% (+20%) |  | 70%
33 | Y | 38.521-5 | 6.5.3.3 | Additional spurious emissions |  | Qualcomm |  |  |  | 1 | 0% | 0% |  | 0%
34 | Y | 38.521-5 | 6.5.4 | Transmit intermodulation |  | Qualcomm |  | R5-235826 R5-235186 | Editor’s Note: This clause is incomplete. The following aspects are either missing or not yet determined: - Addition to applicability spec is pending - Initial condition and call setup procedure to support NR satellite access are TBD - Message exceptions specific to satellite access is TBD - Annex F MU/TT is TBD | 1 | 70% | 70% (+70%) |  | 70%
TS 38.521-5: Conducted RF Receiver Test cases
35 |  | 38.521-5 | 7.1 | General |  | Qualcomm, Keysight | RAN5#97 (Nov-22) | R5-230878 R5-235456 |  | 12 | 100% | 100% (+50%) |  | 100%
36 |  | 38.521-5 | 7.2 | Diversity Characteristics |  | Qualcomm | RAN5#97 (Nov-22) |  |  | 0.5 | 0% | 0% |  | 0%
37 |  | 38.521-5 | 7.3 | Reference sensitivity |  | Qualcomm | RAN5#97 (Nov-22) | R5-230878 | [5 empty] | 100%
38 |  | 38.521-5 | 7.3.1 | General |  | Qualcomm | RAN5#97 (Nov-22) | R5-230878 |  | 0.2 | 100% | 100% |  | 100%
39 | Y | 38.521-5 | 7.3.2 | Reference sensitivity power level |  | Qualcomm |  | R5-230878 R5-235866 R5-235186 | Editor’s Note: This clause is incomplete. The following aspects are either missing or not yet determined: - Addition to applicability spec is pending - Initial condition and call setup procedure to support NR satellite access are TBD - Message exceptions specific to satellite access is TBD - Annex F MU/TT is TBD | 1 | 70% | 70% (+20%) |  | 70%
40 | Y | 38.521-5 | 7.4 | Maximum input level |  | Keysight |  | R5-232346 R5-235825 R5-235186 | Editor’s Note: This clause is incomplete. The following aspects are either missing or not yet determined: - Addition to applicability spec is pending - Initial condition and call setup procedure to support NR satellite access are TBD - Message exceptions specific to satellite access is TBD | 1 | 70% | 70% (+30%) |  | 70%
41 | Y | 38.521-5 | 7.5 | Adjacent channel selectivity |  | CAICT | RAN5#98 (Feb-23) | R5-233567 R5-235186 | Editor’s Note: This clause is incomplete. The following aspects are either missing or not yet determined: - Addition to applicability spec is pending - Initial condition and call setup procedure to support NR satellite access are TBD - Message exceptions specific to satellite access is TBD - Test Points analysis is TBD - Test configuration is TBD - Annex F MU/TT is TBD | 1 | 40% | 40% |  | 40%
42 |  | 38.521-5 | 7.6 | Blocking characteristics |  | CAICT | [7 empty] | 0%
43 |  | 38.521-5 | 7.6.1 | General |  | Apple |  |  |  | 0.2 | 0% | 0% |  | 0%
44 | Y | 38.521-5 | 7.6.2 | In-band blocking |  | Apple |  |  |  | 1 | 0% | 0% |  | 0%
45 | Y | 38.521-5 | 7.6.3 | Out-of-band blocking |  | Apple |  | R5-231383 R5-235186 |  | 1 | 15% | 15% |  | 15%
45 | Y | 38.521-5 | 7.6.4 | Narrow band blocing |  | Apple |  |  |  | 1 | 0% | 0% |  | 0%
46 | Y | 38.521-5 | 7.7 | Spurious response |  | CAICT |  |  |  | 1 | 0% | 0% |  | 0%
47 | Y | 38.521-5 | 7.8 | Intermodulation characteristics |  | CAICT |  |  |  | 1 | 0% | 0% |  | 0%
48 | Y | 38.521-5 | 7.9 | Spurious emissions |  | CAICT |  | R5-231740 R5-232372 R5-235186 |  | 1 | 15% | 15% |  | 15%
TS 38.521-5: Demodulation Performance Test Cases
49 |  | 38.521-5 | 8 | General |  | Qualcomm | RAN5#97 (Nov-22)
50 |  | 38.521-5 | 8.1 | General |  | Keysight | RAN5#97 (Nov-22) | R5-235456
51 |  | 38.521-5 | 8.1.1 | Relationship between minimum requirements and test requirements |  | Qualcomm | RAN5#97 (Nov-22) | R5-231741 |  | 0.2 | 100% | 100% |  | 100%
52 |  | 38.521-5 | 8.1.2 | Applicability of minimum requirements |  | Qualcomm | RAN5#97 (Nov-22) | R5-231741 |  | 0.2 | 100% | 100% |  | 100%
53 |  | 38.521-5 | 8.1.3 | Conducted requirements |  | Qualcomm | RAN5#97 (Nov-22) | R5-231741 |  | 0.2 | 100% | 100% |  | 100%
54 |  | 38.521-5 | 8.2 | Demodulation performance requirements |  | Qualcomm | RAN5#97 (Nov-22)
55 |  | 38.521-5 | 8.2.1 | General |  | Qualcomm | RAN5#97 (Nov-22)
56 |  | 38.521-5 | 8.2.1.2 | PDSCH demodulation requirements |  | Qualcomm | RAN5#97 (Nov-22) | R5-231742 |  | 0.2 | 100% | 100% |  | 100%
57 |  | 38.521-5 | 8.2.1.2.1 | 1RX requirements |  | Qualcomm | RAN5#97 (Nov-22) |  |  | 1 | 0% | 0% |  | 0%
58 |  | 38.521-5 | 8.2.1.2.2 | 2RX requirements |  | Qualcomm | RAN5#97 (Nov-22) | R5-231742 |  |  | 20% | 20% |  | 20%
61 | Y | 38.521-5 | 8.2.1.2.2.1.1_1 | 2Rx FDD FR1 PDSCH Mapping Type A for Satellite Access |  | Qualcomm |  | R5-233570 | Editor's Note: This test cases is incomplete in following aspects: - NTN specific message contents - Initial condition and call setup procedure to support NR satellite access are TBD - Annex F MU/TT analysis - Annex G Minimum test time - Applicability spec update | 1 | 40% | 40% |  | 40%
TS 38.521-5: Annex
59 |  | 38.521-5 | A | Measurement channels |  | CAICT |  | R5-233568 |  | 0.2 | 100% | 100% |  | 100%
59 |  | 38.521-5 | B | Propagation conditions |  | CAICT |  | R5-233568 |  | 0.2 | 100% | 100% |  | 100%
59 |  | 38.521-5 | C.3 | Connection (Conducted) |  | Qualcomm | RAN5#97 (Nov-22) | R5-231741 |  | 0.2 | 100% | 100% |  | 100%
59 |  | 38.521-5 | F | Acceptable uncertainty of Test System |  | Keysight, Qualcomm |  | R5-235824 |  | 0.2 | 50% | 50% |  | 50%
TS 38.905: Derivation of test points for radio transmission and reception test cases
63 |  | 38.905 | 4.4 | Test point analysis for satellite access test cases in TS 38.521-5 |  | Google, Qualcomm, Apple |  | R5-234630 R5-235858 R5-235680 R5-235682 R5-235684 |  | 1 | 50% | 50% |  | 50%
TS 38.522: Applicability for RF Transmitter and Receiver Test cases
60 |  | 38.522 | 4.1, 4.2 | Add test case applicability statements for the new test cases introduced in 38.521-5 | [5 empty] | 1 | 0% | 0% |  | 0%
TS 38.533: RRM Test cases
|  | 38.533 | 3.3 | Abreviations |  | Qualcomm |  | R5-234647 |  | 0.1 | 100% | 100% |  | 100%
|  | 38.533 | 14 | NR standalone tests for Satellite access
|  | 38.533 | 14.0 | General |  | Qualcomm |  | R5-234646 |  | 0.1 | 100% | 100% |  | 100%
|  | 38.533 | 14.1 | RRC_IDLE state mobility
| Y | 38.533 | 14.1.2 | SA FR1 Cell reselection UE configured with the feature for enhanced requirements for Satellite Access | [5 empty] | 1 | 0% | 0% |  | 0%
| Y | 38.533 | 14.1.3 | SA FR1 Time based Cell reselection for Satellite Access | [5 empty] | 1 | 0% | 0% |  | 0%
| Y | 38.533 | 14.1.4 | SA FR1 Location based Cell reselection for Satellite Access | [5 empty] | 1 | 0% | 0% |  | 0%
| Y | 38.533 | 14.1.7 | SA FR1-FR1 Cell reselection for UE configured with [capability for enhanced requirements] for NR satellite access | [5 empty] | 1 | 0% | 0% |  | 0%
| Y | 38.533 | 14.1.8 | SA FR1-FR1 Time-based Cell reselection for NR satellite access | [5 empty] | 1 | 0% | 0% |  | 0%
| Y | 38.533 | 14.1.9 | SA FR1-FR1 Location-based Cell reselection for NR satellite access | [5 empty] | 1 | 0% | 0% |  | 0%
|  | 38.533 | 14.2 | RRC_CONNECTED state mobility
|  | 38.533 | 14.2.1 | Handover
| Y | 38.533 | 14.2.1.3 | SA FR1 SAN time-based conditional Handover for NR satellite access | [5 empty] | 1 | 0% | 0% |  | 0%
| Y | 38.533 | 14.2.1.4 | SA FR1-FR1 SAN time-based conditional Handover for NR satellite access | [5 empty] | 1 | 0% | 0% |  | 0%
| Y | 38.533 | 14.2.1.5 | SA FR1 SAN distance-based conditional Handover for NR satellite access | [5 empty] | 1 | 0% | 0% |  | 0%
| Y | 38.533 | 14.2.1.6 | SA FR1-FR1 SAN distance-based conditional Handover for NR satellite access | [5 empty] | 1 | 0% | 0% |  | 0%
|  | 38.533 | 14.3 | Timing for Satellite Access
|  | 38.533 | 14.3.1 | UE transmit timing for Satellite Access
| Y | 38.533 | 14.3.1.1 | SA FR1 NR UE Transmit Timing Test for NR satellite access | [5 empty] | 1 | 0% | 0% |  | 0%
|  | 38.533 | 14.5 | Measurement procedure
|  | 38.533 | 14.5.1 | Intra-frequency Measurements
| Y | 38.533 | 14.5.1.1 | SA FR1 event triggered reporting tests without gap under non-DRX for NR satellite access |  | Qualcomm |  | R5-234646 | Editor's Note: - MU and TT analysis is incomplete - Message contents are FFS - Call setup and test procedure needs to be updated - Applicability needs to be updated - Exceptionts to connection diagram may need to be updated - Several sections are in brackets - Several test parameters and configuration are still in brackets | 1 | 40% | 40% |  | 40%
| Y | 38.533 | 14.5.1.2 | SA FR1 Event triggered reporting tests without gap under DRX for NR satellite access |  | Qualcomm |  | R5-234646 | Editor's Note: - MU and TT analysis is incomplete - Message contents are FFS - Call setup and test procedure needs to be updated - Applicability needs to be updated - Exceptionts to connection diagram may need to be updated - Several sections are in brackets - Several test parameters and configuration are still in brackets | 1 | 40% | 40% |  | 40%
| Y | 38.533 | 14.5.1.3 | SA FR1 event triggered reporting tests without gap under non-DRX with FDD PCell with SSB index reading for NR satellite access |  | Qualcomm |  | R5-234646 | Editor's Note: - MU and TT analysis is incomplete - Message contents are FFS - Call setup and test procedure needs to be updated - Applicability needs to be updated - Exceptionts to connection diagram may need to be updated - Several sections are in brackets - Several test parameters and configuration are still in brackets | 1 | 40% | 40% |  | 40%
| Y | 38.533 | 14.5.1.4 | SA FR1 event triggered reporting tests with single measurement gap under non-DRX for satellite access for NR satellite access | [5 empty] | 1 | 0% | 0% |  | 0%
| Y | 38.533 | 14.5.1.5 | SA FR1 event triggered reporting tests with FNO concurrent gaps under DRX for satellite access for NR satellite access | [5 empty] | 1 | 0% | 0% |  | 0%
| Y | 38.533 | 14.5.1.6 | SA FR1 event triggered reporting tests with PPO concurrent gaps under non-DRX with SSB index reading for satellite access for NR satellite access | [5 empty] | 1 | 0% | 0% |  | 0%
|  | 38.533 | 14.5.2 | Inter-frequency Measurements
| Y | 38.533 | 14.5.2.1 | SA FR1-FR1 Event triggered reporting test without gap under non-DRX for NR satellite access | [5 empty] | 1 | 0% | 0% |  | 0%
| Y | 38.533 | 14.5.2.2 | SA FR1-FR1 Event triggered reporting tests without gap under DRX for NR satellite access | [5 empty] | 1 | 0% | 0% |  | 0%
|  | 38.533 | 14.6 | Measurement Performance requirements
|  | 38.533 | 14.6.3 | SS-SINR
| Y | 38.533 | 14.6.3.1 | SA FR1 SA measurement accuracy for NR satellite access | [5 empty] | 1 | 0% | 0% |  | 0%
| Y | 38.533 | 14.6.3.2 | SA FR1-FR1 SA measurement accuracy for NR satellite access | [5 empty] | 1 | 0% | 0% |  | 0%
|  | 38.533 | 14.6.4 | L1-RSRP measurement for beam reporting
| Y | 38.533 | 14.6.4.1 | SA FR1 SSB based L1-RSRP measurement for NR satellite access | [5 empty] | 1 | 0% | 0% |  | 0%
| Y | 38.533 | 14.6.4.2 | SA FR1 CSI-RS based L1-RSRP measurement on resource set with repetition off for NR satellite access | [5 empty] | 1 | 0% | 0% |  | 0%
|  | 38.533 | Annex A | RRM test configurations; Satellite access configuration |  | Qualcomm |  | R5-234647 |  | 1 | 70% | 70% |  | 70%
|  | 38.533 | Annex B | Conditions for RRM requirements applicability for operating bands; Satellite access, High level test procedure for SAN RRM tests |  | Qualcomm |  | R5-234647 |  | 1 | 70% | 70% |  | 70%
TS 38.523-1: Protocol test cases - FFS on several aspects of GSO, NGSO etc
Idle Mode
|  | 38.523-1 | 6.1 | [6 empty] | 1 | 0% | 0% |  | 0%
28 | Y | 38.523-1 | 6.7.1.1 | Cell Selection / GNSS location / NTN | (1) with { UE in 5GMM-DEREGISTERED/RRC-IDLE and UE finds a cell which provides access by NR NTN RAT } ensure that { when { UE has no valid GNSS position } then { UE shall not establish RRC connection to perform a Registration procedure } } (2) with { UE in 5GMM-DEREGISTERED/RRC-IDLE and UE finds a cell which provides access by NR NTN } ensure that { when { Cell broadcasts SIB19 and UE has a valid GNSS position } then { UE establishes RRC connection and successfully performs Registration procedure } | Qualcomm | RAN5#100 (Aug-23) | R5-235338 |  | 1 | 80% | 80% |  | 80%
Cell reselection / Neighbor cell ephermis validaty/ ntn-UlSyncValidityDuration
29 | Y | 38.523-1 | 6.7.1.2 | Cell Selection / MultiTAC / NTN/ trackingAreaList-r17 | (1) with { UE in NR RRC_IDLE and UE finds a suitable cell which provides access by NR NTN RAT } ensure that { when { SIB1 broadcast more than one TAC per PLMN } then { UE forwards the trackingAreaList to upper layers for mobility management procedure and reselects the cell} } | Qualcomm | RAN5#100 (Aug-23) | R5-235337 |  |  | 80% | 80% |  | 80%
| Y | 38.523-1 | 6.7.x.x | Cell Selection / Serving cell becomes non-suitable (CellBarredNTN) | TS 38.304, 5.3.1
| Y | 38.523-1 | 6.7.x.x | Cell Reselection / enhancedMeasurementLEO / ServingCellConfigCommonSIB / SIB1 | TS 38.331; TS 38.133
TS38.304, Cl 5.2.4.2 Measurement rules for cell re-selection
| Y | 38.523-1 | 6.7.x.x | Cell reselection, distanceThresh , referenceLocation | TS38.304, Cl 5.2.4.2 |  |  |  |  | 1 | 0% | 0% |  | 0%
MAC
17 |  | 38.523-1 | 7.1 | NR Layer 2 | [5 empty] | 0 | 0% | 0% |  | 0%
18 |  | 38.523-1 | 7.1.1 | MAC | [5 empty] | 0 | 0% | 0% |  | 0%
19 |  | 38.523-1 | 7.1.1.1 | Random Access Procedures | [5 empty] | 0 | 0% | 0% |  | 0%
20 | Y | 38.523-1 | 7.1.1.1.x | Random access procedure / Successful / Contention resolution timer expired / NTN | TS 38.321 Cl 5.1.4; 5.1.5 |  |  |  |  | 1 | 0% | 0% |  | 0%
22 | Y | 38.523-1 | 7.1.1.x.x | NTN / UE specific TA report / UE specific Koffset | TS 38.321 , Cl 5.4.8; 5.18.24 |  |  |  |  | 1 | 0% | 0% |  | 0%
21 |  | 38.523-1 | 7.1.1.3.x | [6 empty] | 0 | 0% | 0% |  | 0%
26 | Y | 38.523-1 | 7.1.1.3.x | NTN / DRX / (UL)HARQ RTT/ HARQ-RTT-TimerDL-NTN / HARQ-RTT-TimerUL-NTN | TS 38.321 Cl 5.7 |  |  |  |  | 1 | 0% | 0% |  | 0%
| Y | 38.523-1 |  | UE failing to acquire sufficiently accurate UE location to calculate UE's TA, should not perform any UL transmissions ( TS 38.211, Clause 4.3.1)
21 |  | 38.523-1 | 7.1.2.x
26 | Y | 38.523-1 | 7.1.2.x.x | NTN / AM RLC / Receiver status triggers / extended t-Reordering configured | [5 empty] | 1 | 0% | 0% |  | 0%
RRC
4 |  | 38.523-1 | 8.1 | Existing sub-clause header | Existing sub-clause header |  |  |  |  | 0 | 0% | 0% |  | 0%
5 |  | 38.523-1 | 8.1.5 | Existing sub-clause header | Existing sub-clause header |  |  |  |  | 0 | 0% | 0% |  | 0%
11 |  | 38.523-1 | 8.1.5.1 | [6 empty] | 0 | 0% | 0% |  | 0%
12 |  | 38.523-1 | 8.1.5.1.1 | UE capability - nonTerrestrialNetwork-r17 | [5 empty] | 0 | 0% | 0% |  | 0%
6 |  | 38.523-1 | 8.1.5.x.x | [6 empty] | 0 | 0% | 0% |  | 0%
7 | Y | 38.523-1 |  | start timer T430 with the timer value set to ntn-UlSyncValidityDuration - NTN / T430 expiry | TS 38.331 5.2.2.6; 5.3.5.5.2; 5.2.2.4.21 |  |  |  |  | 1 | 0% | 0% |  | 0%
8 | Y | 38.523-1 |  | GEO / SIB2 Relaxed measurements - relaxedMeasurement-r17 | [5 empty] | 1 | 0% | 0% |  | 0%
|  |  | 8.1.3 | Measurement configuration control and reporting | [5 empty] | 0 | 0% | 0% |  | 0%
9 | Y | 38.523-1 |  | Measurement configuration control and reporting / NTN / Event D1 | TS 38.331 5.5.4.15; 5.5.4.1 |  |  |  |  | 1 | 0% | 0% |  | 0%
27 | Y | 38.523-1 |  | Measurement configuration control and reporting / NTN / Event T1 | ??
|  | 38.523-1 | 8.1.4.4 | Conditional handover
30 | Y | 38.523-1 |  | Measurement configuration control and reporting / NTN / CondEventD1 / CondEventA4/ condEventA4-r17 | TS 38.331 5.3.5.13.1; 5.3.5.13.4
31 | Y | 38.523-1 |  | Measurement configuration control and reporting / NTN / CondEventD1 | TS 38.331 5.3.5.13.1; 5.3.5.13.4 |  |  |  |  | 1 | 0% | 0% |  | 0%
NAS
4 |  | 38.523-1 | 9.1.x | Existing sub-clause header | Existing sub-clause header |  |  |  | sub-tasks to be identified | 0 | 0% | 0% |  | 0%
5 |  | 38.523-1 | 9.1.x.x | Existing sub-clause header | Existing sub-clause header |  |  |  | sub-tasks to be identified | 0 | 0% | 0% |  | 0%
11 | Y | 38.523-1 | 9.1.x.x.x | NTN / GNSS position reporting / reject cause #78 "PLMN not allowed to operate at the present UE location" | TS 23.122 3.1, TS 24.501 4.23.2; 5.5.1.2.5 |  |  |  |  | 1 | 0% | 0% |  | 0%
| Y | 38.523-1 | 9.1.x.x.x | NTN / Mobility registration update / supported TACs not part of UE registration area | 23.501 Cl 5.4.11.6 |  |  |  |  | 1 | 0% | 0% |  | 0%
| Y | 38.523-1 | 9.1.x.x.x | TAI(s) not allowed / forbidden TAI(s) in the Registration Accept message | 23.501, Cl 5.4.11.8 |  |  |  |  | 1 | 0% | 0% |  | 0%
| Y | 38.523-1 | 9.1.x.x.x | Timer expiry | ?? |  |  |  | sub-tasks to be identified | 1 | 0% | 0% |  | 0%
| Y | 38.523-1 | 9.1.x.x.x | new 5QI value
| Y | 38.523-1 | 9.1.x.x.x | IMS emergency
|  |  |  | PDU session release procedure for #78 | TS 24.501, 6.3.3 and 6.4.3 |  |  |  | sub-tasks to be identified | 0 | 0% | 0% |  | 0%
TS 38.523-2: Applicability for Protocol test cases
23 |  | 38.523-2 | 4.1, 4.2 | Add test case applicability statements for the new test cases introduced in 38.523-1 |  | Qualcomm | RAN5#102 (Feb-24) | R5-235339 R5-235419 |  | 0.1 | 15% (+15%) | 15% (+15%) |  | 15%
TS 38.523-3: Protocol test suites (TTCN)
24 |  | 38.523-3 | NA | Introduction of General and Signaling Test Environment for NR-NTN |  |  | RAN5#99 (May-23) |  |  | 0 | 0% | 0% |  | 0%
End of workplan items. Note! Do not remove this row. Introduce new work plan rows/items above this row.
Note on A6: Unique ID for WP items (unique within the sub-area work plan) Note! As WP item numbers may be referenced from outside of this WP that means: - Do not change number for WP items that have been published. - Do not re-use WP item numbers if a WP item is deleted
Note on B6: Set to Y if the WP item represents a new test case that will be specified in RAN5 test specifications as an executable test case else leave blank.
Note on K6: The WP item's weight number is used to set the reletive weights between WP items used in the overall calculation of completeness. Setting it to 0 for a WP item means that it will not be included at all in the calculation.