## Cover sheet
3GPP TSG-RAN5 Meeting #100 | [10 empty] | R5-234816
Toulouse, France, 21st – 25th Aug, 2023
Agenda Item: | 7.4.2
Source: | CATT
Title: | Work plan: UE Conformance Test Aspects for NR Positioning Support
Work item code: | NR_pos-UEConTest
Release: | Rel-16
Document for: | Information
RAN5 WP template v2.0
1. Introduction
At the RAN#90-e meeting a Rel-16 RAN5 work item for UE Conformance Test Aspects for NR Positioning Support (NR_pos-UEConTest) was approved [1]. The purpose of this present document is to provide a work plan for the RAN5 work item for this. The work plan is updated after each RAN5 meeting to give the status of this work item.
2. Work item status
Estimation of WI overall completion:
Area |  | Completion | Number of new completed test cases (Note 1) | Number of new test cases | Comments
Overall completion |  | 100% (+4%) | 23 | 23
Completion Compensation |  | -
| Note 1: | Only test cases completed for all applicable WP areas and sub-areas are counted. For completed test cases per WP areas and WP sub-areas see below.
Estimation WI completion per area and sub-area:
|  | Completion | Number of new completed test cases | Number of new test cases | Comments
SA Option 2 (SA NR) |  | 100% (+4%) | 22 | 22
FR1 |  | 100% (+4%) | 23 | 23
FR2 |  | 100% (+4%) | 23 | 23
FR1 + FR2
Estimation of completion per TS (area):
|  | TS/TR overall completion |  |  | SA Option 2 (SA NR)
TS/TR Scope | TS/TR | Completion | Number of new completed test cases | Number of new test cases | FR1 |  |  | FR2
[5 empty] | Completion | Number of new completed test cases | Number of new test cases | Completion | Number of new completed test cases | Number of new test cases | Completion | Number of new completed test cases | Number of new test cases
5GS
5GS Common
Common test environment | 38.508-1 | 100% |  |  | 100% |  |  | 100%
Common ICS | 38.508-2 | 100% |  |  | 100% |  |  | 100%
Protocol Test Suites | 38.523-3 | 100% |  |  | 100% |  |  | 100%
Special conformance testing functions | 38.509 | 100% |  |  | 100% |  |  | 100%
NR RF/RRM
Test Tolerances analysis RRM and RF Rx test cases | 38.903 | 100% (+3.3%) |  |  | 100% (+3.3%) |  |  | 100% (+3.3%)
UE Positioning
UE Positioning Min. Performance test cases | 37.571-1 | 100% (+0.2%) | 20 | 20 | 100% (+0.2%) | 20 | 20 | 100% (+0.2%) | 20 | 20
UE Positioning Protocol test cases | 37.571-2 | 100% | 3 | 3 | 100% | 3 | 3 | 100% | 3 | 3
Applicability and ICS UE Positioning test cases | 37.571-3 | 100% |  |  | 100% |  |  | 100%
UE Positioning Test sutes (TTCN) | 37.571-4 | 100% (+10%) |  |  | 100% (+10%) |  |  | 100% (+10%)
UE Positioning test scenarios and assistance data | 37.571-5 | 100% (+100%) |  |  | 100% (+100%) |  |  | 100% (+100%)
5 References
[1] RP-221450 | UE Conformance Test Aspects for NR Positioning Support
Note on B21: Overall completion of the work item reported at an earlier meeting will not be decreased if additional tasks are added or if corrections are made to the work plan. Instead the earlier reported completion status will be kept until necessary progress have been achieved such that completion exceeds the earlier reported completion level. The value of the Completion Compensation value represents the difference in the decrease caused by late additions or corrections to the work plan and the current estimated overall completion. '-' indicates that no compensation is applied.

## WP
WP Title: |  | UE Conformance Test Aspects for NR Positioning Support | [10 empty] | Start of workplan status columns. Note! Do not remove this column. | WP item status |  |  | End of workplan columns. Note! Do not remove this column.
WI code |  | NR_pos-UEConTest
WP Scope: |  | The purpose of this present document is to provide a work plan for the RAN5 work item UE Conformance Test Aspects for NR Positioning Support | [12 empty] | vs Area
WP Resp: |  | Xiaoyang TIAN, CATT |  |  | tianxiaoyang@catt.cn | [5 empty] | WP item completion |  |  | SA Option 2 (SA NR)
TS Resp: |  | n/a |  |  | n/a
WP Item ID | Is new test case? | TS/area | Clause | Title | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | Overall | SA Option 2 (SA NR) |  | FR1 | FR2 | FR1 + FR2
[14 empty] | 100% (+4%) | 100% (+4%)
[14 empty] | 59 | 59 | 0
[14 empty] | 35.4 | 35.4 | 0
5%
Start of work plan items. Note! Do not remove this row. Introduce new work plan rows/items below this row.
5GS
5GS Common
TS 38.508-1: Common test environment
|  | 38.508-1 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
1 |  | 38.508-1 | 4.6 | Introduction of information elements for Release-16 NR positioning support | Adding positioning system information blocks associated parameters in chapter 4.6.2A |  | RAN5#94 (Feb-22) | R5-221591 R5-223387 R5-225311 R5-225312 R5-231219 R5-234194 |  | 0.1 | 100% | 100% |  | 100% | 100%
TS 38.523-3: Protocol Test Suites
|  | 38.523-3 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
63 |  | 38.523-3 |  | NR Positioning: addition of posSIBs support | Addition of posSIBs support |  | RAN5#95 (May-22) | R5-222377 R5-222933 |  | 1 | 100% | 100% |  | 100% | 100%
TS 38.509: Special conformance testing functions
|  | 38.509 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
31 |  | 38.509 |  | Update RESET UE POSITIONING STORED INFORMATION message | Update RESET UE POSITIONING STORED INFORMATION message for Rel 16 NR positioning support | CATT | RAN5#93 (Nov-21) | R5-217935 |  | 1 | 100% | 100% |  | 100% | 100%
NR RF/RRM
TR 38.903: Test Tolerances analysis RRM and RF Rx test cases
|  | 38.903 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
3 |  | 38.903 | 2, 5.2, 9, Annex G | Introduction of NR positioning test cases information | Introduction of NR positioning test cases information | CATT | TBD | R5-224412 R5-234221 |  | 0.2 | 100% (+20%) | 100% (+20%) |  | 100% | 100%
65 |  | 38.903 |  | Addition test tolerance analysis for RSTD measurement period in FR1 test case 14.2.1 and 14.2.2 | Adding TT analysis for RSTD test case 14.2.1 and 14.2.2 | Rohde & Schwarz | TBD | R5-226481 R5-226483 |  | 0.1 | 100% | 100% |  | 100% | 100%
69 |  | 38.903 |  | Addition test tolerance analysis for RSTD measurement period in FR2 test case 14.2.3 and 14.2.4 | Adding TT analysis for RSTD test case 14.2.3 and 14.2.4 | CATT | TBD | R5-230030 R5-230031 |  | 0.1 | 100% | 100% |  | 100% | 100%
70 |  | 38.903 |  | Addition test tolerance analysis for RSTD measurement accuracy in FR1 test case 14.3.1 and 14.3.2 | Adding TT analysis for RSTD test case 14.3.1 and 14.3.2 | Rohde & Schwarz | TBD | R5-226482 R5-226484 R5-231758 |  | 0.1 | 100% | 100% |  | 100% | 100%
68 |  | 38.903 |  | Addition test tolerance analysis for RSTD measurement accuracy in FR2 test case 14.3.3 and 14.3.4 | Adding TT analysis for RSTD test case 14.3.3 and 14.3.4 | CATT | TBD | R5-231756 R5-230033 |  | 0.1 | 100% | 100% |  | 100% | 100%
71 |  | 38.903 |  | Addition test tolerance analysis for UE Rx-Tx time difference measurement period in FR1 test case 15.2.1 and 15.2.2 | Adding TT analysis for UE Rx-Tx time differnece test case 15.2.1 and 15.2.2 | CATT | RAN5#96 (Aug-22) | R5-225616 |  | 0.1 | 100% | 100% |  | 100% | 100%
72 |  | 38.903 |  | Addition test tolerance analysis for UE Rx-Tx time difference measurement period in FR2 test case 15.2.3 and 15.2.4 | Adding TT analysis for UE Rx-Tx time differnece test case 15.2.3 and 15.2.4 | CATT | RAN5#97 (Nov-22) | R5-225939 R5-225940 |  | 0.1 | 100% | 100% |  | 100% | 100%
73 |  | 38.903 |  | Addition test tolerance analysis for UE Rx-Tx time difference measurement accuracy test case 15.3.1 and 15.3.2 | Adding TT analysis for UE Rx-Tx time differnece test case 15.3.1 and 15.3.2 | CATT | RAN5#97 (Nov-22) | R5-225941 R5-225942 |  | 0.1 | 100% | 100% |  | 100% | 100%
74 |  | 38.903 |  | Addition test tolerance analysis for PRS RSRP measurement period in FR1 test case 16.2.1 and 16.2.2 | Adding TT analysis for PRS RSRP test case 16.2.1 and 16.2.2 | Rohde & Schwarz | TBD | R5-232427 R5-232428 |  | 0.1 | 100% | 100% |  | 100% | 100%
75 |  | 38.903 |  | Addition test tolerance analysis for PRS RSRP measurement period in FR1 test case 16.2.3 and 16.2.4 | Adding TT analysis for PRS RSRP test case 16.2.3 and 16.2.4 | CATT | TBD | R5-230034 R5-231757 |  | 0.1 | 100% | 100% |  | 100% | 100%
76 |  | 38.903 |  | Addition test tolerance analysis for PRS RSRP measurement period in FR1 test case 16.3.1 and 16.3.2 | Adding TT analysis for PRS RSRP test case 16.3.1 and 16.3.2 | Rohde & Schwarz CATT | TBD | R5-232429 R5-232078 |  | 0.1 | 100% | 100% |  | 100% | 100%
UE Positioning
TS 37.571-1: UE Positioning -Performance
|  | 37.571-1 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
4 |  | 37.571-1 | 2, 3 | Introduction of Release-16 NR positioning RF conformance contents | 1. Adding reference of TS 38.133 2. Adding Release-16 NR positioning methods associated definitions and abbreviations | CATT | RAN5#92 (Aug-21) | R5-215973 |  | 0.1 | 100% | 100% |  | 100% | 100%
5 |  | 37.571-1 | 4.15 | Addition of Multi-RTT test conditions | Adding Multi-RTT conditions | CATT | RAN5#92 (Aug-21) | R5-215973 R5-221201 R5-222596 R5-230337 |  | 0.1 | 100% | 100% |  | 100% | 100%
6 |  | 37.571-1 | 4.16 | Addition of DL-AoD test conditions | Adding DL-AoD test conditions | CATT | RAN5#92 (Aug-21) | R5-215973 R5-222596 R5-226460 |  | 0.1 | 100% | 100% |  | 100% | 100%
7 |  | 37.571-1 | 4.17 | Addition of DL-TDOA test conditions | Adding DL-TDOA test conditions | CATT | RAN5#92 (Aug-21) | R5-215973 R5-222596 R5-226460 |  | 0.1 | 100% | 100% |  | 100% | 100%
8 |  | 37.571-1 | 14 | NR RSTD measurement requirements
54 |  | 37.571-1 | 14.2 | NR RSTD measurement period test cases
32 | Y | 37.571-1 | 14.2.1 | NR RSTD measurement period test case for single positioning frequency layer in FR1 SA | The purpose of the test is to verify that the RSTD measurement meets the requirements specified in Clause 9.9.2 in an environment with AWGN propagation conditions in FR1 in standalone scenario when single positioning frequency layer is configured. TS 38.133 9.9.2.5 | Rohde & Schwarz | TBD | R5-221202 R5-222597 R5-226485 |  | 1 | 100% | 100% |  | 100% | 100%
33 | Y | 37.571-1 | 14.2.2 | NR RSTD measurement period test case for dual positioning frequency layers in FR1 SA | The purpose of the test is to verify that the RSTD measurement meets the requirements specified in Clause 9.9.2 in an environment with AWGN propagation conditions in FR1 in standalone scenario when dual positioning frequency layers are configured. TS 38.133 9.9.2.5 | Rohde & Schwarz | TBD | R5-221203 R5-222597 R5-225740 R5-226487 |  | 1 | 100% | 100% |  | 100% | 100%
34 | Y | 37.571-1 | 14.2.3 | NR RSTD measurement period test case for single positioning frequency layer in FR2 SA | The purpose of the test is to verify that the RSTD measurement meets the requirements specified in Clause 9.9.2 in an environment with AWGN propagation conditions in FR2 in standalone scenario when single positioning frequency layer is configured. TS 38.133 9.9.2.5 | CATT | TBD | R5-222599 R5-225740 R5-231744 |  | 1 | 100% | 100% |  | 100% | 100%
35 | Y | 37.571-1 | 14.2.4 | NR RSTD measurement period test case for dual positioning frequency layers in FR2 SA | The purpose of the test is to verify that the RSTD measurement meets the requirements specified in Clause 9.9.2 in an environment with AWGN propagation conditions in FR2 in standalone scenario when dual positioning frequency layers are configured. TS 38.133 9.9.2.5 | CATT | TBD | R5-222600 R5-225740 R5-231750 |  | 1 | 100% | 100% |  | 100% | 100%
55 |  | 37.571-1 | 14.3 | NR RSTD measurement accuracy test case
36 | Y | 37.571-1 | 14.3.1 | NR RSTD measurement accuracy test case for single positioning frequency layer in FR1 SA | The purpose of the test is to verify that the RSTD measurement meets the accuracy requirements specified in clause 10.1.23.2 in an environment with AWGN propagation conditions in FR1 in standalone scenario when single positioning frequency layer is configured. TS 38.133 10.1.23 | Rohde & Schwarz | TBD | R5-221204 R5-222597 R5-225740 R5-226486 |  | 1 | 100% | 100% |  | 100% | 100%
37 | Y | 37.571-1 | 14.3.2 | NR RSTD measurement accuracy test case for dual positioning frequency layer in FR1 SA | The purpose of the test is to verify that the RSTD measurement meets the accuracy requirements specified in clause 10.1.23.2 in an environment with AWGN propagation conditions in FR1 in standalone scenario when dual positioning frequency layers are configured. TS 38.133 10.1.2.3 | Rohde & Schwarz | TBD | R5-221205 R5-222597 R5-225740 R5-230927 R5-230928 |  | 1 | 100% | 100% |  | 100% | 100%
38 | Y | 37.571-1 | 14.3.3 | NR RSTD measurement accuracy test case for single positioning frequency layer in FR2 SA | The purpose of the test is to verify that the RSTD measurement meets the accuracy requirements specified in clause 10.1.23.2 in an environment with AWGN propagation conditions in FR2 in standalone scenario when single positioning frequency layer is configured. TS 38.133 10.1.23 | CATT | TBD | R5-222601 R5-225740 R5-231751 |  | 1 | 100% | 100% |  | 100% | 100%
39 | Y | 37.571-1 | 14.3.4 | NR RSTD measurement accuracy test case for dual positioning frequency layer in FR2 SA | The purpose of the test is to verify that the RSTD measurement meets the accuracy requirements specified in clause 10.1.23.2 in an environment with AWGN propagation conditions in FR2 in standalone scenario when dual positioning frequency layers are configured. TS 38.133 10.1.23 | CATT | TBD | R5-223748 R5-225740 R5-231752 |  | 1 | 100% | 100% |  | 100% | 100%
9 |  | 37.571-1 | 15 | NR Rx-Tx Time Difference measurement requirements |  |  | TBD
56 |  | 37.571-1 | 15.2 | UE Rx-Tx time difference measurement period test cases
40 | Y | 37.571-1 | 15.2.1 | UE Rx-Tx time difference measurement period for single positioning frequency layer in FR1 SA | The purpose of the test is to verify that the UE Rx-Tx measurement meets the requirements specified in clause 9.9.4.5 in AWGN propagation condition in FR1 in standalone scenario when single positioning frequency layer is configured. TS 38.133 9.9.4.5 | CATT | RAN5#96 (Aug-22) | R5-220518 R5-222598 R5-225698 |  | 1 | 100% | 100% |  | 100% | 100%
41 | Y | 37.571-1 | 15.2.2 | UE Rx-Tx time difference measurement period for dual positioning frequency layers in FR1 SA | The purpose of the test is to verify that the UE Rx-Tx measurement meets the requirements specified in clause 9.9.4.5 in AWGN propagation condition in FR1 in standalone scenario when dual positioning frequency layers are configured. TS 38.133 9.9.4.5 | CATT | RAN5#96 (Aug-22) | R5-220518 R5-222598 R5-225698 |  | 1 | 100% | 100% |  | 100% | 100%
43 | Y | 37.571-1 | 15.2.3 | UE Rx-Tx time difference measurement period for single positioning frequency layer in FR2 SA | The purpose of the test is to verify that the UE Rx-Tx measurement meets the requirements specified in clause 9.9.4.5 in AWGN propagation condition in FR2 in standalone scenario when single positioning frequency layer is configured. TS 38.133 9.9.4.5 | CATT | TBD | R5-220518 R5-222598 R5-225698 R5-227843 |  | 1 | 100% | 100% |  | 100% | 100%
44 | Y | 37.571-1 | 15.2.4 | UE Rx-Tx time difference measurement period for dual positioning frequency layer in FR2 SA | The purpose of the test is to verify that the UE Rx-Tx measurement meets the requirements specified in clause 9.9.4.5 in AWGN propagation condition in FR2 in standalone scenario when dual positioning frequency layers are configured. TS 38.133 9.9.4.5 | CATT | TBD | R5-220518 R5-222598 R5-227843 |  | 1 | 100% | 100% |  | 100% | 100%
57 |  | 37.571-1 | 15.3 | UE Rx-Tx time difference measurement accuracy test cases
44 | Y | 37.571-1 | 15.3.1 | UE Rx-Tx time difference measurement accuracy for single positioning frequency layer in FR1 SA | The purpose of the test is to verify that the UE Rx-Tx time difference measurement accuracy is within the specified limits in FR1 in standalone scenario when single positioning frequency layer is configured. TS 38.133 10.1.25 | CATT | TBD | R5-222603 R5-224401 R5-227843 |  | 1 | 100% | 100% |  | 100% | 100%
45 | Y | 37.571-1 | 15.3.2 | UE Rx-Tx time difference measurement accuracy for single positioning frequency layers in FR2 SA | The purpose of the test is to verify that the UE Rx-Tx time difference measurement accuracy is within the specified limits in FR2 in standalone scenario when single positioning frequency layer is configured. TS 38.133 10.1.25 | CATT | TBD | R5-222604 R5-224401 R5-227843 |  | 1 | 100% | 100% |  | 100% | 100%
10 |  | 37.571-1 | 16 | PRS-RSRP measurement requirements
58 |  | 37.571-1 | 16.2 | PRS-RSRP measurement period test cases
46 | Y | 37.571-1 | 16.2.1 | PRS-RSRP measurement period test case for single positioning frequency layer in FR1 SA | The purpose of the test is to verify that the PRS-RSRP measurement meets the requirements specified in clause 9.9.3.5 in AWGN propagation condition in FR1 in standalone scenario when single positioning frequency layer is configured. TS 38.133 9.9.3.5 | Rohde & Schwarz | TBD | R5-221206 R5-221206 R5-233651 |  | 1 | 100% | 100% |  | 100% | 100%
47 | Y | 37.571-1 | 16.2.2 | PRS-RSRP measurement period test case for dual positioning frequency layer in FR1 SA | The purpose of the test is to verify that the PRS-RSRP measurement meets the requirements specified in clause 9.9.3.5 in AWGN propagation condition in FR1 in standalone scenario when dual positioning frequency layers are configured. TS 38.133 9.9.3.5 | Rohde & Schwarz | TBD | R5-221207 R5-233657 |  | 1 | 100% | 100% |  | 100% | 100%
48 | Y | 37.571-1 | 16.2.3 | PRS-RSRP measurement period test case for single positioning frequency layer in FR2 SA | The purpose of the test is to verify that the PRS-RSRP measurement meets the requirements specified in clause 9.9.3.5 in AWGN propagation condition in FR2 in standalone scenario when single positioning frequency layer is configured. TS 38.133 9.9.3.5 | CATT | TBD | R5-224403 R5-231753 |  | 1 | 100% | 100% |  | 100% | 100%
49 | Y | 37.571-1 | 16.2.4 | PRS-RSRP measurement period test case for dual positioning frequency layer in FR2 SA | The purpose of the test is to verify that the PRS-RSRP measurement meets the requirements specified in clause 9.9.3.5 in AWGN propagation condition in FR2 in standalone scenario when dual positioning frequency layers are configured. TS 38.133 9.9.3.5 | CATT | TBD | R5-224404 R5-231754 |  | 1 | 100% | 100% |  | 100% | 100%
59 |  | 37.571-1 | 16.3 | PRS-RSRP measurement accuracy test cases
50 | Y | 37.571-1 | 16.3.1 | PRS-RSRP measurement accuracy with PRS in FR1 | The purpose of the test is to verify that the PRS-RSRP measurement accuracy is within the specified limits in FR1 in standalone scenario when single positioning frequency layer is configured. TS 38.133 10.1.24 | Rohde & Schwarz | TBD | R5-221208 R5-232710 |  | 1 | 100% | 100% |  | 100% | 100%
51 | Y | 37.571-1 | 16.3.2 | PRS-RSRP measurement accuracy with PRS in FR2 | The purpose of the test is to verify that the PRS-RSRP measurement accuracy is within the specified limits in FR2 in standalone scenario when single positioning frequency layer is configured. TS 38.133 10.1.24 | CATT | TBD | R5-225741 R5-232079 |  | 1 | 100% | 100% |  | 100% | 100%
52 |  | 37.571-1 | Annex | Annex
53 |  | 37.571-1 | Annex | Addition of conditions for NR PRS-based measurements and connection diagrams | Addition of conditions for NR PRS-based measurements and connection diagrams | CATT Rohde & Schwarz | RAN5#92 (Aug-21) | R5-215974 R5-221887 R5-223972 R5-225944 R5-226489 R5-231755 R5-232080 R5-232438 R5-235786 |  | 1 | 100% (+5%) | 100% (+5%) |  | 100% | 100%
TS 37.571-2: UE Positioning -Protocol
|  | 37.571-2 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
11 |  | 37.571-2 | 2, 3，8 | Introduction of Release-16 NR positioning protocol conformance contents | 1. Adding reference of TS 37.355, TS 38.305 and TS 38.331 2. Adding Release-16 NR positioning methods associated abbreviations 3. Adding Release-16 NR positioning associated definitions | CATT | RAN5#91-e (May-21) | R5-202537 R5-226513 R5-227526 R5-226515 R5-227527 R5-231022 |  | 0.1 | 100% | 100% |  | 100% | 100%
13 |  | 37.571-2 | 9.3.1.1 | Introduction of Release-16 NR positioning methods in Position Capability Transfer | Updating the tables in specific message contents | CATT | RAN5#91-e (May-21) | R5-221592 |  | 1 | 100% | 100% |  | 100% | 100%
14 |  | 37.571-2 | 9.3.1.2 | Introduction of Release-16 NR positioning methods in LPP Abort | 1. Adding Release-16 NR positioning methods associated sub-test 2. Updating the tables in specific message contents | CATT | RAN5#91-e (May-21) | R5-202536 |  | 1 | 100% | 100% |  | 100% | 100%
15 |  | 37.571-2 | 9.3.2 | Introduction of Release-16 NR positioning methods into LPP Transport | Updating the tables in specific message contents | CATT | RAN5#91-e (May-21) | R5-202536 |  | 1 | 100% | 100% |  | 100% | 100%
16 |  | 37.571-2 | 9.3.3.1B | Introduction of Release-16 NR positioning methods into LPP Error handling | 1. Adding Release 16 NR positioning methods features into the test case 2. Updating the tables in specific message contents 3. Addting the table for RESET UE POSITIONING STORED INFORMATION message | CATT | RAN5#91-e (May-21) | R5-202536 R5-217936 R5-217937 |  | 1 | 100% | 100% |  | 100% | 100%
17 |  | 37.571-2 | 9.3.4 | Introduction of Release-16 NR positioning methods into LPP Positioning Procedures | 1. Adding Release 16 NR positioning methods features into the test case 2. Updating the tables in specific message contents 3. Addting the table for RESET UE POSITIONING STORED INFORMATIONi message | CATT | RAN5#91-e (May-21) | R5-202536 R5-217936 R5-217937 |  | 1 | 100% | 100% |  | 100% | 100%
60 | Y | 37.571-2 | 9.4.1 | PosSIB broadcasting followed by location information transfer | TP1：[TS 37.355 7.2] with { a NAS signalling connection existing } ensure that { when { UE has no assistance data stored and receives the positioning assistance data via posSIBs and then UE receives a location request from LMF} then { the UE sends a PROVIDE LOCATION INFORMATION message containing a location estimate } } | CATT | RAN5#94 (Feb-22) | R5-221592 R5-223388 R5-224407 |  | 1 | 100% | 100% |  | 100% | 100%
61 | Y | 37.571-2 | 9.4.2 | PosSIB broadcasting followed by location information transfer / Positioning SI messages offset | TP1：[TS 38.331 5.2.2.3.2] with { a NAS signalling connection existing } ensure that { when { UE has no assistance data stored and receives the positioning assistance data via posSIBs and offsetToSI-Used-r16 is present and then UE receives a location request from LMF} then { the UE acquires the SI message at the correct position and then sends a PROVIDE LOCATION INFORMATION message containing a location estimate } } | CATT | RAN5#95 (May-22) | R5-223389 |  | 1 | 100% | 100% |  | 100% | 100%
64 | Y | 37.571-2 | 9.4.3 | On-demand PosSIB followed by location information transfer / RRC_connected state | TP1：[TS 38.331 5.2.2.3.5] (1) with { a NAS signalling connection existing } ensure that { when { UE has no assistance data stored and receives a REQUEST LOCATION INFORMATION message } then { the UE sends the DedicatedSIBRequest message indicating the requested posSIB } } TP2：[TS 37.355 7.2] (2) with { a NAS signalling connection existing } ensure that { when { UE receives the positioning assistance data via posSIBs after sending the onDemandSIB-Request message } then { the UE sends a PROVIDE LOCATION INFORMATION message containing a location estimate } | CATT |  | R5-225314 R5-225314 |  | 1 | 100% | 100% |  | 100% | 100%
TS 37.571-3: Applicability and ICS UE Positioning test cases
|  | 37.571-3 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
18 |  | 37.571-3 | 2, 3 | Introduction of Release-16 NR positioning support in common contents | 1. Adding reference of TS 37.355 2. Adding Release-16 NR positioning methods associated definitions and abbreviations | CATT | RAN5#91-e (May-21) | R5-202535 |  | 0.1 | 100% | 100% |  | 100% | 100%
19 |  | 37.571-3 | 4 | Introduction of test case applicability for Release-16 NR positioning support | 1. Adding test applicability and additional information for new TS 37.571-2 NR test cases in Table 4-9 2. Adding test applicability and additional information for new TS 37.571-1 NR test cases in Table 4-11 | CATT Rohde & Schwarz | TBD | R5-202534 R5-221888 R5-221594 R5-222608 R5-223391 R5-224409 R5-224411 R5-232439 |  | 0.1 | 100% | 100% |  | 100% | 100%
20 |  | 37.571-3 | Annex A | Addition of PICS for Release-16 NR Positioning Support | Adding Release-16 NR positioning support related PICS according to TS 37.355 | CATT | RAN5#91-e (May-21) | R5-202535 R5-216324 R5-216611 R5-225315 |  | 0.1 | 100% | 100% |  | 100% | 100%
TS 37.571-4: UE Positioning test suites (TTCN)
|  | 37.571-4 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
21 |  | 37.571-4 | <Clause> | Test suites for R16 NR positioning support | <Describe task> |  | TBD | R5-216658 | Progress of TTCN development is tracked in MCC TF160 reports to RAN5/RAN | 1 | 100% (+10%) | 100% (+10%) |  | 100% | 100%
TS 37.571-5: UE Positioning test scenarios and assistance data
|  | 37.571-5 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
22 |  | 37.571-5 | 2, 3 | Introduction of Release-16 NR positioning protocol conformance contents | 1. Adding reference of TS 37.355 2. Adding Release-16 NR positioning methods associated definitions and abbreviations | CATT | TBD | R5-234222 |  | 0.1 | 100% (+100%) | 100% (+100%) |  | 100% | 100%
24 |  | 37.571-5 | 4.6 | Addition of DL-TDOA scenario and assistance data | Adding description of DL-TDOA scenario and assistance data | CATT | TBD | R5-234222 |  | 0.1 | 100% (+100%) | 100% (+100%) |  | 100% | 100%
25 |  | 37.571-5 | 4.7 | Addition of DL-AoD scenario and assistance data | Adding description of DL-AoD scenario and assistance data | CATT | TBD | R5-234222 |  | 0.1 | 100% (+100%) | 100% (+100%) |  | 100% | 100%
28 |  | 37.571-5 | 11 | Addition of DL-TDOA positioning information | Adding DL-TDOA scenario and assistance data for signalling and minimum performance test cases in TS 37.571-1 and TS 37.571-2 | CATT | TBD | R5-234222 |  | 0.5 | 100% (+100%) | 100% (+100%) |  | 100% | 100%
29 |  | 37.571-5 | 12 | Addition of DL-AoD positioning information | Adding DL-AoD scenario and assistance data for signalling and minimum performance test cases in TS 37.571-1 and TS 37.571-2 | CATT | TBD | R5-234222 |  | 0.5 | 100% (+100%) | 100% (+100%) |  | 100% | 100%
End of workplan items. Note! Do not remove this row. Introduce new work plan rows/items above this row.
Note on A6: Unique ID for WP items (unique within the sub-area work plan) Note! As WP item numbers may be referenced from outside of this WP that means: - Do not change number for WP items that have been published. - Do not re-use WP item numbers if a WP item is deleted
Note on B6: Set to Y if the WP item represents a new test case that will be specified in RAN5 test specifications as an executable test case else leave blank.
Note on K6: The WP item's weight number is used to set the reletive weights between WP items used in the overall calculation of completeness. Setting it to 0 for a WP item means that it will not be included at all in the calculation.