## Cover sheet
3GPP TSG-RAN WG5 Meeting #101 | [10 empty] | R5-236854
Chicago, USA, 13 – 17 November 2023
Agenda Item: | 7.5.2
Source: | Samsung, Huawei, Hisilicon
Title: | WP - UE Conformance - Further enhancements on MIMO for NR
Work item code: | NR_feMIMO-UEConTest
Release: | Rel-17
Document for: | Information
RAN5 WP template v2.0-8
1. Introduction
The objective of this work item is to define the UE conformance requirements corresponding to ‘WI NR_feMIMO’, by analysing the test case impact, applicability and test environment, and updating the relevant conformance specifications. This work item will cover Signaling, Demod and RRM conformance test specifications for NR_feMIMO.
2. Work item status
Estimation of WI overall completion:
Area |  | Completion | Number of new completed test cases (Note 1) | Number of new test cases | Comments
Overall completion |  | 67% (+27%) | 3 (+3) | 33
Completion Compensation |  | -
| Note 1: | Only test cases completed for all applicable WP areas and sub-areas are counted. For completed test cases per WP areas and WP sub-areas see below.
Estimation WI completion per area and sub-area:
|  | Completion | Number of new completed test cases | Number of new test cases | Comments
SA Option 2 (SA NR) |  | 64.6% (+23.9%) | 3 (+3) | 27
FR1 |  | 66.4% (+21.4%) | 3 (+3) | 21
FR2 |  | 61.4% (+28.5%) | 3 (+3) | 9
NSA Option 3 (EN-DC) |  | 68.6% (+29.9%) | 3 (+3) | 25
FR1 |  | 76.8% (+25.1%) | 3 (+3) | 21
FR2 |  | 58.3% (+31.1%) | 3 (+3) | 7
FR1 + FR2 |  | 57% (+46.4%) | 3 (+3) | 3
Estimation of completion per TS (area):
|  | TS/TR overall completion |  |  | SA Option 2 (SA NR) | [6 empty] | NSA Option 3 (EN-DC)
TS/TR Scope | TS/TR | Completion | Number of new completed test cases | Number of new test cases | FR1 |  |  | FR2 |  |  |  | FR1 |  |  | FR2 |  |  | FR1 + FR2
[5 empty] | Completion | Number of new completed test cases | Number of new test cases | Completion | Number of new completed test cases | Number of new test cases |  | Completion | Number of new completed test cases | Number of new test cases | Completion | Number of new completed test cases | Number of new test cases | Completion | Number of new completed test cases | Number of new test cases
5GS
5GS Common
Common test environment | 38.508-1 | 9.1% (+0%) |  |  | 9.1% |  |  | 9.1% |  |  |  | 9.1% |  |  | 9.1% |  |  | 9.1%
Common ICS | 38.508-2 | 75% (+65.9%) |  |  | 75% (+65.9%) |  |  | 75% (+65.9%) |  |  |  | 75% (+65.9%) |  |  | 75% (+65.9%) |  |  | 75% (+65.9%)
NR RF/RRM
RF Demod/QSI test cases | 38.521-4 | 84.4% (+19.3%) | 0 | 16 | 84.4% (+19.3%) | 0 | 16 |  |  |  |  | 84.4% (+19.3%) | 0 | 16
RRM test cases | 38.533 | 41.2% (+6.4%) | 0 | 14 | 18.8% (+2.3%) | 0 | 2 | 68.5% (+14.7%) | 0 | 6 |  | 63.3% (+10%) | 0 | 2 | 46.2% (+3.7%) | 0 | 4 | 10.8%
Applicability RF, Demod/QSI and RRM test cases | 38.522 | 29.4% (-0%) |  |  | 36.7% |  |  | 6.7% |  |  |  | 36.7% |  |  | 33.3%
Test Tolerances analysis RRM and RF Rx test cases | 38.903 | 50% (+50%) |  |  | 50% (+50%) |  |  | 50% (+50%) | [9 empty] | 50% (+50%)
5GS RAN and CN protocols
Protocol test cases | 38.523-1 | 100% (+100%) | 3 (+3) | 3 | 100% (+100%) | 3 (+3) | 3 | 100% (+100%) | 3 (+3) | 3 |  | 100% (+100%) | 3 (+3) | 3 | 100% (+100%) | 3 (+3) | 3 | 100% (+100%) | 3 (+3) | 3
Applicability Protocol test cases | 38.523-2 | 100% (+100%) |  |  | 100% (+100%) |  |  | 100% (+100%) |  |  |  | 100% (+100%) |  |  | 100% (+100%) |  |  | 100% (+100%)
Test suites (TTCN) | 38.523-3
5 References
[1] RP-221401 | New WID on UE Conformance - Further enhancements on MIMO for NR
Note on B21: Overall completion of the work item reported at an earlier meeting will not be decreased if additional tasks are added or if corrections are made to the work plan. Instead the earlier reported completion status will be kept until necessary progress have been achieved such that completion exceeds the earlier reported completion level. The value of the Completion Compensation value represents the difference in the decrease caused by late additions or corrections to the work plan and the current estimated overall completion. '-' indicates that no compensation is applied.

## WP
WP Title: |  | WP - UE Conformance - Further enhancements on MIMO for NR | [11 empty] | Start of workplan status columns. Note! Do not remove this column. | WP item status |  |  |  |  | End of workplan columns. Note! Do not remove this column.
WI code |  | NR_feMIMO-UEConTest
WP Scope: |  | The objective of this work item is to define the UE conformance requirements corresponding to ‘WI NR_feMIMO’, by analysing the test case impact, applicability and test environment, and updating the relevant conformance specifications. This work item will cover Signaling, Demod and RRM conformance test specifications for NR_feMIMO. | [13 empty] | vs Area
WP Resp: |  | Chuying Gu ; Sunlin Zhu |  |  | guchunying@HUAWEI.COM ; sunlin.zhu@samsung.com | [5 empty] | WP item completion |  |  |  | SA Option 2 (SA NR) |  | NSA Option 3 (EN-DC)
TS Resp: |  | <TS responsible if a new TS is involved> |  |  | <Email to TS responsible>
WP Item ID | Is new test case? | TS/area | Clause | Title | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | Overall | SA Option 2 (SA NR) | NSA Option 3 (EN-DC) |  | FR1 | FR2 | FR1 | FR2 | FR1 + FR2
[15 empty] | 66.4% (+21.4%) | 61.4% (+28.5%) | 76.8% (+25.1%) | 58.3% (+31.1%) | 57% (+46.4%)
[15 empty] | 53 | 28 | 40 (-1) | 19 (-1) | 17
[15 empty] | 32.7 (+0.9) | 17.8 (+0.9) | 28.2 (-0.1) | 12.3 (-0.1) | 8.8 (+0.9)
5%
Start of work plan items. Note! Do not remove this row. Introduce new work plan rows/items below this row.
5GS
5GS Common
TS 38.508-1: Common test environment
|  | 38.508-1 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
1 |  | 38.508-1 | 4.6 | Default NG-RAN RRC message and information elements contents | Specifiying default message for FeMIMO |  | RAN5#101 (Nov-23) |  |  | 1 | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0%
2 |  | 38.508-1 | 4.6.3 | Radio resource control information elements | The procedure of unified TCI state is specified under NR feMIMO WI. The relevant messages need to be introduced to 38.508-1. | Huawei | RAN5#100 (Aug-23) | R5-235780 |  | 0.1 | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100%
TS 38.508-2: Common ICS
|  | 38.508-2 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
4 |  | 38.508-2 | A.4.3.2 | Physical Layer Baseline Implementation Capabilities | Add ICS as needed for the test case applicability statements for the new test cases introduced in RF, RRM and protocol test cases. | Huawei, HiSilicon, MediaTek | RAN5#101 (Nov-23) | R5-235611 R5-237395 R5-237396 | R5-235611 Addition of PICS for unified TCI state switch delay R5-237395 Addition of PICS for NR feMIMO test cases R5-237396 Addition of PICS for SRS partial sounding | 1 | 62.5% (+62.5%) | 50% (+50%) |  |  | 75% | 75% | 75% | 75% | 75%
NR RF/RRM
TS 38.521-4: Demod/QSI reporting test cases
5 |  | 38.521-4 | 5.1.1.3 | Applicability of requirements for optional UE features | add SFN Requirements applicability |  | RAN5#102 (Feb-24) | R5-233041 |  | 0.1 | 30% (+30%) | 30% (+30%) | 30% (+30%) |  | 30% |  | 30%
6 |  | 38.521-4 | 5.1.1.7 | Applicability of different requirements for HST | add applicability of requirements for HST Enhanced SFN Transmission schemes |  | RAN5#102 (Feb-24) | R5-233041 |  | 0.1 | 30% (+30%) | 30% (+30%) | 30% (+30%) |  | 30% |  | 30%
7 | Y | 38.521-4 | 5.2.2.1.20 | 2Rx FDD FR1 PDSCH HST-SFN Scheme A performance - 2x2 MIMO for both SA and NSA | add 2RX FDD Minimum requirements for HST-SFN Scheme A | Huawei | RAN5#102 (Feb-24) | R5-233588 R5-235145 | R5-235145 corrected the note 1 in the test case | 1 | 90% | 90% | 90% |  | 90% |  | 90%
8 | Y | 38.521-4 | 5.2.2.1.21 | 2Rx FDD FR1 PDSCH HST-SFN Scheme B performance - 2x2 MIMO for both SA and NSA | add 2RX FDD Minimum requirements for HST-SFN Scheme B | Huawei | RAN5#102 (Feb-24) | R5-233589 |  | 1 | 90% | 90% | 90% |  | 90% |  | 90%
9 | Y | 38.521-4 | 5.2.2.2.21 | 2Rx TDD FR1 PDSCH HST-SFN Scheme A performance - 2x2 MIMO for both SA and NSA | add 2RX TDD Minimum requirements for HST-SFN Scheme A | Huawei | RAN5#102 (Feb-24) | R5-233590 R5-235145 | R5-235145 corrected the note 1 in the test case | 1 | 90% | 90% | 90% |  | 90% |  | 90%
10 | Y | 38.521-4 | 5.2.2.2.22 | 2Rx TDD FR1 PDSCH HST-SFN Scheme B performance - 2x2 MIMO for both SA and NSA | add 2RX TDD Minimum requirements for HST-SFN Scheme B | Huawei | RAN5#102 (Feb-24) | R5-233591 |  | 1 | 90% | 90% | 90% |  | 90% |  | 90%
11 | Y | 38.521-4 | 5.2.3.1.19 | 4Rx FDD FR1 PDSCH HST-SFN Scheme A performance - 2x4 MIMO for both SA and NSA | add 4RX FDD Minimum requirements for HST-SFN Scheme A | Huawei | RAN5#102 (Feb-24) | R5-233592 R5-235145 |  | 1 | 90% | 90% | 90% |  | 90% |  | 90%
12 | Y | 38.521-4 | 5.2.3.1.20 | 4Rx FDD FR1 PDSCH HST-SFN Scheme B performance - 2x4 MIMO for both SA and NSA | add 4RX FDD Minimum requirements for HST-SFN Scheme B | Huawei | RAN5#102 (Feb-24) | R5-233593 R5-235145 | R5-235145 corrected the note 1 in the test case | 1 | 90% | 90% | 90% |  | 90% |  | 90%
13 | Y | 38.521-4 | 5.2.3.2.20 | 4Rx TDD FR1 PDSCH HST-SFN Scheme A performance - 2x4 MIMO for both SA and NSA | add 4RX TDD Minimum requirements for HST-SFN Scheme A | Huawei | RAN5#102 (Feb-24) | R5-233594 R5-235145 | R5-235145 corrected the note 1 in the test case | 1 | 90% | 90% | 90% |  | 90% |  | 90%
14 | Y | 38.521-4 | 5.2.3.2.21 | 4Rx TDD FR1 PDSCH HST-SFN Scheme B performance - 2x4 MIMO for both SA and NSA | add 4RX TDD Minimum requirements for HST-SFN Scheme B | Huawei | RAN5#102 (Feb-24) | R5-233595 |  | 1 | 90% | 90% | 90% |  | 90% |  | 90%
15 | Y | 38.521-4 | 5.3.2.1.5 | 2Rx FDD FR1 for PDCCH with intra-slot repetition 2 Tx antenna performance for both SA and NSA | add 2RX FDD Minimum requirements for PDCCH with intra-slot repetition | Samsung | RAN5#102 (Feb-24) | R5-233584 |  | 1 | 80% | 80% | 80% |  | 80% |  | 80%
16 | Y | 38.521-4 | 5.3.2.2.5 | 2Rx TDD FR1 for PDCCH with intra-slot repetition 2 Tx antenna performance for both SA and NSA | add 2RX TDD Minimum requirements for PDCCH with intra-slot repetition | Samsung | RAN5#102 (Feb-24) | R5-233585 R5-235256 | R5-235256 REG bundle size value in Table 5.3.2.2.5.4.3.1-1 was updated according to TS 38.101-4. | 1 | 80% | 80% | 80% |  | 80% |  | 80%
17 | Y | 38.521-4 | 5.3.3.1.4 | 4Rx FDD FR1 for PDCCH with intra-slot repetition 2 Tx antenna performance for both SA and NSA | add 4RX FDD Minimum requirements for PDCCH with intra-slot repetition | Samsung | RAN5#102 (Feb-24) | R5-233586 |  | 1 | 80% | 80% | 80% |  | 80% |  | 80%
18 | Y | 38.521-4 | 5.3.3.2.4 | 4Rx TDD FR1 for PDCCH with intra-slot repetition 2 Tx antenna performance for both SA and NSA | add 4RX TDD Minimum requirements for PDCCH with intra-slot repetition | Samsung | RAN5#102 (Feb-24) | R5-233587 |  | 1 | 80% | 80% | 80% |  | 80% |  | 80%
19 | Y | 38.521-4 | 6.3.2.1.7 | 2Rx FDD FR1 Single PMI with 8 ports TypeI-SinglePanel Codebook for Single-DCI based transmission scheme for both SA and NSA | add 2RX FDD Single PMI with 8 ports TypeI-SinglePanel Codebook for Single-DCI based transmission scheme | Samsung | RAN5#102 (Feb-24) | R5-237832 |  | 1 | 80% (+80%) | 80% (+80%) | 80% (+80%) |  | 80% |  | 80%
20 | Y | 38.521-4 | 6.3.2.2.8 | 2Rx TDD FR1 Single PMI with 8 ports TypeI-SinglePanel Codebook for Single-DCI based transmission scheme for both SA and NSA | add 2RX TDD Single PMI with 8 ports TypeI-SinglePanel Codebook for Single-DCI based transmission scheme | Samsung | RAN5#102 (Feb-24) | R5-237851 |  | 1 | 80% (+80%) | 80% (+80%) | 80% (+80%) |  | 80% |  | 80%
21 | Y | 38.521-4 | 6.3.3.1.7 | 4Rx FDD FR1 Single PMI with 8 ports TypeI-SinglePanel Codebook for Single-DCI based transmission scheme for both SA and NSA | add 4RX FDD Single PMI with 8 ports TypeI-SinglePanel Codebook for Single-DCI based transmission scheme | Samsung | RAN5#102 (Feb-24) | R5-237852 |  | 1 | 80% (+80%) | 80% (+80%) | 80% (+80%) |  | 80% |  | 80%
22 | Y | 38.521-4 | 6.3.3.2.7 | 4Rx TDD FR1 Single PMI with 8 ports TypeI-SinglePanel Codebook for Single-DCI based transmission scheme for both SA and NSA | add 4RX TDD Single PMI with 8 ports TypeI-SinglePanel Codebook for Single-DCI based transmission scheme | Samsung | RAN5#102 (Feb-24) | R5-237853 |  | 1 | 80% (+80%) | 80% (+80%) | 80% (+80%) |  | 80% |  | 80%
23 |  | 38.521-4 | A.3.2.1.1 | Reference measurement channels for SCS 15 kHz FR1 | add PDSCH Reference Channel for FDD PMI reporting requirements add PDSCH Reference Channel for FDD HST scenario |  | RAN5#102 (Feb-24) | R5-233596 |  | 0.1 | 100% | 100% | 100% |  | 100% |  | 100%
24 |  | 38.521-4 | A.3.2.2.2 | Reference measurement channels for SCS 30 kHz FR1 | add PDSCH Reference Channel for TDD PMI reporting requirements with UL-DL pattern FR1.30-1 add PDSCH Reference Channel for TDD UL-DL pattern FR1.30-1 and HST scenario |  | RAN5#102 (Feb-24) | R5-233596 |  | 0.1 | 100% | 100% | 100% |  | 100% |  | 100%
25 |  | 38.521-4 | A.3.3.2.1 | Reference measurement channels for SCS 15 kHz FR1 | add PDCCH Reference Channel (Time domain allocation 2 symbols) |  | RAN5#102 (Feb-24) |  |  | 0.1 | 0% | 0% | 0% |  | 0% |  | 0%
26 |  | 38.521-4 | B.3.5 | HST-SFN Scheme A Channel Profile | add HST-SFN Scheme A Channel Profile |  | RAN5#102 (Feb-24) | R5-233051 |  | 0.1 | 100% | 100% | 100% |  | 100% |  | 100%
27 |  | 38.521-4 | B.3.6 | HST-SFN Scheme B Channel Profile | add HST-SFN Scheme B Channel Profile |  | RAN5#102 (Feb-24) | R5-233051 |  | 0.1 | 100% | 100% | 100% |  | 100% |  | 100%
28 |  | 38.521-4 | Annex F | Measurement uncertainties and test tolerances | Capturing the MU/TT of performance test cases |  | RAN5#102 (Feb-24) | R5-233597 R5-237934 |  | 0.1 | 100% | 100% | 100% |  | 100% |  | 100%
29 |  | 38.521-4 | Annex G | Statistical Testing | Capturing the statistical testing information of performance test cases |  | RAN5#102 (Feb-24) | R5-233688 |  | 0.1 | 100% | 100% | 100% |  | 100% |  | 100%
TS 38.522: Applicability for RF, Demod/QSI reporting and RRM test cases
30 |  | 38.522 | 4 | Test case conditions and selection criteria | Added new conditional statement in Table 4.0-1 | Nokia, Nokia Shanghai Bell Huawei | RAN5#101 (Nov-23) | R5-234359 R5-234862 |  | 1 | 45% | 35% | 55% |  | 60% | 10% | 60% | 50%
31 |  | 38.522 | 4.1.4 | Performance conformance test cases | Add test case applicability statements for the new test cases introduced for 38.521-4. | Huawei, HiSilicon | RAN5#101 (Nov-23) | R5-233689 |  | 1 | 25% | 25% | 25% |  | 50% | 0% | 50% | 0%
32 |  | 38.522 | 4.2 | RRM conformance test cases | Add test case applicability statements for the new test cases introduced for 38.533. | Nokia, Nokia Shanghai Bell Huawei | RAN5#101 (Nov-23) | R5-234359 R5-234862 |  | 1 | 15% | 5% | 25% |  | 0% | 10% | 0% | 50%
TS 38.533: RRM test cases
|  | 38.533 | 4.5.5.0.5 | Minimum conformance requirements for TRP specific beam failure detection and beam failure recovery |  |  | RAN5#102 (Feb-24) |  |  | 1 | 0% |  | 0% |  |  |  | 0%
33 | Y | 38.533 | 4.5.5.7 | EN-DC FR1 TRP specific SSB-based beam failure detection and link recovery in non-DRX | The purpose of this test is to verify that the UE properly detects the TRP specific SSB-based beam failure in the set (q0,0), (q0,1) configured for a serving PSCell and that the UE performs correct SSB-based link recovery based on beam candidate set (q1,0) and (q1,1). The purpose is to test the downlink monitoring for beam failure detection within the UEs active DL BWP of the PSCell with schedulingRequestID-BFR-r17 configured, during the evaluation period, and link recovery, when no DRX is used. | Samsung | RAN5#102 (Feb-24) | R5-231714 R5-235896 | TS 38.522 applicability spec update is pending 508-2 UE Physical Layer Baseline Implementation Capabilities is needed. | 1 | 95% (+15%) |  | 95% (+15%) |  |  |  | 95%
34 | Y | 38.533 | 4.5.5.8 | EN-DC FR1 TRP specific Scell CSI-RS-based Beam Failure Detection and SSB-based Link Recovery in non-DRX | The purpose of this test is to verify that the UE properly detects the CSI-RS-based beam failure on the TRP using the respective configured BFD set q ̅_0,0 for TRP0 and q ̅_0,1for TRP1. | Samsung Huawei, HiSilicon | RAN5#102 (Feb-24) | R5-231715 R5-236362 R5-235896 | TS 38.522 applicability spec update is pending | 1 | 95% (+15%) |  | 95% (+15%) |  |  |  | 95%
35 |  | 38.533 | 5.5.5.0.5 | Minimum conformance requirements for TRP specific beam failure detection and beam failure recovery |  |  | RAN5#102 (Feb-24) |  |  | 1 | 0% |  | 0%
36 | Y | 38.533 | 5.5.5.8 | EN-DC TRP specific Beam Failure Detection and Link Recovery Test for FR2 PSCell configured with CSI-RS-based BFD and LR in DRX mode | The purpose of this test is to verify that the UE properly detects the TRP specific CSI-RS-based beam failure in the set (q0,0), (q0,1) configured for a serving PSCell and a cell with PCID different from the serving cell, and that the UE performs correct CSI-RS-based link recovery based on beam candidate set (q1,0) and (q1,1). The purpose is to test the downlink monitoring for beam failure detection within the UEs active DL BWP of the PSCell, during the evaluation period, and link recovery, when DRX is used. | Samsung | RAN5#102 (Feb-24) | R5-231716 R5-235897 | TS 38.522 applicability spec update is pending | 1 | 95% (+15%) |  | 95% (+15%) |  |  |  |  | 95%
37 |  | 38.533 | 5.5.11 | Unified TCI state switch delay | add sub-title | Huawei | RAN5#102 (Feb-24) |  |  |  | 0% |  | 0% |  |  |  |  | 0%
38 |  | 38.533 | 5.5.11.0 | Minimum conformance requirements |  | Huawei | RAN5#102 (Feb-24) |  |  | 1 | 0% |  | 0%
39 |  | 38.533 | 5.5.11.0.1 | Minimum conformance requirements for MAC-CE based downlink TCI state switch delay |  | Huawei | RAN5#102 (Feb-24) |  |  | 1 | 0% |  | 0%
40 |  | 38.533 | 5.5.11.0.2 | Minimum conformance requirements for MAC-CE based uplink TCI state switch delay |  | Huawei | RAN5#102 (Feb-24) |  |  | 1 | 0% |  | 0%
41 |  | 38.533 | 5.5.11.1 | MAC-CE based active joint TCI state switch | add sub-title | Huawei | RAN5#102 (Feb-24) |  |  |  | 0% |  | 0% |  |  |  |  | 0%
42 | Y | 38.533 | 5.5.11.1.1 | EN-DC FR2 MAC-CE based active joint TCI state switch | The purpose of this test is to verify the MAC-CE based joint TCI state switch delay requirement by a UE capable of beam correspondence without the need for UL beam sweeping. | Huawei | RAN5#102 (Feb-24) |  |  | 1 | 0% |  | 0% |  |  |  |  | 0%
43 |  | 38.533 | 5.5.11.2 | MAC-CE based active uplink TCI state switch | add sub-title | Huawei | RAN5#102 (Feb-24) |  |  |  | 0% |  | 0% |  |  |  |  | 0%
44 | Y | 38.533 | 5.5.11.2.1 | EN-DC FR2 MAC-CE based active uplink TCI state switch | The purpose of this test is to verify the MAC-CE based uplink TCI state switch delay requirement by a UE capable of beam correspondence without the need for UL beam sweeping. | Huawei | RAN5#102 (Feb-24) |  |  | 1 | 0% |  | 0% |  |  |  |  | 0%
45 | Y | 38.533 | 5.5.11.3 | MAC-CE based active downlink TCI state switch EN-DC FR2 MAC-CE based active downlink TCI state switch | add sub-title The purpose of this test is to verify the active DL TCI state switch delay requirement for unified TCI. | Huawei | RAN5#102 (Feb-24) | R5-234857 | Message contents are not complete. TT analysis is missing. | 1 | 90% |  | 90% |  |  |  |  | 90%
46 |  | 38.533 | 6.5.5 | Link recovery procedures |  |  | RAN5#102 (Feb-24) |  |  |  | 0% | 0% |  |  | 0%
47 |  | 38.533 | 6.5.5.0.5 | Minimum conformance requirements for TRP specific beam failure detection and beam failure recovery | [5 empty] | 1
48 | Y | 38.533 | 6.5.5.7 | NR SA FR1 TRP specific CSI-RS-based Beam Failure Detection and Link Recovery Test in DRX | The purpose of this test is to verify that the UE properly detects TRP specific CSI-RS-based beam failure in the sets q0,0 and q0,1 configured for a serving cell and that the UE performs correct CSI-RS-based link recovery based on beam candidate set q1,0 and q1,1. The purpose is to test the downlink monitoring for beam failure detection on TRP1 within the UEs active DL BWP, during the evaluation period, and link recovery, when DRX is used. | Samsung | RAN5#102 (Feb-24) | R5-231717 R5-235898 | TS 38.522 applicability spec update is pending | 1 | 95% (+15%) | 95% (+15%) |  |  | 95%
49 |  | 38.533 | 6.6.4.0.3 | Minimum conformance requirements for Inter-cell SSB based L1-RSRP Reporting | add sub-title | Apple | RAN5#102 (Feb-24) |  |  | 1 | 0% | 0% |  |  | 0%
50 | Y | 38.533 | 6.6.4.6 | NR SA FR1 SSB based Inter-cell L1-RSRP measurement in DRX | The purpose of this test is to verify that the UE makes correct reporting of L1-RSRP measurement in a cell with PCI different from serving cell. | Apple | RAN5#102 (Feb-24) |  |  | 1 | 0% | 0% |  |  | 0%
51 |  | 38.533 | 7.5.5.0.5 | Minimum conformance requirements for TRP specific beam failure detection and beam failure recovery |  | Apple | RAN5#102 (Feb-24) |  |  | 1 | 0% | 0% |  |  | 0%
52 | Y | 38.533 | 7.5.5.9 | NR SA FR2 TRP specific Scell CSI-RS-based Beam Failure Detection and Link Recovery Test in DRX | The purpose of this test is to verify that the UE properly detects TRP specific SSB-based beam failure and link recovery in the sets q ̅_0,0 and q ̅_0,1 for TRP1 when no DRX is used for an FR2 serving cell requirements. | Samsung | RAN5#102 (Feb-24) | R5-231718 R5-235899 | TT analysis has not been provided TS 38.522 applicability spec update is pending | 1 | 95% (+15%) | 95% (+15%) |  |  |  | 95%
53 | Y | 38.533 | 7.5.5.10 | NR SA FR2 TRP specific SSB-based Beam Failure Detection and Link Recovery Test in non-DRX | The purpose of this test is to verify that the UE properly detects TRP specific CSI-RS-based beam failure and link recovery in the sets q ̅_0,0 and q ̅_0,1 for TRP1 when DRX is used for an FR2 active Scell requirements in TS38.133 clause 8.18. | Samsung | RAN5#102 (Feb-24) | R5-231719 R5-235899 | TT analysis has not been provided TS 38.522 applicability spec update is pending | 1 | 95% (+15%) | 95% (+15%) |  |  |  | 95%
54 |  | 38.533 | 7.5.13 | Unified TCI state switching delay | add sub-title | Huawei | RAN5#102 (Feb-24) |  |  |  | 0% | 0% |  |  |  | 0%
55 |  | 38.533 | 7.5.13.0 | Minimum conformance requirements |  | Huawei | RAN5#102 (Feb-24) |  |  |  | 0% | 0% |  |  | 0%
56 |  | 38.533 | 7.5.13.0.1 | Minimum conformance requirements for MAC-CE based downlink TCI state switch delay |  | Huawei | RAN5#102 (Feb-24) |  |  |  | 0% | 0% |  |  | 0%
57 |  | 38.533 | 7.5.13.0.2 | Minimum conformance requirements for MAC-CE based uplink TCI state switch delay |  | Huawei | RAN5#102 (Feb-24) |  |  |  | 0% | 0% |  |  | 0%
58 | Y | 38.533 | 7.5.13.1 | MAC-CE based active joint TCI state switching NR SA FR2 MAC-CE based active joint TCI state switch | add sub-title The purpose of this test is to verify both active downlink and uplinke TCI state switch delay requirement, respectively, by using joint TCI state of unified TCI state switch framework. | Huawei | RAN5#102 (Feb-24) | R5-234858 | Message contents are not complete. TT analysis is missing. | 1 | 90% | 90% |  |  |  | 90%
59 | Y | 38.533 | 7.5.13.2 | MAC-CE based active uplink TCI state switch NR SA FR2 MAC-CE based active uplink TCI state switch | add sub-title The purpose of this test is to verify fulfillment of the uplink TCI switch delay requirement by a UE capable of beam correspondence without the need for UL beam sweeping. | Huawei | RAN5#102 (Feb-24) | R5-234859 | Message contents are not complete. TT analysis is missing. | 1 | 90% | 90% |  |  |  | 90%
60 | Y | 38.533 | 7.5.13.3 | MAC-CE based active downlink TCI state switch NR SA FR2 MAC-CE based active downlink TCI state switch | add sub-title The purpose of this test is to verify the active TCI state switch delay requirement. | Huawei | RAN5#102 (Feb-24) | R5-234860 | Message contents are not complete. TT analysis is missing. | 1 | 90% | 90% |  |  |  | 90%
61 |  | 38.533 | 7.6.3.0.3 | Minimum conformance requirements for Inter-cell SSB based L1-RSRP Reporting | add sub-title | Nokia, Nokia Shanghai Bell. | RAN5#102 (Feb-24) |  |  |  | 0% | 0% |  |  |  | 0%
62 | Y | 38.533 | 7.6.3.6 | NR SA FR2 SSB based Inter-cell L1-RSRP measurement in non-DRX | The purpose of this test is to verify that the UE makes correct reporting of L1-RSRP measurement. | Nokia, Nokia Shanghai Bell. | RAN5#102 (Feb-24) | R5-235703 R5-237793 | Test Applicability in TS 38.522 requires an update | 1 | 95% (+95%) | 95% (+95%) |  |  |  | 95%
63 |  | 38.533 | A.3 | Reference SSB configuration | add new SSB pattern for FR1 and FR2 |  | RAN5#102 (Feb-24) |  |  | 0.1 | 0% | 0% | 0% |  | 0% | 0% |  |  | 0% | 0
64 |  | 38.533 | A.10A | Unified TCI State Configuration | add unified TCI state configuration | Huawei | RAN5#102 (Feb-24) |  |  | 0.1 | 0% | 0% | 0% |  | 0% | 0% |  |  | 0%
65 |  | 38.533 | A.H.3 | RRC message content exceptions | add new message contents for TRP specific BFD and RLM | Samsung | RAN5#102 (Feb-24) | R5-231713 |  | 0.1 | 90% | 90% | 90% |  | 90% | 90% |  |  | 90%
66 |  | 38.533 | Annex E | Cell configuration mapping |  | Huawei | RAN5#102 (Feb-24) | R5-231713 |  | 0.1 | 90% | 90% | 90% |  | 90% | 90% |  |  | 90%
67 |  | 38.533 | Annex F | Measurement uncertainties and test tolerances |  | Huawei Nokia, Nokia Shanghai Bell. Samsung | RAN5#102 (Feb-24) | R5-235705 R5-237793 R5-237702 |  | 0.1 | 90% | 90% | 90% |  | 90% | 90% |  |  | 90%
68 |  | 38.533 | Annex G | Cell configuration mapping |  |  | RAN5#102 (Feb-24) |  |  | 1 | 0% | 0% | 0% |  | 0% | 0% |  |  | 0%
69 |  | 38.533 | Annex H | Default message contents for RRM |  |  | RAN5#102 (Feb-24) |  |  | 1 | 0% | 0% | 0% |  | 0% | 0% |  |  | 0%
TR 38.903: Test Tolerances analysis RRM and RF Rx test cases
70 |  | 38.903 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
71 |  | 38.903 | 8 | Grouping of test cases defined in TS 38.533 | To add TT analysis for NR FeMIMO RRM test cases. | Samsung Nokia, Nokia Shanghai Bell. | RAN5#101 (Nov-23) | R5-235461 R5-235462 R5-235923 R5-235924 R5-235925 R5-235926 R5-236223 |  | 1 | 50% (+50%) | 50% (+50%) | 50% (+50%) |  | 50% | 50% |  |  | 50%
RAN and CN protocol
TS 38.523-1: Protocol test cases
|  | 38.523-1 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
Layer 2
72 | Y | 38.523-1 | 7.1.1.1.19 | Random access procedure / Successful / Beam Failure / Unified TCI | TP1: with { UE in RRC_CONNECTED state with TCI-State_r17 configured and periodic SRS resource configured, and RACH procedure due to beam failure is triggered } ensure that { when { UE initiates the Random Access Procedure, and receives the first PDCCH in the search space provided by recoverySearchSpaceID } then { UE starts to transmit SRS that associates with the indicated unified TCI state } } | MediaTek (Beijing) Inc | RAN5#101 (Nov-23) | R5-236168 |  | 1 | 100% (+100%) | 100% (+100%) | 100% (+100%) |  | 100% | 100% | 100% | 100% | 100%
73 | Y | 38.523-1 | 7.1.1.2.7 | Correct HARQ process handling / Unified TCI Activation | TP1: with { UE in RRC_CONNECTED state with TCI-State_r17 configured and 2 unified TCI states are activated by MAC-CE } ensure that { when { UE receives PDSCH scheduling by DCI_1_1 carring the 1st activated unified TCI state } then { UE sends a HARQ feedback on the HARQ process } } TP2: with { UE in RRC_CONNECTED state with TCI-State_r17 configured and 2 unified TCI states are activated by MAC-CE } ensure that { when { UE receives DCI_1_1 carring the 2nd activated unified TCI state without DL assignment } then { UE sends a HARQ feedback on the HARQ process } } | MediaTek (Beijing) Inc | RAN5#101 (Nov-23) | R5-236169 |  | 1 | 100% (+100%) | 100% (+100%) | 100% (+100%) |  | 100% | 100% | 100% | 100% | 100%
RRC
|  | 38.523-1 | 8.1.5.12 | Partial Sounding | sub-title |  | TBD
74 | Y | 38.523-1 | 8.1.5.12.1 | Partial Sounding / RCC_CONNECTED / RRCReconfiguration / Measurement of NR Cells | TP1: with { UE in NR RRC_CONNECTED state } ensure that { when {UE receives an RRCReconfiguration message with partialFreqSounding-r17 configured } then {UE performs SRS transmission using the resource on UL subframe configured in by partialFreqSounding-r17 } | Huawei, HiSilicon | RAN5#101 (Nov-23) | R5-237397 |  | 1 | 100% (+100%) | 100% (+100%) | 100% (+100%) |  | 100% | 100% | 100% | 100% | 100%
TS 38.523-2: Applicability for Protocol test cases
75 |  | 38.523-2 | 4.1 | Protocol conformance test cases applicability | Add test case applicability statements for the new test cases introduced in 38.523-1 |  | RAN5#101 (Nov-23) | R5-236170 R5-237398 | R5-236170 Addition of applicability for NR feMIMO TC 7.1.1.1.19 and 7.1.1.2.7 R5-237398 Addition of test applicability for SRS partial sounding | 0.1 | 100% (+100%) | 100% (+100%) | 100% (+100%) |  | 100% | 100% | 100% | 100% | 100%
76 |  | 38.523-2 | 4.2 | Protocol conformance test cases Applicability Condition | Add new ICS statements. |  | RAN5#101 (Nov-23) | R5-236170 R5-237398 | R5-236170 Addition of applicability for NR feMIMO TC 7.1.1.1.19 and 7.1.1.2.7 R5-237398 Addition of test applicability for SRS partial sounding | 0.1 | 100% (+100%) | 100% (+100%) | 100% (+100%) |  | 100% | 100% | 100% | 100% | 100%
TS 38.523-3: Protocol test suites (TTCN)
|  | 38.523-3 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
TBD |  | 38.523-3 | <Clause> | <Title of task> | <Describe task> |  | TBD |  |  | TBD | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0%
End of workplan items. Note! Do not remove this row. Introduce new work plan rows/items above this row.
Note on A6: Unique ID for WP items (unique within the sub-area work plan) Note! As WP item numbers may be referenced from outside of this WP that means: - Do not change number for WP items that have been published. - Do not re-use WP item numbers if a WP item is deleted
Note on B6: Set to Y if the WP item represents a new test case that will be specified in RAN5 test specifications as an executable test case else leave blank.
Note on K6: The WP item's weight number is used to set the reletive weights between WP items used in the overall calculation of completeness. Setting it to 0 for a WP item means that it will not be included at all in the calculation.