## Cover sheet
3GPP TSG-RAN WG5 Meeting #101 | [10 empty] | R5-237086
Chicago , United States, 13th – 17th Nov. 2023
Agenda Item: | 7.5.2
Source: | Huawei, HiSilicon
Title: | WP UE Conformance Test Aspects for RF requirements for NR frequency range 1 (FR1)
Work item code: | NR_RF_FR1-UEConTest
Release: | Rel-16
Document for: | Information
RAN5 WP template v2.0
1. Introduction
The objective of the UE Conformance Test Aspects for RF requirements for NR frequency range 1 (FR1) work item is to define the UE conformance requirements corresponding to WID on RF requirements for NR frequency range 1 (FR1) with Unique identifier 830087, analyse the test case impact, applicability, test environment, and update the relevant conformance specifications for the FR1 enhancement the RAN4 work item in Rel-16. At the RAN#87-e meeting the Rel-16 RAN5 work item for RF requirement for NR frequency range 1 (NR_RF_FR1-UEConTest) was approved [1]. The purpose of present document is to provide a work plan for the RAN5 work item. The work plan is updated after each RAN5 meeting to give the status of the work item. Quite a few R16 FR1 NR CA configurations for intra-band contiguous CA/intra-band non-contiguous CA are included in the scope of both "NR_RF_FR1-UEConTest" WI and "NR_CADC_NR_LTE_DC_R16-UEConTest" WI. These overlapped band combos will still be kept and monitored in the WP of "NR_CADC_NR_LTE_DC_R16-UEConTest". CA_n77C is selected as the "UL intra-band contiguous CA configuration" and CA_n77(2A) is selected as the "UL intra-band non-contiguous CA configuration" to complete the test cases in "NR_RF_FR1-UEConTest" WI.
2. Work item status
Estimation of WI overall completion:
Area |  | Completion | Number of new completed test cases (Note 1) | Number of new test cases | Comments
Overall completion |  | 100% (+27%) | 5.2 | 5.2
Completion Compensation |  | -
| Note 1: | Only test cases completed for all applicable WP areas and sub-areas are counted. For completed test cases per WP areas and WP sub-areas see below.
Estimation WI completion per area and sub-area:
|  | Completion | Number of new completed test cases | Number of new test cases | Comments
SA Option 2 (SA NR) |  | 100% (+27.1%) | 3.1 | 3.1
FR1 |  | 100% (+27.1%) | 3.1 | 3.1
FR2
FR1 + FR2
NSA Option 3 (EN-DC) |  | 100% (+21.3%) | 2.1 | 2.1
FR1 |  | 100% (+21.3%) | 2.1 | 2.1
FR2
FR1 + FR2
Estimation of completion per TS (area):
|  | TS/TR overall completion |  |  | SA Option 2 (SA NR) | [8 empty] | NSA Option 3 (EN-DC)
TS/TR Scope | TS/TR | Completion | Number of new completed test cases | Number of new test cases | FR1 |  |  | FR2 |  |  | FR1 + FR2 |  |  | FR1 |  |  | FR2 |  |  | FR1 + FR2
[5 empty] | Completion | Number of new completed test cases | Number of new test cases | Completion | Number of new completed test cases | Number of new test cases | Completion | Number of new completed test cases | Number of new test cases | Completion | Number of new completed test cases | Number of new test cases | Completion | Number of new completed test cases | Number of new test cases | Completion | Number of new completed test cases | Number of new test cases
5GS
5GS Common
Common test environment | 38.508-1 | 100% (+4.6%) |  |  | 100% (+4.6%)
Common ICS | 38.508-2 | 100% (+30%) |  |  | 100% (+30%) | [8 empty] | 100% (+30%)
NR RF/RRM
FR1 RF common parts | 38.521-1 | 100% (+35.4%) |  |  | 100% (+35.4%)
FR1 RF Tx test cases | 38.521-1 Tx | 100% (+26.9%) | 1 | 1 | 100% (+26.9%) | 1 | 1
FR1 RF Rx test cases | 38.521-1 Rx | 100% |  |  | 100%
FR1 and FR2 Interworking operation with other radios RF common parts | 38.521-3
FR1 and FR2 Interworking operation with other radios RF Tx test cases | 38.521-3 Tx | 100% | 1 | 1 | [9 empty] | 100% | 1 | 1
FR1 and FR2 Interworking operation with other radios RF Rx test cases | 38.521-3 Rx
RRM test cases | 38.533 | 100% | 3.2 | 3.2 | 100% | 2.1 | 2.1 | [6 empty] | 100% | 1.1 | 1.1
Applicability RF, Demod/QSI and RRM test cases | 38.522 | 100% (+94.6%) |  |  | 100% (+94.8%) | [8 empty] | 100% (+90%)
Test Tolerances analysis RRM and RF Rx test cases | 38.903 | 100% |  |  | 100% | [8 empty] | 100%
Test Point analysis receiver and transmitter test cases | 38.905 | 100% (+41.9%) |  |  | 100% (+40%)
5GS RAN and CN protocols
Protocol test cases | 38.523-1
Applicability Protocol test cases | 38.523-2
Test suites (TTCN) | 38.523-3
5 References
[1] RP-200094 | New WID on: UE Conformance Test Aspects for RF requirements for NR frequency range 1 (FR1)
Note on B21: Overall completion of the work item reported at an earlier meeting will not be decreased if additional tasks are added or if corrections are made to the work plan. Instead the earlier reported completion status will be kept until necessary progress have been achieved such that completion exceeds the earlier reported completion level. The value of the Completion Compensation value represents the difference in the decrease caused by late additions or corrections to the work plan and the current estimated overall completion. '-' indicates that no compensation is applied.

## WP
WP Title: |  | WP UE Conformance Test Aspects for RF requirements for NR frequency range 1 (FR1) | [11 empty] | Start of workplan status columns. Note! Do not remove this column. | WP item status | [5 empty] | End of workplan columns. Note! Do not remove this column.
WI code |  | NR_RF_FR1-UEConTest
WP Scope: |  | The purpose of this present document is to provide a work plan for the RAN5 work item RF requirements for NR frequency range 1 (FR1) comprising the necessary updates to existing clauses/test cases and new clauses/test cases as appropriate, with the aim of provision of conformance testing to reflect the relevant core and performance requirement (relevant core spec WIs indicated in the WID). | [13 empty] | vs Area
WP Resp: |  | Yuxin HAO, Huawei |  |  | haoyuxin@huawei.com | [5 empty] | WP item completion |  |  |  | SA Option 2 (SA NR) |  |  | NSA Option 3 (EN-DC)
TS Resp: |  | n/a |  |  | n/a
WP Item ID | Is new test case? | TS/area | Clause | Title | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | Overall | SA Option 2 (SA NR) | NSA Option 3 (EN-DC) |  | FR1 | FR2 | FR1 + FR2 | FR1 | FR2 | FR1 + FR2
[15 empty] | 100% (+27.1%) |  |  | 100% (+21.3%)
[15 empty] | 115 | 0 | 0 | 7 (-2) | 0 | 0
[15 empty] | 99 | 0 | 0 | 3.5 (-0.2) | 0 | 0
5%
Start of work plan items. Note! Do not remove this row. Introduce new work plan rows/items below this row.
LTE
LTE Common
TS 36.508: Common test environment
5GS - RAN and CN
5GS Common
TS 38.508-1: Common test environment
|  | 38.508-1 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
1 |  | 38.508-1 | 4.3.1.1.3 | NR intra-band contiguous CA in FR1 | Introduction of Test frequency for CA_n77C | Huawei | RAN5#92 (Aug-21) | R5-205728, R5-206757, R5-206758, R5-206759 | Test frequencies for CA_40B, CA_n78B are completed under this WI. future work will be moved to WI NR_CADC_NR_LTE_DC_R16-UEConTest | 1 | 100% | 100% |  |  | 100%
2 |  | 38.508-1 | 4.3.1.1.3 | NR intra-band non-contiguous CA in FR1 | Introduction of Test frequency for CA_n77(2A) | Huawei | RAN5#92 (Aug-21) | R5-206758 R5-233091 | Note: CA-n77(2A) is selected as example CA configuration to complete the test case | 1 | 100% | 100% |  |  | 100%
3 |  | 38.508-1 | 4.6.3 | Radio resource control information elements | Updating message contents | Huawei | RAN5#98 (Feb-23) | R5-206760 |  | 0.3 | 100% (+40%) | 100% (+40%) |  |  | 100%
131 |  | 38.508-1 | Annex | Set up diagrams，Test frequency calculations | Introducing new connection diagrams Updating test frequency calculation for intra-band non-contiguous UL CA | Ericsson | RAN5#96 (Aug-22) | R5-221292 R5-227892 |  | 0.3 | 100% | 100% |  |  | 100%
TS 38.508-2: Common ICS
|  | 38.508-2 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
4 |  | 38.508-2 | A.x | Annex A (normative):ICS proforma for NR/5GS Generation User Equipment | Add ICS as needed for the test case applicability statements for the new test cases introduced in RF, RRM and protocol test cases. | Huawei | RAN5#98 (Feb-23) | R5-211910 R5-221793 R5-223301 |  | 0.3 | 100% (+30%) | 100% (+30%) | 100% (+30%) |  | 100% |  |  | 100%
NR RF/RRM
TS 38.521-1: FR1 RF test cases - Common parts (general clauses, Annexes)
|  | 38.521-1 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
5 |  | 38.521-1 | 5.5A.0 | Configurations for CA/General | [Almost contiguous allocation for CP-OFDM] Non-contiguous allocation not apply to intra-band CA | Huawei | RAN5#89-e (Nov-20) | R5-205731 | TS 38.101-1, 5.5A.0 | 0.7 | 100% | 100% |  |  | 100%
6 |  | 38.521-1 | 5.2A, 5.5A | Operating bands for CA, Configurations for CA | 5.5A.2, 5.5A: Intra-band non-contiguous UL/DL CA: Adding CA_n77(2A) Intra-band UL contiguous CA: Adding CA_n77C UL switching 5.2A.2: Adding DL interruption capability for UL switching | Huawei | RAN5#93 (Nov-21) | R5-203688 R5-211765 | TS 38.101-1, 5.2A, 5.5A | 0.7 | 100% | 100% |  |  | 100%
7 |  | 38.521-1 | 3.2, 5.3A.3, 5.4A | Symbols, Minimum guardband and transmission bandwidth configuration for CA, Channel arrangement for CA | [Intra-band UL contiguous CA] Adding general requirements for intra-band contiguous UL CA | Huawei | RAN5#89-e (Nov-20) | R5-203687 | TS 38.101-1, 3.2, 5.3A.3, 5.4A | 0.7 | 100% | 100% |  |  | 100%
8 |  | 38.521-1 | 5.3A.5 | UE channel bandwidth per operating band, and Configurations for intra-band non-contiguous for CA | [Intra-band UL non-contiguous CA] Adding general requirements for intra-band non-contiguous UL CA | Huawei | RAN5#93 (Nov-21) | R5-211805 | TS 38.101-1, 5.3A.5 | 0.7 | 100% | 100% |  |  | 100%
9 |  | 38.521-1 | F.1.2 | Measurement of transmitter | [Intra-band UL contiguous and non-contiguous CA] Intra-band contiguous: Adding MU for intra-band UL CA Intra-band non-contiguous: Adding MU for intra-band UL CA | Huawei | RAN5#93 (Nov-21) | R5-203689 R5-211912 R5-210385 R5-225078 R5-237907 |  | 1 | 100% (+85%) | 100% (+85%) |  |  | 100%
10 |  | 38.521-1 | F.3.2 | Measurement of transmitter | [Intra-band UL contiguous and non-contiguous CA] Intra-band contiguous: Adding TT for intra-band UL CA Intra-band non-contiguous: Adding TT for intra-band UL CA | Huawei | RAN5#93 (Nov-21) | R5-203689 R5-211912 R5-210385 R5-225078 R5-237907 |  | 1 | 100% (+85%) | 100% (+85%) |  |  | 100%
TS 38.521-1: FR1 RF test cases - Tx
|  | 38.521-1 Tx |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
11 |  | 38.521-1 Tx | 6.1A | General | [Intra-band UL contiguous CA] Adding instruction of RB allocations for intra-band UL CA | Huawei | RAN5#97 (Nov-22) | R5-203690 R5-217487 R5-221121 R5-225114 R5-231637 R5-231075 R5-235821 | TS 38.101-1 6.1A | 0.5 | 100% | 100% |  |  | 100%
12 |  | 38.521-1 Tx | 6.2.2 | UE maximum output power reduction | [Almost contiguous allocation for CP-OFDM] Adding almost contiguous allocation for PC2; Indicating the applicable release | Huawei | RAN5#89-e (Nov-20) | R5-202957 | TS 38.101-1 6.2.2 | 1 | 100% | 100% |  |  | 100%
6.2A Transmitter power for CA
13 |  | 38.521-1 Tx | 6.2A.1.0 | Minimum conformance requirements | [Intra-band UL contiguous CA] Adding minimum requirement for CA_n77C [Intra-band UL non-contiguous CA] Adding minimum requirement for CA_n77(2A) | Huawei | RAN5#93 (Nov-21) | R5-203691 R5-215298 | TS 38.101-1 6.2A.1 Note: CA_n77C and CA-n77(2A) are selected as example CA configuration to complete the test case | 0.1 | 100% | 100% |  |  | 100%
14 |  | 38.521-1 Tx | 6.2A.1.1 | UE maximum output power for CA (2 UL CA) | [Intra-band UL contiguous CA] Intra-band contiguous UL: adding testing for BW class B and C | Huawei | RAN5#92 (Aug-21) | R5-203691 | TS 38.101-1 6.2A.1.1 TS 38.522: TR 38.905: No test point defined for intra-band contiguous UL CA | 1 | 100% | 100% |  |  | 100%
15 |  | 38.521-1 Tx | 6.2A.1.1 | UE maximum output power for CA (2 UL CA) | [Intra-band UL non-contiguous CA] Intra-band non-contiguous UL CA for CA_n77(2A) |  | RAN5#93 (Nov-21) | R5-215298 | TS 38.101-1 6.2A.1.2 TS 38.522: TR 38.905: R5-221123 Note: CA-n77(2A) is selected as example CA configuration to complete the test case | 1 | 100% | 100% |  |  | 100%
16 |  | 38.521-1 Tx | 6.2A.2.0 | Minimum conformance requirements | [Intra-band UL contiguous CA] Adding minimum requirement for CA_n77C [Intra-band UL non-contiguous CA] Adding minimum requirement for CA_n77(2A) | Huawei | RAN5#93 (Nov-21) | R5-204984 R5-221122 R5-231291 R5-231295 | TS 38.101-1 6.2A.2 TS 38.905: R5-221123 Note: CA_n77C and CA-n77(2A) are selected as example CA configuration to complete the test case | 0.1 | 100% | 100% |  |  | 100%
17 |  | 38.521-1 Tx | 6.2A.2.1 | Maximum Power Reduction (MPR) for CA (2 UL CA) | [Intra-band UL contiguous CA] Intra-band UL contiguous CA: adding testing for CA_n77C | Huawei, OPPO | RAN5#92 (Aug-21) | R5-204984 R5-211804 R5-216032 R5-218457 R5-221122 | TS 38.101-1 6.2A.2.1 TS 38.522: TR 38.905: R5-204727 Note: CA_n77C is selected as example CA configuration to complete the test case | 1 | 100% | 100% |  |  | 100%
18 |  | 38.521-1 Tx | 6.2A.2.1 | Maximum Power Reduction (MPR) for CA (2 UL CA) | [Intra-band UL non-contiguous CA] Adding testing for CA_n77(2A) |  | RAN5#93 (Nov-21) | R5-221122 | TS 38.101-1 6.2A.2.2 TS 38.522 TR 38.905 Note: CA-n77(2A) is selected as example CA configuration to complete the test case | 1 | 100% | 100% |  |  | 100%
22 |  | 38.521-1 Tx | 6.2A.4.0 | Minimum conformance requirements | [Intra-band UL contiguous CA] Intra-band contiguous UL CA: adding minimum requirement for CA_n77C [Intra-band UL non-contiguous CA] Adding minimum requirement for CA_n77(2A) | Huawei | RAN5#93 (Nov-21) | R5-204974 R5-237902 | TS 38.101-1 6.2A.4 Note: CA_n77C and CA-n77(2A) are selected as example CA configuration to complete the test case | 0.1 | 100% (+50%) | 100% (+50%) |  |  | 100%
23 |  | 38.521-1 Tx | 6.2A.4.1 | Configured transmitted power for CA (2 UL CA) | [Intra-band UL contiguous CA] Intra-band contiguous UL CA: adding testing for CA_n77C | Huawei | RAN5#92 (Aug-21) | R5-204974 R5-211804 R5-218292 | TS 38.101-1 6.2A.4.1.1 TS 38.522: TR 38.905: R5-204838 Note: CA_n77C is selected as example CA configuration to complete the test case | 1 | 100% | 100% |  |  | 100%
24 |  | 38.521-1 Tx | 6.2A.4.1 | Configured transmitted power for CA (2 UL CA) | [Intra-band UL non-contiguous CA] Adding testing for CA_n77(2A) |  | RAN5#93 (Nov-21) | R5-237902 | TS 38.101-1 6.2A.4.1.2 TS 38.522 TR 38.905 Note: CA_n77(2A) is selected as example CA configuration to complete the test case | 1 | 100% (+100%) | 100% (+100%) |  |  | 100%
25 |  | 38.521-1 Tx | 6.2D.1 | UE maximum output power for UL MIMO | [UL MIMO] New UL-MIMO bands: n1, n2, n3, n7, n25, n30, n34, n38, n39, n40, n48, n66, n70, n71 | Huawei | RAN5#91-e (May-21) | R5-205734 R5-210918 | TS 38.101-1, 6.2D.1 | 0.5 | 100% | 100% |  |  | 100%
26 |  | 38.521-1 Tx | 6.2D.2 | UE maximum output power reduction for UL MIMO | [UL MIMO] New UL-MIMO bands: n1, n2, n3, n7, n25, n30, n34, n38, n39, n40, n48, n66, n70, n71 | Huawei | RAN5#91-e (May-21) | R5-205735 R5-210918 R5-215297 | TS 38.101-1, 6.2D.2 | 0.5 | 100% | 100% |  |  | 100%
27 |  | 38.521-1 Tx | 6.2D.3 | UE additional maximum output power reduction for UL MIMO | [UL MIMO] New UL-MIMO bands: n1, n2, n3, n7, n25, n30, n38, n39, n48, n66, n70, n71 | Huawei | RAN5#97 (Nov-22) | R5-211678 R5-212988 R5-221794 R5-223699 R5-237650 | TS 38.101-1, 6.2D.3 TR 38.905: | 1 | 100% (+5%) | 100% (+5%) |  |  | 100%
6.3A Output power dynamics for CA
28 |  | 38.521-1 Tx | 6.3A.1.0 | Minimum conformance requirements | [Intra-band UL contiguous CA] Intra-band contiguous UL CA: adding minimum requirement [Intra-band UL non-contiguous CA] Adding minimum requirement | OPPO | RAN5#93 (Nov-21) | R5-204835 R5-211040 | TS 38.101-1 6.3A.1 | 0.1 | 100% | 100% |  |  | 100%
29 |  | 38.521-1 Tx | 6.3A.1.1 | Minimum output power for CA (2UL CA) | [Intra-band UL contiguous CA] Intra-band contiguous UL CA: adding testing details | OPPO | RAN5#92 (Aug-21) | R5-204835, R5-205733 | TS 38.101-1 6.3A.1.1 TS 38.522 TR 38.905 | 1 | 100% | 100% |  |  | 100%
30 |  | 38.521-1 Tx | 6.3A.1.1 | Minimum output power for CA (2UL CA) | [Intra-band UL non-contiguous CA] Adding testing details |  | RAN5#93 (Nov-21) | R5-237903 | TS 38.101-1 6.3A.1.2 TS 38.522 TR 38.905 | 1 | 100% (+100%) | 100% (+100%) |  |  | 100%
31 |  | 38.521-1 Tx | 6.3A.2.0 | Minimum conformance requirements | [Intra-band UL contiguous CA] Intra-band contiguous UL CA: adding minimum requirement for BW class B and C [Intra-band UL non-contiguous CA] Adding minimum requirement for UL non-contiguous CA | OPPO | RAN5#93 (Nov-21) | R5-203735 R5-215307 | TS 38.101-1 6.3A.2 | 0.1 | 100% | 100% |  |  | 100%
32 |  | 38.521-1 Tx | 6.3A.2.1 | Transmit OFF power for CA (2UL CA) | [Intra-band UL contiguous CA] Intra-band contiguous UL CA: adding testing for BW class B and C | OPPO | RAN5#89-e (Nov-20) | R5-203735 | TS 38.101-1 6.3A.2.1 TS 38.522 TR 38.905 | 1 | 100% | 100% |  |  | 100%
33 |  | 38.521-1 Tx | 6.3A.2.1 | Transmit OFF power for CA (2UL CA) | [Intra-band UL non-contiguous CA] Adding testing details | Huawei | RAN5#93 (Nov-21) | R5-215307 | TS 38.101-1 6.3A.2.2 TS 38.522 TR 38.905 | 1 | 100% | 100% |  |  | 100%
34 |  | 38.521-1 Tx | 6.3A.3.0 | Minimum conformance requirements | [Intra-band UL contiguous CA] Intra-band contiguous UL CA: adding minimum requirement for BW class B and C [Intra-band UL non-contiguous CA] Adding minimum requirement for UL non-contiguous CA | OPPO Huawei | RAN5#93 (Nov-21) | R5-204836 R5-211911 | TS 38.101-1 6.3A.3 | 0.1 | 100% | 100% |  |  | 100%
35 |  | 38.521-1 Tx | 6.3A.3.1 | Transmit ON/OFF time mask for CA (2UL CA) | [Intra-band UL contiguous CA] Intra-band contiguous UL CA: adding testing for BW class B and C | OPPO | RAN5#89-e (Nov-20) | R5-205733 R5-204836 | TS 38.101-1 6.3A.3.1 TS 38.522 TR 38.905 | 1 | 100% | 100% |  |  | 100%
36 |  | 38.521-1 Tx | 6.3A.3.1 | Transmit ON/OFF time mask for CA (2UL CA) | [Intra-band UL non-contiguous CA] Adding testing details |  | RAN5#93 (Nov-21) | R5-233515 | TS 38.101-1 6.3A.3.2 TS 38.522 TR 38.905 | 1 | 100% | 100% |  |  | 100%
37 | Y | 38.521-1 Tx | 6.3A.3.1_1 | Transmit ON/OFF time mask for switching between two uplink carriers (2UL CA) | [UL Switching] Adding testing for UL Switching between 2 CCs | Huawei | RAN5#93 (Nov-21) | R5-211911 R5-225722 R5-233236 | TS 38.101-1 6.3A.3.3.2 TS 38.522: R5-211913,R5-225077 TR 38.905 R5-211914,R5-225076 | 1 | 100% | 100% |  |  | 100%
6.3A.4 Power control for CA
38 |  | 38.521-1 Tx | 6.3A.4.1.0 | Minimum conformance requirements | [Intra-band UL contiguous CA] Intra-band contiguous UL CA: adding minimum requirement for BW class B and C [Intra-band UL non-contiguous CA] Adding minimum requirement for UL non-contiguous CA | OPPO | RAN5#93 (Nov-21) | R5-204832 R5-215307 | TS 38.101-1 6.3A.4.1.1, 6.3A.4.2.1 | 0.1 | 100% | 100% |  |  | 100%
39 |  | 38.521-1 Tx | 6.3A.4.1.1 | Absolute power tolerance for CA (2 UL CA) | [Intra-band UL contiguous CA] Intra-band contiguous UL CA: adding testing for BW class B and C | OPPO | RAN5#92 (Aug-21) | R5-204832, R5-206761 R5-210384 R5-218458 R5-221795 | TS 38.101-1 6.3A.4.1.1 TS 38.522: R5-211913 TR 38.905: R5-205264 | 1 | 100% | 100% |  |  | 100%
40 |  | 38.521-1 Tx | 6.3A.4.1.1 | Absolute power tolerance for CA (2 UL CA) | [Intra-band UL non-contiguous CA] Adding testing details | Huawei | RAN5#93 (Nov-21) | R5-216065 R5-221795 R5-223697 | TS 38.101-1 6.3A.4.2.1 TS 38.522: R5-211913 TR 38.905: R5-216068, R5-222429 | 1 | 100% | 100% |  |  | 100%
41 |  | 38.521-1 Tx | 6.3A.4.2.0 | Minimum conformance requirements | [Intra-band UL contiguous CA] Intra-band contiguous UL CA: adding minimum requirement for BW class B and C [Intra-band UL non-contiguous CA] Adding minimum requirement for UL non-contiguous CA | OPPO | RAN5#93 (Nov-21) | R5-204833 R5-216066 | TS 38.101-1 6.3A.4.1.2, 6.3A.4.2.2 | 0.1 | 100% | 100% |  |  | 100%
42 |  | 38.521-1 Tx | 6.3A.4.2.1 | Power Control Relative power tolerance for CA (2 UL CA) | [Intra-band UL CA] Intra-band contiguous UL CA: adding testing for BW class B and C | OPPO | RAN5#92 (Aug-21) | R5-204833, R5-206891 R5-210384 | TS 38.101-1 6.3A.4.1.2 TS 38.522: R5-211913 TR 38.905: R5-205265 R5-210383 | 1 | 100% | 100% |  |  | 100%
43 |  | 38.521-1 Tx | 6.3A.4.2.1 | Power Control Relative power tolerance for CA (2 UL CA) | [Intra-band UL non-contiguous CA] Adding testing for details | Huawei | RAN5#93 (Nov-21) | R5-216066 R5-221130 | TS 38.101-1 6.3A.4.2.2 TS 38.522: R5-211913 TR 38.905: R5-215302 | 1 | 100% | 100% |  |  | 100%
44 |  | 38.521-1 Tx | 6.3A.4.3.0 | Minimum conformance requirements | [Intra-band UL contiguous CA] Intra-band contiguous UL CA: adding minimum requirement for BW class B and C [Intra-band UL non-contiguous CA] Adding minimum requirement for UL non-contiguous CA | OPPO | RAN5#93 (Nov-21) | R5-204834 R5-216067 | TS 38.101-1 6.3A.4.1.3, 6.3A.4.2.3 | 0.1 | 100% | 100% |  |  | 100%
45 |  | 38.521-1 Tx | 6.3A.4.3.1 | Aggregate power tolerance for CA (2UL CA) | [Intra-band UL contiguous CA] Intra-band contiguous UL CA: adding testing for BW class B and C | OPPO | RAN5#92 (Aug-21) | R5-204834, R5-206762 R5-210384 R5-217492 | TS 38.101-1 6.3A.4.1.3 TS 38.522: R5-211913 TR 38.905: R5-205267 | 1 | 100% | 100% |  |  | 100%
46 |  | 38.521-1 Tx | 6.3A.4.3.1 | Aggregate power tolerance for CA (2UL CA) | [Intra-band UL non-contiguous CA] Adding testing for details | Huawei | RAN5#93 (Nov-21) | R5-216067 | TS 38.101-1 6.3A.4.2.3 TS 38.522: R5-211913 TR 38.905: R5-215304 | 1 | 100% | 100% |  |  | 100%
6.3C Output power dynamics for SUL
47 |  | 38.521-1 Tx | 6.3C.3.2 | General transmit ON/OFF time mask for switching between two uplink carriers | [UL switching] Adding testing of UL switching for SUL | Huawei | RAN5#93 (Nov-21) | R5-225721 R5-235048 | TS 38.101-1 6.3C.3.1 TS 38.522 R5-225077 TR 38.905 R5-225074 | 1 | 100% | 100% |  |  | 100%
6.4A Transmit signal quality for CA
48 |  | 38.521-1 Tx | 6.4A.1.0 | Minimum conformance requirements | [Intra-band UL contiguous CA] Intra-band contiguous UL CA: adding minimum requirement for BW class B and C [Intra-band UL non-contiguous CA] Adding minimum requirement for UL non-contiguous CA | Huawei | RAN5#93 (Nov-21) | R5-237631 | TS 38.101-1 6.4A.1 | 0.1 | 100% (+100%) | 100% (+100%) |  |  | 100%
49 |  | 38.521-1 Tx | 6.4A.1.1 | Frequency error for CA (2UL CA) | [Intra-band UL contiguous CA] Intra-band contiguous UL CA: adding testing for BW class B and C | Huawei | RAN5#92 (Aug-21) | R5-237631 | TS 38.101-1 6.4A.1.1 TS 38.522 TR 38.905 | 1 | 100% (+100%) | 100% (+100%) |  |  | 100%
50 |  | 38.521-1 Tx | 6.4A.1.1 | Frequency error for CA (2UL CA) | [Intra-band UL non-contiguous CA] Adding testing details | Apple | RAN5#93 (Nov-21) | R5-237631 | TS 38.101-1 6.4A.1.2 TS 38.522 TR 38.905 | 1 | 100% (+100%) | 100% (+100%) |  |  | 100%
51 |  | 38.521-1 Tx | 6.4A.2 | Transmit modulation quality for CA | Sub-title |  |  |  |  | 0
52 |  | 38.521-1 Tx | 6.4A.2.1.0 6.4A.2.2.0 6.4A.2.3.0 | Minimum conformance requirements | [Intra-band UL contiguous CA] Intra-band contiguous UL CA: adding minimum requirement for BW class B and C [Intra-band UL non-contiguous CA] Adding minimum requirement for UL non-contiguous CA [Inter-band UL CA] Adding minimum requirement for inter-band UL CA | KTL | RAN5#93 (Nov-21) | R5-211037 R5-237905 | TS 38.101-1 6.4A.2.1, 6.4A.2.2, 6.4A.2.3 | 0.1 | 100% (+70%) | 100% (+70%) |  |  | 100%
54 |  | 38.521-1 Tx | 6.4A.2.1.1 | Error Vector Magnitude for CA (2UL CA) | [Intra-band UL contiguous CA] Intra-band contiguous UL CA: adding testing for BW class B and C | KTL | RAN5#92 (Aug-21) | R5-237905 | TS 38.101-1 6.4A.2.1.1 TS 38.522 TR 38.905 | 1 | 100% (+100%) | 100% (+100%) |  |  | 100%
55 |  | 38.521-1 Tx | 6.4A.2.1.1 | Error Vector Magnitude for CA (2UL CA) | [Intra-band UL non-contiguous CA] Adding testing details | Apple | RAN5#93 (Nov-21) | R5-237905 | TS 38.101-1 6.4A.2.1.1 TS 38.522 TR 38.905 | 1 | 100% (+100%) | 100% (+100%) |  |  | 100%
57 |  | 38.521-1 Tx | 6.4A.2.2.1 | Carrier leakage for CA (2UL CA) | [Intra-band UL contiguous CA] Intra-band contiguous UL CA: adding testing for BW class B and C | KTL | RAN5#92 (Aug-21) | R5-237906 | TS 38.101-1 6.4A.2.1 TS 38.522 TR 38.905 | 1 | 100% (+100%) | 100% (+100%) |  |  | 100%
58 |  | 38.521-1 Tx | 6.4A.2.2.1 | Carrier leakage for CA (2UL CA) | [Intra-band UL non-contiguous CA] Adding testing for details | Apple | RAN5#93 (Nov-21) | R5-237906 | TS 38.101-1 6.4A.2.2 TS 38.522 TR 38.905 | 1 | 100% (+100%) | 100% (+100%) |  |  | 100%
60 |  | 38.521-1 Tx | 6.4A.2.3.1 | In-band emissions for CA (2UL CA) | [Intra-band UL contiguous CA] Intra-band contiguous UL CA: adding testing for BW class B and C | KTL | RAN5#92 (Aug-21) | R5-237064 | TS 38.101-1 6.4A.2.1.2 TS 38.522 TR 38.905 | 1 | 100% (+100%) | 100% (+100%) |  |  | 100%
61 |  | 38.521-1 Tx | 6.4A.2.3.1 | In-band emissions for CA (2UL CA) | [Intra-band UL non-contiguous CA] Adding testing for details | Apple | RAN5#93 (Nov-21) | R5-237064 | TS 38.101-1 6.4A.2.2.2 TS 38.522 TR 38.905 | 1 | 100% (+100%) | 100% (+100%) |  |  | 100%
6.5A Output RF spectrum emissions for CA
62 |  | 38.521-1 Tx | 6.5A.1.0 | Minimum conformance requirements | [Intra-band UL contiguous CA] Intra-band contiguous UL CA: adding minimum requirement for BW class B and C [Intra-band UL non-contiguous CA] Adding minimum requirement for UL non-contiguous CA | Huawei LG Electronics | RAN5#93 (Nov-21) | R5-205737 R5-213995 | TS 38.101-1, 6.5A.1 | 0.1 | 100% | 100% |  |  | 100%
63 |  | 38.521-1 Tx | 6.5A.1.1 | Occupied bandwidth for CA (2UL CA) | [Intra-band UL contiguous CA] Intra-band contiguous UL CA: adding testing for BW class B and C | Huawei | RAN5#92 (Aug-21) | R5-205737 | TS 38.101-1, 6.5A.1.1a TS 38.522 TR 38.905: R5-206854 | 1 | 100% | 100% |  |  | 100%
64 |  | 38.521-1 Tx | 6.5A.1.1 | Occupied bandwidth for CA (2UL CA) | [Intra-band UL non-contiguous CA] Adding testing details | Huawei | RAN5#93 (Nov-21) | R5-215305 R5-218459 | TS 38.101-1, 6.5A.1.2 TS 38.522 TR 38.905: R5-215305 | 1 | 100% | 100% |  |  | 100%
65 |  | 38.521-1 Tx | 6.5A.2.2.0 | Minimum conformance requirements | [Intra-band UL contiguous CA] Intra-band contiguous UL CA: adding minimum requirement for BW class B and C [Intra-band UL non-contiguous CA] Adding minimum requirement for UL non-contiguous CA | Huawei | RAN5#93 (Nov-21) | R5-221128 | TS 38.101-1, 6.5A.2.2 | 0.1 | 100% | 100% |  |  | 100%
66 |  | 38.521-1 Tx | 6.5A.2.2.1 | Spectrum emission mask for CA (2UL CA) | [Intra-band UL contiguous CA] Intra-band contiguous UL CA: adding testing for BW class B and C | Huawei | RAN5#92 (Aug-21) | R5-221128 | TS 38.101-1, 6.5A.2.2.1 TS 38.522 TR 38.905 | 1 | 100% | 100% |  |  | 100%
67 |  | 38.521-1 Tx | 6.5A.2.2.1 | Spectrum emission mask for CA (2UL CA) | [Intra-band UL non-contiguous CA] Adding testing for CA_n77(2A) |  | RAN5#93 (Nov-21) | R5-221128 | TS 38.101-1, 6.5A.2.2.2 TS 38.522 TR 38.905 | 1 | 100% | 100% |  |  | 100%
72 |  | 38.521-1 Tx | 6.5A.2.4.1.0 | Minimum conformance requirements | [Intra-band UL contiguous CA] Intra-band contiguous UL CA: adding minimum requirement for BW class B and C [Intra-band UL non-contiguous CA] Adding minimum requirement for UL non-contiguous CA | Huawei | RAN5#93 (Nov-21) | R5-215305 | TS 38.101-1, 6.5A.2.4.1 | 0.1 | 100% | 100% |  |  | 100%
73 |  | 38.521-1 Tx | 6.5A.2.4.1.1 | NR ACLR for CA (2UL CA) | [Intra-band UL contiguous CA] Intra-band contiguous UL CA: adding testing for BW class B and C | Huawei | RAN5#92 (Aug-21) | R5-215080 R5-221796 | TS 38.101-1, 6.5A.2.4.1.1 TS 38.522 TR 38.905 | 1 | 100% | 100% |  |  | 100%
74 |  | 38.521-1 Tx | 6.5A.2.4.1.1 | NR ACLR for CA (2UL CA) | [Intra-band UL non-contiguous CA] Adding testing details |  | RAN5#93 (Nov-21) | R5-215080 R5-221796 | TS 38.101-1, 6.5A.2.4.1.2 TS 38.522 TR 38.905 | 1 | 100% | 100% |  |  | 100%
75 |  | 38.521-1 Tx | 6.5A.3.1.0 | Minimum conformance requirements | [Intra-band UL contiguous CA] Intra-band contiguous UL CA: adding minimum requirement for BW class B and C [Intra-band UL non-contiguous CA] Adding minimum requirement for UL non-contiguous CA | QUALCOMM Huawei | RAN5#93 (Nov-21) | R5-206912 R5-210919 | TS 38.101-1, 6.5A.3.1 | 0.1 | 100% | 100% |  |  | 100%
76 |  | 38.521-1 Tx | 6.5A.3.1.1 | General spurious emissions for CA (2UL CA) | [Intra-band UL contiguous CA] Intra-band contiguous UL CA: adding testing for BW class B and C |  | RAN5#92 (Aug-21) | R5-231645 | TS 38.101-1, 6.5A.3.1 TS 38.522 TR 38.905 | 1 | 100% | 100% |  |  | 100%
77 |  | 38.521-1 Tx | 6.5A.3.1.1 | General spurious emissions for CA (2UL CA) | [Intra-band UL non-contiguous CA] Intra-band contiguous UL CA: adding testing details |  | RAN5#93 (Nov-21) | R5-237904 | TS 38.101-1, 6.5A.3.1 TS 38.522 TR 38.905 | 1 | 100% (+100%) | 100% (+100%) |  |  | 100%
78 |  | 38.521-1 Tx | 6.5A.3.2.0 | Minimum conformance requirements | [Intra-band UL contiguous CA] Intra-band contiguous UL CA: adding minimum requirement CA_n77C [Intra-band UL non-contiguous CA] Adding minimum requirement for CA_n77(2A) |  | RAN5#93 (Nov-21) | R5-231646 R5-235628 | TS 38.101-1, 6.5A.3.2 Note: CA_n77C and CA-n77(2A) are selected as example CA configuration to complete the test case | 0.1 | 100% | 100% |  |  | 100%
79 |  | 38.521-1 Tx | 6.5A.3.2.1 | Spurious emissions for UE co-existence for CA (2UL CA) | [Intra-band UL contiguous CA] Intra-band contiguous UL CA: adding testing for CA_n77C |  | RAN5#92 (Aug-21) | R5-231646 | TS 38.101-1, 6.5A.3.2.1 TS 38.522 TR 38.905 Note: CA_n77C is selected as example CA configuration to complete the test case | 1 | 100% | 100% |  |  | 100%
80 |  | 38.521-1 Tx | 6.5A.3.2.1 | Spurious emissions for UE co-existence for CA (2UL CA) | [Intra-band UL non-contiguous CA] Intra-band contiguous UL CA: adding testing for CA_n77(2A) | Apple | RAN5#93 (Nov-21) | R5-235628 | TS 38.101-1, 6.5A.3.2.2 TS 38.522 TR 38.905 R5-231624 Note: CA-n77(2A) is selected as example CA configuration to complete the test case | 1 | 100% | 100% |  |  | 100%
85 |  | 38.521-1 Tx | 6.5A.4.0 | Minimum conformance requirements | [Intra-band UL contiguous CA] Intra-band contiguous UL CA: adding minimum requirement for BW class B and C |  | RAN5#92 (Aug-21) | R5-237632 | TS 38.101-1, 6.5A.4 | 0.1 | 100% (+100%) | 100% (+100%) |  |  | 100%
86 |  | 38.521-1 Tx | 6.5A.4.1 | Transmit intermodulation for CA (2UL CA) | [Intra-band UL contiguous CA] Intra-band contiguous UL CA: adding testing for BW class B and C | Apple | RAN5#92 (Aug-21) | R5-237632 | TS 38.101-1, 6.5A.4 TS 38.522 TR 38.905 | 1 | 100% (+100%) | 100% (+100%) |  |  | 100%
125 |  | 38.521-1 Tx | 6.5D.2_1.4.2 | UTRA ACLR for UL MIMO (Rel-16 onward) | [UL MIMO] New UL-MIMO bands: n1, n2, n3,, n25, n66 | Huawei | RAN5#93 (Nov-21) | 38.521-1: R5-212989 R5-221119 38.905: R5-212990 | TS 38.101-1, 6.5D.2 TS 38.522 TR 38.905 | 1 | 100% | 100% |  |  | 100%
126 |  | 38.521-1 Tx | 6.5D.3_1.3 | Additional spurious emissions for UL MIMO (Rel-16 onward) | [UL MIMO] New UL-MIMO bands: n1, n7, n30,, n38, n39, n48 | Huawei | RAN5#93 (Nov-21) | 38.521-1: R5-213100 R5-221120 R5-237057 | TS 38.101-1, 6.5D.3 TS 38.522 TR 38.905 | 1 | 100% (+5%) | 100% (+5%) |  |  | 100%
TS 38.521-1: FR1 RF test cases - Rx
|  | 38.521-1 Rx |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
87 |  | 38.521-1 Rx | 7.1 | General | [Intra-band DL CA] Adding instruction of requirements for band n48 | Huawei, Rohde & Schwarz | RAN5#89-e (Nov-20) | R5-202791 | TS 38.101-1 7.1 | 0.1 | 100% | 100% |  |  | 100%
88 |  | 38.521-1 Rx | 7.1A | General | [Intra-band DL CA] Adding instruction of requirements for band n48 | Huawei | RAN5#89-e (Nov-20) | R5-203696 | TS 38.101-1 7.1A | 0.1 | 100% | 100% |  |  | 100%
7.3A Reference sensitivity power for CA
89 |  | 38.521-1 Rx | 7.3A.0 | Minimum conformance requirements | [Intra-band DL CA] Intra-band contiguous: Adding minimum requirement of BW class B and D Intra-band non-contiguous: Adding minimum requirement of CA_n77(2A) Configurations: Adding minimum requirement of: CA_n40B, CA_n78B, CA_n77A-n78A, CA_n77D, CA_n78D, CA_n79D | Huawei | RAN5#89-e (Nov-20) | R5-203697 R5-235641 | TS 38.101-1 7.3A.2 Note: Requirements for CA_40B, CA_n78B are introduced under this WI. Future work will be moved to WI NR_CADC_NR_LTE_DC_R16-UEConTest | 0.1 | 100% | 100% |  |  | 100%
90 |  | 38.521-1 Rx | 7.3A.1 | Reference sensitivity power level for 2DL CA without exceptions | [Intra-band DL CA] Intra-band contiguous: Adding testing of CA_40B, CA_n78B Intra-band non-contiguous: Adding testing of CA_n77(2A) | Huawei | RAN5#92 (Aug-21) | R5-206864 | TS 38.101-1 7.3A.2 TS 38.522 TR 38.905: R5-206893 Note: Testing for CA_40B, CA_n78B are completed under this WI. Future work will be moved to WI NR_CADC_NR_LTE_DC_R16-UEConTest | 1 | 100% | 100% |  |  | 100%
91 |  | 38.521-1 Rx | 7.3A.2 | Reference sensitivity power level for 3DL CA | [Test case structure, Intra-band DL CA] Inter-band: The structure of test case for at least one inter-band configuration | Huawei | RAN5#92 (Aug-21) | R5-206892 R5-227081 | TS 38.101-1 7.3A.2 TS 38.522: TR 38.905: R5-206893 Note: Testing for CA_77D, CA_n78D are completed under this WI. Future work will be moved to WI NR_CADC_NR_LTE_DC_R16-UEConTest | 1 | 100% | 100% |  |  | 100%
7.4A Maximum input level for CA
92 |  | 38.521-1 Rx | 7.4A.0 | Minimum conformance requirements | [Intra-band DL CA] Intra-band contiguous: Adding BW class B, D Removing BW class E Intra-band non-contiguous: Adding minimum requirement for intra-band non-contiguous for >3300MHz | Huawei | RAN5#89-e (Nov-20) | R5-201749 | TS 38.101-1 7.4A | 0.1 | 100% | 100% |  |  | 100%
93 |  | 38.521-1 Rx | 7.4A.1 | Maximum input level for CA (2DL CA) | [Intra-band DL CA] Intra-band contiguous: Adding test requirement for BW class B Removing test requirement for BW class D and E Intra-band non-contiguous: Adding testing for intra-band non-contiguous | Huawei | RAN5#89-e (Nov-20) | R5-201749 | TS 38.101-1 7.4A TS 38.522 TR 38.905 | 1 | 100% | 100% |  |  | 100%
94 |  | 38.521-1 Rx | 7.4A.2 | Maximum input level for CA (3DL CA) | [Test case structure, Intra-band DL CA] Inter-band: The structure of test case for at least one inter-band configuration Intra-band contiguous: Adding testing for maximum input level BW class D | Huawei | RAN5#92 (Aug-21) | R5-201750, R5-203698, R5-205743 R5-225723 R5-227081 | TS 38.101-1 7.4A TS 38.522: TR 38.905: R5-202932, R5-206855 | 1 | 100% | 100% |  |  | 100%
7.5A Adjacent channel selectivity
95 |  | 38.521-1 Rx | 7.5A.0 | Minimum conformance requirements | [Intra-band DL CA] Intra-band contiguous: Adding BW class B, D Removing BW class E Intra-band non-contiguous: Adding minimum requirement for intra-band non-contiguous requirement for >3300MHz | Samsung | RAN5#89-e (Nov-20) | R5-204898 | TS 38.101-1 7.5A | 0.1 | 100% | 100% |  |  | 100%
96 |  | 38.521-1 Rx | 7.5A.1 | Adjacent channel selectivity for 2DL CA | [Intra-band DL CA] Intra-band contiguous: Adding test requirement for BW class B and removing BW class D and E Intra-band non-contiguous: Adding testing for intra-band non-contiguous |  | RAN5#89-e (Nov-20) | R5-204898 | TS 38.522 TR 38.905 | 1 | 100% | 100% |  |  | 100%
97 |  | 38.521-1 Rx | 7.5A.2 | Adjacent channel selectivity for 3DL CA | [Test case structure, Intra-band DL CA] Inter-band: The structure of test case for at least one inter-band configuration Intra-band contiguous: Adding testing for BW class D | Guangdong OPPO Mobile Telecom, China Telecom, Samsung, WE Certification, DISH Network | RAN5#89-e (Nov-20) | R5-204897, R5-205745 R5-227081 | TS 38.522 TR 38.905 | 1 | 100% | 100% |  |  | 100%
7.6.2 - 7.6.4 In-band blocking / Out-of-band blocking / Narrow band blocking
98 |  | 38.521-1 Rx | 7.6.2 | In-band blocking | [Intra-band DL CA] Adding band 48 | Huawei | RAN5#89-e (Nov-20) | R5-204962 | TS 38.101-1 7.6.2 R5-204962 is in NR_bands_BW_R16-UEConTest WI | 0.5 | 100% | 100% |  |  | 100%
99 |  | 38.521-1 Rx | 7.6.3 | Out-of-band blocking | [Intra-band DL CA] Adding band 48 | Huawei | RAN5#89-e (Nov-20) | R5-204837 | TS 38.101-1 7.6.3 | 0.5 | 100% | 100% |  |  | 100%
100 |  | 38.521-1 Rx | 7.6.4 | Narrow band blocking | [Intra-band DL CA] Adding band 48 | Huawei | RAN5#89-e (Nov-20) | R5-204837 | TS 38.101-1 7.6.4 | 0.5 | 100% | 100% |  |  | 100%
7.6A Blocking characteristics for CA
101 |  | 38.521-1 Rx | 7.6A.2.0 | Minimum Requirements | [Intra-band DL CA] Intra-band contiguous: Adding BW class B, D Removing BW class E Adding band 48 Intra-band non-contiguous: Adding minimum requirement for intra-band non-contiguous requirement for >3300MHz | Huawei | RAN5#89-e (Nov-20) | R5-202928, R5-203700 | TS 38.101-1 7.6A.2 | 0.1 | 100% | 100% |  |  | 100%
102 |  | 38.521-1 Rx | 7.6A.2.1 | In-band blocking for CA (2DL CA) | [Intra-band DL CA] Intra-band contiguous: Adding BW class B Removing BW class D and E Adding band 48 Intra-band non-contiguous: Adding testing for intra-band non-contiguous requirement for >3300MHz | Huawei | RAN5#89-e (Nov-20) | R5-202928, R5-203700 R5-231092 | TS 38.101-1 7.6A.2 TS 38.522 TR 38.905 | 1 | 100% | 100% |  |  | 100%
103 |  | 38.521-1 Rx | 7.6A.2.2 | In-band blocking for CA (3DL CA) | [Test case structure, Intra-band DL CA] Inter-band: The structure of test case for at least one inter-band configuration Intra-band contiguous: Adding testing for BW class D Adding band 48 | Huawei | RAN5#92 (Aug-21) | R5-201752, R5-203701, R5-205746 R5-227081 R5-227082 | TS 38.522 TR 38.905: R5-202933, R5-206856 | 1 | 100% | 100% |  |  | 100%
104 |  | 38.521-1 Rx | 7.6A.3.0 | Minimum conformance requirements | [Intra-band DL CA] Intra-band contiguous: Adding BW class B, D Removing BW class E Adding band 48 Intra-band non-contiguous: Adding minimum requirement and testing for intra-band non-contiguous requirement for >3300MHz | CAICT, Huawei | RAN5#89-e (Nov-20) | R5-202931, R5-204035 | TS 38.101-1 7.6A.3 | 0.1 | 100% | 100% |  |  | 100%
105 |  | 38.521-1 Rx | 7.6A.3.1 | Out-of-band blocking for CA (2DL CA) | [Intra-band DL CA] Intra-band contiguous: Adding BW class B Removing BW class D and E Adding band 48 Intra-band non-contiguous: Adding testing for intra-band non-contiguous | CAICT, Huawei | RAN5#89-e (Nov-20) | TS 38.521-1 R5-202930, R5-204035 TS 38.522 TR 38.905 | TS 38.101-1 7.6A.3 | 1 | 100% | 100% |  |  | 100%
106 |  | 38.521-1 Rx | 7.6A.3.2 | Out-of-band blocking for CA (3DL CA) | [Test case structure, Intra-band DL CA] Inter-band: The structure of test case for at least one inter-band configuration Intra-band contiguous: Adding testing for BW Class D Adding band 48 | CAICT | RAN5#89-e (Nov-20) | R5-202034, R5-204035 R5-230304 | TS 38.101-1 7.6A.3 TS 38.522 TR 38.905 | 1 | 100% | 100% |  |  | 100%
107 |  | 38.521-1 Rx | 7.6A.3.3 | Out-of-band blocking for CA (4DL CA) | Adding testing for 4DL CA | CAICT | RAN5#89-e (Nov-20) | R5-201866, R5-202035 R5-230304 | TS 38.101-1 7.6A.3 Test case will be moved to Rel-16 CA/DC basket WI | 0.5 | 100% | 100% |  |  | 100%
108 |  | 38.521-1 Rx | 7.6A.4.0 | Minimum conformance requirements | [Intra-band DL CA] Intra-band contiguous: Adding band 48 | CAICT Huawei | RAN5#91-e (May-21) | R5-210922 | TS 38.101-1 7.6A.4 | 0.1 | 100% | 100% |  |  | 100%
109 |  | 38.521-1 Rx | 7.6A.4.1 | Narrow band blocking for CA (2DL CA) | [Intra-band DL CA] Intra-band contiguous: Adding band 48 | Huawei | RAN5#89-e (Nov-20) | R5-202041, R5-205748 R5-210922 | TS 38.101-1 7.6A.4 TS 38.522 TR 38.905 | 1 | 100% | 100% |  |  | 100%
110 |  | 38.521-1 Rx | 7.6A.4.2 | Narrow band blocking for CA (3DL CA) | [Test case structure, Intra-band DL CA] Inter-band: The structure of test case for at least one inter-band configuration |  | RAN5#89-e (Nov-20) | R5-202036, R5-205748 R5-223700 | TS 38.101-1 7.6A.4 TS 38.522 TR 38.905 | 1 | 100% | 100% |  |  | 100%
111 |  | 38.521-1 Rx | 7.6A.4.3 | Narrow band blocking for CA (4DL CA) | Adding testing for 4DL CA |  | RAN5#89-e (Nov-20) | R5-202037 | TS 38.101-1 7.6A.4 Test case will be moved to Rel-16 CA/DC basket WI | 0.5 | 100% | 100% |  |  | 100%
7.7A Spurious response for CA
112 |  | 38.521-1 Rx | 7.7A.0 | Minimum conformance requirements | [Intra-band DL CA] Intra-band contiguous: Adding BW class B, D Removing BW class E Intra-band non-contiguous: Adding minimum requirement for intra-band non-contiguous requirement for >3300MHz | Samsung | RAN5#89-e (Nov-20) | R5-204040 | TS 38.101-1 7.7A | 0.1 | 100% | 100% |  |  | 100%
113 |  | 38.521-1 Rx | 7.7A.1 | Spurious response for 2DL CA | [Intra-band DL CA] Intra-band contiguous: Adding BW class B Removing BW class D and E Intra-band non-contiguous: Adding testing for intra-band non-contiguous | Samsung | RAN5#89-e (Nov-20) | R5-204040 | TS 38.101-1 7.7A TS 38.522 TR 38.905 | 1 | 100% | 100% |  |  | 100%
114 |  | 38.521-1 Rx | 7.7A.2 | Spurious response for 3DL CA | [Test case structure, Intra-band DL CA] Inter-band: The structure of test case for at least one inter-band configuration Intra-band contiguous: Complete Initial conditions for BW class D | Samsung | RAN5#89-e (Nov-20) | R5-204040 | TS 38.101-1 7.7A The initial conditions shall be the same as in clause 7.6A.3.2 TS 38.522 TR 38.905 | 1 | 100% | 100% |  |  | 100%
7.8A Intermodulation characteristics for CA
115 |  | 38.521-1 Rx | 7.8A.2.0 | Minimum conformance requirements | [Intra-band DL CA] Intra-band contiguous: Adding BW class B, D Removing BW class E Updating minimum requirement for intra-band contiguous for <2700MHz Intra-band non-contiguous: Adding minimum requirement and testing for intra-band non-contiguous requirement for >3300MHz | Samsung, CAICT | RAN5#89-e (Nov-20) | R5-202931 | TS 38.101-1 7.8A.2 | 0.1 | 100% | 100% |  |  | 100%
116 |  | 38.521-1 Rx | 7.8A.2.1 | Wide band Intermodulation for CA (2DL CA) | [Intra-band DL CA] Intra-band contiguous: Adding BW class B Removing BW class D and E Updating test requirement for intra-band contiguous for <2700MHz Intra-band non-contiguous: Adding testing for intra-band non-contiguous | Samsung, CAICT | RAN5#89-e (Nov-20) | R5-202042 | TS 38.101-1 7.8A.2 TS 38.522 TR 38.905 | 1 | 100% | 100% |  |  | 100%
117 |  | 38.521-1 Rx | 7.8A.2.2 | Wide band Intermodulation for CA (3DL CA) | [Test case structure, Intra-band DL CA] Inter-band: The structure of test case for at least one inter-band configuration Intra-band contiguous: Adding testing for BW class D | Samsung, CAICT, Huawei | RAN5#89-e (Nov-20) | R5-202929, R5-206763 R5-227081 | TS 38.101-1 7.8A.2 TS 38.522 TR 38.905 | 1 | 100% | 100% |  |  | 100%
118 |  | 38.521-1 Rx | 7.8A.2.3 | Wide band Intermodulation for CA (4DL CA) | Intra-band contiguous: Adding testing for 4DL CA | Samsung, CAICT | RAN5#89-e (Nov-20) | R5-202039 | TS 38.101-1 7.8A.2 Test case will be moved to Rel-16 CA/DC basket WI TS 38.522 TR 38.905 | 0.5 | 100% | 100% |  |  | 100%
TS 38.521-3: FR1 and FR2 Interworking operation with other radios RF test cases - Common parts (general clauses, Annexes)
|  | 38.521-3 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
TS 38.521-3: FR1 and FR2 Interworking operation with other radios RF test cases - Tx
120 |  | 38.521-3 Tx | 6.3B.3_1 | E-UTRA and NR switching time mask for switching between two uplink carriers | New sub.clause title | China Telecom | RAN5#97 (Nov-22) |  |  | 0
121 | Y | 38.521-3 Tx | 6.3B.3_1.1 | E-UTRA and NR switching time mask for switching between two uplink carriers for inter-band EN-DC | [UL switching] Adding testing for inter-band EN-DC with 2UL CCs | China Telecom | RAN5#97 (Nov-22) | R5-218293 R5-231840 | TS 38.101-3 6.3B.4 TS 38.522 R5-218460 TR 38.905 | 1 | 100% |  | 100% |  |  |  |  | 100%
TS 38.522: Applicability for RF, Demod/QSI reporting and RRM test cases
|  | 38.522 | 4.1.1 | FR1 standalone conformance test cases | Adding applicability for test cases in 38.521-1 |  | RAN5#97 (Nov-22) | R5-211913 R5-225077 R5-237779 |  | 10 | 100% (+95%) | 100% (+95%) |  |  | 100%
|  | 38.522 | 4.1.3 | NR interworking between NR FR1 and NR FR2 and between NR and LTE conformance test cases | Adding applicability for test cases in 38.521-3 |  | RAN5#97 (Nov-22) | R5-218460 |  | 0.1 | 100% (+90%) |  | 100% (+90%) |  |  |  |  | 100%
|  | 38.522 | 4.2 | RRM conformance test cases | Adding applicability for test cases in 38.533 |  | RAN5#97 (Nov-22) | R5-218460 R5-221797 R5-223701 |  | 0.5 | 100% (+90%) | 100% (+90%) | 100% (+90%) |  | 100% |  |  | 100%
TS 38.533: RRM test cases
|  | 38.533 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
127 |  | 38.533 | 4.5.8 | UL switching | [5 empty] | 0
128 | Y | 38.533 | 4.5.8.0 | Minimum conformance requirements | [UL switching] Adding minimum requirements of DL interruption at switching between two EN-DC uplink carriers | Huawei | RAN5#94 (Feb-22) | R5-218372 |  | 0.1 | 100% |  | 100% |  |  |  |  | 100%
122 | Y | 38.533 | 4.5.8.1 | EN-DC FR1 DL Interruptions at switching between two uplink carriers | [UL switching] Adding testing of DL interruption at switching between two EN-DC uplink carriers | Huawei | RAN5#94 (Feb-23) | R5-218372 | TS 38.133 A.4.5.8 TS 38.522 TR 38.903 | 1 | 100% |  | 100% |  |  |  |  | 100%
132 | Y | 38.533 | 6.5.7.0 | Minimum conformance requirements | [UL switching] Adding minumum requirements of DL interruption at switching between two CA uplink carriers | Ericsson | RAN5#94 (Feb-24) | R5-221297 R5-222882 | TS 38.133 A.6.5.7.1 TS 38.522 TR 38.903 | 0.1 | 100% | 100% |  |  | 100%
123 | Y | 38.533 | 6.5.7.1 | NR SA FR1 DL Interruptions at switching between two uplink carriers in FDD-TDD CA | [UL switching] Adding testing of DL interruption at switching between two CA uplink carriers | Ericsson | RAN5#94 (Feb-24) | R5-221298 R5-225146 | TS 38.133 A.6.5.7.1 TS 38.522 TR 38.903 | 1 | 100% | 100% |  |  | 100%
124 | Y | 38.533 | 6.5.7.2 | NR SA FR1 DL Interruptions at switching between two uplink carriers in TDD-TDD CA | [UL switching] Adding testing of DL interruption at switching between two CA uplink carriers | Ericsson | RAN5#94 (Feb-25) | R5-221798 R5-225147 | TS 38.133 A.6.5.7.2 TS 38.522 TR 38.903 | 1 | 100% | 100% |  |  | 100%
129 |  | 38.533 | Annex.E.x | Cell configuration mapping for EN-DC FR1 test cases in Chapter 4 | [UL switching] Adding Cell configuration mapping for DL interruption at switching between two CA uplink carriers |  | RAN5#97 (Nov-22) | R5-218294 R5-221300 |  | 1 | 100% | 100% |  |  | 100%
130 |  | 38.533 | ,Annex.F 1.1.2 | Measurement of RRM requirements | [UL switching] Adding MU and TT for DL interruption at switching between two CA uplink carriers |  | RAN5#97 (Nov-22) | R5-218294 R5-225148 |  | 1 | 100% | 100% |  |  | 100%
TR 38.903: Test Tolerances analysis RRM and RF Rx test cases
1 |  | 38.903 | 8 | Grouping of test cases defined in TS 38.533 | Adding TT analysis for RRM test cases |  | RAN5#93 (Nov-21) | R5-218295 R5-225612 |  | 0.5 | 100% | 100% | 100% |  | 100% |  |  | 100%
TR 38.905: Test Point analysis receiver and transmitter test cases
|  | 38.905 | 4.1 | Test point analysis for FR1 test cases in TS 38.521-1 | Adding TP analysis for test cases in 38.521-1 |  | RAN5#98 (Feb-23) | R5-202932, R5-202933, R5-204727, R5-204838, R5-205264, R5-205265, R5-205267, R5-206854, R5-206855, R5-206856, R5-206893 R5-210383 R5-211914 R5-212990 R5-216068 R5-215302 R5-215304 R5-215306 R5-221123 R5-221125 R5-221127 R5-221129 R5-222429 R5-225074 R5-225076 R5-231624 R5-233094 R5-234839 R5-237049 R5-237052 R5-237054 R5-237056 R5-237059 R5-237061 R5-237630 R5-237065 |  | 10 | 100% (+40%) | 100% (+40%) |  |  | 100%
RAN and CN protocol
TS 38.523-1: Protocol test cases
|  | 38.523-1 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
TS 38.523-2: Applicability for Protocol test cases
|  | 38.523-2 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | 0.1
TS 38.523-3: Protocol test suites (TTCN)
|  | 38.523-3 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
End of workplan items. Note! Do not remove this row. Introduce new work plan rows/items above this row.
Note on A6: Unique ID for WP items (unique within the sub-area work plan) Note! As WP item numbers may be referenced from outside of this WP that means: - Do not change number for WP items that have been published. - Do not re-use WP item numbers if a WP item is deleted
Note on B6: Set to Y if the WP item represents a new test case that will be specified in RAN5 test specifications as an executable test case else leave blank.
Note on K6: The WP item's weight number is used to set the reletive weights between WP items used in the overall calculation of completeness. Setting it to 0 for a WP item means that it will not be included at all in the calculation.