## Cover sheet
3GPP TSG-RAN5 Meeting #102 | [8 empty] | R5-240033
Athens, Greece, 26th Feb 2024 – 1st Mar 2024
Agenda Item: | 7.4.2
Source: | Ericsson
Title: | WP UE Conformance - NR QoE management and optimizations for diverse services
Work item code: | NR_QoE-UEConTest
Release: | Rel-17
Document for: | Information
RAN5 WP template v2.0-9
1. Introduction
The objective of this work item is to define the UE conformance requirements corresponding to the WID on Rel-17 NR_QoE, analyse the test case impact, applicability, test environment, and update the relevant conformance specifications for Rel-17.
2. Work item status
Estimation of WI overall completion:
Area |  | Completion | Number of new completed test cases (Note 1) | Number of new test cases | Comments
Overall completion |  | 19% (+5%) | 0 | 3 (+2)
Completion Compensation |  | -
| Note 1: | Only test cases completed for all applicable WP areas and sub-areas are counted. For completed test cases per WP areas and WP sub-areas see below.
Estimation WI completion per area and sub-area:
|  | Completion | Number of new completed test cases | Number of new test cases | Comments
Band independent (BI) |  | 19.2% (+4.7%) | 0 | 3 (+2)
BI |  | 19.2% (+4.7%) | 0 | 3 (+2)
Estimation of completion per TS (area):
|  | TS/TR overall completion |  |  | Band independent
TS/TR Scope | TS/TR | Completion | Number of new completed test cases | Number of new test cases | BI
[5 empty] | Completion | Number of new completed test cases | Number of new test cases
5GS
5GS Common
Common test environment | 38.508-1 | 60% (+60%) |  |  | 60% (+60%)
Common ICS | 38.508-2
UE specific test functions | 38.509
5GS RAN and CN protocols
Protocol test cases | 38.523-1 | 0% | 0 | 3 (+3) | 0% | 0 | 3 (+3)
Applicability Protocol test cases | 38.523-2
Test suites (TTCN) | 38.523-3
IMS
IMS over LTE protocol test cases | 34.229-1
IMS over 5GS protocol test cases | 34.229-5
Applicability and ICS IMS test cases | 34.229-2
IMS Test suite (TTCN) | 34.229-3
5 References
[1] RP-222102 | New WID on UE Conformance - NR QoE management and optimizations for diverse services
Note on B21: Overall completion of the work item reported at an earlier meeting will not be decreased if additional tasks are added or if corrections are made to the work plan. Instead the earlier reported completion status will be kept until necessary progress have been achieved such that completion exceeds the earlier reported completion level. The value of the Completion Compensation value represents the difference in the decrease caused by late additions or corrections to the work plan and the current estimated overall completion. '-' indicates that no compensation is applied.

## WP
WP Title: |  | WP UE Conformance - NR QoE management and optimizations for diverse services | [10 empty] | Start of workplan status columns. Note! Do not remove this column. | WP item status | End of workplan columns. Note! Do not remove this column.
WI code |  | NR_QoE-UEConTest
WP Scope: |  | <WP Scope description>
WP Resp: |  | Bo Jönsson |  |  | bo.jonssson@ericsson.com | [5 empty] | WP item completion |  |  | Band independent
TS Resp: |  | <TS responsible if a new TS is involved> |  |  | <Email to TS responsible>
WP Item ID | Is new test case? | TS/area | Clause | Title | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | Overall | Band independent |  | BI
19.2% (+4.7%)
4 (+3)
4 (+3)
5%
Start of work plan items. Note! Do not remove this row. Introduce new work plan rows/items below this row.
5GS
5GS Common
TS 38.508-1: Common test environment
|  | 38.508-1 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
TBD |  | 38.508-1 | <Clause> | <Title of new sub-clause header> | New sub-clause header |  | TBD |  |  | 0
1 |  | 38.508-1 | 4.6.3, 4.8.1 | ASN.1 for SRB4 | Update common environment for application layer testing. |  | RAN5#102 (Feb-23) | R5-234303, R5-235376, R5-234305, R5-234306, R5-234307, R5-234308, R5-234310, R5-235377, R5-235378 |  | 1 | 60% (+60%) | 60% (+60%) |  | 60%
TBD |  | 38.508-1 | <Clause> | <Title of task> | <Describe task> |  | TBD |  |  | TBD
TS 38.508-2: Common ICS
|  | 38.508-2 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
TBD |  | 38.508-2 | <Clause> | <Title> | Add ICS as needed for the test case applicability statements for the new test cases introduced in RF, RRM and protocol test cases. |  | TBD |  |  | TBD
TS 38.509: UE specific testing functions
|  | 38.509 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
TBD |  | 38.509 | <Clause> | <Title of new sub-clause header> | New sub-clause header |  | TBD |  |  | 0
TBD |  | 38.509 | <Clause> | <Title of task> | <Describe task> |  | TBD |  |  | TBD
RAN and CN protocol
TS 38.523-1: Protocol test cases
|  | 38.523-1 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
RRC
TBD |  | 38.523-1 | <Clause> | <Title of new sub-clause header> | New sub-clause header |  | TBD |  |  | 0
TBD |  | 38.523-1 | <Clause> | <Title of modified existing test case> | <Describe required change of the existing test case> |  | TBD |  |  | TBD
TBD | Y | 38.523-1 | <Clause> | <Title of new test case> | Test Purpose(s): <Describe test purpose(s)> |  | TBD |  |  | 1
3 | Y | 38.523-1 | 8.1.2.1.8 | RRC reconfiguration / application layer measurement / QoE | Test Purpose(s): Configure application layer measurement. TS:38.331 clause 5.3.5.13d | Ericsson | RAN5#102 (Feb-23) |  |  | 1 | 0% | 0% |  | 0%
4 | Y | 38.523-1 | 8.1.3.1.24 | Measurement configuration control and reporting for voice / QoE | Test Purpose(s): Measurement reporting voice. TS:38.331 clause 5.7.16, TS:26.114 clause 16 |  | RAN5#102 (Feb-23) |  |  | 1 | 0% | 0% |  | 0%
5 | Y | 38.523-1 | 8.1.3.1.25 | Measurement configuration control and reporting for video / QoE | Test Purpose(s): Measurement reporting video. TS:38.331 5.7.16, TS 26.114 clause 16 |  | RAN5#102 (Feb-23) |  |  | 1 | 0% | 0% |  | 0%
TBD | Y | 38.523-1 | <Clause> | <Title of new test case> | Test Purpose(s): <Describe test purpose(s)> |  | TBD |  |  | 0
NAS
TBD |  | 38.523-1 | <Clause> | <Title of new sub-clause header> | New sub-clause header |  | TBD |  |  | 0
TBD |  | 38.523-1 | <Clause> | <Title of modified existing test case> | <Describe required change of the existing test case> |  | TBD |  |  | TBD
TBD | Y | 38.523-1 | <Clause> | <Title of new test case> | Test Purpose(s): <Describe test purpose(s)> |  | TBD |  |  | 1
TS 38.523-2: Applicability for Protocol test cases
TBD |  | 38.523-2 | <Clause> | <Title> | Add new ICS statements. |  | TBD |  |  | 0.1
6 |  | 38.523-2 | 4 | <Title> | Add test case applicability statements for the new test cases introduced in 38.523-1 |  | RAN5#102 (Feb-23) |  |  | 0.1
TS 38.523-3: Protocol test suites (TTCN)
|  | 38.523-3 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
TBD |  | 38.523-3 | <Clause> | <Title of task> | <Describe task> |  | TBD |  |  | TBD
TS 34.229-1: IMS over LTE protocol test cases
|  | 34.229-1 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
TBD |  | 34.229-1 | <Clause> | <Title of new sub-clause header> | New sub-clause header |  | TBD |  |  | 0
TBD |  | 34.229-1 | <Clause> | <Title of modified existing test case> | <Describe required change of the existing test case> |  | TBD |  |  | TBD
TBD | Y | 34.229-1 | <Clause> | <Title of new test case> | Test Purpose(s): <Describe test purpose(s)> |  | TBD |  |  | 1
TS 34.229-5: IMS over 5GS protocol test cases
|  | 34.229-5 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
TBD |  | 34.229-5 | <Clause> | <Title of new sub-clause header> | New sub-clause header |  | TBD |  |  | 0
TBD |  | 34.229-5 | <Clause> | <Title of modified existing test case> | <Describe required change of the existing test case> |  | TBD |  |  | TBD
TBD | Y | 34.229-5 | <Clause> | <Title of new test case> | Test Purpose(s): <Describe test purpose(s)> |  | TBD |  |  | 1
TS 34.229-2: Applicability and ICS for IMS protocol test cases
TBD |  | 34.229-2 | <Clause> | <Title> | Add new ICS statements. |  | TBD |  |  | 0.1
TBD |  | 34.229-2 | <Clause> | <Title> | Add test case applicability statements for the new test cases introduced in 34.229-1 and/or 34.229-5. |  | TBD |  |  | 0.1
TS 34.229-3: IMS test suite (TTCN)
|  | 34.229-3 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
TBD |  | 34.229-3 | <Clause> | <Title of task> | <Describe task> |  | TBD |  |  | TBD
End of workplan items. Note! Do not remove this row. Introduce new work plan rows/items above this row.
Note on A6: Unique ID for WP items (unique within the sub-area work plan) Note! As WP item numbers may be referenced from outside of this WP that means: - Do not change number for WP items that have been published. - Do not re-use WP item numbers if a WP item is deleted
Note on B6: Set to Y if the WP item represents a new test case that will be specified in RAN5 test specifications as an executable test case else leave blank.
Note on K6: The WP item's weight number is used to set the reletive weights between WP items used in the overall calculation of completeness. Setting it to 0 for a WP item means that it will not be included at all in the calculation.