## Cover sheet
3GPP TSG-RAN WG5 Meeting #103 | [10 empty] | R5-242842
Fukuoka, Japan, 20 – 24 May 2024
Agenda Item: | 7.5.2
Source: | China Telecom, Huawei, HiSilicon
Title: | WP UE Conformance – Multi-carrier enhancements for NR
Work item code: | NR_MC_enh-UEConTest
Release: | Rel-18
Document for: | Information
RAN5 WP template v3.0.0
1. Introduction
The objective of the UE Conformance Test Aspects for Multi-carrier enhancements for NR work item is to define the UE conformance requirements corresponding to WID on Multi-carrier enhancements for NR with Unique identifier 940094, analyse the test case impact, applicability, test environment, and update the relevant conformance specifications. At the RAN#103 meeting, the Rel-18 RAN5 work item for Multi-carrier enhancements for NR (NR_MC_enh-UEConTest) was approved [1]. The purpose of present document is to provide a work plan for the RAN5 work item. The work plan is updated after each RAN5 meeting to give the status of the work item.
2. Work item status
Estimation of WI overall completion:
Area |  | Completion | Number of new completed test cases (Note 1) | Number of new test cases | Comments
Overall completion |  | 18% (+18%) | 0 | 22 (+22)
Completion Compensation |  | -
| Note 1: | Only test cases completed for all applicable WP areas and sub-areas are counted. For completed test cases per WP areas and WP sub-areas see below.
Estimation WI completion per area and sub-area:
|  | Completion | Number of new completed test cases | Number of new test cases | Comments
SA Option 2 (SA NR) |  | 18.2% (+18.2%) | 0 | 22 (+22)
FR1 |  | 22.1% (+22.1%) | 0 | 22 (+22)
FR2 |  | 5% (+5%) | 0 | 12 (+12)
Estimation of completion per TS (area):
|  | TS/TR overall completion |  |  | SA Option 2 (SA NR)
TS/TR Scope | TS/TR | Completion | Number of new completed test cases | Number of new test cases | FR1 |  |  | FR2
[5 empty] | Completion | Number of new completed test cases | Number of new test cases | Completion | Number of new completed test cases | Number of new test cases
5GS
5GS Common
Common test environment | 38.508-1 | 0% |  |  | 0%
Common ICS | 38.508-2 | 10% (+10%) |  |  | 10% (+10%)
NR RF/RRM
FR1 RF common parts | 38.521-1 | 38% (+38%) |  |  | 38% (+38%)
FR1 RF Tx test cases | 38.521-1 Tx | 71.7% (+71.7%) | 0 | 6 (+6) | 71.7% (+71.7%) | 0 | 6 (+6)
FR1 RF Rx test cases | 38.521-1 Rx
RRM test cases | 38.533 | 38.3% (+38.3%) | 0 | 4 (+4) | 38.3% (+38.3%) | 0 | 4 (+4)
Applicability RF. Demod/QSI and RRM test cases | 38.522 | 6.7% (+6.7%) |  |  | 6.7% (+6.7%)
Test Tolerances analysis RRM and RF Rx test cases | 38.903 | 0% |  |  | 0%
Test Point analysis receiver and transmitter test cases | 38.905 | 10% (+10%) |  |  | 10% (+10%)
5GS RAN and CN protocols
Protocol test cases | 38.523-1 | 0% | 0 | 12 (+12) | 0% | 0 | 12 (+12) | 0% | 0 | 12 (+12)
Applicability Protocol test cases | 38.523-2 | 0% |  |  | 0% |  |  | 0%
Test suites (TTCN) | 38.523-3
5 References
[1] RP-240346 | New WID on UE Conformance – Multi-carrier enhancements for NR
Note on B21: Overall completion of the work item reported at an earlier meeting will not be decreased if additional tasks are added or if corrections are made to the work plan. Instead the earlier reported completion status will be kept until necessary progress have been achieved such that completion exceeds the earlier reported completion level. The value of the Completion Compensation value represents the difference in the decrease caused by late additions or corrections to the work plan and the current estimated overall completion. '-' indicates that no compensation is applied.

## WP
WP Title: |  | WP UE Conformance – Multi-carrier enhancements for NR | [10 empty] | Start of workplan status columns. Note! Do not remove this column. | WP item status |  | End of workplan columns. Note! Do not remove this column.
WI code |  | NR_MC_enh-UEConTest
WP Scope: |  | The purpose of this present document is to provide a work plan for the RAN5 work item Multi-carrier enhancements for NR comprising the necessary updates to existing clauses/test cases and new clauses/test cases as appropriate, with the aim of provision of conformance testing to reflect the relevant core and performance requirement (relevant core spec WIs indicated in the WID). | [12 empty] | vs Area
WP Resp: |  | Lu YANG (China Telecom), Yuxin HAO (Huawei,Hisilicon) |  |  | Lu YANG <yangl75@chinatelecom.cn>, Yuxin HAO <haoyuxin@huawei.com> | [5 empty] | WP item completion |  |  | SA Option 2 (SA NR)
TS Resp: |  | N/A |  |  | N/A
WP Item ID | Is new test case? | TS/area | Clause | Title | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | Overall | SA Option 2 (SA NR) |  | FR1 | FR2
[14 empty] | 22.1% (+22.1%) | 5% (+5%)
[14 empty] | 41 (+41) | 14 (+14)
[14 empty] | 44 (+44) | 13 (+13)
5%
Start of work plan items. Note! Do not remove this row. Introduce new work plan rows/items below this row.
5GS
5GS Common
TS 38.508-1: Common test environment
|  | 38.508-1 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
TBD |  | 38.508-1 | 4.3.6 | Physical layer parameters | Add physical layer parameters for DCI format 1_3 and DCI format 0_3 |  | RAN5#109 (Nov-25) |  |  | 0.5 | 0% | 0% |  | 0%
TBD |  | 38.508-1 | 4.6.3 | Radio resource control information elements | Updating message contents |  | RAN5#109 (Nov-25) |  |  | 0.5 | 0% | 0% |  | 0%
TBD |  | 38.508-1 | 7.3.1 | Radio resource control information elements | Updating RRM-specific message contents |  | RAN5#109 (Nov-25) |  |  | 0.5 | 0% | 0% |  | 0%
TBD |  | 38.508-1 | Annex | Set up diagrams | Introducing new connection diagrams |  | RAN5#109 (Nov-25) |  |  | 0.5 | 0% | 0% |  | 0%
TS 38.508-2: Common ICS
|  | 38.508-2 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
TBD |  | 38.508-2 | A.x | Annex A (normative): ICS proforma for NR/5GS Generation User Equipment | Add ICS as needed for the test case applicability statements for the new test cases introduced in RF, RRM and protocol test cases. |  | RAN5#109 (Nov-25) | R5-242865 |  | 0.5 | 10% (+10%) | 10% (+10%) |  | 10%
Enhancement for Multi-carrier UL Operation
TS 38.521-1: FR1 RF test cases - Common parts (general clauses, Annexes)
|  | 38.521-1 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
TBD |  | 38.521-1 | 5.2A.2 | Operating bands for CA | Adding DL interruption capability for UL Tx switching |  | RAN5#109 (Nov-25) |  |  | 0.5 | 0% | 0% |  | 0%
TBD |  | 38.521-1 | 5.5A | Configurations for CA | 5.5A.3.0: Adding general requirements for UL Tx switching |  | RAN5#109 (Nov-25) | R5-243208 |  | 0.5 | 90% (+90%) | 90% (+90%) |  | 90%
TBD |  | 38.521-1 | 5.5C | Configurations for SUL | Adding general requirements for UL Tx switching |  | RAN5#109 (Nov-25) | R5-243208 |  | 0.5 | 90% (+90%) | 90% (+90%) |  | 90%
TBD |  | 38.521-1 | F.1.2 | Measurement of transmitter | Adding MU for UL Tx switching |  | RAN5#109 (Nov-25) | R5-243645 |  | 0.5 | 5% (+5%) | 5% (+5%) |  | 5%
TBD |  | 38.521-1 | F.3.2 | Measurement of transmitter | Adding TT for UL Tx switching |  | RAN5#109 (Nov-25) | R5-243645 |  | 0.5 | 5% (+5%) | 5% (+5%) |  | 5%
TS 38.521-1: FR1 RF test cases - Tx
|  | 38.521-1 Tx |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
6.3A Output power dynamics for CA
|  | 38.521-1 Tx |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD | 0% | 0% |  | 0%
TBD | Y | 38.521-1 Tx | 6.3A.3.0.3.6, 6.3A.3.0.3.6a | Time mask for switching across up to four uplink bands | [UL Tx switching] Minimum requirements for switching across up to four uplink bands, and additional requirements for three-band switching with dual TAG | Huawei, HiSilicon | RAN5#109 (Nov-25) | R5-243658 | TS 38.101-1 6.3A.3.3.6, 6.3A.3.3.6a | 1 | 90% (+90%) | 90% (+90%) |  | 90%
TBD | Y | 38.521-1 Tx | 6.3A.3.6 | Time mask for switching across three uplink bands | [UL Tx switching] The test case for switching across three uplink bands | Huawei, HiSilicon | RAN5#109 (Nov-25) | R5-243658 | TS 38.101-1 6.3A.3.3.6, 6.3A.3.3.6a | 1 | 70% (+70%) | 70% (+70%) |  | 70%
TBD | Y | 38.521-1 Tx | 6.3A.3.7 | Time mask for switching across four uplink bands | [UL Tx switching] The test case for switching across four uplink bands | Huawei, HiSilicon | RAN5#109 (Nov-25) | R5-243659 | TS 38.101-1 6.3A.3.3.6 | 1 | 60% (+60%) | 60% (+60%) |  | 60%
6.3C Output power dynamics for SUL
|  | 38.521-1 Tx |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
TBD | Y | 38.521-1 Tx | 6.3C.3.0.6, 6.3C.3.0.6a | Time mask for switching across up to four uplink bands | [UL Tx switching] Minimum requirements for switching across up to four uplink bands, and additional requirements for three-band switching with dual TAG | Huawei, HiSilicon | RAN5#109 (Nov-25) | R5-243620 | TS 38.101-1 6.3C.3.5, 6.3C.3.5a | 1 | 90% (+90%) | 90% (+90%) |  | 90%
TBD | Y | 38.521-1 Tx | 6.3C.3.6 | Time mask for switching across three uplink bands | [UL Tx switching] The test case for switching across three uplink bands | Huawei, HiSilicon | RAN5#109 (Nov-25) | R5-243620 | TS 38.101-1 6.3C.3.5, 6.3C.3.5a | 1 | 70% (+70%) | 70% (+70%) |  | 70%
TBD | Y | 38.521-1 Tx | 6.3C.3.7 | Time mask for switching across four uplink bands | [UL Tx switching] The test case for switching across four uplink bands | Huawei, HiSilicon | RAN5#109 (Nov-25) | R5-243644 | TS 38.101-1 6.3C.3.5 | 1 | 50% (+50%) | 50% (+50%) |  | 50%
TS 38.521-1: FR1 RF test cases - Rx
|  | 38.521-1 Rx |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
TS 38.522: Applicability for RF, Demod/CSI reporting and RRM test cases
TBD |  | 38.522 | 4.0 | Test case conditions and selection criteria | Adding test case conditions and selection criteria for the new test cases introduced for 38.521-1 and 38.533 |  | RAN5#109 (Nov-25) | R5-243914 |  | 1 | 10% (+10%) | 10% (+10%) |  | 10%
TBD |  | 38.522 | 4.1.1 | FR1 standalone conformance test cases | Adding test case applicability statements for the new test cases introduced for 38.521-1 |  | RAN5#109 (Nov-25) |  |  | 1 | 0% | 0% |  | 0%
TBD |  | 38.522 | 4.2 | RRM conformance test cases | Adding test case applicability statements for the new test cases introduced for 38.533 |  | RAN5#109 (Nov-25) | R5-243914 |  | 1 | 10% (+10%) | 10% (+10%) |  | 10%
TS 38.533: RRM test cases
|  | 38.533 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
TBD | Y | 38.533 | 6.5.7D.1 | NR SA FR1 DL interruptions at switching across three uplink bands in TDD-TDD CA for single TAG | [UL Tx switching] Adding new RRM test case of DL interruptions at switching across three uplink bands in TDD-TDD CA for single TAG | Huawei, HiSilicon | RAN5#109 (Nov-25) | R5-242867 | TS 38.133 A.6.5.7D.1 | 1 | 70% (+70%) | 70% (+70%) |  | 70%
TBD | Y | 38.533 | 6.5.7D.2 | NR SA FR1 DL interruptions at switching across four uplink bands in FDD-TDD CA for single TAG | [UL Tx switching] Adding new RRM test case of DL interruptions at switching across four uplink bands in FDD-TDD CA for single TAG | Huawei, HiSilicon | RAN5#109 (Nov-25) | R5-242868 | TS 38.133 A.6.5.7D.2 | 1 | 70% (+70%) | 70% (+70%) |  | 70%
TBD | Y | 38.533 | 6.5.7D.3 | NR SA FR1 DL interruptions at switching across three uplink bands in FDD-TDD CA for two TAGs | [UL Tx switching] Adding new RRM test case of DL interruptions at switching across three uplink bands in FDD-TDD CA for two TAGs | Huawei, HiSilicon | RAN5#109 (Nov-25) | R5-242869 | TS 38.133 A.6.5.7D.3 | 1 | 70% (+70%) | 70% (+70%) |  | 70%
TBD | Y | 38.533 | 6.5.7D.4 | NR SA FR1 DL interruptions at switching across four uplink bands in TDD-TDD CA for two TAGs | [UL Tx switching] Adding new RRM test case of DL interruptions at switching across four uplink bands in TDD-TDD CA for two TAGs | China Telecom | RAN5#109 (Nov-25) |  | TS 38.133 A.6.5.7D.4 | 1 | 0% | 0% |  | 0%
TBD |  | 38.533 | Annexes | RMCs, Cell mapping, Measurement uncertainties and test tolerances and default configurations etc. | [UL Tx switching] Adding RMCs, Cell mapping, Measurement uncertainties and test tolerances and default configurations etc for DL interruptions at switching across three or four uplink bands RRM TCs |  | RAN5#109 (Nov-25) | R5-242870 |  | 2 | 10% (+10%) | 10% (+10%) |  | 10%
TR 38.903: Test Tolerances analysis RRM and RF Rx test cases
|  | 38.903 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
TBD |  | 38.903 | 8 | Grouping of test cases defined in TS 38.533 | Adding TT analysis for RRM test cases |  | RAN5#109 (Nov-25) |  |  | 10 | 0% | 0% |  | 0%
TR 38.905: Test Point analysis receiver and transmitter test cases
|  | 38.905 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
TBD |  | 38.905 | 4.1 | Test point analysis for FR1 test cases in TS 38.521-1 | Adding TP analysis for test cases in 38.521-1 |  | RAN5#109 (Nov-25) | R5-243618 R5-243796 |  | 1 | 10% (+10%) | 10% (+10%) |  | 10%
Multi-cell PUSCH/PDSCH scheduling with a single DCI
TS 38.523-1: Protocol test cases
|  | 38.523-1 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
Idle Mode
Layer 2
7.1.1.2 Downlink Data Transfer
|  | 38.523-1 | 7.1.1.2.X | Multi-cell PDSCH scheduling with a single DCI / FDRA field based | [5 empty] | 0
TBD | Y | 38.523-1 | 7.1.1.2.X.1 | Multi-cell PDSCH scheduling with a single DCI / FDRA field based / Intra-band Contiguous CA | TP1:[TS 38.212:7.3.1] WITH: UE in RRC_CONNECTED state, SCell is configured, DCI format 1-3 is configured and ScheduledCellComboListDCI-1-3 is not configured. WHEN: UE receives DCI format 1-3 on scheduling Cell, and FDRA field of DCI format 1-3 indicated that PCell is scheduled Cell. THEN: UE sends a HARQ feedback on the HARQ process. TP2:[TS 38.212:7.3.1] WITH: UE in RRC_CONNECTED state, SCell is configured, DCI format 1-3 is configured and ScheduledCellComboListDCI-1-3 is not configured. WHEN: UE receives DCI format 1-3 on scheduling Cell, and FDRA field of DCI format 1-3 indicated that SCell is scheduled Cell. THEN: UE sends a HARQ feedback on the HARQ process. TP3:[TS 38.212:7.3.1, 38.213: 9.2.3] WITH: UE in RRC_CONNECTED state, SCell is configured, DCI format 1-3 is configured and ScheduledCellComboListDCI-1-3 is not configured . WHEN: UE receives DCI format 1-3 on scheduling Cell, and FDRA field of DCI format 1-3 indicated that PCell and SCell are scheduled Cell. THEN: UE sends HARQ-ACK information including two HARQ feedback and the timing of PUCCH carrying HARQ-ACK information is determined by the last PDSCH. | Huawei, HiSilicon | RAN5#109 (Nov-25) |  |  | 1 | 0% | 0% |  | 0% | 0%
TBD | Y | 38.523-1 | 7.1.1.2.X.2 | Multi-cell PDSCH scheduling with a single DCI / FDRA field based / Inter-band CA | same as 7.1.1.2.X.1 | Huawei, HiSilicon | RAN5#109 (Nov-25) |  |  | 1 | 0% | 0% |  | 0% | 0%
TBD | Y | 38.523-1 | 7.1.1.2.X.3 | Multi-cell PDSCH scheduling with a single DCI / FDRA field based / Intra-band non-Contiguous CA | same as 7.1.1.2.X.1 | Huawei, HiSilicon | RAN5#109 (Nov-25) |  |  | 1 | 0% | 0% |  | 0% | 0%
|  | 38.523-1 | 7.1.1.2.Y | Multi-cell PDSCH scheduling with a single DCI / Scheduled cell indicator field based | [5 empty] | 0
TBD | Y | 38.523-1 | 7.1.1.2.Y.1 | Multi-cell PDSCH scheduling with a single DCI / Scheduled cell indicator field based / Intra-band Contiguous CA | TP1:[TS 38.212:7.3.1] WITH: UE in RRC_CONNECTED state, SCell is configured, DCI format 1-3 is configured and ScheduledCellComboListDCI-1-3 is configured. WHEN: UE receives DCI format 1-3 on scheduling Cell, and Scheduled cell indicator field of DCI format 1-3 indicated that PCell is scheduled Cell. THEN: UE sends a HARQ feedback on the HARQ process. TP2:[TS 38.212:7.3.1] WITH: UE in RRC_CONNECTED state, SCell is configured, DCI format 1-3 is configured and ScheduledCellComboListDCI-1-3 is configured. WHEN: UE receives DCI format 1-3 on scheduling Cell, and Scheduled cell indicator field of DCI format 1-3 indicated that SCell is scheduled Cell. THEN: UE sends a HARQ feedback on the HARQ process. TP3:[TS 38.212:7.3.1, 38.213: 9.2.3] WITH: UE in RRC_CONNECTED state, SCell is configured, DCI format 1-3 is configured and ScheduledCellComboListDCI-1-3 is configured . WHEN: UE receives DCI format 1-3 on scheduling Cell, and Scheduled cell indicator field of DCI format 1-3 indicated that PCell and SCell are scheduled Cell. THEN: UE sends HARQ-ACK information including two HARQ feedback and the timing of PUCCH carrying HARQ-ACK information is determined by the last PDSCH. | Huawei, HiSilicon | RAN5#109 (Nov-25) |  |  | 1 | 0% | 0% |  | 0% | 0%
TBD | Y | 38.523-1 | 7.1.1.2.Y.2 | Multi-cell PDSCH scheduling with a single DCI / Scheduled cell indicator field based / Inter-band CA | same as 7.1.1.2.Y.1 | Huawei, HiSilicon | RAN5#109 (Nov-25) |  |  | 1 | 0% | 0% |  | 0% | 0%
TBD | Y | 38.523-1 | 7.1.1.2.Y.3 | Multi-cell PDSCH scheduling with a single DCI / Scheduled cell indicator field based / Inter-band CA Intra-band non-Contiguous CA | same as 7.1.1.2.Y.1 | Huawei, HiSilicon | RAN5#109 (Nov-25) |  |  | 1 | 0% | 0% |  | 0% | 0%
7.1.1.3 Uplink Data Transfer
TBD |  | 38.523-1 | 7.1.1.3.X | Multi-cell PUSCH scheduling with a single DCI / FDRA field based | [5 empty] | 0
TBD | Y | 38.523-1 | 7.1.1.3.X.1 | Multi-cell PUSCH scheduling with a single DCI / FDRA field based / Intra-band Contiguous CA | TP1:[TS 38.212:7.3.1] WITH: UE in RRC_CONNECTED state, SCell is configured, DCI format 0-3 is configured and ScheduledCellComboListDCI-0-3 is not configured. WHEN: UE receives DCI format 0-3 on scheduling Cell, and FDRA field of DCI format 0-3 indicated that PCell is scheduled Cell. THEN: UE transmits MAC PDU on PCell. TP2:[TS 38.212:7.3.1] WITH: UE in RRC_CONNECTED state, SCell is configured, DCI format 0-3 is configured and ScheduledCellComboListDCI-0-3 is not configured. WHEN: UE receives DCI format 0-3 on scheduling Cell, and FDRA field of DCI format 0-3 indicated that SCell is scheduled Cell. THEN: UE transmits MAC PDU on SCell. TP3:[TS 38.212:7.3.1, 38.213: 9.2.3] WITH: UE in RRC_CONNECTED state, SCell is configured, DCI format 0-3 is configured and ScheduledCellComboListDCI-0-3 is not configured . WHEN: UE receives DCI format 0-3 on scheduling Cell, and FDRA field of DCI format 0-3 indicated that PCell and SCell are scheduled Cell. THEN: UE transmits MAC PDU on PCell and SCell. | MediaTek Inc. | RAN5#109 (Nov-25) |  |  | 1 | 0% | 0% |  | 0% | 0%
TBD | Y | 38.523-1 | 7.1.1.3.X.2 | Multi-cell PUSCH scheduling with a single DCI / FDRA field based / Inter-band CA | same as 7.1.1.3.X.1 | MediaTek Inc. | RAN5#109 (Nov-25) |  |  | 1 | 0% | 0% |  | 0% | 0%
TBD | Y | 38.523-1 | 7.1.1.3.X.3 | Multi-cell PUSCH scheduling with a single DCI / FDRA field based / Intra-band non-Contiguous CA | same as 7.1.1.3.X.1 | MediaTek Inc. | RAN5#109 (Nov-25) |  |  | 1 | 0% | 0% |  | 0% | 0%
TBD |  | 38.523-1 | 7.1.1.3.Y | Multi-cell PUSCH scheduling with a single DCI / Scheduled cells indicator field based |  |  | RAN5#109 (Nov-25) |  |  | 0
TBD | Y | 38.523-1 | 7.1.1.3.Y.1 | Multi-cell PDSCH scheduling with a single DCI / Scheduled cell indicator field based / Intra-band Contiguous CA | TP1:[TS 38.212:7.3.1] WITH: UE in RRC_CONNECTED state, SCell is configured, DCI format 0-3 is configured and ScheduledCellComboListDCI-0-3 is configured. WHEN: UE receives DCI format 0-3 on scheduling Cell, and Scheduled cell indicator field of DCI format 0-3 indicated that PCell is scheduled Cell. THEN: UE transmits MAC PDU on PCell. TP2:[TS 38.212:7.3.1] WITH: UE in RRC_CONNECTED state, SCell is configured, DCI format 0-3 is configured and ScheduledCellComboListDCI-0-3 is configured. WHEN: UE receives DCI format 0-3 on scheduling Cell, and Scheduled cell indicator field of DCI format 0-3 indicated that SCell is scheduled Cell. THEN: UE transmits MAC PDU on SCell. TP3:[TS 38.212:7.3.1] WITH: UE in RRC_CONNECTED state, SCell is configured, DCI format 0-3 is configured and ScheduledCellComboListDCI-0-3 is configured. WHEN: UE receives DCI format 0-3 on scheduling Cell, and Scheduled cell indicator field of DCI format 0-3 indicated that PCell and SCell are scheduled Cell. THEN: UE transmits MAC PDU on PCell and SCell. | Lenovo/Motorola Mobility | RAN5#109 (Nov-25) |  |  | 1 | 0% | 0% |  | 0% | 0%
TBD | Y | 38.523-1 | 7.1.1.3.Y.2 | Multi-cell PDSCH scheduling with a single DCI / Scheduled cell indicator field based / Inter-band CA | same as 7.1.1.3.Y.1 | Lenovo/Motorola Mobility | RAN5#109 (Nov-25) |  |  | 1 | 0% | 0% |  | 0% | 0%
TBD | Y | 38.523-1 | 7.1.1.3.Y.3 | Multi-cell PDSCH scheduling with a single DCI / Scheduled cell indicator field based /Intra-band non-Contiguous CA | same as 7.1.1.3.Y.1 | Lenovo/Motorola Mobility | RAN5#109 (Nov-25) |  |  | 1 | 0% | 0% |  | 0% | 0%
RRC
NAS
TS 38.523-2: Applicability for Protocol test cases
TBD |  | 38.523-2 | 4.1 | Protocol conformance test cases applicability | Adding test case applicability statements for the new test cases introduced in 38.523-1 |  | RAN5#109 (Nov-25) |  |  | 0.5 | 0% | 0% |  | 0% | 0%
TBD |  | 38.523-2 | 4.2 | Protocol conformance test cases Applicability Condition | Adding test case applicability statements for the new test cases introduced in 38.523-1 |  | RAN5#109 (Nov-25) |  |  | 0.5 | 0% | 0% |  | 0% | 0%
TS 38.523-3: Protocol test suites (TTCN)
|  | 38.523-3 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
TBD |  | 38.523-3 | <Clause> | <Title of task> | <Describe task> |  | TBD |  |  | TBD
End of workplan items. Note! Do not remove this row. Introduce new work plan rows/items above this row.
Note on A6: Unique ID for WP items (unique within the sub-area work plan) Note! As WP item numbers may be referenced from outside of this WP that means: - Do not change number for WP items that have been published. - Do not re-use WP item numbers if a WP item is deleted
Note on B6: Set to Y if the WP item represents a new test case that will be specified in RAN5 test specifications as an executable test case else leave blank.
Note on K6: The WP item's weight number is used to set the reletive weights between WP items used in the overall calculation of completeness. Setting it to 0 for a WP item means that it will not be included at all in the calculation.