## Cover sheet
3GPP TSG RAN WG5#106 | [8 empty] | R5-250167
<Athens, Greece, 17th Feb 2025 - 21st Feb 2025>
Agenda Item: | 7.5.2
Source: | China Unicom, Huawei, Hisilicon
Title: | UE Conformance - Additional NR bands for UL-MIMO in Rel-18
Work item code: | NR_bands_UL_MIMO_R18-UEContest
Release: | Rel-18
Document for: | Information
RAN5 WP template v2.0
1. Introduction
The objective of this work item is to define the UE conformance requirements for NR SUL band with UL MIMO for PC3, PC2 and NR band with UL-MIMO for PC5, PC3, PC2 and PC1.5 covered in RAN4 work item in Rel-18.
2. Work item status
Estimation of WI overall completion:
Area |  | Completion | Number of new completed configurations (Note 1) | Number of new configurations | Comments
Overall completion |  | 76% (+2%) | 15 (+4) | 20
Completion Compensation |  | -
| Note 1: | Only test cases / configurations completed for all applicable WP areas and sub-areas are counted. For completed test cases / configurations per WP areas and WP sub-areas see below.
Estimation WI completion per area and sub-area:
|  | Completion | Number of new completed configurations | Number of new configurations | Comments
SA Option 2 (SA NR) (FR1) |  | 76.2% (+2.2%) | 15 (+4) | 20
FR1 |  | 76.2% (+2.2%) | 15 (+4) | 20
Estimation of completion per TS (area):
|  | TS/TR overall completion |  |  | SA Option 2 (SA NR)
TS:Area Scope | TS/Area | Completion | Number of new completed PC3/PC2 configurations | Number of new PC3/PC2 configurations | FR1
[5 empty] | Completion | Number of new completed test cases / configurations | Number of new test cases / configurations
NR bands for UL-MIMO configurations
NR bands for UL-MIMO configurations
NR bands for UL-MIMO | PC3 NR band for UL-MIMO | 87.5% (+3.7%) | 7 (+3) | 8 | 87.5% (+3.7%) | 7 (+3) | 8
NR bands for UL-MIMO | PC2 NR band for UL-MIMO
5 References
[1]RP-232772 | Revised WID on UE Conformance - Additional NR bands for UL-MIMO in Rel-18
Note on B21: Overall completion of the work item reported at an earlier meeting will not be decreased if additional tasks are added or if corrections are made to the work plan. Instead the earlier reported completion status will be kept until necessary progress have been achieved such that completion exceeds the earlier reported completion level. The value of the Completion Compensation value represents the difference in the decrease caused by late additions or corrections to the work plan and the current estimated overall completion. '-' indicates that no compensation is applied.

## WP
WP Title: |  | UE Conformance - Additional NR bands for UL-MIMO in Rel-18 | [12 empty] | Start of workplan status columns. Note! Do not remove this column. | WP item status | Relative weight of effort vs TS contribution | [8 empty] | End of workplan columns. Note! Do not remove this column.
WI code |  | NR_bands_UL_MIMO_R18-UEContest | [14 empty] | 1 | 1 | 1 | 3 | 3 | 1 | 1 | 5 | 5
WP Scope: |  | The purpose of this present document is to provide a work plan for the RAN5 work item Additional NR bands for UL-MIMO in Rel-18 comprising the necessary updates to existing clauses/test cases and new clauses/test cases as appropriate, with the aim of provision of conformance testing to reflect the relevant core requirement (relevant core spec WIs indicated in the WID). | [14 empty] | 38.508-1: Test frequencies | 38.508-2: UE capabilities | 38.521-1: Common Clause | 38.521-1: Tx test cases | 38.521-1: Rx test cases | 38.522: Test case applicability | 38.533: RRM test cases / 38:.522 Test case applicability | 38.903: MU and TT | 38.905: Test point analysis
WP Resp: |  | Yu Shi, China Unicom |  |  | shiyu19@chinaunicom.cn | [7 empty] | WP item completion |  |  | SA Option 2 (SA NR)
TS Resp: |  | N/A |  |  | N/A
WP Item ID | Is new configuration or test case? | TS/Area | Configuration / Test case clause | UL configuration(s) / Test case title | Type of change | Interested Operator | Company | Status | Target | TDOC(s) | Comments | Weight | Overall | SA Option 2 (SA NR) |  | FR1
76.2% (+2.2%)
21
20
5%
Start of work plan items. Note! Do not remove this row. Introduce new work plan rows/items below this row. | [15 empty] | CALCULATED CELLS | TS STATUS INPUT
NR bands for UL-MIMO
1 | Y | PC3 NR band for UL-MIMO | n28 |  | New PC3 Config | CMCC | CMCC | Completed | RAN5#101 (Nov-23) | 38.521-1: R5-234748 R5-234749 R5-234747 R5-236668 R5-247744 38.508-2： R5-234752 38.522: R5-234751 | Discussion paper：R5-234753 | 1 | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  |  | 100%
2 | Y | PC3 NR band for UL-MIMO | n8 |  | New PC3 Config | China Unicom | China Unicom | Completed | RAN5#101 (Nov-23) | 38.508-2: R5-235120 38.521-1: R5-235016 R5-235180 R5-234828 R5-247745 (AMPR) |  | 1 | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  |  | 100%
3 | Y | PC2 NR band for UL-MIMO | n1 |  | New PC2 Config | China Unicom | China Unicom | Completed | RAN5#101 (Nov-23) | 38.521-1: R5-235016 R5-237637 |  | 1 | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  |  | 100%
4 | Y | PC2 NR band for UL-MIMO | n3 |  | New PC2 Config | China Unicom | China Unicom | Completed | RAN5#101 (Nov-23) | 38.521-1: R5-235016 R5-237637 |  | 1 | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  |  | 100%
5 | Y | PC2 NR band for UL-MIMO | n80 |  | New PC2 Config | China Unicom | China Unicom | Completed | RAN5#101 (Nov-23) | 38.521-1: R5-235154 R5-234828 R5-237091 |  | 1 | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  |  | 100%
6 | Y | PC2 NR band for UL-MIMO | n84 |  | New PC2 Config | China Unicom | China Unicom | Completed | RAN5#101 (Nov-23) | 38.521-1: R5-235154 R5-237091 |  | 1 | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  |  | 100%
7 | Y | PC3 NR band for UL-MIMO | n5 |  | New PC3 Config | China Unicom | China Unicom | Completed | RAN5#103 (May-24) | 38.521-1： R5-241745 R5-241263 R5-241260 38.508-2: R5-241262 |  | 1 | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  |  | 100%
8 | Y | PC3 NR band for UL-MIMO | n26 |  | New PC3 Config | Southern Linc | Nokia | Completed | RAN5#105 (Nov-24) | 38.521-1: R5-247743 R5-246453 R5-251516 38.508-2： R5-246452 38.905： R5-250240 | CDS：R5-250238 | 1 | 100% (+10%) | 100% (+10%) |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  |  | 100%
9 | Y | PC3 NR band for UL-MIMO | n13 |  | New PC3 Config | Bell Mobility, TELUS | Nokia | Completed | RAN5#105 (Nov-24) | 38.521-1: R5-247743 R5-246453 R5-251516 38.508-2： R5-246452 38.905： R5-250239 | CDS：R5-250238 | 1 | 100% (+10%) | 100% (+10%) |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  |  | 100%
10 | Y | PC2 NR band for UL-MIMO | n66 |  | New PC2 Config | MTK | MTK | Completed | RAN5#104 (Aug-24) | 38.521-1： R5-242287(MOP) R5-242288(MPR) TS38.508-2: R5-242289 |  | 1 | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  |  | 100%
11 | Y | PC2 NR band for UL-MIMO | n70 |  | New PC2 Config | MTK | MTK | Completed | RAN5#104 (Aug-24) | 38.521-1： R5-244105（MOP） R5-244106（MPR） R5-245820（MPR general for PC2） |  | 1 | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  |  | 100%
12 | Y | PC2 NR band for UL-MIMO | n71 |  | New PC2 Config |  |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  |  | 0%
13 | Y | PC3 NR band for UL-MIMO | n83 |  | New PC3 Config |  |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  |  | 0%
14 | Y | PC3 NR band for UL-MIMO | n81 |  | New PC3 Config | China Unicom | China Unicom | Completed | TBD | 38.521-1: R5-247220(MOP，MPR) R5-247219 R5-251539（AMPR） 38.508-2： R5-247222 |  | 1 | 100% (+10%) | 100% (+10%) |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  |  | 100%
15 | Y | PC2 NR band for UL-MIMO | n25 |  | New PC2 Config |  |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  |  | 0%
16 | Y | PC2 and PC3 NR band for UL-MIMO | n85 |  | New PC2 and PC3 Config | T-Mobile USA | Nokia | Completed | RAN5#105 (Nov-24) | 38.521-1: R5-247743 R5-246453 38.508-2： R5-246452 | CDS：R5-246451 | 1 | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  |  | 100%
17 | Y | PC2 and PC3 NR band for UL-MIMO | n86 |  | New PC2 and PC3 Config |  |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  |  | 0%
18 | Y | PC3 NR band for UL-MIMO | n105 |  | New PC3 Config | Spark NZ Ltd | Nokia | Completed | RAN5#105 (Nov-24) | 38.521-1: R5-247743 R5-246453 38.508-2： R5-246452 | CDS：R5-246451 | 1 | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  |  | 100%
19 | Y | PC2 and PC3 NR band for UL-MIMO | n104 |  | New PC2 and PC3 Config | CMCC | CMCC | Ongoing | RAN5#107 (May-25) | 38.521-1： R5-250175 |  | 1 | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  |  | 0%
20 | Y | PC2 NR band for UL-MIMO | n8 |  | New PC2 Config | China Unicom | China Unicom | Completed | RAN5#105 (Nov-24) | 38.521-1： R5-243123 R5-250436（MPR） R5-251538 (AMPR) |  | 1 | 100% (+16.7%) | 100% (+16.7%) |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  |  | 100%
Note on S1: The TS's weight number is used to set the reletive weights between TS contributions used in the overall calculation of completeness of teh WP item. Setting it to 0 for a WP item means that it will not be included at all in the calculation.
Note on A6: Unique ID for WP items (unique within the sub-area work plan) Note! As WP item numbers may be referenced from outside of this WP that means: - Do not change number for WP items that have been published. - Do not re-use WP item numbers if a WP item is deleted
Note on B6: Set to Y if the WP item represents a new configuration or a new test case that will be specified in RAN5 test specifications as an executable test case else leave blank.
Note on M6: The WP item's weight number is used to set the reletive weights between WP items used in the overall calculation of completeness. Setting it to 0 for a WP item means that it will not be included at all in the calculation.
Note on Q12: Rapporteur guideline to assign applicable sub-areas for a WP item (columns S to X) To Set applicable sub-area(s) for a WP item do: - Copy the formula/cell content from one of the other non-empty cells under the "WP item status vs Area" section (columns S to X). To Clear applicable sub-area(s) for a WP item do: - Select the cell for teh WP item for the sub-area and press <Delete>-botton (clear content of the cell).