## Cover sheet
RAN5 meeting #106 | [10 empty] | R5-250372
Athens, Greece, 17th February - 21st February 2025
Agenda Item: | 7.4.2
Source: | Qualcomm Incorporated
Title: | New WID on UE Conformance - Alignment of eCall over IMS with CEN
Work item code: | eCallCEN-UEConTest
Release: | Rel-19
Document for: | Information
RAN5 WP template v2.0
1. Introduction
The objective of this work plan is to define the UE conformance test aspects corresponding to WID on Rel-19 eCallCEN-UEConTest.
2. Work item status
Estimation of WI overall completion:
Area |  | Completion | Number of new completed test cases (Note 1) | Number of new test cases | Comments
Overall completion |  | 80% | 8 (+8) | 8 (+8)
Completion Compensation |  | -
| Note 1: | Only test cases completed for all applicable WP areas and sub-areas are counted. For completed test cases per WP areas and WP sub-areas see below.
Estimation WI completion per area and sub-area:
|  | Completion | Number of new completed test cases | Number of new test cases | Comments
SA Option 2 (SA NR) |  | 80%
FR1 |  | 80% | 8 (+8) | 8 (+8)
FR2 |  |  | 8 (+8) | 8 (+8)
LTE |  | 98.3% (+98.3%) | 8 (+8) | 8 (+8)
FR1 |  | 98.3% (+98.3%) | 8 (+8) | 8 (+8)
Estimation of completion per TS (area):
|  | TS/TR overall completion |  |  | SA Option 2 (SA NR) | [6 empty] | LTE
TS/TR Scope | TS/TR | Completion | Number of new completed test cases | Number of new test cases | FR1 |  |  | FR2 |  |  |  | FR1
[5 empty] | Completion | Number of new completed test cases | Number of new test cases | Completion | Number of new completed test cases | Number of new test cases |  | Completion | Number of new completed test cases | Number of new test cases
5GS
5GS Common
Common test environment | 38.508-1
Common ICS | 38.508-2
5GS RAN and CN protocols
Protocol test cases | 38.523-1
Applicability Protocol test cases | 38.523-2 | 90% |  |  | 100% (+100%) | [6 empty] | 0%
Test suites (TTCN) | 38.523-3
IMS
IMS over LTE protocol test cases | 34.229-1 | 99.9% (+99.9%) | 8 (+8) | 8 (+8) | [7 empty] | 99.9% (+99.9%) | 8 (+8) | 8 (+8)
IMS over 5GS protocol test cases | 34.229-5
Applicability and ICS IMS test cases | 34.229-2 | 80% (+80%) | [9 empty] | 80% (+80%)
IMS Test suite (TTCN) | 34.229-3
5 References
RP-242495 - New WID on UE Conformance - Alignment of eCall over IMS with CEN
Note on B21: Overall completion of the work item reported at an earlier meeting will not be decreased if additional tasks are added or if corrections are made to the work plan. Instead the earlier reported completion status will be kept until necessary progress have been achieved such that completion exceeds the earlier reported completion level. The value of the Completion Compensation value represents the difference in the decrease caused by late additions or corrections to the work plan and the current estimated overall completion. '-' indicates that no compensation is applied.

## WP
WP Title: |  | New WID on UE Conformance - Alignment of eCall over IMS with CEN | [11 empty] | Start of workplan status columns. Note! Do not remove this column. | WP item status |  |  | End of workplan columns. Note! Do not remove this column.
WI code |  | eCallCEN-UEConTest
WP Scope: |  | The objective of this work plan is to define the UE conformance test aspects corresponding to WID on Rel-19 eCallCEN-UEConTest. | [13 empty] | vs Area
WP Resp: |  | Yogesh Tugnawat |  |  | yogesht@qti.qualcomm.com | [5 empty] | WP item completion |  |  |  | SA Option 2 (SA NR) |  | LTE
TS Resp: |  | n/a |  |  | n/a
WP Item ID | Is new test case? | TS/area | Clause | Title | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | Overall | SA Option 2 (SA NR) | LTE |  | FR1 | FR2 | FR1
[15 empty] | 100% (+100%) |  | 98.3% (+98.3%)
[15 empty] | 9 (+9) | 0 | 12 (+12)
[15 empty] | 0.1 (+0.1) | 0 | 8.4 (+8.4)
5%
Start of work plan items. Note! Do not remove this row. Introduce new work plan rows/items below this row.
5GS
5GS Common
TS 38.508-1: Common test environment
7 |  | 38.508-1 | 4 | Placeholder for generic procedures | [5 empty] | TBD
TS 38.508-2: Common ICS
8 |  | 38.508-2 | A.4 | Introduce/update PICS parameters for eCall over IMS for NR test cases | [5 empty] | TBD
RAN and CN protocol
TS 38.523-1: Protocol test cases
General tests
9 |  | 38.523-1 | 11.5 | eCall over IMS | New sub-clause header |  |  |  |  | 0
TS 38.523-2: Applicability for Protocol test cases
11 |  | 38.523-2 | 4.1, 4.2 | Add/update PICS and test case applicability statements for the test cases in 38.523-1 | Add/update PICS and test case applicability statements for the test cases in 38.523-1 |  |  | R5-250385 |  | 0.1 | 100% | 100% | 0% |  | 100% |  | 0%
TS 38.523-3: Protocol test suites (TTCN)
12 |  | 38.523-3 | [7 empty] | TBD
LTE
LTE Common
TS 36.508: Common test environment
1 |  | 36.508 | 4 | Placeholder for generic procedures | [5 empty] | 0.5
RAN and CN protocol
TS 36.523-1: Protocol test cases
General tests
2 |  | 36.523-1 | 11.3 | Placeholder | [5 empty] | 0
TS 36.523-2: Applicability for Protocol test cases
5 |  | 36.523-2 | 4.1, 4.2 | Placeholder | [5 empty] | 0.1
TS 36.523-3: Protocol test suites (TTCN)
6 |  | 36.523-3 |  | Introduction of Signaling Test Environment for eCall over IMS for NR | [5 empty] | TBD
IMS
TS 34.229-1: IMS over LTE protocol test cases
13 |  | 34.229-1 | 21 | eCall over IMS | [5 empty] | 0
14 | Y | 34.229-1 | 21.19 | eCall only mode / Manual initiation / Emergency registration / Abnormal case / IM CN sends a 486 (Busy Here) with positive ACK / Successful MSD | Test to verify that on reception of reject cause 486 Busy here with positive acknowledgement for a manually initiated INVITE for eCall over IMS, UE considers MSD transmission as successful. | Qualcomm | RAN5#106 (Feb-25) | R5-251340 |  | 1 | 100% (+100%) |  | 100% (+100%) |  |  |  | 100%
15 | Y | 34.229-1 | 21.2 | eCall only mode / Automatic initiation / Emergency registration / Abnormal case / IM CN sends a 600 (Busy Everywhere) with positive ACK / Successful MSD | Test to verify that on reception of reject cause 600 Busy Everywhere with positive acknowledgement for automatically initiated INVITE for eCall over IMS, UE considers MSD transmission as successful. | Qualcomm | RAN5#106 (Feb-25) | R5-251341 |  | 1 | 100% (+100%) |  | 100% (+100%) |  |  |  | 100%
16 | Y | 34.229-1 | 21.21 | eCall only mode / Manual initiation / Emergency registration / Abnormal case / IM CN sends a 603 (Decline) with positive ACK / Successful MSD | Test to verify that on reception of reject cause 603 Decline with positive acknowledgement for a manually initiated INVITE for eCall over IMS, UE considers MSD transmission as successful. | Qualcomm | RAN5#106 (Feb-25) | R5-251342 |  | 1 | 100% (+100%) |  | 100% (+100%) |  |  |  | 100%
17 | Y | 34.229-1 | 21.22 | eCall Capable / Manual initiation / Normal registration / Emergency registration / 200 OK with NACK | Test to verify that the UE can correctly perform eCall over IMS when initiated manually and continues with call establishment after 200 OK with NACK is received from SS. The process consists of emergency registration and MSD included in INVITE during call setup. | Qualcomm | RAN5#106 (Feb-25) | R5-251343 |  | 1 | 100% (+100%) |  | 100% (+100%) |  |  |  | 100%
34 | Y | 34.229-1 | 21.23 | eCall Capable / Automatic initiation / Normal registration / Emergency registration / 200 OK with NACK | Test to verify that the UE can correctly perform eCall over IMS when initiated automatically and continues with call establishment after 200 OK with NACK is received. The process consists of emergency registration and MSD included in INVITE during call setup. | Qualcomm | RAN5#106 (Feb-25) | R5-251344 |  | 1 | 100% (+100%) |  | 100% (+100%) |  |  |  | 100%
19 | Y | 34.229-1 | 21.24 | eCall Capable / eCall to URI for test service / Normal registration / 200 OK with NACK | Test to verify that the UE can correctly perform test eCall over IMS when initiated and continues with call establishment after 200 OK with NACK is received. The process consists of normal registration and MSD included in INVITE during call setup. | Qualcomm | RAN5#106 (Feb-25) | R5-251345 |  | 1 | 100% (+100%) |  | 100% (+100%) |  |  |  | 100%
32 | Y | 34.229-1 | 21.25 | eCall only mode / Automatic initiation / MSD transfer and 200 OK with ACK / SIP INFO request for MSD Update / PSAP Callback / Success | Test to verify that the UE sends correctly composed SIP INFO for MSD transfer during automatically initiated eCall over IMS and PSAP callback after successful completion of eCall over IMS in ecall only mode. | Qualcomm | RAN5#106 (Feb-25) | R5-251274 |  | 1 | 100% (+100%) |  | 100% (+100%) |  |  |  | 100%
33 | Y | 34.229-1 | 21.26 | eCall only mode / eCall to URI for test service / MSD transfer and 200 OK with ACK / SIP INFO request for MSD Update / PSAP Callback / Success | Test to verify that the UE sends correctly composed SIP INFO for MSD transfer during test ecall and during PSAP callback after successful completion of test eCall over IMS in ecall only mode. | Qualcomm | RAN5#106 (Feb-25) | R5-251275 |  | 1 | 100% (+100%) |  | 100% (+100%) |  |  |  | 100%
20 |  | 34.229-1 | A | Annexes | [5 empty] | 0
21 |  | 34.229-1 | A | Updates to Annexes - default messages | A.2.9, A.3.1, A.2.19, A.2.20 updates | Qualcomm | RAN5#107 (May-25) | R5-251338, R5-251339, R5-251276 |  | 0.1 | 90% (+90%) |  | 90% (+90%) |  |  |  | 90%
TS 34.229-5: IMS over 5GS protocol test cases
22 |  | 34.229-5 | Annex | [6 empty] | 1
23 |  | 34.229-5 | 11 | eCall over IMS
24 | Y | 34.229-5 | 11.7 | eCall only mode / Manual initiation / Emergency registration / Abnormal case / IM CN sends a 486 (Busy Here) with positive ACK / Successful MSD | Test to verify that on reception of reject cause 486 Busy here with positive acknowledgement for a manually initiated INVITE for eCall over IMS, UE considers MSD transmission as successful. | Qualcomm | RAN5#106 (Feb-25) | R5-251398 |  | 1 | 90% | 90% |  |  | 90% | 90%
25 | Y | 34.229-5 | 11.8 | eCall only mode / Automatic initiation / Emergency registration / Abnormal case / IM CN sends a 600 (Busy Everywhere) with positive ACK / Successful MSD | Test to verify that on reception of reject cause 600 Busy Everywhere with positive acknowledgement for automatically initiated INVITE for eCall over IMS, UE considers MSD transmission as successful. | Qualcomm | RAN5#106 (Feb-25) | R5-251399 |  | 1 | 90% | 90% |  |  | 90% | 90%
26 | Y | 34.229-5 | 11.9 | eCall only mode / Manual initiation / Emergency registration / Abnormal case / IM CN sends a 603 (Decline) with positive ACK / Successful MSD | Test to verify that on reception of reject cause 603 Decline with positive acknowledgement for a manually initiated INVITE for eCall over IMS, UE considers MSD transmission as successful. | Qualcomm | RAN5#106 (Feb-25) | R5-251400 |  | 1 | 90% | 90% |  |  | 90% | 90%
27 | Y | 34.229-5 | 11.1 | eCall over IMS / Manual initiation / Normal registration / Emergency registration / 200 OK with NACK | Test to verify that the UE can correctly perform eCall over IMS when initiated manually and continues with call establishment after 200 OK with NACK is received from SS. The process consists of emergency registration and MSD included in INVITE during call setup. | Qualcomm | RAN5#106 (Feb-25) | R5-251401 |  | 1 | 90% | 90% |  |  | 90% | 90%
28 | Y | 34.229-5 | 11.11 | eCall over IMS / Automatic initiation / Normal registration / Emergency registration / 200 OK with NACK | Test to verify that the UE can correctly perform eCall over IMS when initiated automatically and continues with call establishment after 200 OK with NACK is received. The process consists of emergency registration and MSD included in INVITE during call setup. | Qualcomm | RAN5#106 (Feb-25) | R5-251402 |  | 1 | 90% | 90% |  |  | 90% | 90%
29 | Y | 34.229-5 | 11.12 | Test eCall over IMS / Normal registration / 200 OK with NACK | Test to verify that the UE can correctly perform test eCall over IMS when initiated and continues with call establishment after 200 OK with NACK is received. The process consists of normal registration and MSD included in INVITE during call setup. | Qualcomm | RAN5#106 (Feb-25) | R5-251403 |  | 1 | 90% | 90% |  |  | 90% | 90%
30 | Y | 34.229-5 | 11.13 | eCall only mode / Automatic initiation / MSD transfer and 200 OK with ACK / SIP INFO request for MSD Update / PSAP Callback / Success | (1) with { UE subjected to national regulations in CEN EN 17184 having previously established eCall type of emergency service } ensure that { when { UE receives INVITE for an incoming IMS call } then { UE checks the header fields in incoming IMS call for PSAP callback and responds with 200 OK } } (2) with { UE subjected to national regulations in CEN EN 17184 having previously established eCall type of emergency service } ensure that { when { SS requests for tranfer of MSD during an incoming IMS call } then { The UE sends 200 OK and performs MSD transfer } } | Qualcomm | RAN5#106 (Feb-25) | R5-251404 |  | 1 | 90% | 90% |  |  | 90% | 90%
31 | Y | 34.229-5 | 11.14 | eCall only mode / eCall to URI for test service / MSD transfer and 200 OK with ACK / SIP INFO request for MSD Update / PSAP Callback / Success | (1) with { UE subjected to national regulations in CEN EN 17184 UE has an ongoing ecall to uri for test services } ensure that { when { SS sends SIP INFO message for MSD } then { the UE sends SIP INFO message including MSD } } (2) with { UE subjected to national regulations in CEN EN 17184 having previously established eCall to URI for test services } ensure that { when { UE receives INVITE for an incoming IMS call } then { UE checks the header fields in incoming IMS call for PSAP callback and responds with 200 OK } } (3) with { UE subjected to national regulations in CEN EN 17184 having previously established eCall to URI for test services } ensure that { when { SS requests for tranfer of MSD during an incoming IMS call } then { The UE sends 200 OK and performs MSD transfer } } | Qualcomm | RAN5#106 (Feb-25) | R5-251398 |  | 1 | 90% | 90% |  |  | 90% | 90%
TS 34.229-2: Applicability and ICS for IMS protocol test cases
24 |  | 34.229-2 | 2, A.4.5 | PICS for CEN support |  | Qualcomm | RAN5#107 (May-25) | R5-250472 |  | 0.1 | 100% |  | 100% |  |  |  | 90%
25 |  | 34.229-2 | 4.1, 4.2 | Applicability updates to test cases in TS 34.229-1/5 |  | Qualcomm | RAN5#107 (May-25) | R5-251346 R5-251406 |  | 0.1 | 90% |  | 90% |  |  |  | 70%
TS 34.229-3: IMS test suite (TTCN)
26 |  | 34.229-3 | [7 empty] | TBD
End of workplan items. Note! Do not remove this row. Introduce new work plan rows/items above this row.
Note on A6: Unique ID for WP items (unique within the sub-area work plan) Note! As WP item numbers may be referenced from outside of this WP that means: - Do not change number for WP items that have been published. - Do not re-use WP item numbers if a WP item is deleted
Note on B6: Set to Y if the WP item represents a new test case that will be specified in RAN5 test specifications as an executable test case else leave blank.
Note on K6: The WP item's weight number is used to set the reletive weights between WP items used in the overall calculation of completeness. Setting it to 0 for a WP item means that it will not be included at all in the calculation.