## Cover sheet
3GPP TSG RAN WG5 Meeting #106 | [7 empty] | R5-251337
Athens, Greece, 17th Feb 2025 - 21st Feb 2025
Agenda Item: | 6.6.6.6
Source: | Vodafone, Ericsson
Title: | IMS real-time text
Work item code: | TEI12_Test (LTE), TEI15_Test (NR/5GC)
Release: | Rel-12 (LTE), Rel-15 (NR/5GC)
Document for: | Information
RAN5 WP template v3.0.0
1. Introduction
Adding IMS RTT test coverage to support the requirements of the EU directive 2019/882
2. Work item status
Estimation of WI overall completion:
Area |  | Completion | Number of new completed test cases (Note 1) | Number of new test cases | Comments
Overall completion |  | 25% | 0 | 8
Completion Compensation |  | -
| Note 1: | Only test cases completed for all applicable WP areas and sub-areas are counted. For completed test cases per WP areas and WP sub-areas see below.
Estimation WI completion per area and sub-area:
|  | Completion | Number of new completed test cases | Number of new test cases | Comments
SA Option 2 (SA NR) |  | 24.7% | 0 | 4
|  | 24.7% | 0 | 4
LTE |  |  | 0 | 4
Estimation of completion per TS (area):
|  | TS/TR overall completion |  |  | SA Option 2 (SA NR) |  |  |  | LTE
TS/TR Scope | TS/TR | Completion | Number of new completed test cases | Number of new test cases
[5 empty] | Completion | Number of new completed test cases | Number of new test cases
LTE
LTE Common
Common test environment | 36.508
UE specific test functions | 36.509
LTE RAN and CN protocols
Protocol test cases | 36.523-1
Applicability Protocol test cases | 36.523-2
Test suites (TTCN) | 36.523-3
5GS
5GS Common
Common test environment | 38.508-1 | 0% |  |  | 0%
Common ICS | 38.508-2
UE specific test functions | 38.509
5GS RAN and CN protocols
Protocol test cases | 38.523-1
Applicability Protocol test cases | 38.523-2
Test suites (TTCN) | 38.523-3
IMS
IMS over LTE protocol test cases | 34.229-1 |  | 0 | 4
IMS over 5GS protocol test cases | 34.229-5 | 25% | 0 | 4 | 25% | 0 | 4
Applicability and ICS IMS test cases | 34.229-2 | 33.3% |  |  | 33.3%
IMS Test suite (TTCN) | 34.229-3
5 References
[1] R5-251335 | Discussion paper: IMS real time text
Note on B21: Overall completion of the work item reported at an earlier meeting will not be decreased if additional tasks are added or if corrections are made to the work plan. Instead the earlier reported completion status will be kept until necessary progress have been achieved such that completion exceeds the earlier reported completion level. The value of the Completion Compensation value represents the difference in the decrease caused by late additions or corrections to the work plan and the current estimated overall completion. '-' indicates that no compensation is applied.

## WP
WP Title: |  | IMS real-time text | [11 empty] | Start of workplan status columns. Note! Do not remove this column. | WP item status |  | End of workplan columns. Note! Do not remove this column.
WI code |  | TEI12_Test (LTE), TEI15_Test (NR/5GC)
WP Scope: |  | Add RTT test coverage for IMS
WP Resp: |  | Petra Rauer |  |  | petra.rauer@vodafone.com | [5 empty] | WP item completion |  |  |  | SA Option 2 (SA NR) | LTE
TS Resp: |  | n/a |  |  | n/a
WP Item ID | Is new test case? | TS/area | Clause | Title | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | Overall | SA Option 2 (SA NR) | LTE |  |  | N/A
[15 empty] | 24.7% | 5%
[15 empty] | 9 | 0
[15 empty] | 5.3 | 0
5%
Start of work plan items. Note! Do not remove this row. Introduce new work plan rows/items below this row.
LTE
LTE Common
TS 36.508: Common test environment
|  | 36.508 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
TBD |  | 36.508 | <Clause> | <Title of new sub-clause header> | New sub-clause header |  | TBD |  |  | 0
TBD |  | 36.508 | <Clause> | <Title of task> | <Describe task> |  | TBD |  |  | TBD
1 |  | 36.508 | 4.5A.x | Test procedure for emergency call with real-time text in 5GC | Procedure for adding QoS flow for RTT | Ericsson | RAN5#107 (May-25) |  |  | 0.5 | 0% |  | 0% |  |  | 0%
2 |  | 36.508 | 4.5A.x | Test procedure for adding real-time text to a speech call in 5GC | Procedure for adding QoS flow for RTT | Ericsson | RAN5#107 (May-25) |  |  | 0.5 | 0% |  | 0% |  |  | 0%
TS 36.509: UE specific testing functions
|  | 36.509 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
TBD |  | 36.509 | <Clause> | <Title of new sub-clause header> | New sub-clause header |  | TBD |  |  | 0
TBD |  | 36.509 | <Clause> | <Title of task> | <Describe task> |  | TBD |  |  | TBD
TS 36.523-1: Protocol test cases
|  | 36.523-1 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
Idle Mode
TBD |  | 36.523-1 | <Clause> | <Title of modified existing test case> | <Describe required change of the existing test case> |  | TBD |  |  | TBD
TBD |  | 36.523-1 | <Clause> | <Title of new sub-clause header> | New sub-clause header |  | TBD |  |  | 0
TBD | Y | 36.523-1 | <Clause> | <Title of new test case> | Test Purpose(s): <Describe test purpose(s)> |  | TBD |  |  | 1
Layer 2
TBD |  | 36.523-1 | <Clause> | <Title of modified existing test case> | <Describe required change of the existing test case> |  | TBD |  |  | TBD
TBD |  | 36.523-1 | <Clause> | <Title of new sub-clause header> | New sub-clause header |  | TBD |  |  | 0
TBD | Y | 36.523-1 | <Clause> | <Title of new test case> | Test Purpose(s): <Describe test purpose(s)> |  | TBD |  |  | 1
RRC
TBD |  | 36.523-1 | <Clause> | <Title of modified existing test case> | <Describe required change of the existing test case> |  | TBD |  |  | TBD
TBD |  | 36.523-1 | <Clause> | <Title of new sub-clause header> | New sub-clause header |  | TBD |  |  | 0
TBD | Y | 36.523-1 | <Clause> | <Title of new test case> | Test Purpose(s): <Describe test purpose(s)> |  | TBD |  |  | 1
NAS
TBD |  | 36.523-1 | <Clause> | <Title of modified existing test case> | <Describe required change of the existing test case> |  | TBD |  |  | TBD
TBD |  | 36.523-1 | <Clause> | <Title of new sub-clause header> | New sub-clause header |  | TBD |  |  | 0
TBD | Y | 36.523-1 | <Clause> | <Title of new test case> | Test Purpose(s): <Describe test purpose(s)> |  | TBD |  |  | 1
TS 36.523-2: Applicability for Protocol test cases
TBD |  | 36.523-2 | <Clause> | <Title> | Add new ICS statements. |  | TBD |  |  | 0.1
TBD |  | 36.523-2 | <Clause> | <Title> | Add test case applicability statements for the new test cases introduced in 36.523-1 |  | TBD |  |  | 0.1
TS 36.523-3: Protocol test suites (TTCN)
|  | 36.523-3 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
TBD |  | 36.523-3 | <Clause> | <Title of task> | <Describe task> |  | TBD |  |  | TBD
5GS
5GS Common
TS 38.508-1: Common test environment
|  | 38.508-1 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
TBD |  | 38.508-1 | <Clause> | <Title of new sub-clause header> | New sub-clause header |  | TBD |  |  | 0
TBD |  | 38.508-1 | <Clause> | <Title of task> | <Describe task> |  | TBD |  |  | TBD
3 |  | 38.508-1 | 4.9.x | Test procedure for emergency call with real-time text in 5GC | Procedure for adding QoS flow for RTT | Ericsson | RAN5#107 (May-25) |  |  | 0.5 | 0% | 0% |  |  | 0%
4 |  | 38.508-1 | 4.9.x | Test procedure for adding real-time text to a speech call in 5GC | Procedure for adding QoS flow for RTT | Ericsson | RAN5#107 (May-25) |  |  | 0.5 | 0% | 0% |  |  | 0%
TS 38.508-2: Common ICS
|  | 38.508-2 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
TBD |  | 38.508-2 | <Clause> | <Title> | Add ICS as needed for the test case applicability statements for the new test cases introduced in RF, RRM and protocol test cases. |  | TBD |  |  | TBD
TS 38.509: UE specific testing functions
|  | 38.509 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
TBD |  | 38.509 | <Clause> | <Title of new sub-clause header> | New sub-clause header |  | TBD |  |  | 0
TBD |  | 38.509 | <Clause> | <Title of task> | <Describe task> |  | TBD |  |  | TBD
RAN and CN protocol
TS 38.523-1: Protocol test cases
|  | 38.523-1 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
Idle Mode
TBD |  | 38.523-1 | <Clause> | <Title of new sub-clause header> | New sub-clause header |  | TBD |  |  | 0
TBD |  | 38.523-1 | <Clause> | <Title of modified existing test case> | <Describe required change of the existing test case> |  | TBD |  |  | TBD
TBD | Y | 38.523-1 | <Clause> | <Title of new test case> | Test Purpose(s): <Describe test purpose(s)> |  | TBD |  |  | 1
Layer 2
TBD |  | 38.523-1 | <Clause> | <Title of new sub-clause header> | New sub-clause header |  | TBD |  |  | 0
TBD |  | 38.523-1 | <Clause> | <Title of modified existing test case> | <Describe required change of the existing test case> |  | TBD |  |  | TBD
TBD | Y | 38.523-1 | <Clause> | <Title of new test case> | Test Purpose(s): <Describe test purpose(s)> |  | TBD |  |  | 1
RRC
TBD |  | 38.523-1 | <Clause> | <Title of new sub-clause header> | New sub-clause header |  | TBD |  |  | 0
TBD |  | 38.523-1 | <Clause> | <Title of modified existing test case> | <Describe required change of the existing test case> |  | TBD |  |  | TBD
TBD | Y | 38.523-1 | <Clause> | <Title of new test case> | Test Purpose(s): <Describe test purpose(s)> |  | TBD |  |  | 1
NAS
TBD |  | 38.523-1 | <Clause> | <Title of new sub-clause header> | New sub-clause header |  | TBD |  |  | 0
TBD |  | 38.523-1 | <Clause> | <Title of modified existing test case> | <Describe required change of the existing test case> |  | TBD |  |  | TBD
TBD | Y | 38.523-1 | <Clause> | <Title of new test case> | Test Purpose(s): <Describe test purpose(s)> |  | TBD |  |  | 1
TS 38.523-2: Applicability for Protocol test cases
TBD |  | 38.523-2 | <Clause> | <Title> | Add new ICS statements. |  | TBD |  |  | 0.1
TBD |  | 38.523-2 | <Clause> | <Title> | Add test case applicability statements for the new test cases introduced in 38.523-1 |  | TBD |  |  | 0.1
TS 38.523-3: Protocol test suites (TTCN)
|  | 38.523-3 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
TBD |  | 38.523-3 | <Clause> | <Title of task> | <Describe task> |  | TBD |  |  | TBD
IMS
TS 34.229-1: IMS over LTE protocol test cases
|  | 34.229-1 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
TBD |  | 34.229-1 | <Clause> | <Title of new sub-clause header> | New sub-clause header |  | TBD |  |  | 0
TBD |  | 34.229-1 | <Clause> | <Title of modified existing test case> | <Describe required change of the existing test case> |  | TBD |  |  | TBD
TBD | Y | 34.229-1 | <Clause> | <Title of new test case> | Test Purpose(s): <Describe test purpose(s)> |  | TBD |  |  | 1
5 | Y | 34.229-1 | 17.xx | MO Speech / add RTT and remove RTT / EVS / Default configuration | Test Purpose(s): Add and remove RTT to/from ongoing MTSI MO voice call | Ericsson | RAN5#107 (May-25) |  |  | 1 | 0% |  | 0% |  |  | 0%
6 | Y | 34.229-1 | 17.xx | MT Speech / add RTT and remove RTT / EVS / Default configuration | Test Purpose(s): Add and remove RTT to/from ongoing MTSI MT voice call | Ericsson | RAN5#107 (May-25) |  |  | 1 | 0% |  | 0% |  |  | 0%
7 | Y | 34.229-1 | 19.1.x | Emergency call / RTT activated | Test Purpose(s): Setup 4G emergency call with real-time text (RTT) enabled | Qualcomm | RAN5#107 (May-25) |  |  | 1 | 0% |  | 0% |  |  | 0%
8 | Y | 34.229-1 | 19.1.x | Emergency call / add RTT and remove RTT | Test Purpose(s): Add and remove RTT to/from ongoing 4G emergency voice call | Ericsson | RAN5#107 (May-25) |  |  | 1 | 0% |  | 0% |  |  | 0%
TS 34.229-5: IMS over 5GS protocol test cases
|  | 34.229-5 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
TBD |  | 34.229-5 | <Clause> | <Title of new sub-clause header> | New sub-clause header |  | TBD |  |  | 0
TBD |  | 34.229-5 | <Clause> | <Title of modified existing test case> | <Describe required change of the existing test case> |  | TBD |  |  | TBD
TBD | Y | 34.229-5 | <Clause> | <Title of new test case> | Test Purpose(s): <Describe test purpose(s)> |  | TBD |  |  | 1
9 | Y | 34.229-5 | 7.35 | MTSI MO Voice Call / add RTT and remove RTT / with preconditions at both originating UE and terminating UE / 5GS | Test Purpose(s): Setup MTSI voice call with real-time text (RTT) enabled | Qualcomm | RAN5#107 (May-25) | R5-251057 (WD) |  | 1 | 0% | 0% |  |  | 0%
10 | Y | 34.229-5 | 7.36 | MTSI MO Voice Call / add RTT and remove RTT / without preconditions at both originating UE and terminating UE / 5GS | Test Purpose(s): Add and remove RTT to/from ongoing MTSI voice call | Vodafone | RAN5#107 (May-25) | R5-251058 (WD) |  | 1 | 0% | 0% |  |  | 0%
11 | Y | 34.229-5 | 10.16 | Emergency Call with emergency registration / RTT activated / 5GS | Test Purpose(s): Setup 5G emergency call with real-time text (RTT) enabled | Vodafone | RAN5#106 (Feb-25) | R5-251386 |  | 1 | 50% | 50% |  |  | 50%
12 | Y | 34.229-5 | 10.17 | Emergency Call with emergency registration / add RTT and remove RTT / 5GS | Test Purpose(s): Add and remove RTT to/from ongoing 5G emergency voice call | Vodafone | RAN5#106 (Feb-25) | R5-251387 |  | 1 | 50% | 50% |  |  | 50%
TS 34.229-2: Applicability and ICS for IMS protocol test cases
TBD |  | 34.229-2 | <Clause> | <Title> | Add new ICS statements. |  | TBD |  |  | 0.1
TBD |  | 34.229-2 | <Clause> | <Title> | Add test case applicability statements for the new test cases introduced in 34.229-1 and/or 34.229-5. |  | TBD |  |  | 0.1
13 |  | 34.229-2 | 4.1 | Addition of applicability of new test case 17.xx | Add test case applicability statements for the new test cases introduced in 34.229-1 | Ericsson | RAN5#107 (May-25) |  |  | 0.1 | 0% |  | 0% |  |  | 0%
14 |  | 34.229-2 | 4.1 | Addition of applicability of new test case 19.1.xx | Add test case applicability statements for the new test cases introduced in 34.229-1 | Ericsson | RAN5#107 (May-25) |  |  | 0.1 | 0% |  | 0% |  |  | 0%
15 |  | 34.229-2 | 4.1 | Addition of applicability of new test case 19.1.xx | Add test case applicability statements for the new test cases introduced in 34.229-1 | Qualcomm | RAN5#107 (May-25) |  |  | 0.1 | 0% |  | 0% |  |  | 0%
16 |  | 34.229-2 | 4.2 | Addition of applicability of new test case 7.35 MTSI MO adding RTT | Add test case applicability statements for the new test cases 7.35 in TS 34.229-5 | Qualcomm | RAN5#107 (May-25) | R5-251059 (WD) |  | 0.1 | 0% | 0% |  |  | 0%
17 |  | 34.229-2 | 4.2 | Addition of applicability of new test case 7.36 MTSI MO adding RTT | Add test case applicability statements for the new test cases 7.36 in TS 34.229-5 | Vodafone | RAN5#107 (May-25) | R5-251060 (WD) |  | 0.1 | 0% | 0% |  |  | 0%
18 |  | 34.229-2 | 4.2 and A.4.7 | Addition of applicability of new RTT test cases | Add test case applicability statements for the new test cases 10.16 in TS 34.229-5 | Vodafone | RAN5#106 (Feb-25) | R5-251480 |  | 0.1 | 100% | 100% |  |  | 100%
TS 34.229-3: IMS test suite (TTCN)
|  | 34.229-3 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
TBD |  | 34.229-3 | <Clause> | <Title of task> | <Describe task> |  | TBD |  |  | TBD
End of workplan items. Note! Do not remove this row. Introduce new work plan rows/items above this row.
Note on A6: Unique ID for WP items (unique within the sub-area work plan) Note! As WP item numbers may be referenced from outside of this WP that means: - Do not change number for WP items that have been published. - Do not re-use WP item numbers if a WP item is deleted
Note on B6: Set to Y if the WP item represents a new test case that will be specified in RAN5 test specifications as an executable test case else leave blank.
Note on K6: The WP item's weight number is used to set the reletive weights between WP items used in the overall calculation of completeness. Setting it to 0 for a WP item means that it will not be included at all in the calculation.