## Cover sheet
3GPP TSG-RAN5 Meeting #106 | [10 empty] | R5-251447
Athens, Greece, 17th Feb 2025 - 21st Feb 2025
Agenda Item: | 7.4.2
Source: | Qualcomm Inc
Title: | WP - UE Conformance - NR NTN (Non-Terrestrial Networks) enhancements
Work item code: | NR_NTN_enh_plus_CT-UEConTest
Release: | Rel-18
Document for: | Information
RAN5 WP template v3.0.0
1. Introduction
<Description of work item and its scope>
2. Work item status
Estimation of WI overall completion:
Area |  | Completion | Number of new completed test cases (Note 1) | Number of new test cases | Comments
Overall completion |  | 10% (+4%) | 1 (+1) | 70 (-2)
Completion Compensation |  | -
| Note 1: | Only test cases completed for all applicable WP areas and sub-areas are counted. For completed test cases per WP areas and WP sub-areas see below.
Estimation WI completion per area and sub-area:
|  | Completion | Number of new completed test cases | Number of new test cases | Comments
SA Option 2 (SA NR) |  | 10.4% (+4.4%) | 1 (+1) | 70 (-2)
FR1 |  | 14.8% (+9.8%) | 1 (+1) | 29 (-3)
FR2 |  | 6.8% | 0 | 42
NSA Option 3 (EN-DC)
FR1
FR2
Estimation of completion per TS (area):
|  | TS/TR overall completion |  |  | SA Option 2 (SA NR) | [6 empty] | NSA Option 3 (EN-DC)
TS/TR Scope | TS/TR | Completion | Number of new completed test cases | Number of new test cases | FR1 |  |  | FR2 |  |  |  | FR1 |  |  | FR2
[5 empty] | Completion | Number of new completed test cases | Number of new test cases | Completion | Number of new completed test cases | Number of new test cases |  | Completion | Number of new completed test cases | Number of new test cases | Completion | Number of new completed test cases | Number of new test cases
5GS
5GS Common
Common test environment | 38.508-1 | 20% (+20%) |  |  | 20% (+20%)
Common ICS | 38.508-2 | 20% (+20%) |  |  | 20% (+20%)
UE specific test functions | 38.509
NR RF/RRM
FR2-NTN RF Transmitter test cases | 38.521-5 | 2.5% | 0 | 32 |  |  |  | 2.5% | 0 | 32
FR2-NTN RF Demodulation test cases | 38.521-5
RRM test cases | 38.533
Applicability RF. Demod/QSI and RRM test cases | 38.522
Test Tolerances analysis RRM and RF Rx test cases | 38.903
Test Point analysis receiver and transmitter test cases | 38.905 | 10% (+10%) |  |  | 10% (+10%)
5GS RAN and CN protocols
Protocol test cases | 38.523-1 | 11.8% (+11.8%) | 1 (+1) | 21 (-2) | 11.8% (+11.8%) | 1 (+1) | 22 (-3)
Applicability Protocol test cases | 38.523-2 | 20% (+20%) |  |  | 20% (+20%)
Test suites (TTCN) | 38.523-3
5 References
[1] RP-242024 | New WID on UE Conformance - NR NTN (Non-Terrestrial Networks) enhancements_plusCTaspects
[2] R5-247131 | WP - UE Conformance - NR NTN (Non-Terrestrial Networks) enhancements
Note on B21: Overall completion of the work item reported at an earlier meeting will not be decreased if additional tasks are added or if corrections are made to the work plan. Instead the earlier reported completion status will be kept until necessary progress have been achieved such that completion exceeds the earlier reported completion level. The value of the Completion Compensation value represents the difference in the decrease caused by late additions or corrections to the work plan and the current estimated overall completion. '-' indicates that no compensation is applied.

## WP
WP Title: |  | WP - UE Conformance - NR NTN (Non-Terrestrial Networks) enhancements | [11 empty] | Start of workplan status columns. Note! Do not remove this column. | WP item status |  |  |  | End of workplan columns. Note! Do not remove this column.
WI code |  | NR_NTN_enh_plus_CT-UEConTest
WP Scope: |  | This part of the work plan covers all applicable test cases for NR-NTN (Non-Terrestrial Networks) Enhancements Work item | [13 empty] | vs Area
WP Resp: |  | Vijay Balasubramanian |  |  | vijayb@qti.qualcomm.com | [5 empty] | WP item completion |  |  |  | SA Option 2 (SA NR) |  | NSA Option 3 (EN-DC)
TS Resp: |  | <TS responsible if a new TS is involved> |  |  | <Email to TS responsible>
WP Item ID | Is new test case? | TS/area | Clause | Title | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | Overall | SA Option 2 (SA NR) | NSA Option 3 (EN-DC) |  | FR1 | FR2 | FR1 | FR2
[15 empty] | 14.8% (+9.8%) | 6.8%
[15 empty] | 38 (+1) | 46 | 0 | 0
[15 empty] | 35.1 (+0.1) | 43.1 | 0 | 0
5%
Start of work plan items. Note! Do not remove this row. Introduce new work plan rows/items below this row.
5GS
5GS Common
TS 38.508-1: Common test environment
|  | 38.508-1 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
2 |  | 38.508-1 | 4 | Introduction of General Test Environment for Rel17 NTN solutions | SIB19, SIB25 | Qualcomm, Keysight | RAN5#109 (Nov-25) | R5-246879, R5-247672 R5-250756 |  | 1 | 20% (+20%) | 20% (+20%) |  |  | 20%
TS 38.508-2: Common ICS
7 |  | 38.508-2 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
5 |  | 38.508-2 | A.4.3 | Introduction of common implementation conformance statements for Rel-18 NTN solutions | Add ICS as needed for the test case applicability statements for the new test cases introduced in RF, RRM and protocol test cases. | Qualcomm | RAN5#109 (Nov-25) | R5-247599, R5-251298, R5-251365 |  | 1 | 20% (+20%) | 20% (+20%) |  |  | 20%
TS 38.509: UE specific testing functions
8 |  | 38.509 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
9 |  | 38.509 | <Clause> | <Title of new sub-clause header> | New sub-clause header |  | TBD |  |  | 0
10 |  | 38.509 | <Clause> | <Title of task> | <Describe task> |  | TBD |  |  | TBD
NR RF/Demod/RRM
TS 38.521-5: FR2-NTN RF Transmitter test cases
11 |  | 38.521-5 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
13 |  | 38.521-5 | 3,4,5 | Common Clauses |  | Qualcomm | RAN5#109 (Nov-25) | R5-247152 |  | 0.5 | 75% | 75% |  |  |  | 75%
55 |  | 38.521-5 | 6 |  |  | ZTE | RAN5#109 (Nov-25) | R5-251085 |  | 0.1
12 |  | 38.521-5 | 9 | Radiated transmitter characteristics | New sub-clause header |  | RAN5#109 (Nov-25) |  |  | 0
13 |  | 38.521-5 | 9.1 | General | <Describe required change of the existing test case> |  | RAN5#109 (Nov-25) |  |  | TBD
14 |  | 38.521-5 | 9.2 | Transmitter power | <Describe required change of the existing test case> |  | RAN5#109 (Nov-25) |  |  | TBD
15 |  | 38.521-5 | 9.2.1 | NTN VSAT maximum output power | <Describe required change of the existing test case> |  | RAN5#109 (Nov-25) |  |  | TBD
16 | Y | 38.521-5 | 9.2.1.1 | NTN VSAT maximum output power for Fixed VSAT | requirements define the maximum output power radiated by the Fixed VSAT for any transmission bandwidth within the channel bandwidth for non-CA configuration |  | RAN5#109 (Nov-25) |  |  | 1 | 0% | 0% |  |  |  | 0%
17 | Y | 38.521-5 | 9.2.1.2 | NTN VSAT maximum output power for Mobile VSAT | requirements define the maximum output power radiated by the Mobile VSAT for any transmission bandwidth within the channel bandwidth for non-CA configuration |  | RAN5#109 (Nov-25) |  |  | 1 | 0% | 0% |  |  |  | 0%
18 |  | 38.521-5 | 9.2.2 | Off-axis EIRP emission density limit within the operating band | <Describe required change of the existing test case> |  | RAN5#109 (Nov-25) |  |  | TBD
19 | Y | 38.521-5 | 9.2.2.2 | Minimum requirement for bands n510 and n511 | Test Purpose(s): <Describe test purpose(s)> |  | RAN5#109 (Nov-25) |  |  | 1 | 0% | 0% |  |  |  | 0%
20 | Y | 38.521-5 | 9.2.2.3.1 | Additional regional minimum requirement for band n512 (NS_201N) for Fixed VSAT | Off-axis EIRP density limits for co-polarized and cross-polarized transmissions |  | RAN5#109 (Nov-25) |  |  | 1 | 0% | 0% |  |  |  | 0%
21 | Y | 38.521-5 | 9.2.2.3.2 | Additional regional minimum requirement for band n512 (NS_201N) for Mobile VSAT | Off-axis EIRP density limits for co-polarized and cross-polarized transmissions |  | RAN5#109 (Nov-25) |  |  | 1 | 0% | 0% |  |  |  | 0%
22 | Y | 38.521-5 | 9.2.2.3.3 | Additional Off-axis EIRP density requirements for protection of fixed services | Additional Off-axis EIRP density requirements for protection of fixed services |  | RAN5#109 (Nov-25) |  |  | 1 | 0% | 0% |  |  |  | 0%
23 | Y | 38.521-5 | 9.2.3 | Configured transmitted power | configured NTN VSAT maximum output power requirements |  | RAN5#109 (Nov-25) |  |  | 1 | 0% | 0% |  |  |  | 0%
24 |  | 38.521-5 | 9.3 | Output power dynamics | <Describe required change of the existing test case> |  | TBD |  |  | TBD
25 | Y | 38.521-5 | 9.3.1 | Minimum output power | Test Purpose(s): <Describe test purpose(s)> |  | RAN5#109 (Nov-25) |  | The requirement is not applicable in this version of the specification | 1 | 0% | 0% |  |  |  | 0%
26 | Y | 38.521-5 | 9.3.2 | Transmit OFF power | Transmit OFF power requirements |  | RAN5#109 (Nov-25) |  |  | 1 | 0% | 0% |  |  |  | 0%
27 |  | 38.521-5 | 9.3.3 | Transmit ON/OFF time mask | <Describe required change of the existing test case> |  | TBD |  |  | TBD
28 | Y | 38.521-5 | 9.3.3.2 | General ON/OFF time mask | General ON/OFF time mask requirements |  | RAN5#109 (Nov-25) |  |  | 1 | 0% | 0% |  |  |  | 0%
29 | Y | 38.521-5 | 9.3.3.3 | Transmit power time mask for slot and short or long subslot boundaries | Transmit power time mask for slot and short or long subslot boundaries requirements |  | RAN5#109 (Nov-25) |  |  | 1 | 0% | 0% |  |  |  | 0%
30 | Y | 38.521-5 | 9.3.3.4 | PRACH time mask | PRACH time mask requirements |  | RAN5#109 (Nov-25) |  |  | 1 | 0% | 0% |  |  |  | 0%
31 | Y | 38.521-5 | 9.3.3.6 | SRS time mask | SRS time mask requirements |  | RAN5#109 (Nov-25) |  |  | 1 | 0% | 0% |  |  |  | 0%
32 | Y | 38.521-5 | 9.3.3.7 | PUSCH-PUCCH and PUSCH-SRS time masks | PUSCH-PUCCH and PUSCH-SRS time masksrequirements |  | RAN5#109 (Nov-25) |  |  | 1 | 0% | 0% |  |  |  | 0%
33 | Y | 38.521-5 | 9.3.3.8 | Transmit power time mask for consecutive slot or long subslot transmission and short subslot transmission boundaries |  |  | RAN5#109 (Nov-25) |  |  | 1 | 0% | 0% |  |  |  | 0%
34 | Y | 38.521-5 | 9.3.3.9 | Transmit power time mask for consecutive short subslot transmissions boundaries |  |  | RAN5#109 (Nov-25) |  |  | 1 | 0% | 0% |  |  |  | 0%
35 | Y | 38.521-5 | 9.3.4.1 | Power control |  |  | RAN5#109 (Nov-25) |  | The applicant shall declare the method and accuracy of uplink power control. Further clarifications needed in 38.101-5 | 1 | 0% | 0% |  |  |  | 0%
36 |  | 38.521-5 | 9.4 | Transmitter signal quality | <Describe required change of the existing test case> |  | TBD |  |  | TBD
37 | Y | 38.521-5 | 9.4.1 | Frequency Error | Frequency Error requirements |  | RAN5#109 (Nov-25) |  |  | 1 | 0% | 0% |  |  |  | 0%
38 |  | 38.521-5 | 9.4.2 | Transmit modulation quality | <Describe required change of the existing test case> |  | TBD |  |  | TBD
39 | Y | 38.521-5 | 9.4.2.2 | Error vector magnitude | EVM requirements |  | RAN5#109 (Nov-25) |  |  | 1 | 0% | 0% |  |  |  | 0%
40 |  | 38.521-5 | 9.5 | Output RF spectrum emissions | <Describe required change of the existing test case> |  | TBD |  |  | TBD
41 | Y | 38.521-5 | 9.5.1 | Occupied bandwidth | Occupied bandwidth requirements |  | RAN5#109 (Nov-25) |  |  | 1 | 0% | 0% |  |  |  | 0%
42 |  | 38.521-5 | 9.5.2 | Out of Band Emissions | <Describe required change of the existing test case> |  | TBD |  |  | TBD
43 |  | 38.521-5 | 9.5.2.2 | Spectrum emission mask | <Describe required change of the existing test case> |  | TBD |  |  | TBD
44 | Y | 38.521-5 | 9.5.2.2.1 | General NR spectrum emission mask | General NR spectrum emission mask requirements |  | RAN5#109 (Nov-25) |  |  | 1 | 0% | 0% |  |  |  | 0%
45 | Y | 38.521-5 | 9.5.2.2.2 | Additional spectrum emission mask | Additional spectrum emission mask requirements |  | RAN5#109 (Nov-25) |  |  | 1 | 0% | 0% |  |  |  | 0%
46 | Y | 38.521-5 | 9.5.2.3 | Adjacent channel leakage ratio | ACLR requirements |  | RAN5#109 (Nov-25) |  |  | 1 | 0% | 0% |  |  |  | 0%
47 | Y | 38.521-5 | 9.5.3.1 | General Spurious emissions | General Spurious emissions requirements |  | RAN5#109 (Nov-25) |  |  | 1 | 0% | 0% |  |  |  | 0%
48 | Y | 38.521-5 | 9.5.3.2 | On-axis spurious requirement | On-axis spurious requirement |  | RAN5#109 (Nov-25) |  |  | 1 | 0% | 0% |  |  |  | 0%
49 | Y | 38.521-5 | 9.5.3.3 | Off-axis spurious requirement | Off-axis spurious requirement |  | RAN5#109 (Nov-25) |  |  | 1 | 0% | 0% |  |  |  | 0%
50 |  | 38.521-5 | 9.6 | Antenna pointing accuracy and performance | <Describe required change of the existing test case> |  | TBD |  |  | TBD
51 | Y | 38.521-5 | 9.6.1.1 | Minimum requirements for NTN VSAT | On-axis cross polarization isolation requirements |  | RAN5#109 (Nov-25) |  |  | 1 | 0% | 0% |  |  |  | 0%
52 | Y | 38.521-5 | 9.6.1.2 | Minimum requirement for Fixed VSAT types 1 or 2 | additional regional requirements are applicable to Fixed VSAT types 1 or 2 operating in band n512 when connected to Geostationary Satellite Orbit (GSO) SAN (NS_201N) |  | RAN5#109 (Nov-25) |  |  | 1 | 0% | 0% |  |  |  | 0%
53 | Y | 38.521-5 | 9.6.2 | Antenna performance | Co-polarization and cross-polarization gain requirements |  | RAN5#109 (Nov-25) |  |  | 1 | 0% | 0% |  |  |  | 0%
54 | Y | 38.521-5 | 9.7 | Additional regional requirements indicated by NS | NS_200N, NS_201N, NS_202N requirements |  | RAN5#109 (Nov-25) |  |  | 1 | 0% | 0% |  |  |  | 0%
TS 38.521-5: FR2-NTN RF Receiver test cases
|  | 38.521-5 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
TBD |  | 38.521-5 | <Clause> | <Title of new sub-clause header> | New sub-clause header |  | TBD |  |  | 0
TBD |  | 38.521-5 | <Clause> | <Title of modified existing test case> | <Describe required change of the existing test case> |  | TBD |  |  | TBD
TBD | Y | 38.521-5 | <Clause> | <Title of new test case> | Test Purpose(s): <Describe test purpose(s)> |  | TBD |  |  | 1
TS 38.521-5: FR2-NTN RF Demodulation test cases
|  | 38.521-5 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
TBD |  | 38.521-5 | 11 | Demodulation performance requirements (Radiated requirements) | New sub-clause header |  | RAN5#109 (Nov-25) |  |  | 0
TBD |  | 38.521-5 | 11.1 | General | <Describe required change of the existing test case> |  | RAN5#109 (Nov-25) | R5-247153 |  | TBD
TBD |  | 38.521-5 | 11.2 | Demodulation performance requirements | <Describe required change of the existing test case> |  | RAN5#109 (Nov-25) |  |  | TBD
TBD |  | 38.521-5 | 11.2.1 | General | Applicability of requirements |  | RAN5#109 (Nov-25) | R5-247153 |  | TBD
TBD |  | 38.521-5 | 11.2.2 | PDSCH demodulation requirements |  |  | RAN5#109 (Nov-25) |  |  | TBD
TBD |  | 38.521-5 | 11.2.2.1 | 1Rx requirements |  |  | RAN5#109 (Nov-25) |  |  | TBD
TBD | Y | 38.521-5 | 11.2.2.1.1 | 1Rx FDD PDSCH Mapping Type A for FR2-NTN | Verify 1Rx PDSCH requirements | Qualcomm | RAN5#109 (Nov-25) |  |  | 1 | 0% | 0% |  |  |  | 0%
TBD |  | 38.521-5 | 11.2.3 | PDCCH demodulation requirements |  |  | RAN5#109 (Nov-25) |  |  | TBD
TBD |  | 38.521-5 | 11.2.3.1 | 1Rx requirements |  |  | RAN5#109 (Nov-25) |  |  | TBD
TBD | Y | 38.521-5 | 11.2.3.1.1 | 1Rx FDD PDCCH Mapping Type A for 1Tx antenna for FR2-NTN | Verify 1Rx PDCCH requirements for 1Tx antenna | Qualcomm | RAN5#109 (Nov-25) |  |  | 1 | 0% | 0% |  |  |  | 0%
TBD |  | 38.521-5 | Annex A | Measurement channels | RMC for NR NTN Enhancements |  | RAN5#109 (Nov-25) | R5-247153 |  | 0.2 | 75% | 75% |  |  |  | 75%
TBD |  | 38.521-5 | Annex B | Propagation conditions | New propagation models for NR NTN Enh |  | RAN5#109 (Nov-25) | R5-247153 |  | 0.2 | 75% | 75% |  |  |  | 75%
TBD |  | 38.521-5 | Annex C | Downlink physical channels | Connection setup parameters for NR NTN Enh |  | RAN5#109 (Nov-25) | R5-247153 |  | 0.2 | 75% | 75% |  |  |  | 75%
TS 38.522: Applicability for RF, Demod/CSI reporting and RRM test cases
TBD |  | 38.522 | <Clause> | <Title> | Add new ICS statements. |  | TBD |  |  | 0.1
TBD |  | 38.522 | <Clause> | <Title> | Add test case applicability statements for the new test cases introduced for 38.521-x and 38.533. |  | TBD |  |  | 0.1
TS 38.533: RRM test cases
|  | 38.533 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | 0
|  | 38.533 | 14 | NR standalone tests for Satellite access | [5 empty] | 0
|  | 38.533 | 14.0 | General | [5 empty] | 0
|  | 38.533 | 14.1 | RRC_IDLE state mobility | [5 empty] | 0
| Y | 38.533 | 14.1.11 | NR SA FR1 inter-RAT Cell reselection with NTN cCarrier for Satellite Access |  |  | RAN5#109 (Nov-25) |  |  | 1 | 0% | 0% |  |  | 0%
| Y | 38.533 | 14.1.12 | NR SA FR1-FR1 Cell re-selection with TN carrier for Satellite Access |  |  | RAN5#109 (Nov-25) |  |  | 1 | 0% | 0% |  |  | 0%
|  | 38.533 | 14.2 | RRC_CONNECTED state mobility | [5 empty] | 0
|  | 38.533 | 14.2.1 | Handover | [5 empty] | 0
| Y | 38.533 | 14.2.1.7 | NR SA FR2-NTN intra-satellite Handover for Satellite Access |  |  | RAN5#111 (May-26) |  | FR2-NTN VSAT testability is TBD | 1 | 0% | 0% |  |  |  | 0%
| Y | 38.533 | 14.2.1.8 | NR SA FR1 Handover for Satellite Access |  |  | RAN5#109 (Nov-25) |  |  | 1 | 0% | 0% |  |  | 0%
| Y | 38.533 | 14.2.1.9 | NR SA FR2-NTN inter-satellite Handover for Satellite Access |  |  | RAN5#111 (May-26) |  | FR2-NTN VSAT testability is TBD | 1 | 0% | 0% |  |  |  | 0%
|  | 38.533 | 14.2.2 | RRC Connection Mobility Control | [5 empty] | 0
| Y | 38.533 | 14.2.2.4 | NR SA FR1 RACH-based Hard Satellite switching with re-synchronization for Satellite Access |  | Qualcomm | RAN5#109 (Nov-25) | R5-251564 | Editor's Note: This test is incomplete in the following aspects: - MU and TT analysis is incomplete - Message contents need to be updated - Applicability needs to be updated - Test procedure needs to be updated - Annex E and F need to be updated - AT command configuration needs to be updated | 1 | 25% (+25%) | 25% (+25%) |  |  | 25%
| Y | 38.533 | 14.2.2.5 | NR SA FR1 RACH-less Soft Satellite switching with re-synchronization for Satellite Access |  | Qualcomm | RAN5#109 (Nov-25) | R5-251565 | Editor's Note: This test is incomplete in the following aspects: - MU and TT analysis is incomplete - Message contents need to be updated - Applicability needs to be updated - Test procedure needs to be updated - Annex E and F need to be updated - AT command configuration needs to be updated | 1 | 25% (+25%) | 25% (+25%) |  |  | 25%
| Y | 38.533 | 14.2.3 | NR SA FR1 Time-based conditional Handover without L3 measurement criteria for Satellite Access |  |  | RAN5#109 (Nov-25) |  |  | 1 | 0% | 0% |  |  | 0%
| Y | 38.533 | 14.2.4 | NR SA FR1-FR1 Time-based conditional Handover without L3 measurement criteria for Satellite Access |  |  | RAN5#109 (Nov-25) |  |  | 1 | 0% | 0% |  |  | 0%
|  | 38.533 | 14.3 | Timing for Satellite Access | [5 empty] | 0
|  | 38.533 | 14.3.1 | UE transmit timing for Satellite Access | [5 empty] | 0
| Y | 38.533 | 14.3.1.2 | NR SA FR2-NTN UE Transmit Timing accuracy for Satellite Access |  |  | RAN5#111 (May-26) |  | FR2-NTN VSAT testability is TBD | 1 | 0% | 0% |  |  |  | 0%
|  | 38.533 | 14.3.2 | UE transmit timing for Satellite Access | [5 empty] | 0
| Y | 38.533 | 14.3.2.3 | NR SA FR2-NTN Timing Advance adjustment accuracy for Satellite Access |  |  | RAN5#111 (May-26) |  | FR2-NTN VSAT testability is TBD | 1 | 0% | 0% |  |  |  | 0%
|  | 38.533 | 14.4 | Signalling Characteristics for Satellite Access | [5 empty] | 0
|  | 38.533 | 14.4.1 | Radio Link Monitoring for SAN | [5 empty] | 0
| Y | 38.533 | 14.4.1.9 | NR SA FR2-NTN Radio Link Monitoring Out-of-sync for PCell configured with SSB-based RLM RS in non-DRX mode for Satellite Access |  |  | RAN5#111 (May-26) |  | FR2-NTN VSAT testability is TBD | 1 | 0% | 0% |  |  |  | 0%
| Y | 38.533 | 14.4.1.10 | NR SA FR2-NTN Radio Link Monitoring In-sync for PCell configured with SSB-based RLM RS in non-DRX mode for Satellite Access |  |  | RAN5#111 (May-26) |  | FR2-NTN VSAT testability is TBD | 1 | 0% | 0% |  |  |  | 0%
|  | 38.533 | 14.5 | Measurement procedure | [5 empty] | 0
|  | 38.533 | 14.5.1 | Intra-frequency Measurements | [5 empty] | 0
| Y | 38.533 | 14.5.1.7 | NR SA FR2-NTN event-triggered reporting with SSB time index reading without gap under non-DRX for Satellite Access |  |  | RAN5#111 (May-26) |  | FR2-NTN VSAT testability is TBD | 1 | 0% | 0% |  |  |  | 0%
|  | 38.533 | 14.5.3 | L1-RSRP measurement for beam reporting for SAN | [5 empty] | 0
| Y | 38.533 | 14.5.3.5 | NR SA FR2 SSB based L1-RSRP measurement when DRX is not used for Satellite Access |  |  | RAN5#111 (May-26) |  | FR2-NTN VSAT testability is TBD | 1 | 0% | 0% |  |  |  | 0%
|  | 38.533 | 14.6 | Measurement Performance requirements | [5 empty] | 0
|  | 38.533 | 14.6.1 | SS-RSRP for SAN | [5 empty] | 0
| Y | 38.533 | 14.6.1.3 | NR SA FR2-NTN SS-RSRP measurement accuracy for Satellite Access |  |  | RAN5#111 (May-26) |  | FR2-NTN VSAT testability is TBD | 1 | 0% | 0% |  |  |  | 0%
|  | 38.533 | 14.6.4 | L1-RSRP measurement for beam reporting | [5 empty] | 0
| Y | 38.533 | 14.6.4.3 | NR SA FR2-NTN SSB based L1-RSRP measurement for VSAT UE when DRX is not used for Satellite Access |  |  | RAN5#111 (May-26) |  | FR2-NTN VSAT testability is TBD | 1 | 0% | 0% |  |  |  | 0%
|  | 38.533 | Annex A | RRM test configurations; Satellite access configuration | [5 empty] | 0.5 | 0% | 0% |  |  | 0%
|  | 38.533 | Annex B | Conditions for RRM requirements applicability for operating bands; Satellite access, High level test procedure for SAN RRM tests | [5 empty] | 0.5 | 0% | 0% |  |  | 0%
|  | 38.533 | Annex E | Cell configuration mapping | [5 empty] | 1 | 0% | 0% |  |  | 0%
|  | 38.533 | Annex F | Measurement uncertainties and test tolerances | [5 empty] | 1 | 0% | 0% |  |  | 0%
TR 38.903: Test Tolerances analysis RRM and RF Rx test cases
|  | 38.903 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
TBD |  | 38.903 | <Clause> | <Title of new sub-clause header> | New sub-clause header |  | TBD |  |  | 0
TBD |  | 38.903 | <Clause> | <Title of task> | <Describe task> |  | TBD |  |  | TBD
TR 38.905: Test Point analysis receiver and transmitter test cases
|  | 38.905 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
TBD |  | 38.905 | <Clause> | <Title of new sub-clause header> | New sub-clause header | All contributing companies | RAN5#109 (Nov-25) | R5-250755 |  | 1 | 10% (+10%) | 10% (+10%) |  |  | 10%
TBD |  | 38.905 | <Clause> | <Title of task> | <Describe task> |  | TBD |  |  | TBD
RAN and CN protocol
TS 38.523-1: Protocol test cases
|  | 38.523-1 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
Idle Mode
TBD | Y | 38.523-1 | 6.7.1.7 | NR NTN Enhancementsancements / Cell reselection, Sintrasearch, Snonintrasearch / location based measurementsl | Test Purpose(s): <Describe test purpose(s)> | Qualcomm | TBD | R5-251299 | 38.304 5.2.4.2 (For Inter and Intra) | 1 | 80% (+80%) | 80% (+80%) |  |  | 80%
TBD | Y | 38.523-1 | 6.7.1.8 | NR NTN Enhancementsancements / Cell reselection, Sintrasearch, Snonintrasearch / location based measurements / Earth Moving Cell with Cell Ranking | Test Purpose(s): <Describe test purpose(s)> | Qualcomm | TBD |  | 38.304 5.2.4.2 (For Inter and Intra) | 1 | 0% | 0% |  |  | 0%
TBD | Y | 38.523-1 | 6.7.1.9 | NR NTN Enhancementsancements / Cell Selection / NTN Serving cell becomes non-suitable | Test Purpose(s): <Describe test purpose(s)> | Qualcomm | TBD |  | 38.304 5.3.1 (cellBarredFixedVSAT, cellBarredMobileVSAT) | 1 | 0% | 0% |  |  | 0%
TBD | Y | 38.523-1 | 6.7.2.16 | NR NTN Enhancementsancements / Cell reselection/ Reselection with Coverage Enhancement | Test Purpose(s): <Describe test purpose(s)> | Qualcomm | TBD |  | SIB19 with new IE | 1 | 0% | 0% |  |  | 0%
TBD | Y | 38.523-1 | 6.7.2.18 | NR NTN Enhancementsancements / inter and intra frequency cell re-selections | Test Purpose(s): <Describe test purpose(s)> | Qualcomm | TBD |  | SIB1,4,5 | 1 |  |  |  |  | 0%
MAC
TBD | Y | 38.523-1 | 7.1.1.1.31 | NR NTN Enhancementsancements / Random access procedure / Coverage Enhancement | Test Purpose(s): <Describe test purpose(s)> | Qualcomm | TBD | R5-251323 | LCID extension for CCCH/CCCH1 [LCID-extension], Msg4 ACK can be transmitted Multiple Times | 1 | 100% (+100%) | 100% (+100%) |  |  | 100%
TBD | Y | 38.523-1 | 7.1.1.10.x | NR NTN Enhancements/ Maintenance of UL Sync/ UE specific Koffset and NTA | Test Purpose(s): <Describe test purpose(s)> |  | TBD |  | Maintenance of UL Sync 38.331 5.2a | 1 | 0% | 0% |  |  | 0%
TBD | Y | 38.523-1 | 7.1.1.x.y | NR NTN Enhancements/ RACHLESS Handover | Test Purpose(s): <Describe test purpose(s)> |  | TBD |  | RACHLESS HO | 1 | 0% | 0% |  |  | 0%
RRC
TBD | Y | 38.523-1 | 8.1.3.1.27 | NR NTN Enhancements / Measurement configuration control and reporting / Event D2 | Test Purpose(s): <Describe test purpose(s)> | Qualcomm | TBD | R5-251300 | 38.331 5.5.4.15a Event D2 (Distance between UE and the serving cell moving reference location is above threshold1 and distance between UE and a moving reference location is below threshold2) 5.5.4 Measurement report triggering | 1 | 80% (+80%) | 80% (+80%) |  |  | 80%
TBD |  | 38.523-1 | 8.1.4.4 | Conditional handover | Existing sub-clause header |  | TBD |  |  | TBD
TBD | Y | 38.523-1 | 8.1.4.4.x | NR NTN Enhancements / Conditional handover / Success / CondEventD2 | Test Purpose(s): <Describe test purpose(s)> | Qualcomm | TBD |  | 5.5.4 Measurement report triggering | 1 | 0% | 0% |  |  | 0%
TBD | Y | 38.523-1 | <Clause> | <Title of new test case> | Test Purpose(s): <Describe test purpose(s)> |  | TBD |  |  | 1 | 0% | 0% |  |  | 0%
TBD | Y | 38.523-1 | <Clause> | <Title of new test case> | Test Purpose(s): <Describe test purpose(s)> |  | TBD |  |  | 1 | 0% | 0% |  |  | 0%
TBD |  | 38.523-1 | 8.1.5 | RRC others | Existing sub-clause header |  | TBD |  |  | 1
TBD | Y | 38.523-1 | 8.1.5.1.x | UE capability transfer | Test Purpose(s): <Describe test purpose(s)> |  | TBD |  | FFS | 1 | 0% | 0% |  |  | 0%
TBD |  | 38.523-1 | 8.1.5.14 | NTN Other RRC Topics | Test Purpose(s): <Describe test purpose(s)> |  | TBD |  |  | 1
TBD | Y | 38.523-1 | 8.1.5.14.x | NR NTN Enhancements / SIB19 / Sateliite Hard Switch with Resync | Test Purpose(s): <Describe test purpose(s)> |  | TBD |  | 38.331 5.7.19 Satellite switch with resynchronization T430 Timer Expiry | [5 empty] | 0%
TBD | Y | 38.523-1 | 8.1.5.14.x | NR NTN Enhancements / SIB19 / Sateliite Soft Switch with Resync | Test Purpose(s): <Describe test purpose(s)> |  | TBD |  | 38.331 5.7.19 Satellite switch with resynchronization T430 Timer Expiry | 1 | 0% | 0% |  |  | 0%
NAS
TBD |  | 38.523-1 | 9.4 | Non-Terrestrial Network | Existing sub-clause header |  | TBD |  | 23.122 Have to check against NR-NTN R-17 "CP-223157 - Common requirements on satellite access technologies" CP-230209 - Emergency service and limited service state for satellite access | 0
TBD |  | 38.523-1 | 9.4.1 | 5GS mobility management for Non-Terrestrial Network | Existing sub-clause header |  | TBD |  |  | TBD
TBD | Y | 38.523-1 | 9.4.1.x | NR NTN Enhancements / Disabling and re-enabling of UE's satellite NG-RAN capability | Test Purpose(s): <Describe test purpose(s)> |  | TBD |  | 24.501 4.9.4 Disabling and re-enabling of UE's satellite NG-RAN capability Disable of the satellite NG-RAN capability shall only be performed when the UE is in 5GMM-IDLE mode. When disabling the satellite NG-RAN capability, the UE: a) may disable the NR NTN access capability (see 3GPP TS 38.304 [28] and 3GPP TS 38.306 [28A]); b) shall memorize the identity of the PLMN where the satellite NG-RAN capability was disabled; and c) shall use that stored information in subsequent PLMN selections as specified in 3GPP TS 23.122 [6]. NOTE: As an implementation option, the UE can disable satellite NG-RAN capability by disabling N1 mode capability for satellite NG-RAN access. As an implementation option, the UE may start a timer for enabling satellite NG-RAN capability and on expiry of this timer UE shall remove the PLMN from the memorized identity of the PLMNs where the satellite NG-RAN capability | 1 | 0% | 0% |  |  | 0%
TBD | Y | 38.523-1 | 9.4.1.x | NR NTN Enhancements / Support for Unavailbility Period | Test Purpose(s): <Describe test purpose(s)> |  | TBD |  | 24.501 5.3.26 Support for unavailability period Multiple Shall requirement | 1 | 0% | 0% |  |  | 0%
TBD | Y | 38.523-1 | 9.4.1.x | NR NTN Enhancements / Discontinuous coverage Update | Test Purpose(s): <Describe test purpose(s)> |  | TBD |  | 24.501 5.4.4.3 If the UE receives, the Discontinuous coverage maximum time offset IE in the CONFIGURATION UPDATE COMMAND message, the UE shall replace any previously received discontinuous coverage maximum time offset value on the same satellite NG-RAN RAT type and PLMN with the latest received timer value. 24.501 5.5.1.3.4 Mobility and periodic registration update accepted by the network If the UE receives, the Discontinuous coverage maximum time offset IE in the REGISTRATION ACCEPT message, the UE shall replace any previously received maximum time offset value on the same satellite NG-RAN RAT type and PLMN with the latest received timer value. | 1 | 0% | 0% |  |  | 0%
TBD | Y | 38.523-1 | 9.4.1.x | NR NTN Enhancements / GNSS position reporting / reject cause #78 | Test Purpose(s): <Describe test purpose(s)> |  | TBD |  | 24.501 5.4.5.3.3 Network-initiated NAS transport of messages accepted by the UE Check additional Requirement for Cause code #78 23.122 NR NTN / GNSS position reporting / reject cause #78 Updates for R.18, Now includes NTN E-UTRA scenario | 1 | 0% | 0% |  |  | 0%
TBD | Y | 38.523-1 | 9.4.1.x | NR NTN Enhancements / Initial registration initiation for Netowrk Verified UE location Satellite NG-RAN | Test Purpose(s): <Describe test purpose(s)> |  | TBD |  | 24.501 5.5.1.2.2 Initial registration initiation If the UE supports network verified UE location over satellite NG-RAN as specified in 3GPP TS 23.501 [8], the UE shall set the NVL-SATNR bit to "Network verified UE location over satellite NG-RAN supported" in the 5GMM capability IE of the REGISTRATION REQUEST message. 23.501 5.4.11.4 Verification of UE location | 1 | 0% | 0% |  |  | 0%
TBD | Y | 38.523-1 | 9.4.1.x | NR NTN Enhancements/ Mobility registration update | Test Purpose(s): <Describe test purpose(s)> |  | TBD |  | 24.501 5.5.1.3.2 Mobility and periodic registration update initiation For case zm1, if the network indicated support for the unavailability period in the last registration procedure, the UE shall include the Unavailability information IE in the REGISTRATION REQUEST message. If the UE did not include a start of the unavailability period in the Unavailability information IE, the UE shall set the Follow-on request indicator to "No follow-on request pending" in the REGISTRATION REQUEST message and shall not include the Uplink data status IE or the Allowed PDU session status IE in the REGISTRATION REQUEST message even if the UE has one or more active always-on PDU sessions associated with the 3GPP access. If the UE includes the Unavailability information IE to indicate the type of the unavailability and the UE will be unavailable due to NR satellite access discontinuous coverage, the UE shall set the Unavailability type bit to "unavailability due to discontinuous coverage" in the Unavailability information IE. | 1 | 0% | 0% |  |  | 0%
TBD | Y | 38.523-1 | 9.4.1.x | NR NTN Enhancements / 5GMM cause code #15 indicating Satellite NG-RAN not allowed in PLMN | Test Purpose(s): <Describe test purpose(s)> |  | TBD |  | 24.501 5.5.1.3.5 Mobility and periodic registration update not accepted by the network #15 (No suitable cells in tracking area). The UE shall set the 5GS update status to 5U3 ROAMING NOT ALLOWED (and shall store it according to subclause 5.1.3.2.2). The UE shall reset the registration attempt counter. Additionally, the UE shall enter the state 5GMM-REGISTERED.LIMITED-SERVICE and: 1) if the Extended 5GMM cause IE with value "Satellite NG-RAN not allowed in PLMN" is included in the REGISTRATION REJECT message, i) the message has been successfully integrity checked by the NAS and the UE is configured for "Satellite Disabling Allowed for 5GMM cause #15" as specified in 3GPP TS 24.368 [17] or 3GPP TS 31.102 [22], then the UE shall disable satellite NG-RAN capability (see subclause 4.9.4); or ii) otherwise, the UE shall ignore the Extended 5GMM cause IE; and | 1 | 0% | 0% |  |  | 0%
TBD | Y | 38.523-1 | 9.4.1.x | NR NTN Enhancements / UE-initiated de-registration procedure | Test Purpose(s): <Describe test purpose(s)> |  | TBD |  | 24.501 5.5.2.2.1 UE-initiated de-registration procedure initiation If the network indicated support for the unavailability period in the last registration procedure; and an event is triggered in the UE that would make the UE unavailable for a certain period, the use of unavailability period is not due to NR satellite access discontinuous coverage and the UE is unable to store its 5GMM and 5GSM contexts, the UE shall include the unavailability period duration in the Unavailability information IE, set the Unavailability type to "unavailability due to UE reasons" and set the De-registration type to "Normal de-registration" in the DEREGISTRATION REQUEST message. The UE shall start the timer T3521 and enter the state 5GMM-DEREGISTERED-INITIATED. | 1 | 0% | 0% |  |  | 0%
TBD | Y | 38.523-1 | 9.4.1.x | NR NTN Enhancements/ TBD | Test Purpose(s): <Describe test purpose(s)> |  | TBD |  | 9.11.3 5GS mobility management (5GMM) information elements | 1
TBD | Y | 38.523-1 | 9.4.1.x | NR NTN Enhancements/ TBD | Test Purpose(s): <Describe test purpose(s)> |  | TBD |  | 9.11.3.109 Extended 5GMM cause | 1
TS 38.523-2: Applicability for Protocol test cases
TBD |  | 38.523-2 | <Clause> | <Title> | Add new ICS statements. |  | TBD |  |  | 0.1
TBD |  | 38.523-2 | <Clause> | <Title> | Add test case applicability statements for the new test cases introduced in 38.523-1 | Qualcomm | TBD | R5-251366 |  | 0.1 | 20% (+20%) | 20% (+20%) |  |  | 20%
TS 38.523-3: Protocol test suites (TTCN)
|  | 38.523-3 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
TBD |  | 38.523-3 | <Clause> | <Title of task> | <Describe task> |  | TBD |  |  | TBD
End of workplan items. Note! Do not remove this row. Introduce new work plan rows/items above this row.
Note on A6: Unique ID for WP items (unique within the sub-area work plan) Note! As WP item numbers may be referenced from outside of this WP that means: - Do not change number for WP items that have been published. - Do not re-use WP item numbers if a WP item is deleted
Note on B6: Set to Y if the WP item represents a new test case that will be specified in RAN5 test specifications as an executable test case else leave blank.
Note on K6: The WP item's weight number is used to set the reletive weights between WP items used in the overall calculation of completeness. Setting it to 0 for a WP item means that it will not be included at all in the calculation.