## Cover sheet
3GPP TSG-RAN WG5 Meeting #106 | [10 empty] | R5-250150
Athens, Greece, Feb 17th - Feb 21st, 2025
Agenda Item: | 7.5.2
Source: | CMCC, Xiaomi
Title: | UE Conformance - In-Device Co-existence (IDC) enhancements for NR and MR-DC
Work item code: | NR_IDC_enh-UEConTest
Release: | Rel-18
Document for: | Information
RAN5 WP template v2.0-7
1. Introduction
This work item covers the protocol conformance testing for Rel-18 enhancement of in-Device Co-existence (IDC) for NR and MR-DC (EN-DC, NE-DC, NR-DC)
2. Work item status
Estimation of WI overall completion:
Area |  | Completion | Number of new completed test cases (Note 1) | Number of new test cases | Comments
Overall completion |  | 39% (+21%) | 2 (+2) | 5
Completion Compensation |  | -
| Note 1: | Only test cases completed for all applicable WP areas and sub-areas are counted. For completed test cases per WP areas and WP sub-areas see below.
Estimation WI completion per area and sub-area:
|  | Completion | Number of new completed test cases | Number of new test cases | Comments
Option 2 (SA NR) |  | 39% (+15%) | 2 (+2) | 5 (+2)
FR1 |  | 39% (+15%) | 2 (+2) | 5 (+2)
FR2 |  | 39% (+15%) | 2 (+2) | 5 (+2)
FR1 + FR2
Option 3 (EN-DC)
FR1
FR2
Estimation of completion per TS (area):
|  | TS/TR overall completion |  |  | Option 2 (SA NR) | [8 empty] | Option 3 (EN-DC)
TS/TR Scope | TS/TR | Completion | Number of new completed test cases | Number of new test cases | FR1 |  |  | FR2 | [5 empty] | FR1 |  |  | FR2
[5 empty] | Completion | Number of new completed test cases | Number of new test cases | Completion | Number of new completed test cases | Number of new test cases | Completion | Number of new completed test cases | Number of new test cases | Completion | Number of new completed test cases | Number of new test cases | Completion | Number of new completed test cases | Number of new test cases
5GS
5GS Common
Common test environment | 38.508-1 | 0% |  |  | 0% |  |  | 0%
Common ICS | 38.508-2 | 30% (+10%) |  |  | 30% (+10%) |  |  | 30% (+10%)
UE specific test functions | 38.509
5GS RAN and CN protocols
Protocol test cases | 38.523-1 | 40% (+21.9%) | 2 (+2) | 5 | 40% (+16.7%) | 2 (+2) | 5 (+2) | 40% (+16.7%) | 2 (+2) | 5 (+2)
Applicability Protocol test cases | 38.523-2 | 30% (+10%) |  |  | 30% (+10%) |  |  | 30% (+10%)
Test suites (TTCN) | 38.523-3
5 References
[1] RP-241195 | New WID on UE Conformance - In-Device Co-existence (IDC) enhancements for NR and MR-DC
Note on B21: Overall completion of the work item reported at an earlier meeting will not be decreased if additional tasks are added or if corrections are made to the work plan. Instead the earlier reported completion status will be kept until necessary progress have been achieved such that completion exceeds the earlier reported completion level. The value of the Completion Compensation value represents the difference in the decrease caused by late additions or corrections to the work plan and the current estimated overall completion. '-' indicates that no compensation is applied.

## WP
WP Title: |  | UE Conformance - In-Device Co-existence (IDC) enhancements for NR and MR-DC | [11 empty] | Start of workplan status columns. Note! Do not remove this column. | WP item status |  |  |  |  | End of workplan columns. Note! Do not remove this column.
WI code |  | NR_IDC_enh-UEConTest
WP Scope: |  | UE Conformance Test Aspects for Rel-18 enhancement of in-Device Co-existence (IDC) in NR and MR-DC (UID-1040104) | [13 empty] | vs Area
WP Resp: |  | Danni Song, CMCC; Yumin Wu, Xiaomi |  |  | songdan@chinamobile.com, wuyumin@xiaomi.com | [5 empty] | WP item completion |  |  |  | Option 2 (SA NR) |  |  | Option 3 (EN-DC)
TS Resp: |  | n/a |  |  | n/a
WP Item ID | Is new test case? | TS/area | Clause | Title | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | Overall | Option 2 (SA NR) | Option 3 (EN-DC) |  | FR1 | FR2 | FR1 + FR2 | FR1 | FR2
[15 empty] | 39% (+15%) | 39% (+15%)
[15 empty] | 9 (+2) | 9 (+2) | 0 | 0 (-2) | 0 (-2)
[15 empty] | 6 (+2) | 6 (+2) | 0 | 0 (-2) | 0 (-2)
5%
Start of work plan items. Note! Do not remove this row. Introduce new work plan rows/items below this row.
5GS
5GS Common
TS 38.508-1: Common test environment
|  | 38.508-1 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | 0
1 |  | 38.508-1 | 4.6 | RRC default messages | Add Rel-18 IDC changes to default messages if needed | CMCC | RAN5#108 (Aug-26) |  |  | 0.5 | 0% | 0% |  |  | 0% | 0%
TS 38.508-2: Common ICS
|  | 38.508-2 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | 0
2 |  | 38.508-2 | A.4 | Additional information | Add ICS as needed for the test case applicability statements for the new test cases introduced in protocol test cases. | CMCC | RAN5#108 (Aug-26) | R5-246703, R5-250155 |  | 0.3 | 30% (+10%) | 30% (+10%) |  |  | 30% | 30%
RAN and CN protocol
TS 38.523-1: Protocol test cases
Connected mode
3 |  | 38.523-1 | 8.1.5.10 | UE Assistance Information | [5 empty] | 0
4 | Y | 38.523-1 | 8.1.5.10.9 | UE Assistance Information / IDC / FDM assistance configuration | ****TP1: [TS 38.331: 5.7.4.2]**** WITH: UE in NR RRC_CONNECTED state WHEN: UE configured to provide IDC assistance information based on idc-FDM-AssistanceConfig and UE did not transmit a UEAssistanceInformation message with idc-FDM-Assistance and UE is experiencing IDC problems that it cannot solve by itself THEN: The UE transmits a UEAssistanceInformation message to provide IDC assistance information ****TP2: [TS 38,331: 5.7.4.2]**** WITH: UE in NR RRC_CONNECTED state and UE already transmits a UEAssistanceInformation message with idc-FDM-Assistance WHEN: UE configured to provide IDC assistance information based on idc-FDM-AssistanceConfig and the current idc-FDM-Assistance information for the cell group is different from the one indicated in the last transmission of the UEAssistanceInformation message and UE is experiencing IDC problems that it cannot solve by itself THEN: The UE transmits a UEAssistanceInformation message to provide IDC assistance information | CMCC | RAN5#108 (Aug-26) | R5-247619, R5-251320 |  | 1 | 100% (+30%) | 100% (+30%) |  |  | 100% | 100%
5 | Y | 38.523-1 | 8.1.5.10.10 | UE Assistance Information / IDC / TDM assistance configuration | ****TP1: [TS 38.331: 5.7.4.2]**** WITH: UE in NR RRC_CONNECTED state WHEN: UE configured to provide IDC assistance information based on idc-TDM-AssistanceConfig and UE did not transmit a UEAssistanceInformation message with idc-TDM-Assistance and UE is experiencing IDC problems that it cannot solve by itself THEN: The UE transmits a UEAssistanceInformation message to provide IDC assistance information ****TP2: [TS 38,331: 5.7.4.2]**** WITH: UE in NR RRC_CONNECTED state and UE already transmits a UEAssistanceInformation message with idc-TDM-Assistance WHEN: UE configured to provide IDC assistance information based on idc-TDM-AssistanceConfig and the current idc-TDM-Assistance information for the cell group is different from the one indicated in the last transmission of the UEAssistanceInformation message and UE is experiencing IDC problems that it cannot solve by itself THEN: The UE transmits a UEAssistanceInformation message to provide IDC assistance information | CMCC | RAN5#108 (Aug-26) | R5-251321 |  | 1 | 100% (+100%) | 100% (+100%) |  |  | 100% | 100%
7 |  | 38.523-1 | 8.1.2 | RRC reconfiguration | [5 empty] | 0
8 | Y | 38.523-1 | 8.1.2.1.7 | RRC reconfiguration / UL slot autonomous Denial | ****TP1: [TS 38.331: 5.3.5.5.1]**** WITH: UE in NR RRC_CONNECTED state WHEN: UE configured with autonomousDenialParameters THEN: The total denied UL slots of the UE fewer than the autonomousDenialSlots within the same cell group |  | RAN5#108 (Aug-26) |  |  | 1 | 0% | 0% |  |  | 0% | 0%
NR-DC
9 |  | 38.523-1 | 8.2.6.5 | UE Assistance Information | [5 empty] | 0
10 | Y | 38.523-1 | 8.2.6.5.1 | UE Assistance Information / IDC / FDM assistance configuration / NR-DC | ****TP1: [TS 38.331: 5.7.4.2]**** WITH: UE in NR RRC_CONNECTED state WHEN: UE configured to provide IDC assistance information based on idc-FDM-AssistanceConfig and UE did not transmit a UEAssistanceInformation message with idc-FDM-Assistance and UE is experiencing IDC problems that it cannot solve by itself THEN: The UE transmits a UEAssistanceInformation message to provide IDC assistance information |  | RAN5#108 (Aug-26) |  |  | 1 | 0% | 0% |  |  | 0% | 0%
11 | Y | 38.523-1 | 8.2.6.5.2 | UE Assistance Information / IDC / TDM assistance configuration / NR-DC | ****TP1: [TS 38.331: 5.7.4.2]**** WITH: UE in NR RRC_CONNECTED state WHEN: UE configured to provide IDC assistance information based on idc-TDM-AssistanceConfig and UE did not transmit a UEAssistanceInformation message with idc-TDM-Assistance and UE is experiencing IDC problems that it cannot solve by itself THEN: The UE transmits a UEAssistanceInformation message to provide IDC assistance information |  | RAN5#108 (Aug-26) |  |  | 1 | 0% | 0% |  |  | 0% | 0%
TS 38.523-2: Applicability for Protocol test cases
19 |  | 38.523-2 | 4.1 | Protocol conformance test cases applicability | Add test case applicability statements for the new test cases introduced in 38.523-1 | CMCC | RAN5#108 (Aug-26) | R5-247662, R5-251322 |  | 0.1 | 30% (+10%) | 30% (+10%) |  |  | 30% | 30%
20 |  | 38.523-2 | 4.2 | Protocol conformance test cases Applicability Condition | Add Applicability Condition for new test cases | CMCC | RAN5#108 (Aug-26) | R5-247662, R5-251322 |  | 0.1 | 30% (+10%) | 30% (+10%) |  |  | 30% | 30%
TS 38.523-3: Protocol test suites (TTCN)
|  | 38.523-3 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
21 |  | 38.523-3 | <Clause> | <Title of task> | <Describe task> |  | TBD |  |  | TBD
End of workplan items. Note! Do not remove this row. Introduce new work plan rows/items above this row.
Note on A6: Unique ID for WP items (unique within the sub-area work plan) Note! As WP item numbers may be referenced from outside of this WP that means: - Do not change number for WP items that have been published. - Do not re-use WP item numbers if a WP item is deleted
Note on B6: Set to Y if the WP item represents a new test case that will be specified in RAN5 test specifications as an executable test case else leave blank.
Note on K6: The WP item's weight number is used to set the reletive weights between WP items used in the overall calculation of completeness. Setting it to 0 for a WP item means that it will not be included at all in the calculation.