## Cover sheet
3GPP TSG-RAN WG5 meeting#106 | [8 empty] | R5-250425
Athens, Greece, Feb 17-21, 2025
Agenda Item: | 7.5.2
Source: | Huawei, HiSilicon, Ericsson
Title: | UE Conformance - Rel-17 NR CA and DC; and NR and LTE DC Configurations
Work item code: | NR_CADC_NR_LTE_DC_R17-UEConTest
Release: | Rel-17
Document for: | Information
RAN5 WP template v2.0-7
1. Introduction
At the RAN#90 meeting in December 2020 the Rel-17 RAN5 work item for UE Conformance Test Aspects of Rel-17 NR CA and DC; and NR and LTE DC Configurations was approved [1]. The purpose of present document is to provide a work plan for the RAN5 work item introducing the Rel-16 NR CA and DC; and NR and LTE DC Configurations into RAN5 test specifications. The work plan is updated after each RAN5 meeting to give the status of the work item. Section 2 gives an overview of the work item status. Note: This work plan is limited to the addition of new and update of existing NR CA, NR-DC and EN-DC test cases for the new types of configurations introduced by this basket work item. Tracking of status, interested operator and responsible companies for configurations can be found in the RAN5 Permanent Reference Document [2] PRD21. Introducing new Rel-16 NR CA, NR-DC and EN-DC shall be in accordance to the guidelines in [2] PRD21.
2. Work item status
Estimation of WI overall completion:
Area |  | Completion | Number of new completed test cases (Note 1) | Number of new test cases | Comments
Overall completion |  | 11% | 3 | 49
Completion Compensation |  | -
| Note 1: | Only test cases completed for all applicable WP areas and sub-areas are counted. For completed test cases per WP areas and WP sub-areas see below.
Estimation WI completion per area and sub-area:
|  | Completion | Number of new completed test cases | Number of new test cases | Comments
SA Option 2 (SA NR) (FR1) |  | 10.8% | 3 | 49
FR1 |  | 10.8% | 3 | 49
NSA Option 3 (EN-DC)
FR1
FR2
Estimation of completion per TS (area):
|  | TS/TR overall completion |  |  | SA Option 2 (SA NR) |  |  |  |  | NSA Option 3 (EN-DC)
TS/TR Scope | TS/TR | Completion | Number of new completed test cases | Number of new test cases | FR1 |  |  |  |  | FR1 |  |  | FR2
[5 empty] | Completion | Number of new completed test cases | Number of new test cases |  |  | Completion | Number of new completed test cases | Number of new test cases | Completion | Number of new completed test cases | Number of new test cases
Rel-16 New CADC test cases
TS 38.521-1
Common (Section 5) | 38.521-1: Common
NR CA FR1 Tx test cases | 38.521-1: NR CA Tx | 0% | 0 | 22 | 0% | 0 | 22
NR CA FR1 Rx test cases | 38.521-1: NR CA Rx | 11.1% | 3 | 27 | 11.1% | 3 | 27
TS 38.521-2
Common (Section 5) | 38.521-2: Common
NR CA FR2 Tx test cases | 38.521-2: NR CA Tx
NR CA FR2 Rx test cases | 38.521-2: NR CA Rx
TS 38.521-3
Common (Section 5) | 38.521-3: Common
EN-DC FR1 tx test cases | 38.521-3: EN-DC FR1 Tx
EN-DC FR2 tx test cases | 38.521-3: EN-DC FR2 Tx
EN-DC FR1 Rx test cases | 38.521-3: EN-DC FR1 Rx
EN-DC FR2 Rx test cases | 38.521-3: EN-DC FR2 Rx
5 References
[1] RP-231237 | Revised WID on UE Conformance - Rel-17 NR CA and DC; and NR and LTE DC Configurations
[2] RAN5 PRD21 | NR bands and 5G NR CADC configuration handling in RAN5 (Release 15 and later releases)
Download PRD21 from here: ftp://ftp.3gpp.org/TSG_RAN/WG5_Test_ex-T1/PRD/
Note on B21: Overall completion of the work item reported at an earlier meeting will not be decreased if additional tasks are added or if corrections are made to the work plan. Instead the earlier reported completion status will be kept until necessary progress have been achieved such that completion exceeds the earlier reported completion level. The value of the Completion Compensation value represents the difference in the decrease caused by late additions or corrections to the work plan and the current estimated overall completion. '-' indicates that no compensation is applied.

## WP
WP Title: |  | Work plan UE Conformance - Rel-17 NR CA and DC; and NR and LTE DC Configurations | [11 empty] | Start of workplan status columns. Note! Do not remove this column. | WP item status |  |  | End of workplan columns. Note! Do not remove this column.
WI code |  | NR_CADC_NR_LTE_DC_R17-UEConTest
WP Scope: |  | This work plan covers the tasks needed to include Rel-17 NR band, NR CA-, NR DC- and EN-DC-configurations in to TS 38.508-1, TS 38.508-2. TS 38.521-1, TS 38.521-2, TS 38.521-3, TS 38.533, TR 38.903 and TR 39.905. NOTE! The company listed in column "Company" is responsible to secure that required information for the EN-DC/NR CA/DC configuration is complete in the TSs and TRs as listed in status columns.
WP Resp: |  | Yuxin Hao (Huawei,Hisilicon), Niclas Weiler (Ericsson) |  |  | haoyuxin <haoyuxin@huawei.com>@huawei.com, Niclas Weiler <niclas.weiler@ericsson.com> | [5 empty] | WP item completion |  |  |  | SA Option 2 (SA NR) | NSA Option 3 (EN-DC)
TS Resp: |  | N/A |  |  | N/A
WP Item ID | Is new test case? | TS/area | Clause | Title | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | Overall | SA Option 2 (SA NR) | NSA Option 3 (EN-DC) |  | FR1 | FR1 | FR2
10.8%
[15 empty] | 49 | 0 | 0
[15 empty] | 49 | 0 | 0
5%
Start of work plan items. Note! Do not remove this row. Introduce new work plan rows/items below this row.
Rel-17 New CADC test cases
TS 38.521-1: NR CA FR1
TS 38.521-1: NR CA Transmitter Characterstics (Section 6)
1 | Y | 38.521-1: NR CA Tx | 6.2A.1.2 | UE maximum output power for CA (3UL CA) | 3UL CA test case to handle UL CA configurations nxA-nyB or nxB-nyA *Needs to first study whether this specific test cases is needed. *The test case could be added only when at least one relevant configuration is 'ongoing' in PRD21 |  |  | TS 38.521-1: TR 38.905: TS 38.522: |  | 1 | 0% | 0% |  |  | 0%
2 | Y | 38.521-1: NR CA Tx | 6.2A.2.2 | UE maximum output power reduction for CA (3UL CA) | 3UL CA test case to handle UL CA configurations nxA-nyB or nxB-nyA *Needs to first study whether this specific test cases is needed. *The test case could be added only when at least one relevant configuration is 'ongoing' in PRD21 |  |  | TS 38.521-1: TR 38.905: TS 38.522: |  | 1 | 0% | 0% |  |  | 0%
3 | Y | 38.521-1: NR CA Tx | 6.2A.3.2 | UE additional maximum output power reduction for CA (3UL CA) | 3UL CA test case to handle UL CA configurations nxA-nyB or nxB-nyA *Needs to first study whether this specific test cases is needed. *The test case could be added only when at least one relevant configuration is 'ongoing' in PRD21 |  |  | TS 38.521-1: TR 38.905: TS 38.522: |  | 1 | 0% | 0% |  |  | 0%
4 | Y | 38.521-1: NR CA Tx | 6.2A.4.1 | Configured transmitted power for CA (3UL CA) | 3UL CA test case to handle UL CA configurations nxA-nyB or nxB-nyA *Needs to first study whether this specific test cases is needed. *The test case could be added only when at least one relevant configuration is 'ongoing' in PRD21 |  |  | TS 38.521-1: TR 38.905: TS 38.522: |  | 1 | 0% | 0% |  |  | 0%
5 | Y | 38.521-1: NR CA Tx | 6.3A.1.2 | Minimum output power for CA (3UL CA) | 3UL CA test case to handle UL CA configurations nxA-nyB or nxB-nyA *Needs to first study whether this specific test cases is needed. *The test case could be added only when at least one relevant configuration is 'ongoing' in PRD21 | KTL |  | TS 38.521-1: TR 38.905: TS 38.522: |  | 1 | 0% | 0% |  |  | 0%
6 | Y | 38.521-1: NR CA Tx | 6.3A.2.2 | Transmit OFF power for CA (3UL CA) | 3UL CA test case to handle UL CA configurations nxA-nyB or nxB-nyA *Needs to first study whether this specific test cases is needed. *The test case could be added only when at least one relevant configuration is 'ongoing' in PRD21 | KTL |  | TS 38.521-1: TR 38.905: TS 38.522: |  | 1 | 0% | 0% |  |  | 0%
7 | Y | 38.521-1: NR CA Tx | 6.3A.3.2 | Transmit ON/OFF time mask for CA (3UL CA) | 3UL CA test case to handle UL CA configurations nxA-nyB or nxB-nyA *Needs to first study whether this specific test cases is needed. *The test case could be added only when at least one relevant configuration is 'ongoing' in PRD21 |  |  | TS 38.521-1: TR 38.905: TS 38.522: |  | 1 | 0% | 0% |  |  | 0%
8 | Y | 38.521-1: NR CA Tx | 6.3A.4.1.2 | Absolute power tolerance for CA (3UL CA) | 3UL CA test case to handle UL CA configurations nxA-nyB or nxB-nyA *Needs to first study whether this specific test cases is needed. *The test case could be added only when at least one relevant configuration is 'ongoing' in PRD21 |  |  | TS 38.521-1: TR 38.905: TS 38.522: |  | 1 | 0% | 0% |  |  | 0%
9 | Y | 38.521-1: NR CA Tx | 6.3A.4.2.2 | Relative power tolerance for CA (3UL CA) | 3UL CA test case to handle UL CA configurations nxA-nyB or nxB-nyA *Needs to first study whether this specific test cases is needed. *The test case could be added only when at least one relevant configuration is 'ongoing' in PRD21 |  |  | TS 38.521-1: TR 38.905: TS 38.522: |  | 1 | 0% | 0% |  |  | 0%
10 | Y | 38.521-1: NR CA Tx | 6.3A.4.3.2 | Aggregate power tolerance for CA (3UL CA) | 3UL CA test case to handle UL CA configurations nxA-nyB or nxB-nyA *Needs to first study whether this specific test cases is needed. *The test case could be added only when at least one relevant configuration is 'ongoing' in PRD21 |  |  | TS 38.521-1: TR 38.905: TS 38.522: |  | 1 | 0% | 0% |  |  | 0%
11 | Y | 38.521-1: NR CA Tx | 6.4A.1.2 | Frequency error for CA (3UL CA) | 3UL CA test case to handle UL CA configurations nxA-nyB or nxB-nyA *Needs to first study whether this specific test cases is needed. *The test case could be added only when at least one relevant configuration is 'ongoing' in PRD21 | KTL |  | TS 38.521-1: TR 38.905: TS 38.522: |  | 1 | 0% | 0% |  |  | 0%
12 | Y | 38.521-1: NR CA Tx | 6.4A.2.1.2 | Error Vector Magnitude for CA (3UL CA) | 3UL CA test case to handle UL CA configurations nxA-nyB or nxB-nyA *Needs to first study whether this specific test cases is needed. *The test case could be added only when at least one relevant configuration is 'ongoing' in PRD21 |  |  | TS 38.521-1: TR 38.905: TS 38.522: |  | 1 | 0% | 0% |  |  | 0%
13 | Y | 38.521-1: NR CA Tx | 6.4A.2.2.2 | Carrier leakage for CA (3UL CA) | 3UL CA test case to handle UL CA configurations nxA-nyB or nxB-nyA *Needs to first study whether this specific test cases is needed. *The test case could be added only when at least one relevant configuration is 'ongoing' in PRD21 |  |  | TS 38.521-1: TR 38.905: TS 38.522: |  | 1 | 0% | 0% |  |  | 0%
14 | Y | 38.521-1: NR CA Tx | 6.4A.2.3.2 | In-band emissions for CA (3UL CA) | 3UL CA test case to handle UL CA configurations nxA-nyB or nxB-nyA *Needs to first study whether this specific test cases is needed. *The test case could be added only when at least one relevant configuration is 'ongoing' in PRD21 |  |  | TS 38.521-1: TR 38.905: TS 38.522: |  | 1 | 0% | 0% |  |  | 0%
15 | Y | 38.521-1: NR CA Tx | 6.5A.1.2 | Occupied bandwidth for CA (3UL CA) | 3UL CA test case to handle UL CA configurations nxA-nyB or nxB-nyA *Needs to first study whether this specific test cases is needed. *The test case could be added only when at least one relevant configuration is 'ongoing' in PRD21 |  |  | TS 38.521-1: TR 38.905: TS 38.522: |  | 1 | 0% | 0% |  |  | 0%
16 | Y | 38.521-1: NR CA Tx | 6.5A.2.2.2 | Spectrum emission mask for CA (3UL CA) | 3UL CA test case to handle UL CA configurations nxA-nyB or nxB-nyA *Needs to first study whether this specific test cases is needed. *The test case could be added only when at least one relevant configuration is 'ongoing' in PRD21 |  |  | TS 38.521-1: TR 38.905: TS 38.522: |  | 1 | 0% | 0% |  |  | 0%
17 | Y | 38.521-1: NR CA Tx | 6.5A.2.3.2 | Additional spectrum emission mask for CA (3UL CA) | 3UL CA test case to handle UL CA configurations nxA-nyB or nxB-nyA *Needs to first study whether this specific test cases is needed. *The test case could be added only when at least one relevant configuration is 'ongoing' in PRD21 |  |  | TS 38.521-1: TR 38.905: TS 38.522: |  | 1 | 0% | 0% |  |  | 0%
18 | Y | 38.521-1: NR CA Tx | 6.5A.2.4.1.2 | NR ACLR for CA (3UL CA) | 3UL CA test case to handle UL CA configurations nxA-nyB or nxB-nyA *Needs to first study whether this specific test cases is needed. *The test case could be added only when at least one relevant configuration is 'ongoing' in PRD21 |  |  | TS 38.521-1: TR 38.905: TS 38.522: |  | 1 | 0% | 0% |  |  | 0%
19 | Y | 38.521-1: NR CA Tx | 6.5A.2.4.2.2 | UTRA ACLR for CA (3UL CA) | 3UL CA test case to handle UL CA configurations nxA-nyB or nxB-nyA *Needs to first study whether this specific test cases is needed. *The test case could be added only when at least one relevant configuration is 'ongoing' in PRD21 |  |  | TS 38.521-1: TR 38.905: TS 38.522: |  | 1 | 0% | 0% |  |  | 0%
20 | Y | 38.521-1: NR CA Tx | 6.5A.3.1.2 | General spurious emissions for CA (3UL CA) | 3UL CA test case to handle UL CA configurations nxA-nyB or nxB-nyA *Needs to first study whether this specific test cases is needed. *The test case could be added only when at least one relevant configuration is 'ongoing' in PRD21 |  |  | TS 38.521-1: TR 38.905: TS 38.522: |  | 1 | 0% | 0% |  |  | 0%
21 | Y | 38.521-1: NR CA Tx | 6.5A.3.2.2 | Spurious emissions for UE co-existence for CA (3UL CA) | 3UL CA test case to handle UL CA configurations nxA-nyB or nxB-nyA *Needs to first study whether this specific test cases is needed. *The test case could be added only when at least one relevant configuration is 'ongoing' in PRD21 |  |  | TS 38.521-1: TR 38.905: TS 38.522: |  | 1 | 0% | 0% |  |  | 0%
22 | Y | 38.521-1: NR CA Tx | 6.5A.4.2 | Transmit intermodulation for CA (3UL CA) | 3UL CA test case to handle UL CA configurations nxA-nyB or nxB-nyA *Needs to first study whether this specific test cases is needed. *The test case could be added only when at least one relevant configuration is 'ongoing' in PRD21 |  |  | TS 38.521-1: TR 38.905: TS 38.522: |  | 1 | 0% | 0% |  |  | 0%
TS 38.521-1: NR CA Receiver Characterstics (section 7)
23 | Y | 38.521-1: NR CA Rx | 7.3A.5 | Reference sensitivity power level for 6DL CA | *The test case could be added only when at least one relevant configuration is 'ongoing' in PRD21 |  |  | TS 38.521-1: TR 38.905: TS 38.522: |  | 1 | 0% | 0% |  |  | 0%
24 | Y | 38.521-1: NR CA Rx | 7.3A.6 | Reference sensitivity power level for 7DL CA | *The test case could be added only when at least one relevant configuration is 'ongoing' in PRD21 |  |  | TS 38.521-1: TR 38.905: TS 38.522: |  | 1 | 0% | 0% |  |  | 0%
25 | Y | 38.521-1: NR CA Rx | 7.3A.7 | Reference sensitivity power level for 8DL CA | *The test case could be added only when at least one relevant configuration is 'ongoing' in PRD21 |  |  | TS 38.521-1: TR 38.905: TS 38.522: |  | 1 | 0% | 0% |  |  | 0%
26 | Y | 38.521-1: NR CA Rx | 7.3C.3 | Reference sensitivity power level for SUL with 2 DL CA |  | Huawei | RAN5#97 (Nov-22) | TS 38.521-1: R5-212999 R5-210934 |  | 1 | 100% | 100% |  |  | 100%
27 | Y | 38.521-1: NR CA Rx | 7.4A.5 | Maximum input level for CA (6DL CA) | *The test case could be added only when at least one relevant configuration is 'ongoing' in PRD21 | KTL |  | TS 38.521-1: TR 38.905: TS 38.522: |  | 1 | 0% | 0% |  |  | 0%
28 | Y | 38.521-1: NR CA Rx | 7.4A.6 | Maximum input level for CA (7DL CA) | *The test case could be added only when at least one relevant configuration is 'ongoing' in PRD21 | KTL |  | TS 38.521-1: TR 38.905: TS 38.522: |  | 1 | 0% | 0% |  |  | 0%
29 | Y | 38.521-1: NR CA Rx | 7.4A.7 | Maximum input level for CA (8DL CA) | *The test case could be added only when at least one relevant configuration is 'ongoing' in PRD21 | KTL |  | TS 38.521-1: TR 38.905: TS 38.522: |  | 1 | 0% | 0% |  |  | 0%
30 | Y | 38.521-1: NR CA Rx | 7.5A.5 | Adjacent channel selectivity for 6DL CA | *The test case could be added only when at least one relevant configuration is 'ongoing' in PRD21 | KTL |  | TS 38.521-1: TR 38.905: TS 38.522: |  | 1 | 0% | 0% |  |  | 0%
31 | Y | 38.521-1: NR CA Rx | 7.5A.6 | Adjacent channel selectivity for 7DL CA | *The test case could be added only when at least one relevant configuration is 'ongoing' in PRD21 | KTL |  | TS 38.521-1: TR 38.905: TS 38.522: |  | 1 | 0% | 0% |  |  | 0%
32 | Y | 38.521-1: NR CA Rx | 7.5A.7 | Adjacent channel selectivity for 8DL CA | *The test case could be added only when at least one relevant configuration is 'ongoing' in PRD21 | KTL |  | TS 38.521-1: TR 38.905: TS 38.522: |  | 1 | 0% | 0% |  |  | 0%
33 | Y | 38.521-1: NR CA Rx | 7.6A.2.5 | In-band blocking for CA (6DL CA) | *The test case could be added only when at least one relevant configuration is 'ongoing' in PRD21 | KTL |  | TS 38.521-1: TR 38.905: TS 38.522: |  | 1 | 0% | 0% |  |  | 0%
34 | Y | 38.521-1: NR CA Rx | 7.6A.2.6 | In-band blocking for CA (7DL CA) | *The test case could be added only when at least one relevant configuration is 'ongoing' in PRD21 | KTL |  | TS 38.521-1: TR 38.905: TS 38.522: |  | 1 | 0% | 0% |  |  | 0%
35 | Y | 38.521-1: NR CA Rx | 7.6A.2.7 | In-band blocking for CA (8DL CA) | *The test case could be added only when at least one relevant configuration is 'ongoing' in PRD21 | KTL |  | TS 38.521-1: TR 38.905: TS 38.522: |  | 1 | 0% | 0% |  |  | 0%
36 | Y | 38.521-1: NR CA Rx | 7.6A.3.5 | Out-of-band blocking for CA (6DL CA) | *The test case could be added only when at least one relevant configuration is 'ongoing' in PRD21 |  |  | TS 38.521-1: TR 38.905: TS 38.522: |  | 1 | 0% | 0% |  |  | 0%
37 | Y | 38.521-1: NR CA Rx | 7.6A.3.6 | Out-of-band blocking for CA (7DL CA) | *The test case could be added only when at least one relevant configuration is 'ongoing' in PRD21 |  |  | TS 38.521-1: TR 38.905: TS 38.522: |  | 1 | 0% | 0% |  |  | 0%
38 | Y | 38.521-1: NR CA Rx | 7.6A.3.7 | Out-of-band blocking for CA (8DL CA) | *The test case could be added only when at least one relevant configuration is 'ongoing' in PRD21 |  |  | TS 38.521-1: TR 38.905: TS 38.522: |  | 1 | 0% | 0% |  |  | 0%
39 | Y | 38.521-1: NR CA Rx | 7.6A.4.5 | Narrow band blocking for CA (6DL CA) | *The test case could be added only when at least one relevant configuration is 'ongoing' in PRD21 | KTL |  | TS 38.521-1: TR 38.905: TS 38.522: |  | 1 | 0% | 0% |  |  | 0%
40 | Y | 38.521-1: NR CA Rx | 7.6A.4.6 | Narrow band blocking for CA (7DL CA) | *The test case could be added only when at least one relevant configuration is 'ongoing' in PRD21 | KTL |  | TS 38.521-1: TR 38.905: TS 38.522: |  | 1 | 0% | 0% |  |  | 0%
41 | Y | 38.521-1: NR CA Rx | 7.6A.4.7 | Narrow band blocking for CA (8DL CA) | *The test case could be added only when at least one relevant configuration is 'ongoing' in PRD21 | KTL |  | TS 38.521-1: TR 38.905: TS 38.522: |  | 1 | 0% | 0% |  |  | 0%
42 | Y | 38.521-1: NR CA Rx | 7.6C.2_1.1 | Inband Blocking for SUL with 2 DL CA |  | Huawei | RAN5#97 (Nov-22) | R5-213004 R5-214023 |  | 1 | 100% | 100% |  |  | 100%
43 | Y | 38.521-1: NR CA Rx | 7.6C.3_1.1 | Out-of-band Blocking for SUL with 2 DL CA |  | Huawei | RAN5#97 (Nov-22) | R5-213004 R5-214024 |  | 1 | 100% | 100% |  |  | 100%
44 | Y | 38.521-1: NR CA Rx | 7.7A.5 | Spurious response for 6DL CA | *The test case could be added only when at least one relevant configuration is 'ongoing' in PRD21 | KTL |  | TS 38.521-1: TR 38.905: TS 38.522: |  | 1 | 0% | 0% |  |  | 0%
45 | Y | 38.521-1: NR CA Rx | 7.7A.6 | Spurious response for 7DL CA | *The test case could be added only when at least one relevant configuration is 'ongoing' in PRD21 | KTL |  | TS 38.521-1: TR 38.905: TS 38.522: |  | 1 | 0% | 0% |  |  | 0%
46 | Y | 38.521-1: NR CA Rx | 7.7A.7 | Spurious response for 8DL CA | *The test case could be added only when at least one relevant configuration is 'ongoing' in PRD21 | KTL |  | TS 38.521-1: TR 38.905: TS 38.522: |  | 1 | 0% | 0% |  |  | 0%
47 | Y | 38.521-1: NR CA Rx | 7.8A.2.5 | Wide band Intermodulation for CA (6DL CA) | *The test case could be added only when at least one relevant configuration is 'ongoing' in PRD21 |  |  | TS 38.521-1: TR 38.905: TS 38.522: |  | 1 | 0% | 0% |  |  | 0%
48 | Y | 38.521-1: NR CA Rx | 7.8A.2.6 | Wide band Intermodulation for CA (7DL CA) | *The test case could be added only when at least one relevant configuration is 'ongoing' in PRD21 |  |  | TS 38.521-1: TR 38.905: TS 38.522: |  | 1 | 0% | 0% |  |  | 0%
49 | Y | 38.521-1: NR CA Rx | 7.8A.2.7 | Wide band Intermodulation for CA (8DL CA) | *The test case could be added only when at least one relevant configuration is 'ongoing' in PRD21 |  |  | TS 38.521-1: TR 38.905: TS 38.522: |  | 1 | 0% | 0% |  |  | 0%
TS 38.521-2: NR CA FR2
TS 38.521-2: NR CA Transmitter Characterstics (Section 6)
TS 38.521-2: NR CA Receiver Characterstics (Section 7)
TS 38.521-3: NR CA FR1+FR2, NR-DC FR1+FR2, EN-DC
TS 38.521-3: EN-DC FR1 Transmitter Characterstics (Section 6)
TS 38.521-3: EN-DC FR2 Transmitter Characterstics (Section 6)
TS 38.521-3: EN-DC FR1 Receiver Characterstics (Section 7)
TS 38.521-3: EN-DC FR2 Receiver Characterstics (Section 7)
TS 38.522: Applicability
TS 38.522: Recommended test case applicability (Section 4)
50 |  | 38.522: Applicability for the R17 CADC new test cases | [6 empty] | The corresponding Tdocs have been captured in the specific test cases | 0
TS 38.905: Derivation of test points for radio transmission and reception
TS 38.905: Test coverage analysis (Section 4)
51 |  | 38.905: TP analysis for R17 CADC new test cases | [6 empty] | The corresponding Tdocs have been captured in the specific test cases | 0
End of workplan items. Note! Do not remove this row. Introduce new work plan rows/items above this row.
Note on A6: Unique ID for WP items (unique within the sub-area work plan) Note! As WP item numbers may be referenced from outside of this WP that means: - Do not change number for WP items that have been published. - Do not re-use WP item numbers if a WP item is deleted
Note on B6: Set to Y if the WP item represents a new test case that will be specified in RAN5 test specifications as an executable test case else leave blank.
Note on K6: The WP item's weight number is used to set the reletive weights between WP items used in the overall calculation of completeness. Setting it to 0 for a WP item means that it will not be included at all in the calculation.