## Cover sheet
3GPP TSG-RAN WG5 Meeting #106 | [8 empty] | R5-250990
Athens, Greece, 17 - 21 Feb 2025
Agenda Item: | 7.5.2
Source: | CATT, Huawei
Title: | WP UE Conformance - NR sidelink enhancement
Work item code: | NR_SL_enh-UEConTest
Release: | Rel-17
Document for: | Information
RAN5 WP template v2.0-8
1. Introduction
<Description of work item and its scope>
2. Work item status
Estimation of WI overall completion:
Area |  | Completion | Number of new completed test cases (Note 1) | Number of new test cases | Comments
Overall completion |  | 50%
Completion Compensation |  | -
| Note 1: | Only test cases completed for all applicable WP areas and sub-areas are counted. For completed test cases per WP areas and WP sub-areas see below.
Estimation WI completion per area and sub-area:
|  | Completion | Number of new completed test cases | Number of new test cases | Comments
PC5 (FR1) |  | 50%
FR1 |  | 50%
Estimation of completion per TS (area):
|  | TS/TR overall completion |  |  | PC5
TS/TR Scope | TS/TR | Completion | Number of new completed test cases | Number of new test cases | FR1
[5 empty] | Completion | Number of new completed test cases | Number of new test cases
LTE
LTE Common
Common test environment | 36.508
UE specific test functions | 36.509
LTE RF/RRM
RF common parts | 36.521-1
RF Rx test cases | 36.521-1 Rx
RF Tx test cases | 36.521-1 Tx
RF Demod test cases | 36.521-1 Demod
Applicability RF, Demod/QSI and RRM test cases | 36.521-2
RRM test cases | 36.521-3
Test Tolerances analysis RRM test cases | 36.903
Test Tolerances analysis receiver test cases | 36.904
Test Point analysis receiver and transmitter test cases | 36.905
LTE RAN and CN protocols
Protocol test cases | 36.523-1
Applicability Protocol test cases | 36.523-2
Test suites (TTCN) | 36.523-3
5GS
5GS Common
Common test environment | 38.508-1 | 0% |  |  | 0%
Common ICS | 38.508-2 | 0% |  |  | 0%
UE specific test functions | 38.509
NR RF/RRM
FR1 RF common parts | 38.521-1 | 0% |  |  | 0%
FR1 RF Tx test cases | 38.521-1 Tx | 61% (+61%) |  |  | 61% (+61%)
FR1 RF Rx test cases | 38.521-1 Rx | 0% |  |  | 0%
FR2 RF common parts | 38.521-2
FR2 RF Tx test cases | 38.521-2 Tx
FR2 RF Rx test cases | 38.521-2 Rx
FR1 and FR2 Interworking operation with other radios RF common parts | 38.521-3
FR1 and FR2 Interworking operation with other radios RF Tx test cases | 38.521-3 Tx
FR1 and FR2 Interworking operation with other radios RF Rx test cases | 38.521-3 Rx
RF Demod/QSI test cases | 38.521-4
RRM test cases | 38.533
Applicability RF, Demod/QSI and RRM test cases | 38.522 | 6.7% (+6.7%) |  |  | 6.7% (+6.7%)
Test Tolerances analysis RRM and RF Rx test cases | 38.903 | 20% (+20%) |  |  | 20% (+20%)
Test Point analysis receiver and transmitter test cases | 38.905 | 0% |  |  | 0%
5GS RAN and CN protocols
Protocol test cases | 38.523-1 | 0% |  |  | 0%
Applicability Protocol test cases | 38.523-2 | 0% |  |  | 0%
Test suites (TTCN) | 38.523-3
UE Positioning
UE Positioning Min. Performance test cases | 37.571-1
UE Positioning Protocol test cases | 37.571-2
Applicability and ICS UE Positioning test cases | 37.571-3
UE Positioning Test sutes (TTCN) | 37.571-4
UE Positioning test scenarios and assistance data | 37.571-5
IMS
IMS over LTE protocol test cases | 34.229-1
IMS over 5GS protocol test cases | 34.229-5
Applicability and ICS IMS test cases | 34.229-2
IMS Test suite (TTCN) | 34.229-3
Mission Critical Services
MC Common test environment | 36.579-1
MCPTT UE test cases | 36.579-2
MC Server Application test cases | 36.579-3
Applicability and ICS MC test cases | 36.579-4
MC Test suite (TTCN) | 36.579-5
MC Video UE test cases | 36.579-6
MC Data UE test cases | 36.579-7
5 References
[1] RP-yyxxxx | <WID document title>
Note on B21: Overall completion of the work item reported at an earlier meeting will not be decreased if additional tasks are added or if corrections are made to the work plan. Instead the earlier reported completion status will be kept until necessary progress have been achieved such that completion exceeds the earlier reported completion level. The value of the Completion Compensation value represents the difference in the decrease caused by late additions or corrections to the work plan and the current estimated overall completion. '-' indicates that no compensation is applied.

## WP
WP Title: |  | WP UE Conformance - NR sidelink enhancement | [8 empty] | Start of workplan status columns. Note! Do not remove this column. | WP item status | End of workplan columns. Note! Do not remove this column.
WI code |  | NR_SL_enh-UEConTest
WP Scope: |  | The objective of this work item is to specify solutions to UE conformance testing corresponding to the features described in WID of NR Sidelink enhancement, including protocol, RF and RRM test cases and associated test environment, test applicability, etc.
WP Resp: |  | Xiaozhong CHEN | [6 empty] | WP item completion |  |  | PC5
TS Resp: |  | <TS responsible if a new TS is involved>
WP Item ID | Is new test case? | TS/area | Clause | Company | Target | TDOC(s) | Comments | Weight | Overall | PC5 |  | FR1
38.4% (+38.4%)
88 (+88)
66.3 (+66.3)
5%
Start of work plan items. Note! Do not remove this row. Introduce new work plan rows/items below this row.
5GS
5GS Common
TS 38.508-1: Common test environment
|  | 38.508-1 | [5 empty] | TBD
TBD |  | 38.508-1 | 4.3.1.8 |  | RAN5#99 (May-23) |  | Contributions could be accepted only when the band is 'Ongoing' in PRD21 | 1 | 0% | 0% |  | 0%
TBD |  | 38.508-1 | 4.10.1 |  | RAN5#99 (May-23) |  | Contributions could be accepted only when the PC1 and PC2 on relevant band is 'Ongoing' in PRD21 | 1 | 0% | 0% |  | 0%
TBD |  | 38.508-1 | 6.2.3 |  | RAN5#99 (May-23) |  | Contributions could be accepted only when the band is 'Ongoing' in PRD21 | 1 | 0% | 0% |  | 0%
TS 38.508-2: Common ICS
|  | 38.508-2 | [5 empty] | TBD
TBD |  | 38.508-2 | A.4.3.10 |  | RAN5#99 (May-23) |  |  | 1 | 0% | 0% |  | 0%
TS 38.509: UE specific testing functions
|  | 38.509 | [5 empty] | TBD
NR RF/RRM
TS 38.521-1: FR1 RF test cases - Common parts (general clauses, Annexes)
|  | 38.521-1 | [5 empty] | TBD
TBD |  | 38.521-1 | 5 |  | RAN5#100 (Aug-23) |  |  | 1 | 0% | 0% |  | 0%
TBD |  | 38.521-1 | Annex A |  | RAN5#100 (Aug-23) |  |  | 1 | 0% | 0% |  | 0%
TBD |  | 38.521-1 | Annex F |  | RAN5#100 (Aug-23) | R5-245832 |  | 1 | 0% | 0% |  | 0%
TS 38.521-1: FR1 RF test cases - Tx
|  | 38.521-1 Tx | [5 empty] | TBD
TBD |  | 38.521-1 Tx | 6.1E |  | RAN5#100 (Aug-23) | R5-243145 |  | 1 | 100% (+100%) | 100% (+100%) |  | 100%
TBD |  | 38.521-1 Tx | 6.2E.1 |  |  | R5-243145 |  | 0 | 100% (+100%) | 100% (+100%) |  | 100%
TBD |  | 38.521-1 Tx | 6.2E.1.0 |  | RAN5#100 (Aug-23) | R5-243145 | Contributions could be accepted only when the band is 'Ongoing' in PRD21 | 0.1 | 100% (+100%) | 100% (+100%) |  | 100%
TBD |  | 38.521-1 Tx | 6.2E.1.1 |  | RAN5#100 (Aug-23) | R5-243145 | Contributions could be accepted only when the band is 'Ongoing' in PRD21 | 1 | 100% (+100%) | 100% (+100%) |  | 100%
TBD |  | 38.521-1 Tx | 6.2E.1.1D |  | RAN5#100 (Aug-23) | R5-243145 | Contributions could be accepted only when the band is 'Ongoing' in PRD21 | 1 | 100% (+100%) | 100% (+100%) |  | 100%
TBD |  | 38.521-1 Tx | 6.2E.1.2 |  | RAN5#100 (Aug-23) | R5-243145 | Contributions could be accepted only when the band is 'Ongoing' in PRD21 | 1 | 100% (+100%) | 100% (+100%) |  | 100%
TBD |  | 38.521-1 Tx | 6.2E.2 |  |  |  |  | 0
TBD |  | 38.521-1 Tx | 6.2E.2.0 |  | RAN5#100 (Aug-23) | R5-243146 | Contributions could be accepted only when the band is 'Ongoing' in PRD21 | 0.1 | 90% (+90%) | 90% (+90%) |  | 90%
TBD |  | 38.521-1 Tx | 6.2E.2.1 |  | RAN5#100 (Aug-23) | R5-243146 | Contributions could be accepted only when the band is 'Ongoing' in PRD21 | 1 | 90% (+90%) | 90% (+90%) |  | 90%
TBD |  | 38.521-1 Tx | 6.2E.2.1D |  | RAN5#100 (Aug-23) | R5-243146 | Contributions could be accepted only when the band is 'Ongoing' in PRD21 | 1 | 90% (+90%) | 90% (+90%) |  | 90%
TBD |  | 38.521-1 Tx | 6.2E.2.2 |  | RAN5#100 (Aug-23) | R5-243146 | Contributions could be accepted only when the band is 'Ongoing' in PRD21 | 1 | 0% | 0% |  | 0%
TBD |  | 38.521-1 Tx | 6.2E.3 |  |  |  |  | 0
TBD |  | 38.521-1 Tx | 6.2E.3.0 |  | RAN5#100 (Aug-23) | R5-243148 | Contributions could be accepted only when the band is 'Ongoing' in PRD21 | 0.1 | 100% (+100%) | 100% (+100%) |  | 100%
TBD |  | 38.521-1 Tx | 6.2E.3.1 |  | RAN5#100 (Aug-23) | R5-243148 | Contributions could be accepted only when the band is 'Ongoing' in PRD21 | 1 | 100% (+100%) | 100% (+100%) |  | 100%
TBD |  | 38.521-1 Tx | 6.2E.3.1D |  | RAN5#100 (Aug-23) | R5-243148 | Contributions could be accepted only when the band is 'Ongoing' in PRD21 | 1 | 100% (+100%) | 100% (+100%) |  | 100%
TBD |  | 38.521-1 Tx | 6.2E.3.2 |  | RAN5#100 (Aug-23) | R5-243148 | Contributions could be accepted only when the band is 'Ongoing' in PRD21 | 1 | 100% (+100%) | 100% (+100%) |  | 100%
TBD |  | 38.521-1 Tx | 6.2E.4 |  |  |  |  | 0
TBD |  | 38.521-1 Tx | 6.2E.4.0 |  | RAN5#100 (Aug-23) | R5-244997 | Contributions could be accepted only when the band is 'Ongoing' in PRD21 | 0.1 | 100% | 100% |  | 100%
TBD |  | 38.521-1 Tx | 6.2E.4.1 |  | RAN5#100 (Aug-23) | R5-244997 | Contributions could be accepted only when the band is 'Ongoing' in PRD21 | 1 | 100% | 100% |  | 100%
TBD |  | 38.521-1 Tx | 6.2E.4.1D |  | RAN5#100 (Aug-23) | R5-244997 | Contributions could be accepted only when the band is 'Ongoing' in PRD21 | 1 | 100% | 100% |  | 100%
TBD |  | 38.521-1 Tx | 6.2E.4.2 |  | RAN5#100 (Aug-23) | R5-244997 | Contributions could be accepted only when the band is 'Ongoing' in PRD21 | 1 | 100% | 100% |  | 100%
TBD |  | 38.521-1 Tx | 6.3E.1.0 |  | RAN5#100 (Aug-23) | R5-244999 | Contributions could be accepted only when the band is 'Ongoing' in PRD21 | 0.1 | 100% | 100% |  | 100%
TBD |  | 38.521-1 Tx | 6.3E.1.2 |  | RAN5#100 (Aug-23) | R5-244999 | Contributions could be accepted only when the band is 'Ongoing' in PRD21 | 1 | 100% | 100% |  | 100%
TBD |  | 38.521-1 Tx | 6.3E.2.0 |  | RAN5#100 (Aug-23) | R5-245000 | Contributions could be accepted only when the band is 'Ongoing' in PRD21 | 0.1 | 100% | 100% |  | 100%
TBD |  | 38.521-1 Tx | 6.3E.2.2 |  | RAN5#100 (Aug-23) | R5-245000 | Contributions could be accepted only when the band is 'Ongoing' in PRD21 | 1 | 100% | 100% |  | 100%
TBD |  | 38.521-1 Tx | 6.3E.3.0 |  | RAN5#100 (Aug-23) | R5-247432 | Contributions could be accepted only when the band is 'Ongoing' in PRD21 | 0.1 | 100% | 100% |  | 100%
TBD |  | 38.521-1 Tx | 6.3E.3.1.2 |  | RAN5#100 (Aug-23) |  | Contributions could be accepted only when the band is 'Ongoing' in PRD21 | 1 | 0% | 0% |  | 0%
TBD |  | 38.521-1 Tx | 6.3E.3.2.2 |  | RAN5#100 (Aug-23) |  | Contributions could be accepted only when the band is 'Ongoing' in PRD21 | 1 | 0% | 0% |  | 0%
TBD |  | 38.521-1 Tx | 6.3E.4.0 |  | RAN5#100 (Aug-23) | R5-247433 | Contributions could be accepted only when the band is 'Ongoing' in PRD21 | 0.1 | 100% | 100% |  | 100%
TBD |  | 38.521-1 Tx | 6.3E.4.1.2 |  | RAN5#100 (Aug-23) |  | Contributions could be accepted only when the band is 'Ongoing' in PRD21 | 1 | 0% | 0% |  | 0%
TBD |  | 38.521-1 Tx | 6.4E.1.0 |  | RAN5#100 (Aug-23) | R5-244998 R5-251126 | Contributions could be accepted only when the band is 'Ongoing' in PRD21 | 0.1 | 100% | 100% |  | 100%
TBD |  | 38.521-1 Tx | 6.4E.1.2 |  | RAN5#100 (Aug-23) | R5-244998 | Contributions could be accepted only when the band is 'Ongoing' in PRD21 | 1 | 100% | 100% |  | 100%
TBD |  | 38.521-1 Tx | 6.4E.2.1 |  | RAN5#100 (Aug-23) | R5-244998 | Contributions could be accepted only when the band is 'Ongoing' in PRD21 | 1 | 100% | 100% |  | 100%
TBD |  | 38.521-1 Tx | 6.4E.2.2.2 |  | RAN5#100 (Aug-23) | R5-244998 | Contributions could be accepted only when the band is 'Ongoing' in PRD21 | 1 | 100% | 100% |  | 100%
TBD |  | 38.521-1 Tx | 6.4E.2.3.2 |  | RAN5#100 (Aug-23) | R5-244998 | Contributions could be accepted only when the band is 'Ongoing' in PRD21 | 1 | 100% | 100% |  | 100%
TBD |  | 38.521-1 Tx | 6.4E.2.4.2 |  | RAN5#100 (Aug-23) | R5-244998 | Contributions could be accepted only when the band is 'Ongoing' in PRD21 | 1 | 100% | 100% |  | 100%
TBD |  | 38.521-1 Tx | 6.4E.2.5.2 |  | RAN5#100 (Aug-23) | R5-244998 | Contributions could be accepted only when the band is 'Ongoing' in PRD21 | 1 | 100% | 100% |  | 100%
TBD |  | 38.521-1 Tx | 6.5E.1.0 |  | RAN5#100 (Aug-23) | R5-251127 | Contributions could be accepted only when the band is 'Ongoing' in PRD21 | 0.1 | 100% (+100%) | 100% (+100%) |  | 100%
TBD |  | 38.521-1 Tx | 6.5E.1.2 |  | RAN5#100 (Aug-23) | R5-251128 | Contributions could be accepted only when the band is 'Ongoing' in PRD21 | 1 | 100% (+100%) | 100% (+100%) |  | 100%
TBD |  | 38.521-1 Tx | 6.5E.2.2 |  |  |  |  | 0
TBD |  | 38.521-1 Tx | 6.5E.2.2.0 |  | RAN5#100 (Aug-23) |  | Contributions could be accepted only when the band is 'Ongoing' in PRD21 | 0.1 | 0% | 0% |  | 0%
TBD |  | 38.521-1 Tx | 6.5E.2.2.1 |  | RAN5#100 (Aug-23) |  | Contributions could be accepted only when the band is 'Ongoing' in PRD21 | 1 | 0% | 0% |  | 0%
TBD |  | 38.521-1 Tx | 6.5E.2.2.1D |  | RAN5#100 (Aug-23) |  | Contributions could be accepted only when the band is 'Ongoing' in PRD21 | 1 | 0% | 0% |  | 0%
TBD |  | 38.521-1 Tx | 6.5E.2.2.2 |  | RAN5#100 (Aug-23) |  | Contributions could be accepted only when the band is 'Ongoing' in PRD21 | 1 | 0% | 0% |  | 0%
TBD |  | 38.521-1 Tx | 6.5E.2.3 |  |  |  |  | 0
TBD |  | 38.521-1 Tx | 6.5E.2.3.0 |  | RAN5#100 (Aug-23) |  | Contributions could be accepted only when the band is 'Ongoing' in PRD21 | 0.1 | 0% | 0% |  | 0%
TBD |  | 38.521-1 Tx | 6.5E.2.3.1 |  | RAN5#100 (Aug-23) |  | Contributions could be accepted only when the band is 'Ongoing' in PRD21 | 1 | 0% | 0% |  | 0%
TBD |  | 38.521-1 Tx | 6.5E.2.3.1D |  | RAN5#100 (Aug-23) |  | Contributions could be accepted only when the band is 'Ongoing' in PRD21 | 1 | 0% | 0% |  | 0%
TBD |  | 38.521-1 Tx | 6.5E.2.3.2 |  | RAN5#100 (Aug-23) | R5-251543 | Contributions could be accepted only when the band is 'Ongoing' in PRD21 | 1 | 100% (+100%) | 100% (+100%) |  | 100%
TBD |  | 38.521-1 Tx | 6.5E.2.4 |  |  |  |  | 0
TBD |  | 38.521-1 Tx | 6.5E.2.4.0 |  | RAN5#100 (Aug-23) |  | Contributions could be accepted only when the band is 'Ongoing' in PRD21 | 0.1 | 0% | 0% |  | 0%
TBD |  | 38.521-1 Tx | 6.5E.2.4.1 |  | RAN5#100 (Aug-23) |  | Contributions could be accepted only when the band is 'Ongoing' in PRD21 | 1 | 0% | 0% |  | 0%
TBD |  | 38.521-1 Tx | 6.5E.2.4.1D |  | RAN5#100 (Aug-23) |  | Contributions could be accepted only when the band is 'Ongoing' in PRD21 | 1 | 0% | 0% |  | 0%
TBD |  | 38.521-1 Tx | 6.5E.2.4.2 |  | RAN5#100 (Aug-23) |  | Contributions could be accepted only when the band is 'Ongoing' in PRD21 | 1 | 0% | 0% |  | 0%
TBD |  | 38.521-1 Tx | 6.5E.3.2.0 |  | RAN5#100 (Aug-23) |  | Contributions could be accepted only when the band is 'Ongoing' in PRD21 | 0.1 | 0% | 0% |  | 0%
TBD |  | 38.521-1 Tx | 6.5E.3.2.2 |  | RAN5#100 (Aug-23) |  | Contributions could be accepted only when the band is 'Ongoing' in PRD21 | 1 | 0% | 0% |  | 0%
TBD |  | 38.521-1 Tx | 6.5E.4.0 |  | RAN5#100 (Aug-23) | R5-251132 | Contributions could be accepted only when the band is 'Ongoing' in PRD21 | 0.1 | 100% (+100%) | 100% (+100%) |  | 100%
TBD |  | 38.521-1 Tx | 6.5E.4.2 |  | RAN5#100 (Aug-23) |  | Contributions could be accepted only when the band is 'Ongoing' in PRD21 | 1 | 0% | 0% |  | 0%
TS 38.521-1: FR1 RF test cases - Rx
|  | 38.521-1 Rx | [5 empty] | TBD
TBD |  | 38.521-1 Rx | 7.3E |  |  |  |  | 0
TBD |  | 38.521-1 Rx | 7.3E.1 |  | RAN5#100 (Aug-23) |  | Contributions could be accepted only when the band is 'Ongoing' in PRD21 | 0.1 | 0% | 0% |  | 0%
TBD |  | 38.521-1 Rx | 7.3E.2 |  | RAN5#100 (Aug-23) |  | Contributions could be accepted only when the band is 'Ongoing' in PRD21 | 1 | 0% | 0% |  | 0%
TBD |  | 38.521-1 Rx | 7.3E.3 |  | RAN5#100 (Aug-23) |  | Contributions could be accepted only when the band is 'Ongoing' in PRD21 | 1 | 0% | 0% |  | 0%
TBD |  | 38.521-1 Rx | 7.4E |  |  |  |  | 0
TBD |  | 38.521-1 Rx | 7.4E.0 |  | RAN5#100 (Aug-23) |  | Contributions could be accepted only when the band is 'Ongoing' in PRD21 | 0.1 | 0% | 0% |  | 0%
TBD |  | 38.521-1 Rx | 7.4E.1 |  | RAN5#100 (Aug-23) |  | Contributions could be accepted only when the band is 'Ongoing' in PRD21 | 1 | 0% | 0% |  | 0%
TBD |  | 38.521-1 Rx | 7.4E.2 |  | RAN5#100 (Aug-23) |  | Contributions could be accepted only when the band is 'Ongoing' in PRD21 | 1 | 0% | 0% |  | 0%
TBD |  | 38.521-1 Rx | 7.5E |  |  |  |  | 0
TBD |  | 38.521-1 Rx | 7.5E.0 |  | RAN5#100 (Aug-23) |  | Contributions could be accepted only when the band is 'Ongoing' in PRD21 | 0.1 | 0% | 0% |  | 0%
TBD |  | 38.521-1 Rx | 7.5E.1 |  | RAN5#100 (Aug-23) |  | Contributions could be accepted only when the band is 'Ongoing' in PRD21 | 1 | 0% | 0% |  | 0%
TBD |  | 38.521-1 Rx | 7.5E.2 |  | RAN5#100 (Aug-23) |  | Contributions could be accepted only when the band is 'Ongoing' in PRD21 | 1 | 0% | 0% |  | 0%
TBD |  | 38.521-1 Rx | 7.6E.2 |  |  |  |  | 0
TBD |  | 38.521-1 Rx | 7.6E.2.0 |  | RAN5#100 (Aug-23) |  | Contributions could be accepted only when the band is 'Ongoing' in PRD21 | 0.1 | 0% | 0% |  | 0%
TBD |  | 38.521-1 Rx | 7.6E.2.1 |  | RAN5#100 (Aug-23) |  | Contributions could be accepted only when the band is 'Ongoing' in PRD21 | 1 | 0% | 0% |  | 0%
TBD |  | 38.521-1 Rx | 7.6E.2.2 |  | RAN5#100 (Aug-23) |  | Contributions could be accepted only when the band is 'Ongoing' in PRD21 | 1 | 0% | 0% |  | 0%
TBD |  | 38.521-1 Rx | 7.6E.3 |  |  |  |  | 0
TBD |  | 38.521-1 Rx | 7.6E.3.0 |  | RAN5#100 (Aug-23) |  | Contributions could be accepted only when the band is 'Ongoing' in PRD21 | 0.1 | 0% | 0% |  | 0%
TBD |  | 38.521-1 Rx | 7.6E.3.1 |  | RAN5#100 (Aug-23) |  | Contributions could be accepted only when the band is 'Ongoing' in PRD21 | 1 | 0% | 0% |  | 0%
TBD |  | 38.521-1 Rx | 7.6E.3.2 |  | RAN5#100 (Aug-23) |  | Contributions could be accepted only when the band is 'Ongoing' in PRD21 | 1 | 0% | 0% |  | 0%
TBD |  | 38.521-1 Rx | 7.7E |  |  |  |  | 0
TBD |  | 38.521-1 Rx | 7.7E.0 |  | RAN5#100 (Aug-23) |  | Contributions could be accepted only when the band is 'Ongoing' in PRD21 | 0.1 | 0% | 0% |  | 0%
TBD |  | 38.521-1 Rx | 7.7E.1 |  | RAN5#100 (Aug-23) |  | Contributions could be accepted only when the band is 'Ongoing' in PRD21 | 1 | 0% | 0% |  | 0%
TBD |  | 38.521-1 Rx | 7.7E.2 |  | RAN5#100 (Aug-23) |  | Contributions could be accepted only when the band is 'Ongoing' in PRD21 | 1 | 0% | 0% |  | 0%
TBD |  | 38.521-1 Rx | 7.8E.2 |  |  |  |  | 0
TBD |  | 38.521-1 Rx | 7.8E.2.0 |  | RAN5#100 (Aug-23) |  | Contributions could be accepted only when the band is 'Ongoing' in PRD21 | 0.1 | 0% | 0% |  | 0%
TBD |  | 38.521-1 Rx | 7.8E.2.1 |  | RAN5#100 (Aug-23) |  | Contributions could be accepted only when the band is 'Ongoing' in PRD21 | 1 | 0% | 0% |  | 0%
TBD |  | 38.521-1 Rx | 7.8E.2.2 |  | RAN5#100 (Aug-23) |  | Contributions could be accepted only when the band is 'Ongoing' in PRD21 | 1 | 0% | 0% |  | 0%
TS 38.521-4: Demod/QSI reporting test cases
|  | 38.521-4 | [5 empty] | TBD
TS 38.522: Applicability for RF, Demod/QSI reporting and RRM test cases
TBD |  | 38.522 | 4.1.1 |  | RAN5#100 (Aug-23) | R5-245002 |  | 1 | 20% | 20% |  | 20%
TBD |  | 38.522 | 4.1.4 |  | RAN5#100 (Aug-23) |  |  | 1 | 0% | 0% |  | 0%
TBD |  | 38.522 | 4.2 |  | RAN5#100 (Aug-23) |  |  | 1 | 0% | 0% |  | 0%
TS 38.533: RRM test cases
|  | 38.533 | [5 empty] | TBD
TBD |  | 38.533 | <Clause> |  | TBD |  |  | 0
TBD |  | 38.533 | <Clause> |  | TBD |  |  | TBD
TBD | Y | 38.533 | <Clause> |  | TBD |  |  | 1
TR 38.903: Test Tolerances analysis RRM and RF Rx test cases
|  | 38.903 | [5 empty] | TBD
TBD |  | 38.903 | 8 |  | RAN5#100 (Aug-23) |  |  | 1 | 20% | 20% |  | 20%
TR 38.905: Test Point analysis receiver and transmitter test cases
|  | 38.905 | [5 empty] | TBD
TBD |  | 38.905 | 4.1 |  | RAN5#100 (Aug-23) | R5-244998 |  | 1 | 0% | 0% |  | 0%
RAN and CN protocol
TS 38.523-1: Protocol test cases
|  | 38.523-1 | [5 empty] | TBD
PC5-only operation
TBD |  | 38.523-1 | <Clause> |  | TBD |  |  | 0
TBD |  | 38.523-1 | <Clause> |  | TBD |  |  | 1 | 0% | 0% |  | 0%
TBD |  | 38.523-1 | <Clause> |  | TBD |  |  | 1 | 0% | 0% |  | 0%
Inter-carrier concurrent operation
TBD |  | 38.523-1 | 12.2 |  | TBD |  |  | 0
12.2.11
TBD | Y | 38.523-1 | 12.2.11.1 |  | TBD |  |  | TBD
TBD | Y | 38.523-1 | 12.2.11.2 |  | TBD |  |  | 1
TS 38.523-2: Applicability for Protocol test cases
TBD |  | 38.523-2 | <Clause> |  | TBD |  |  | 0.1
TBD |  | 38.523-2 | 4.1 |  | TBD |  |  | 0.1 | 0% | 0% |  | 0%
TS 38.523-3: Protocol test suites (TTCN)
|  | 38.523-3 | [5 empty] | TBD
TBD |  | 38.523-3 | <Clause> |  | TBD |  |  | TBD
End of workplan items. Note! Do not remove this row. Introduce new work plan rows/items above this row.
Note on A6: Unique ID for WP items (unique within the sub-area work plan) Note! As WP item numbers may be referenced from outside of this WP that means: - Do not change number for WP items that have been published. - Do not re-use WP item numbers if a WP item is deleted
Note on B6: Set to Y if the WP item represents a new test case that will be specified in RAN5 test specifications as an executable test case else leave blank.
Note on I6: The WP item's weight number is used to set the reletive weights between WP items used in the overall calculation of completeness. Setting it to 0 for a WP item means that it will not be included at all in the calculation.