## R5#107
3GPP TSG RAN WG5 (RAN5) Meeting #107 | [9 empty] | R5-251814
St Julian's, Malta, 19 - 23 May 2025
WI Progress and Target Completion Date Review
Source: RAN5 Chair
To: RAN5
Purpose: For Endorsement
UIC | WI Name | Rel | Tdoc# | Pre TCD | pre % | post % | post TCD | change (mths) | Rapporteur | other comments
830083 | UE Conformance Test Aspects - Rel-16 NR CA and DC; and NR and LTE DC Configurations | Rel-16 | R5-252081 | 2025-06-01 | 63% | 64% | 2025-12-01 | +6 | CMCC
880069 | UE Conformance Test Aspects - 5G V2X with NR sidelink | Rel-16 | R5-252742 | 2025-06-01 | 87% | 100% | 2025-06-01 |  | Huawei
900056 | UE Conformance - Rel-17 NR CA and DC; and NR and LTE DC Configurations | Rel-17 | R5-253232 | 2025-12-01 | 11% | 11% | 2025-12-01 |  | Huawei
950062 | UE Conformance - Introduction of FR2 FWA (Fixed Wireless Access) UE with maximum TRP (Total Radiated Power) of 23dBm for band n257 and n258 | Rel-17 | R5-252744 | 2025-12-01 | 63% | 73% | 2025-12-01 |  | Huawei
960074 | UE Conformance - Solutions for NR to support non-terrestrial networks (NTN) | Rel-17 | R5-252978 | 2025-06-01 | 89% | 93% | 2025-12-01 | +6 | Qualcomm
960080 | UE Conformance - NR support for high speed train scenario in frequency range 2 | Rel-17 | R5-252763 | 2025-12-01 | 69% | 70% | 2025-12-01 |  | Samsung
960083 | UE Conformance - NR Sidelink Relay | Rel-17 | R5-252547 | 2025-06-01 | 80% | 90% | 2025-09-01 | +3 | CATT
960084 | UE Conformance - NR Sidelink enhancement | Rel-17 | R5-252545 | 2025-09-01 | 50% | 50% | 2025-09-01 |  | CATT
960089 | UE Conformance Test Aspects - NR RRM enhancement | Rel-16 | R5-252395 | 2025-06-01 | 85% | 90% | 2025-09-01 | +3 | Apple
1000050 | UE Conformance - Additional NR bands for UL-MIMO in Rel-18 | Rel-18 | R5-252370 | 2025-06-01 | 76% | 100% | 2025-06-01 |  | China Unicom
1000051 | UE Conformance - High power UE (power class 2) for NR FR1 FDD single band | Rel-18 | R5-252368 | 2025-06-01 | 33% | 34% | 2025-09-01 | +3 | China Unicom
1000054 | UE Conformance - Rel-18 High Power UE for NR CA and DC; and NR and LTE DC Configurations | Rel-18 | R5-251884 | 2025-06-01 | 85% | 90% | 2025-12-01 | +6 | China Telecom
1000056 | UE Conformance - UE Conformance - Rel-17 Power Class 2 UE for NR inter-band CA/DC with or without SUL configurations with x (6>=x>2) bands DL and y (y=1, 2) bands UL | Rel-17 | R5-251997 | 2025-06-01 | 20% | 21% | 2025-12-01 | +6 | Huawei
1000057 | UE Conformance - Rel-18 NR CA and DC; and NR and LTE DC Configurations | Rel-18 | R5-252002 | 2025-06-01 | 76% | 76% | 2025-12-01 | +6 | Huawei
1020087 | UE Conformance - Air-to-ground network for NR | Rel-18 | R5-252075 | 2025-06-01 | 64% | 64% | 2025-12-01 | +6 | CMCC
1030060 | UE Conformance - NR support for dedicated spectrum less than 5MHz for FR1 | Rel-18 | R5-251859 | 2025-12-01 | 65% | 78% | 2025-12-01 |  | Nokia
1030061 | UE Conformance - Dual Transmission/Reception (Tx/Rx) Multi-SIM for NR | Rel-18 | R5-252207 | 2025-06-01 | 90% | 100% | 2025-06-01 |  | China Telecom
1030062 | UE Conformance - Enhanced support of reduced capability NR devices plus CT1 | Rel-18 | R5-252364 | 2025-12-01 | 64% | 70% | 2025-12-01 |  | China Unicom
1030063 | UE Conformance - XR (eXtended Reality) enhancements for NR plus CT1 aspects | Rel-18 | R5-252607 | 2025-12-01 | 71% | 80% | 2025-12-01 |  | Nokia
1030064 | UE Conformance - Introduction of 900 MHz LTE band in the US | Rel-18 | R5-251966 | 2025-06-01 | 85% | 95% | 2025-09-01 | +3 | Nokia
1030065 | UE Conformance - NR RF requirements enhancement for frequency range 2 (FR2), Phase 3 | Rel-18 | R5-252990 | 2025-06-01 | 40% | 65% | 2025-12-01 | +6 | Apple
1030066 | UE Conformance - Further RF requirements enhancement for NR and EN-DC in frequency range 1 | Rel-18 | R5-253024 | 2025-12-01 | 35% | 54% | 2025-12-01 |  | Huawei
1030067 | UE Conformance - Network energy savings for NR | Rel-18 | R5-252312 | 2025-12-01 | 73% | 90% | 2025-12-01 |  | Huawei
1030069 | UE Conformance - Further NR coverage enhancements | Rel-18 | R5-252193 | 2025-12-01 | 30% | 76% | 2025-12-01 |  | China Telecom
1030070 | UE Conformance - Multi-carrier enhancements for NR | Rel-18 | R5-252436 | 2025-12-01 | 88% | 95% | 2025-12-01 |  | China Telecom
1030071 | UE Conformance - Enhanced NR support for high speed train scenario in frequency range 2 (FR2) | Rel-18 | R5-252759 | 2025-12-01 | 38% | 38% | 2025-12-01 |  | Samsung
1030072 | UE Conformance - NR MIMO evolution for downlink and uplink | Rel-18 | R5-252761 | 2025-12-01 | 50% | 59% | 2025-12-01 |  | Samsung
1030073 | UE Conformance - IoT (Internet of Things) NTN (non-terrestrial network) enhancements plus CT1 aspects | Rel-18 | R5-252071 | 2025-12-01 | 56% | 80% | 2025-12-01 |  | CMCC
1040102 | UE Conformance 4Rx for NR bands for FWA UEs (up to 2.6GHz) and handheld UEs (1GHz to 2.6GHz) | Rel-18 | R5-252871 | 2025-06-01 | 95% | 100% | 2025-06-01 |  | ZTE
1040103 | UE Conformance - Mobile Terminated-Small Data Transmission (MT-SDT) for NR | Rel-18 | R5-251986 | 2025-12-01 | 65% | 90% | 2025-12-01 |  | Qualcomm
1040104 | UE Conformance - In-Device Co-existence (IDC) enhancements for NR and MR-DC | Rel-18 | R5-252113 | 2026-06-01 | 39% | 55% | 2026-06-01 |  | CMCC
1040105 | UE Conformance - NR demodulation performance evolution | Rel-18 | R5-251905 | 2025-12-01 | 57% | 77% | 2025-12-01 |  | China Telecom
1040106 | UE Conformance - Non-Public Networks Phase 2: NG-RAN aspects plus CT1 aspects | Rel-18 | R5-251886 | 2025-12-01 | 17% | 32% | 2025-12-01 |  | China Telecom
1040107 | UE Conformance - Expanded and improved NR positioning | Rel-18 | R5-252285 | 2026-06-01 | 7% | 9% | 2026-06-01 |  | CATT
1040108 | UE Conformance - Further NR mobility enhancements | Rel-18 | R5-252612 | 2025-12-01 | 55% | 70% | 2025-12-01 |  | MediaTek
1040110 | UE Conformance - Introduction of the Extended L-band (UL 1668-1675MHz, DL 1518-1525MHz) for IoT NTN | Rel-18 | R5-252614 | 2025-06-01 | 95% | 100% | 2025-06-01 |  | MediaTek
1040111 | UE Conformance - Enhancement of UE TRP (Total Radiated Power) and TRS (Total Radiated Sensitivity) requirements and test methodologies | Rel-18 | R5-252992 | 2025-06-01 | 70% | 100% | 2025-06-01 |  | Apple
1040112 | UE Conformance - Enhancement of Multiple Input Multiple Output (MIMO) Over-the-Air (OTA) test methodology and requirements for NR UEs | Rel-18 | R5-252813 | 2025-06-01 | 65% | 100% | 2025-06-01 |  | Apple
1040113 | UE Conformance - Requirement for NR frequency range 2 (FR2) multi-Rx chain DL reception | Rel-18 | R5-252984 | 2025-12-01 | 20% | 30% | 2025-12-01 |  | Qualcomm
1050128 | UE Conformance - Protocol enhancements for Mission Critical Services (MCPTT, MCVideo, MCData) for Rel-17 | Rel-17 | R5-252289 | 2025-12-01 | 23% | 47% | 2025-12-01 |  | Ericsson
1050129 | UE Conformance - Rel-18 downlink interruption for NR and EN-DC band combinations at dynamic Tx Switching in Uplink | Rel-18 | R5-252439 | 2025-12-01 | 69% | 100% | 2025-06-01 | -6 | China Telecom
1050130 | UE Conformance - NR NTN (non-Terrestrial Networks) enhancements plus CT aspects | Rel-18 | R5-252980 | 2025-12-01 | 10% | 15% | 2025-12-01 |  | Qualcomm
1050131 | UE Conformance - New bands and bandwidth allocation for LTE based 5G terrestrial broadcast | Rel-18 | R5-252982 | 2025-12-01 | 15% | 15% | 2025-12-01 |  | Qualcomm
1050132 | UE Conformance - Further enhancements on NR and MR-DC measurement gaps and measurements without gaps | Rel-18 | R5-252616 | 2025-12-01 | 35% | 71% | 2025-12-01 |  | MediaTek
1050133 | UE Conformance - IMS Data Channel for NG RTC (Real Time Communication) | Rel-18 | R5-252592 | 2025-12-01 | 21% | 71% | 2025-12-01 |  | Huawei
1060075 | UE Conformance - Alignment of eCall over IMS with CEN | Rel-19 | R5-251988 | 2025-06-01 | 80% | 90% | 2025-12-01 | +6 | Qualcomm
1060077 | UE Conformance - Enhancements of NR Multicast and Broadcast Services including CT aspects | Rel-18 | R5-252549 | 2025-12-01 | 5% | 5% | 2025-12-01 |  | CATT
1070060 | UE Conformance - NR Support for UAV (Uncrewed Aerial Vehicles) plus CT1 aspects | Rel-18 | R5-252366 | 2026-03-01 |  | 28% | 2026-03-01 |  | China Unicom
1070061 | UE Conformance - Access Traffic Steering, Switch and Splitting support in the 5G system architecture; Phase 3 | Rel-18 | R5-252205 | 2026-03-01 |  | 5% | 2026-03-01 |  | China Telecom
1070062 | UE Conformance - Introduction of Power Class 2 and UE 40MHz Channel Bandwidth in NR band n28 | Rel-19 | R5-252189 | 2026-03-01 |  | 54% | 2026-03-01 |  | CMCC
1070063 | UE Conformance - Rel-19 NR CA and DC; and NR and LTE DC Configurations | Rel-19 | R5-252004 | 2026-12-01 |  | 5% | 2026-12-01 |  | Huawei