## Cover sheet
3GPP TSG-RAN WG5 Meeting # 107 | [10 empty] | R5-251885
St Julian, Malta, 19 - 23 May 2025
Agenda Item: | 7.5.2
Source: | China Telecom
Title: | WP for Non-Public Networks Phase 2: NG-RAN aspects plus CT1 aspects
Work item code: | eNPN_Ph2-NGRAN_plus_CT1-UEConTest
Release: | Rel-18
Document for: | Information
RAN5 WP template v3.0.0
1. Introduction
<Description of work item and its scope>
2. Work item status
Estimation of WI overall completion:
Area |  | Completion | Number of new completed test cases (Note 1) | Number of new test cases | Comments
Overall completion |  | 32% (+15%) | 1 (+1) | 9
Completion Compensation |  | -
| Note 1: | Only test cases completed for all applicable WP areas and sub-areas are counted. For completed test cases per WP areas and WP sub-areas see below.
Estimation WI completion per area and sub-area:
|  | Completion | Number of new completed test cases | Number of new test cases | Comments
SA Option 2 (SA NR) |  | 32% (+15%) | 1 (+1) | 9
FR1 |  | 32% (+15%) | 1 (+1) | 9
FR2 |  | 32% (+15%) | 1 (+1) | 9
Estimation of completion per TS (area):
|  | TS/TR overall completion |  |  | SA Option 2 (SA NR)
TS/TR Scope | TS/TR | Completion | Number of new completed test cases | Number of new test cases | FR1 |  |  | FR2
[5 empty] | Completion | Number of new completed test cases | Number of new test cases | Completion | Number of new completed test cases | Number of new test cases
5GS
5GS Common
Common test environment | 38.508-1 | 0% |  |  | 0% |  |  | 0%
Common ICS | 38.508-2 | 60% (+30%) |  |  | 30% (+30%) |  |  | 30% (+30%)
5GS RAN and CN protocols
Protocol test cases | 38.523-1 | 32% (+15%) | 1 (+1) | 9 | 11.1% (+11.1%) | 1 (+1) | 9 | 11.1% (+11.1%) | 1 (+1) | 9 (+9)
Applicability Protocol test cases | 38.523-2 | 32% (+15%) |  |  | 30% (+30%) |  |  | 30% (+30%)
Test suites (TTCN) | 38.523-3
5 References
[1] RP-241307 | New WID: UE Conformance - Non-Public Networks Phase 2: NG-RAN aspects plus CT1 aspects，China Telecom, Qualcomm, ZTE, RAN#104
Note on B21: Overall completion of the work item reported at an earlier meeting will not be decreased if additional tasks are added or if corrections are made to the work plan. Instead the earlier reported completion status will be kept until necessary progress have been achieved such that completion exceeds the earlier reported completion level. The value of the Completion Compensation value represents the difference in the decrease caused by late additions or corrections to the work plan and the current estimated overall completion. '-' indicates that no compensation is applied.

## WP
WP Title: |  | WP for Non-Public Networks Phase 2: NG-RAN aspects plus CT1 aspects | [10 empty] | Start of workplan status columns. Note! Do not remove this column. | WP item status |  | End of workplan columns. Note! Do not remove this column.
WI code |  | eNPN_Ph2-NGRAN_plus_CT1-UEConTest
WP Scope: |  | <WP Scope description> | [12 empty] | vs Area
WP Resp: |  | Lei GAO |  |  | gaol8@chinatelecom.cn | [5 empty] | WP item completion |  |  | SA Option 2 (SA NR)
TS Resp: |  | <TS responsible if a new TS is involved> |  |  | <Email to TS responsible>
WP Item ID | Is new test case? | TS/area | Clause | Title | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | Overall | SA Option 2 (SA NR) |  | FR1 | FR2
[14 empty] | 32% (+15%) | 32% (+15%)
[14 empty] | 12 | 12
[14 empty] | 10.5 | 10.5 (+10.5)
5%
Start of work plan items. Note! Do not remove this row. Introduce new work plan rows/items below this row.
5GS
5GS Common
TS 38.508-1: Common test environment
|  | 38.508-1 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
TBD |  | 38.508-1 | 4 | Introduction of General and Signaling Test Environment for Rel-18 eNPN Tests | Equivalent PLMN information added |  | RAN5#105 (Nov-24) |  |  | 0.5 | 0% | 0% |  | 0% | 0%
TS 38.508-2: Common ICS
|  | 38.508-2 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
TBD |  | 38.508-2 | A.4.3.7 | Introduction of common implementation conformance statements for Rel-18 eNPN Tests Cases | Add ICS as needed for the test case applicability statements for the new test cases introduced in protocol test cases. |  | RAN5#105 (Nov-24) | R5-251332 R5-253170 | localized services support | 0.5 | 60% (+40%) | 60% (+60%) |  | 60% | 60%
RAN and CN protocol
TS 38.523-1: Protocol test cases
|  | 38.523-1 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
Idle Mode
TBD | Y | 38.523-1 | 6.5.3.10 | SNPN Selection in Automatic Mode / Selecting equivalent SNPN | Test Purpose(s): <Describe test purpose(s)> |  | TBD | R5-251333 R5-253174 |  | 1 | 100% (+100%) | 100% (+100%) |  | 100% | 100%
TBD | Y | 38.523-1 | 6.5.3.11 | SNPN Selection in Automatic Mode / Access for localized services in SNPN | Test Purpose(s): <Describe test purpose(s)> |  | TBD | R5-253171 |  | 1 | 100% (+100%) | 100% (+100%) |  | 100% | 100%
TBD | Y | 38.523-1 | 6.5.3.12 | SNPN Selection in Manual Mode / Automatically Selecting equivalent SNPN | Test Purpose(s): <Describe test purpose(s)> |  | TBD |  |  | 1 | 0% | 0% |  | 0% | 0%
TBD | Y | 38.523-1 | 6.5.3.13 | SNPN Selection in Manual Mode / Access for localized services in SNPN | Test Purpose(s): <Describe test purpose(s)> |  | TBD | R5-253172 |  | 1 | 100% (+100%) | 100% (+100%) |  | 100% | 100%
TBD | Y | 38.523-1 | 6.5.3.14 | SNPN / User Reselection in Automatic Mode / Selecting equivalent SNPN | Test Purpose(s): <Describe test purpose(s)> |  | TBD |  |  | 1 | 0% | 0% |  | 0% | 0%
TBD | Y | 38.523-1 | 6.5.3.15 | SNPN / User Reselection in Automatic Mode / Access for localized services in SNPN | Test Purpose(s): <Describe test purpose(s)> |  | TBD | R5-253173 |  | 1 | 100% (+100%) | 100% (+100%) |  | 100% | 100%
TBD | Y | 38.523-1 | 6.5.3.16 | Steering of Roaming in SNPN / After registration / Security check successful / Access for localized services in SNPN | Test Purpose(s): <Describe test purpose(s)> |  | TBD |  |  | 1 | 0% | 0% |  | 0% | 0%
TBD |  | 38.523-1 | <Clause> | <Title of new test case> | Test Purpose(s): <Describe test purpose(s)> |  | TBD |  |  | 0
RRC
TBD |  | 38.523-1 | <Clause> | <Title of new sub-clause header> | New sub-clause header |  | TBD |  |  | 0
NAS
TBD | Y | 38.523-1 | 9.1.11.8 | SNPN / Initial registration / Abnormal cases in the UE / Access for localized services in current SNPN is no longer allowed | New sub-clause header |  | TBD |  |  | 1 | 0% | 0% |  | 0% | 0%
TBD | Y | 38.523-1 | 9.1.11.9 | SNPN / Mobility and periodic registration update accepted by the network / Support equivalent SNPN | <Describe required change of the existing test case> |  | TBD |  | 24.501 cl.5.5.1.3.2 | 1 | 0% | 0% |  | 0% | 0%
TBD |  | 38.523-1 | <Clause> | <Title of modified existing test case> | <Describe required change of the existing test case> |  | TBD |  |  | 0
TS 38.523-2: Applicability for Protocol test cases
TBD |  | 38.523-2 | 4 | Protocol conformance test cases applicability | Add test case applicability statements for the new test cases introduced in 38.523-1 |  | TBD | R5-251334 R5-253175 |  | 0.5 | 60% (+30%) | 60% (+30%) |  | 60% | 60%
TS 38.523-3: Protocol test suites (TTCN)
TBD |  | 38.523-3 | <Clause> | <Title of task> | <Describe task> |  | TBD |  |  | TBD
End of workplan items. Note! Do not remove this row. Introduce new work plan rows/items above this row.
Note on A6: Unique ID for WP items (unique within the sub-area work plan) Note! As WP item numbers may be referenced from outside of this WP that means: - Do not change number for WP items that have been published. - Do not re-use WP item numbers if a WP item is deleted
Note on B6: Set to Y if the WP item represents a new test case that will be specified in RAN5 test specifications as an executable test case else leave blank.
Note on K6: The WP item's weight number is used to set the reletive weights between WP items used in the overall calculation of completeness. Setting it to 0 for a WP item means that it will not be included at all in the calculation.