## Cover sheet
3GPP TSG-RAN5 Meeting #107 | [8 empty] | R5-252811
Malta, MT, 19th – 23rd May 2025
Agenda Item: | 7.5.2
Source: | Apple, CAICT, Keysight technologies
Title: | WP - Enhancement of Multiple Input Multiple Output (MIMO) Over-the-Air (OTA) test methodology and requirements for NR UEs
Work item code: | NR_MIMO_OTA_enh-UEConTest
Release: | Rel-18
Document for: | Information
RAN5 WP template v2.0-8
1. Introduction
The objective of this work plan is to track contributions towards the RAN5 test specifications enable UE conformance testing for the corresponding Rel-18 NR MIMO OTA Enhancement Work Items
2. Work item status
Estimation of WI overall completion:
Area |  | Completion | Number of new completed test cases (Note 1) | Number of new test cases | Comments
Overall completion |  | 100% | 0 | 0
Completion Compensation |  | -
| Note 1: | Only test cases completed for all applicable WP areas and sub-areas are counted. For completed test cases per WP areas and WP sub-areas see below.
Estimation WI completion per area and sub-area:
|  | Completion | Number of new completed test cases | Number of new test cases | Comments
FR1 |  | 100% | 0 | 0
FR2 |  | 100% | 0 | 0 | Only placeholder and skeleton structure added as core and test requirements are not within Rel-17 scope.
Estimation of completion per TS (area):
|  | TS overall completion |  |  | FR1 |  |  |  |  | FR2
TS/TR Scope | TS/TR | Completion | Number of new completed test cases | Number of new test cases | FR1 |  |  |  |  | FR2
[5 empty] | Completion | Number of new completed test cases | Number of new test cases |  |  | Completion | Number of new completed test cases | Number of new test cases
5GS
NR MIMO OTA requirements and test methodologies for FR1 and FR2
TS 38.551:Common Clauses 1-5 | 38.561 | 100%
TS 38.551 Clause 6 - FR1 | 38.561 | 100% | 0 | 0 | 100% |  | 0 |  |  | 100% |  | 0
TS 38.551 Clause 7 - FR2 | 38.561 | 100% | 0 | 0 |  |  | 0 |  |  |  |  | 0
TS 38.551 Annexes | 38.561 | 100%
5 References
[1] RP-241504 | New WID on UE Conformance - Enhancement of Multiple Input Multiple Output (MIMO) Over-the-Air (OTA) test methodology and requirements for NR UEs
Note on B21: Overall completion of the work item reported at an earlier meeting will not be decreased if additional tasks are added or if corrections are made to the work plan. Instead the earlier reported completion status will be kept until necessary progress have been achieved such that completion exceeds the earlier reported completion level. The value of the Completion Compensation value represents the difference in the decrease caused by late additions or corrections to the work plan and the current estimated overall completion. '-' indicates that no compensation is applied.

## WP
WP Title: |  | Enhancement of Multiple Input Multiple Output (MIMO) Over-the-Air (OTA) test methodology and requirements for NR UEs | [11 empty] | Start of workplan status columns. Note! Do not remove this column. | WP item status |  | End of workplan columns. Note! Do not remove this column.
WI code |  | NR_MIMO_OTA_enh-UEConTest
WP Scope: |  | The purpose of this document is to create and track development of test requirements and procedures for Rel-18 enhancements for FR1 and FR2 MIMO OTA
WP Resp: |  | Istvan Szini, Siting Zhou, Thorsten Hertel |  |  | Istvan@apple.com | [5 empty] | WP item completion
TS Resp: |  | Istvan Szini |  |  | Istvan@apple.com
WP Item ID | Is new test case? | TS/area | Clause | Title | Test purpose / Task | Company | Target | TDOC(s) | Comments (include where references to CTIA are included) | Weight | Overall | FR1 | FR2 |  | FR1 | FR2
[15 empty] | 100% | 100%
100%
Start of work plan items. Note! Do not remove this row. Introduce new work plan rows/items below this row.
UE Conformance - Enhancement of Multiple Input Multiple Output (MIMO) Over-the-Air (OTA) test methodology and requirements for NR Ues
TS 38.551: Scope, References, Definitions, Frequency Bands
1 |  | 38.551 | 1 | Scope |  | Apple | RAN5#107 (May-25) |  | 3GPP Defined | 0.3 | 100% | 100% | 100% | 100% | 100% | 100%
2 |  | 38.551 | 2 | References | The reference, especially of CTIA test plans, is updated to the latest active version. | Apple | RAN5#107 (May-25) |  | 3GPP Defined | 0.3 | 100% | 100% | 100% | 100% | 100% | 100%
3 |  | 38.551 | 3 | Definition of terms, symbols and abbreviations | Some Abbreviations are added | Apple | RAN5#107 (May-25) |  | 3GPP Defined | 0.3 | 100% | 100% | 100% | 100% | 100% | 100%
TS 38.551: General Information Clause
4 |  | 38.551 | 4 | General | Relationship between minimum conformance requirements and test requirements, Applicability Rules. No updates expected in Rel-18 | Apple | RAN5#107 (May-25) |  | Aligns with TR 38.151 | 0.3 | 100% | 100% | 100% | 100% | 100% | 100%
5 |  | 38.551 | 5 | Frequency Bands | Clause Header | Apple | RAN5#107 (May-25) |  | Aligns with TR 38.151 | 0.3 | 100% | 100% | 100% | 100% | 100% | 100%
6 |  | 38.551 | 6 | FR1 MIMO OTA Performance | Clause Header | Apple | RAN5#107 (May-25) |  | Aligns with TR 38.151 | 1 | 100% | 100% | 100% | 100% | 100% | 100%
7 |  | 38.551 | 7 | FR2 MIMO OTA requirements | Clause Header | Apple | RAN5#107 (May-25) |  | Aligns with TR 38.151 | 1 | 100% | 100% | 100% | 100% | 100% | 100%
38.551 Annex A : FR1 Test methodology
8 |  | 38.551 Annex A | Annex A.1 | General |  | Apple | RAN5#107 (May-25) |  | Aligns with TR 38.151 | 0.5 | 100% | 100% |  |  | 100%
9 |  | 38.551 Annex A | Annex A.2 | Multi-Probe Anechoic Chamber (MPAC) |  | Apple | RAN5#107 (May-25) |  | Aligns with TR 38.151 | 0.5 | 100% | 100% |  |  | 100%
10 |  | 38.551 Annex A | Annex A.2.1 | System setup |  | Apple | RAN5#107 (May-25) |  | Aligns with TR 38.151 | 0.5 | 100% | 100% |  |  | 100%
11 |  | 38.551 Annex A | Annex A.2.2 | Calibration procedure |  | Apple | RAN5#107 (May-25) |  | Aligns with TR 38.151 | 0.5 | 100% | 100% |  |  | 100%
12 |  | 38.551 Annex A | Annex A.2.3 | Void |  | Apple | RAN5#107 (May-25) |  | Aligns with TR 38.151 | 0 | 100% | 100% |  |  | 100%
13 |  | 38.551 Annex A | Annex A.2.4 | Minimum Range Length |  | Apple | RAN5#107 (May-25) |  | Aligns with TR 38.151 | 0.5 | 100% | 100% |  |  | 100%
14 |  | 38.551 Annex A | Annex A.3 | EUT positioning |  | Apple | RAN5#107 (May-25) |  | Aligns with TR 38.151 | 0.5 | 100% | 100% |  |  | 100%
15 |  | 38.551 Annex A | Annex A.4 | Reference coordinate system |  | Apple | RAN5#107 (May-25) |  | Aligns with TR 38.151 | 0.5 | 100% | 100% |  |  | 100%
38.551 Annex B : Estimation of FR1 measurement uncertainty
15 |  | 38.551 Annex B | Annex B.1 | MU budget of FR1 MPAC system |  | Apple | RAN5#107 (May-25) |  | Aligns with TR 38.151 | 1 | 100% | 100% |  |  | 100%
16 |  | 38.551 Annex B | Annex B.2 | Measurement error contribution descriptions for MPAC |  | Apple | RAN5#107 (May-25) |  | Aligns with TR 38.151 | 1 | 100% | 100% |  |  | 100%
38.551 Annex C : FR1 Channel models and Validation procedure
17 |  | 38.551 Annex C | Annex C.1 | FR1 Channel models |  | Apple | RAN5#107 (May-25) |  | Aligns with TR 38.151 | 1 | 100% | 100% |  |  | 100%
18 |  | 38.551 Annex C | Annex C.2 | FR1 Base Station beam configuration |  | Apple | RAN5#107 (May-25) |  | Aligns with TR 38.151 | 1 | 100% | 100% |  |  | 100%
19 |  | 38.551 Annex C | Annex C.3 | FR1 Channel model validation |  | Apple | RAN5#107 (May-25) |  | Aligns with TR 38.151 | 1 | 100% | 100%
20 |  | 38.551 Annex C | Annex C.4 | Validation Pass/fail limit |  | Apple | RAN5#107 (May-25) |  | Aligns with TR 38.151 | 1 | 100% | 100%
38.551 Annex D : FR1 gNB configurations
21 |  | 38.551 Annex D | Annex D.1 | FR1 gNB configurations |  | Apple | RAN5#107 (May-25) |  | Aligns with TR 38.151 | 0.5 | 100% | 100% |  |  | 100%
22 |  | 38.551 Annex D | Annex D.2 | FR2 gNB configurations |  | Apple | RAN5#107 (May-25) |  | Aligns with TR 38.151 | 0.5 | 100% | 100% |  |  | 100%
38.551 Annex E: Environmental requirements
23 |  | 38.551 Annex E | Annex E.1 | Scope |  | Apple | RAN5#107 (May-25) |  | Aligns with TR 38.151 | 0.3 | 100% | 100% | 100% | 100% | 100% | 100%
24 |  | 38.551 Annex E | Annex E.2 | Ambient temperature |  | Apple | RAN5#107 (May-25) |  | Aligns with TR 38.151 | 0.3 | 100% | 100% | 100% | 100% | 100% | 100%
25 |  | 38.551 Annex E | Annex E.3 | Operating voltage |  | Apple | RAN5#107 (May-25) |  | Aligns with TR 38.151 | 0.3 | 100% | 100% | 100% | 100% | 100% | 100%
38.551 Annex F: Maximum uncertainty of test system and test tolerance
26 |  | 38.551 Annex F | Annex F.1 | Maximum uncertainty of test system |  | Apple | RAN5#107 (May-25) |  | Aligns with TR 38.151 | 1 | 100% | 100% | 100% | 100% | 100% | 100%
27 |  | 38.551 Annex F | Annex F.2 | Test tolerances |  | Apple | RAN5#107 (May-25) |  | Aligns with TR 38.151 | 1 | 100% | 100% | 100% | 100% | 100% | 100%
38.551 Annex G : FR2 Test methodology
28 |  | 38.551 Annex G | Annex G.1 | General |  | Apple | RAN5#107 (May-25) |  | Aligns with TR 38.151 | 1 | 100% |  | 100% |  |  | 100%
29 |  | 38.551 Annex G | Annex G.2 | Multi-Probe Anechoic Chamber (MPAC) |  | Apple | RAN5#107 (May-25) |  | Aligns with TR 38.151 | 1 | 100% |  | 100% |  |  | 100%
30 |  | 38.551 Annex G | Annex G.2.1 | System setup |  | Apple | RAN5#107 (May-25) |  | Aligns with TR 38.151 | 1 | 100% |  | 100% |  |  | 100%
31 |  | 38.551 Annex G | Annex G.2.2 | Calibration procedure |  | Apple | RAN5#107 (May-25) |  | Aligns with TR 38.151 | 0 | 100% |  | 100% |  |  | 100%
32 |  | 38.551 Annex G | Annex G.2.3 | Void |  | Apple | RAN5#107 (May-25) |  | Aligns with TR 38.151 | 1 | 100% |  | 100% |  |  | 100%
33 |  | 38.551 Annex G | Annex G.2.4 | Minimum Range Length |  | Apple | RAN5#107 (May-25) |  | Aligns with TR 38.151 | 1 | 100% |  | 100% |  |  | 100%
34 |  | 38.551 Annex G | Annex G.2.5 | Sample Device Orientations for Selected Test Points |  | Apple | RAN5#107 (May-25) |  | Aligns with TR 38.152 | 1 | 100% |  | 100% |  |  | 100%
35 |  | 38.551 Annex G | Annex G.3 | Coordinate System and Device positioning |  | Apple | RAN5#107 (May-25) |  | Aligns with TR 38.153 | 1 | 100% |  | 100% |  |  | 100%
38.551 Annex H : Estimation of FR2 measurement uncertainty
36 |  | 38.551 Annex H | Annex H.1 | MU budget of FR2 MPAC system |  | Apple | RAN5#107 (May-25) |  |  | 1 | 100% |  | 100% |  |  | 100%
37 |  | 38.551 Annex H | Annex H.2 | Measurement error contribution descriptions for MPAC |  | Apple | RAN5#107 (May-25) |  |  | 1 | 100% |  | 100% |  |  | 100%
38.551 Annex I : FR2 Channel models and Validation procedure
38 |  | 38.551 Annex I | Annex I.1 | FR1 Channel models |  | Apple | RAN5#107 (May-25) |  | Aligns with TR 38.151 | 1 | 100% |  | 100% |  |  | 100%
39 |  | 38.551 Annex I | Annex I.2 | FR1 Base Station beam configuration |  | Apple | RAN5#107 (May-25) |  | Aligns with TR 38.151 | 1 | 100% |  | 100% |  |  | 100%
40 |  | 38.551 Annex I | Annex I.3 | FR1 Channel model validation |  | Apple | RAN5#107 (May-25) |  | Aligns with TR 38.151 | 1 | 100% |  | 100% |  |  | 100%
41 |  | 38.551 Annex I | Annex I.4 | Validation Pass/fail limit |  | Apple | RAN5#107 (May-25) |  | Aligns with TR 38.151 | 1 | 100% |  | 100% |  |  | 100%
End of workplan items. Note! Do not remove this row. Introduce new work plan rows/items above this row.
|  |  | NOTE 1 | Only placeholder and skeleton structure added as no test requirements are in Rel-18 WID scope
Note on A6: Unique ID for WP items (unique within the sub-area work plan) Note! As WP item numbers may be referenced from outside of this WP that means: - Do not change number for WP items that have been published. - Do not re-use WP item numbers if a WP item is deleted
Note on B6: Set to Y if the WP item represents a new test case that will be specified in RAN5 test specifications as an executable test case else leave blank.
Note on K6: The WP item's weight number is used to set the reletive weights between WP items used in the overall calculation of completeness. Setting it to 0 for a WP item means that it will not be included at all in the calculation.

## Agreed_RAN4_CRs_Rel-18_NR_MIMO
TDoc# | CR title | Contributor | RAN4 meeting# | Summary of change | RAN4 Clauses Impacted
R4-2411245 | Clarification of voltage environmental requirement | Keysight Technologies UK Ltd, MVG, Rohde & Schwarz, ETS-Lindgren | 112 | The voltage environmental requirement is properly clarified to be performed at normal condition and not at extreme conditions. | 38.151, clause F.3
R4-2505848 | Correction of SCF CM Validation Frequency for n3 and corresponding reference values and limits | Keysight Technologies UK Ltd | 115 | The SCF validation frequency was changed from 1800MHz to 1880MHz. With it, the refernce vales and limits were corrected | 38.151, clauses C.3.4 and C.4.4