## WP scope
Work plan for introduction of NR CA PC2 FR1 configurations into 3GPP UE conformance test specifications
| WP template: | WP NR CA PC1.5 FR1 v1.12.0
Note! A copy of this work plan shall be included in a Completion Declaration Statement (CDS) to be submitted as a TDOC to the RAN5 meeting when the configuration(s) are completed.
Workplan scope
| Workplan Name |  | WP NR CA PC1.5 TDD FR1 Verizon after RAN5#107 | [6 empty] | <= Default workplan name is the filename. To change replace the formula with preferred text.
| Company (Contact) | [8 empty] | <= Enter Responsible Company and Contact for the configurations in the WP
| Target completion |  | RAN5#107 | [6 empty] | <= Enter target completion date here. Format RAN5#<xx>, where <xx> is the RAN5 meeting, e.g. RAN5#94-e>
Comments
| Overall completion |  | 100%
| Note |  | Only TDD PC1.5 NR bands have been defined and included in this WP template
Target configurations
Note: A work plan can include multiple target configurations but it is recommended to create separate work plans for Intra-band continuous, Intra-band Non-Continuous and Inter-band configurations. Copy target configuration(s) for the WP from the "PRD21 NR bands and 5G NR CADC list" as values in the table below by: 1. Select and copy the complete rows of the target configuration(s) in the "PRD21 NR bands and 5G NR CADC list". 2. Select cell A15 in the table below and right-click. 3. Select paste option "Paste as values" (see picture). It may take a few seconds before the pasted information is shown. 4. To include additional configurations, repeat steps 1 to 3, but in step 2 select the cell in column A next below the last configuration in the list.
Marked config | Release introduced in TS 38.101-x | Type of configuration | TS and Source Table | Configuration | Uplink configuration | PC1.5 Status | PC2 completed? | RAN5 Completion Meeting (PC3) | Completion Reference (PC3) | Interested operator (PC1.5) | Responsible Company (contact) (PC1.5) | Assignment [RAN5 meeting] (PC3) | Applicable RAN5 WI code(s) for CRs | Comments | Introduced in PRD version
| Rel-17 | NR CA FR1 inter-band (2 bands) | 38.101-1:Table 5.5A.3.1-1b | CA_n2A-n77A | n77 PC1.5 | onglong |  |  |  | AT&T, Verizon | Verizon (jinwen.ma@verizonwireless.com) | RAN5#107 |  |  | v.1.0.0
| Rel-17 | NR CA FR1 inter-band (2 bands) | 38.101-1:Table 5.5A.3.1-1d | CA_n5A-n77A | n77 PC1.5 | Ongoing |  |  |  | AT&T, Verizon | Verizon (jinwen.ma@verizonwireless.com) | RAN5#107 |  |  | v.1.0.0
| Rel-17 | NR CA FR1 inter-band (2 bands) | 38.101-1:Table 5.5A.3.1-1l | CA_n48A-n77A | n77 PC1.5 | Ongoing |  |  |  | Boost Mobile Network | Boost Mobile Network (wuri.hapsari@dish.com) | RAN5#107
| Rel-17 | NR CA FR1 inter-band (2 bands) | 38.101-1:Table 5.5A.3.1-1m | CA_n66A-n77A | n77 PC1.5 | Ongoing |  |  |  | AT&T, Verizon | Verizon (jinwen.ma@verizonwireless.com) | RAN5#107
| Rel-17 | NR CA FR1 inter-band (3 bands) | 38.101-1:Table 5.5A.3.2-1 | CA_n2A-n5A-n77A | n77 PC1.5 | Ongoing |  |  |  | AT&T, Verizon | Verizon (jinwen.ma@verizonwireless.com) | RAN5#107
| Rel-17 | NR CA FR1 inter-band (3 bands) | 38.101-1:Table 5.5A.3.2-1 | CA_n2A-n66A-n77A | n77 PC1.5 | Ongoing |  |  |  | AT&T, Verizon | Verizon (jinwen.ma@verizonwireless.com) | RAN5#107
| Rel-17 | NR CA FR1 inter-band (3 bands) | 38.101-1:Table 5.5A.3.2-1 | CA_n5A-n66A-n77A | n77 PC1.5 | Ongoing |  |  |  | AT&T, Verizon | Verizon (jinwen.ma@verizonwireless.com) | RAN5#107
| Rel-17 | NR CA FR1 inter-band (3 bands) | 38.101-1:Table 5.5A.3.2-1 | CA_n2A-n48A-n77A | n77 PC1.5 | Ongoing |  |  |  | Verizon | Verizon (jinwen.ma@verizonwireless.com) | RAN5#107
| Rel-17 | NR CA FR1 inter-band (3 bands) | 38.101-1:Table 5.5A.3.2-1 | CA_n5A-n48A-n77A | n77 PC1.5 | Ongoing |  |  |  | Verizon | Verizon (jinwen.ma@verizonwireless.com) | RAN5#107
| Rel-17 | NR CA FR1 inter-band (3 bands) | 38.101-1:Table 5.5A.3.2-1 | CA_n48A-n66A-n77A | n77 PC1.5 | Ongoing |  |  |  | Boost Mobile Network | Boost Mobile Network (wuri.hapsari@dish.com) | RAN5#107

## WP NR CA PC1.5 FR1
Work plan for introduction of NR CA PC2 FR1 configurations into 3GPP UE conformance test specifications
Note! A copy of this work plan shall be included in a Completion Declaration Statement (CDS) to be submitted as a TDOC to the RAN5 meeting when the configuration(s) are completed. | [13 empty] | WP template: WP NR CA PC1.5 FR1 v1.12.0
1. Configurations covered by the work plan
|  | Type of CA configurations |  |  |  | WP item Applicability Label | CA configurations [DL/UL]
|  | New NR CA configuration with UL CA |  |  |  | DL/UL BCS0 | CA_n2A-n77A/n77 PC1.5, CA_n5A-n77A/n77 PC1.5, CA_n48A-n77A/n77 PC1.5, CA_n66A-n77A/n77 PC1.5, CA_n2A-n5A-n77A/n77 PC1.5, CA_n2A-n66A-n77A/n77 PC1.5, CA_n5A-n66A-n77A/n77 PC1.5, CA_n2A-n48A-n77A/n77 PC1.5, CA_n5A-n48A-n77A/n77 PC1.5, CA_n48A-n66A-n77A/n77 PC1.5
|  | New BCS for NR CA configuration with UL CA |  |  |  | DL/UL new BCS
|  | All configurations |  |  |  | All | CA_n2A-n77A/n77 PC1.5, CA_n5A-n77A/n77 PC1.5, CA_n48A-n77A/n77 PC1.5, CA_n66A-n77A/n77 PC1.5, CA_n2A-n5A-n77A/n77 PC1.5, CA_n2A-n66A-n77A/n77 PC1.5, CA_n5A-n66A-n77A/n77 PC1.5, CA_n2A-n48A-n77A/n77 PC1.5, CA_n5A-n48A-n77A/n77 PC1.5, CA_n48A-n66A-n77A/n77 PC1.5
|  | All BCS0 configurations (No BCS included in config.name) |  |  |  | All BCS0 | CA_n2A-n77A/n77 PC1.5, CA_n5A-n77A/n77 PC1.5, CA_n48A-n77A/n77 PC1.5, CA_n66A-n77A/n77 PC1.5, CA_n2A-n5A-n77A/n77 PC1.5, CA_n2A-n66A-n77A/n77 PC1.5, CA_n5A-n66A-n77A/n77 PC1.5, CA_n2A-n48A-n77A/n77 PC1.5, CA_n5A-n48A-n77A/n77 PC1.5, CA_n48A-n66A-n77A/n77 PC1.5
|  | All new BCS configurations with BCS>0 |  |  |  | All new BCS
2. Overall status vs WP steps
[7 empty] | Overall Sub-WI |  | Handling of not applicable WP item rows: - WP item rows not applicable for the target configurations are indicated as being strikethrough text. You can hide those not applicable WP items by filtering on excluding "(Blanks)" in column "Impacted config(s)". - Some WP items may still not be applicable for the target configurations based on the applicability information in the "Task" column. To NOT include those WP items in the overall status calculations You need to clear the "Detailed Completion Status" cells for the WP item row and state "N/A" in the comments field. Note: It is not recomended to completly delete not applicable WP item rows in case additional target configurations added at a later stage may require those WP Item rows.
|  | Overall completeness |  |  |  |  | 100%
|  | Step 1: Work plan pre-requisite |  |  |  |  | 100%
|  | Step 2: Complete Test Point (TP) analysis for impacted NR CA configurations |  |  |  |  | 100%
Step 3.1: CR(s) to common test environment (TS 38.508-1)
Step 3.2: CR(s) to common clauses for RF / Performance testing area (TS 38.521-1)
|  | Step 3.3: CR(s) for RF transmitter test cases (TS 38.521-1, clause 6) |  |  |  |  | 100%
|  | Step 3.4: CR(s) for RF receiver test cases (TS 38.521-1, clause 7) |  |  |  |  | #DIV/0!
Step 3.5: CR(s) for RF Performance test cases (TS 38.521-4)
Step 3.6: CRs to protocol test cases (TS 38.523-1, TS 38.523-2)
Step 4: CR(s) for new ICS/capabilities (TS 38.508-2)
3. Details
Do not edit | [7 empty] | WP item columns to be filled in |  |  |  | Do not edit |  |  | WP item columns to be filled in
Step 1: Work plan pre-requisite
WP item applicability | WP item ID | Area | TS/PRD | TC / Clause Number | Description / Title | Impacted config(s) [DL/UL] | Task | Company | Target | TDOC(s) | Comments | Weight | Item Overall Completeness |  | Detailed Completion Status per area
[15 empty] | PC3 completed | PC2 completed
[15 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1
All BCS0 | 1-1 | Pre-requisite | PRD21 | 5G NR CADC Configurations worksheet | Corresponding configuration completed for PC3 and PC2 | CA_n2A-n77A/n77 PC1.5, CA_n5A-n77A/n77 PC1.5, CA_n48A-n77A/n77 PC1.5, CA_n66A-n77A/n77 PC1.5, CA_n2A-n5A-n77A/n77 PC1.5, CA_n2A-n66A-n77A/n77 PC1.5, CA_n5A-n66A-n77A/n77 PC1.5, CA_n2A-n48A-n77A/n77 PC1.5, CA_n5A-n48A-n77A/n77 PC1.5, CA_n48A-n66A-n77A/n77 PC1.5 | Set status in column "PC3 completed" and "PC2 completed" to 100% when all impacted item have been confirmed completed in RAN5 PRD21 worksheet "5G NR CADC Configurations worksheet". |  | RAN5#107 |  |  | 1 | 100% |  | 100% | 100%
All new BCS | 1-2 | Pre-requisite | PRD21 | 5G NR CADC Configurations worksheet | Corresponding configuration completed for PC3 |  | Set status in column "PC3 completed" to 100% when all impacted item have been confirmed completed in RAN5 PRD21 worksheet "5G NR CADC Configurations worksheet". |  | RAN5#107 |  |  | 1 |  |  | 0%
End list sub-area WP items (insert any additional WP items for this area above this row)
Step 2: Complete Test Point (TP) analysis for impacted NR CA configurations
WP item applicability | WP item ID | Area | TR | TC / Clause Number | Description / Title | Impacted CA config(s) [UDL/UL] | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | Item Overall Completeness |  | Detailed Completion Status per area
TP analysis
[15 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1
All | 2-1 | TP Analysis | 38.905 | 4.1.2 | Test point (TP) analysis for A-MPR | CA_n2A-n77A/n77 PC1.5, CA_n5A-n77A/n77 PC1.5, CA_n48A-n77A/n77 PC1.5, CA_n66A-n77A/n77 PC1.5, CA_n2A-n5A-n77A/n77 PC1.5, CA_n2A-n66A-n77A/n77 PC1.5, CA_n5A-n66A-n77A/n77 PC1.5, CA_n2A-n48A-n77A/n77 PC1.5, CA_n5A-n48A-n77A/n77 PC1.5, CA_n48A-n66A-n77A/n77 PC1.5 | For each UL CA configuration perform an A-MPR TP analysis as described in TR 38.905 clause 4.1.2 for intra-band contiguous UL CA and in clause 4.1.3 for inter-band UL CA. The TP analysis is documented by a CR to 38.905 clause 4.1.x including the details of the TP analysis in an attached zip-file. The status column "TP analysis" is set to 100% when all required A-MPR TP analysis have been included in TR 38.905. |  | RAN5#107 | R5-252026 | Update the Table 4.1.3.1-2: Reference Sensitivity test cases per CA configuration (two bands), for related PC1.5 cases | 1 | 100% |  | 100%
End list sub-area WP items (insert any additional WP items for this area above this row)
Step 3: CRs to impacted TSs areas
Step 3.1: CR(s) to common test environment (TS 38.508-1)
WP item applicability | WP item ID | Area | TS | TC / Clause Number | Description / Title | Impacted CA config(s) [UDL/UL] | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | Item Overall Completeness |  | Detailed Completion Status per area
Test Freq.
1
| 3.1-1 | [5 empty] | No changes needed |  | RAN5#107 |  |  | 1 |  |  | 0%
End list sub-area WP items (insert any additional WP items for this area above this row)
Step 3.2: CR(s) to common clauses for RF / Performance testing area (TS 38.521-1)
WP item applicability | WP item ID | Area | TS/PRD | TC / Clause Number | Description / Title | Impacted CA config(s) [UDL/UL] | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | Item Overall Completeness |  | Detailed Completion Status per area
[15 empty] | Discussion paper | Clause 7
[15 empty] | 1 | 1
All | 3.2-1 | 38.521-1 - General | PRD21 | 4.1 | Discussion paper on adding configuration to chapter 5 without changes to RF transmitter and receiver test cases. | CA_n2A-n77A/n77 PC1.5, CA_n5A-n77A/n77 PC1.5, CA_n48A-n77A/n77 PC1.5, CA_n66A-n77A/n77 PC1.5, CA_n2A-n5A-n77A/n77 PC1.5, CA_n2A-n66A-n77A/n77 PC1.5, CA_n5A-n66A-n77A/n77 PC1.5, CA_n2A-n48A-n77A/n77 PC1.5, CA_n5A-n48A-n77A/n77 PC1.5, CA_n48A-n66A-n77A/n77 PC1.5 | If it is thought there are no configuration specific changes needed for Chapter 6/7, a paper shall be submitted to justify why no such changes are needed to Chapter 6/7. If deemed that no discussion paper is needed then set status to 100% and add comment in the comments column why no discussion paper is needed. |  | RAN5#107 |  | No discussion needed | 1 | 100% |  | 100%
End list sub-area WP items (insert any additional WP items for this area above this row)
Step 3.x: CR(s) for RF transmitter test cases (TS 38.521-1, clause 5)
All | THIS STEP SHOULD BE INCLUDED INTO prd21 FORMAT | 38.521-1 CH5 | 38.521-1 | 5.5A.3 | Related UL PC1.5 configurations should be included into the corresponding band configuration tables | CA_n2A-n77A/n77 PC1.5, CA_n5A-n77A/n77 PC1.5, CA_n48A-n77A/n77 PC1.5, CA_n66A-n77A/n77 PC1.5, CA_n2A-n5A-n77A/n77 PC1.5, CA_n2A-n66A-n77A/n77 PC1.5, CA_n5A-n66A-n77A/n77 PC1.5, CA_n2A-n48A-n77A/n77 PC1.5, CA_n5A-n48A-n77A/n77 PC1.5, CA_n48A-n66A-n77A/n77 PC1.5 | Related UL PC1.5 configurations should be included into the corresponding band configuration tables |  | RAN5#107 | R5-252171 | Update the following tables •Table 5.5A.3.1-1: NR CA configurations and bandwidth combinations sets defined for inter-band CA (two bands) •Table 5.5A.3.2-1: NR CA configurations and bandwidth combinations sets defined for inter-band CA (three bands) |  | 100% |  | 100%
Step 3.3: CR(s) for RF transmitter test cases (TS 38.521-1, clause 6)
WP item applicability | WP item ID | Area | TS | TC / Clause Number | Description / Title | Impacted CA config(s) [UDL/UL] | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | Item Overall Completeness |  | Detailed Completion Status per area
[15 empty] | Min. Req. | Test proc. | Test Pts | Test Req |  |  | Other Areas
[15 empty] | 1 | 5 | 5 | 2 |  |  | 2
All | 3.3-1 | 38.521-1- RF Tx | 38.521-1 | 6.2G.1 | UE maximum output power for Tx Diversity | CA_n2A-n77A/n77 PC1.5, CA_n5A-n77A/n77 PC1.5, CA_n48A-n77A/n77 PC1.5, CA_n66A-n77A/n77 PC1.5, CA_n2A-n5A-n77A/n77 PC1.5, CA_n2A-n66A-n77A/n77 PC1.5, CA_n5A-n66A-n77A/n77 PC1.5, CA_n2A-n48A-n77A/n77 PC1.5, CA_n5A-n48A-n77A/n77 PC1.5, CA_n48A-n66A-n77A/n77 PC1.5 | For configurations including any PC1.5 UL CA CCs add the UE maximum output power for UL CA to Table 6.2G.1.3-1. |  | RAN5#107 |  | n77 PC1.5 has already defined in Table 6.2G.1.3-1: UE Power Class | 1 | 100% |  | 100%
All | 3.3-2 | 38.521-1- RF Tx | 38.521-1 | 6.2G.3 | UE additional maximum output power reduction for Tx Diversity Note! This WP item is dependent [UDL/UL] on A-MPR TP analysis (Step 2, WP item 2-1) | CA_n2A-n77A/n77 PC1.5, CA_n5A-n77A/n77 PC1.5, CA_n48A-n77A/n77 PC1.5, CA_n66A-n77A/n77 PC1.5, CA_n2A-n5A-n77A/n77 PC1.5, CA_n2A-n66A-n77A/n77 PC1.5, CA_n5A-n66A-n77A/n77 PC1.5, CA_n2A-n48A-n77A/n77 PC1.5, CA_n5A-n48A-n77A/n77 PC1.5, CA_n48A-n66A-n77A/n77 PC1.5 | For configurations with specific PC1.5 A-MPR requirements add the Initial Conditions and Test requirement. |  | RAN5#107 |  | no related A-MPR requirement for n77 PC1.5 | 1
All | 3.3-3 | 38.521-1- RF Tx | 38.521-1 | 6.5G.2.2 | Additional spectrum emission mask for Tx Diversity | CA_n2A-n77A/n77 PC1.5, CA_n5A-n77A/n77 PC1.5, CA_n48A-n77A/n77 PC1.5, CA_n66A-n77A/n77 PC1.5, CA_n2A-n5A-n77A/n77 PC1.5, CA_n2A-n66A-n77A/n77 PC1.5, CA_n5A-n66A-n77A/n77 PC1.5, CA_n2A-n48A-n77A/n77 PC1.5, CA_n5A-n48A-n77A/n77 PC1.5, CA_n48A-n66A-n77A/n77 PC1.5 | For configurations with specific PC1.5 A-MPR requirements related to A-SEM: - For initial condition, align the tes configuration with A-MPR - Add test requirement |  | RAN5#107 |  | no related A-MPR requirement for n77 PC1.5 | 1
All | 3.3-4 | 38.521-1- RF Tx | 38.521-1 | 6.5G.3.3 | Additional spurious emissions for Tx Diversity | CA_n2A-n77A/n77 PC1.5, CA_n5A-n77A/n77 PC1.5, CA_n48A-n77A/n77 PC1.5, CA_n66A-n77A/n77 PC1.5, CA_n2A-n5A-n77A/n77 PC1.5, CA_n2A-n66A-n77A/n77 PC1.5, CA_n5A-n66A-n77A/n77 PC1.5, CA_n2A-n48A-n77A/n77 PC1.5, CA_n5A-n48A-n77A/n77 PC1.5, CA_n48A-n66A-n77A/n77 PC1.5 | For configurations with specific PC1.5 A-MPR requirements related to A-SE: - For initial condition, align the tes configuration with A-MPR - Add test requirement |  | RAN5#107 |  | no related A-MPR requirement for n77 PC1.5 | 1
End list sub-area WP items (insert any additional WP items for this area above this row)
Step 3.4: CR(s) for RF receiver test cases (TS 38.521-1, clause 7)
WP item applicability | WP item ID | Area | TS | TC / Clause Number | Description / Title | Impacted CA config(s) [UDL/UL] | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | Item Overall Completeness |  | Detailed Completion Status per area
[15 empty] | Min. Req. | Test proc. | Test Pts | Test Req |  |  | Other Areas
[15 empty] | 1 | 5 | 5 | 2 |  |  | 2
| 3.4-1 | [5 empty] | No changes needed |  | RAN5#107 |  |  | 1 | [5 empty] | 0%
| 7.3A | [5 empty] | All ref sense parts need test point analysis for impacted PC1.5 cases |  | RAN5#107 | R5-253424 | Update the following tables for a few band configurations with PC1.5 single UL of n77: • Table 7.3A.0.4-4d: Reference sensitivity exceptions and uplink/downlink configurations due to harmonic mixing from a PC1.5 aggressor NR UL band • Table 7.3A.0.6-3b: Reference sensitivity exceptions (MSD) and uplink/downlink configurations due to cross band isolation from a PC1.5 aggressor NR single UL band for DL NR CA FR1 • Table 7.3A.1_1.4.1-1: Test Configuration Table for inter-band 2DL CA exceptions • Table 7.3A.1_1.5-1b: Reference sensitivity requirement for inter band CA with PC1.5 single UL carrier or PC1.5 2UL CA In addition, minor editorial changes for the following tables: • Table 7.3A.0.5-1a: 2DL/2UL interband Reference sensitivity QPSK PREFSENS and uplink/downlink configurations for PC2 CA • Table 7.3A.0.6-3a: Reference sensitivity exceptions (MSD) and uplink/downlink configurations due to cross band isolation from a PC2 aggressor NR Also, remake the changes for RAN5 agreed CR R5-233712, PC2 part of test ID 6 in Table 7.3A.1_1.4.1-1 and Table 7.3A.1_1.5-1b for CA_n66A-n77A, which wasn’t implemented. |  | 100% |  | 100% |  | 100% | 100%
End list sub-area WP items (insert any additional WP items for this area above this row)
Step 3.5: CR(s) for RF Performance test cases (TS 38.521-4)
WP item applicability | WP item ID | Area | TS | TC / Clause Number | Description / Title | Impacted CA config(s) [UDL/UL] | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | Item Overall Completeness |  | Detailed Completion Status per area
[15 empty] | Min. Req. | Test proc. | Test Pts | Test Req |  |  | Other Areas
[15 empty] | 1 | 5 | 5 | 2 |  |  | 2
| 3.5-1 | [5 empty] | No changes needed |  | RAN5#107 |  |  | 1
End list sub-area WP items (insert any additional WP items for this area above this row)
Step 3.6: CRs to protocol test cases (TS 38.523-1, TS 38.523-2)
WP item applicability | WP item ID | Area | TS | TC / Clause Number | Description / Title | Impacted CA config(s) [UDL/UL] | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | Item Overall Completeness |  | Detailed Completion Status per area
ICS / TC appli.
1
| 3.6-1 | [5 empty] | No changes needed |  | RAN5#107 |  |  | 1
End list sub-area WP items (insert any additional WP items for this area above this row)
Step 4: CR(s) for new ICS/capabilities (TS 38.508-2)
WP item applicability | WP item ID | Area | TS | TC / Clause Number | Description / Title | Impacted CA config(s) [UDL/UL] | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | Item Overall Completeness |  | Detailed Completion Status per area
ICS / TC appli.
1
All | 4-1 | 38.508-2 - ICS | 38.508-2 | Annex A.4.3.2A.2.1 | NR CA Intra-band contiguous | CA_n2A-n77A/n77 PC1.5, CA_n5A-n77A/n77 PC1.5, CA_n48A-n77A/n77 PC1.5, CA_n66A-n77A/n77 PC1.5, CA_n2A-n5A-n77A/n77 PC1.5, CA_n2A-n66A-n77A/n77 PC1.5, CA_n5A-n66A-n77A/n77 PC1.5, CA_n2A-n48A-n77A/n77 PC1.5, CA_n5A-n48A-n77A/n77 PC1.5, CA_n48A-n66A-n77A/n77 PC1.5 | Add PC1.5 indication for Intra-band contiguous CA within FR1 to the relevant table in clause A.4.3.2A.2.1 |  | RAN5#107 |  | NA | 1
All | 4-2 | 38.508-2 - ICS | 38.508-2 | Annex A.4.3.2A.3.1 | NR CA Intra-band non-contiguous | CA_n2A-n77A/n77 PC1.5, CA_n5A-n77A/n77 PC1.5, CA_n48A-n77A/n77 PC1.5, CA_n66A-n77A/n77 PC1.5, CA_n2A-n5A-n77A/n77 PC1.5, CA_n2A-n66A-n77A/n77 PC1.5, CA_n5A-n66A-n77A/n77 PC1.5, CA_n2A-n48A-n77A/n77 PC1.5, CA_n5A-n48A-n77A/n77 PC1.5, CA_n48A-n66A-n77A/n77 PC1.5 | Add PC1.5 indication for NR Intra-band non-contiguous CA within FR1 to the relevant table in clause A.4.3.2A.3.1 |  | RAN5#107 |  | NA | 1
All | 4-3 | 38.508-2 - ICS | 38.508-2 | Annex A.4.3.2A.4 | NR Inter-band CA | CA_n2A-n77A/n77 PC1.5, CA_n5A-n77A/n77 PC1.5, CA_n48A-n77A/n77 PC1.5, CA_n66A-n77A/n77 PC1.5, CA_n2A-n5A-n77A/n77 PC1.5, CA_n2A-n66A-n77A/n77 PC1.5, CA_n5A-n66A-n77A/n77 PC1.5, CA_n2A-n48A-n77A/n77 PC1.5, CA_n5A-n48A-n77A/n77 PC1.5, CA_n48A-n66A-n77A/n77 PC1.5 | Add PC1.5 indication for NR Inter-band CA within FR1 to the relevant table in clause A.4.3.2A.4 |  | RAN5#107 |  | not relevant for single UL PC1.5 | 1
End list sub-area WP items (insert any additional WP items for this area above this row)
Note on N29: Used to calculate item's relative impact on work item's completeness. Should be set from a WI overall perspective. Default value is 1.
Note on N37: Used to calculate item's relative impact on work item's completeness. Should be set from a WI overall perspective. Default value is 1.
Note on N45: Used to calculate item's relative impact on work item's completeness. Should be set from a WI overall perspective. Default value is 1. If a more work intesive item is added set to value >1.
Note on N52: Used to calculate item's relative impact on work item's completeness. Should be set from a WI overall perspective. Default value is 1.
Note on N62: Used to calculate item's relative impact on work item's completeness. Should be set from a WI overall perspective. Default value is 1.
Note on N72: Used to calculate item's relative impact on work item's completeness. Should be set from a WI overall perspective. Default value is 1.
Note on N80: Used to calculate item's relative impact on work item's completeness. Should be set from a WI overall perspective. Default value is 1.
Note on N87: Used to calculate item's relative impact on work item's completeness. Should be set from a WI overall perspective. Default value is 1.
Note on N94: Used to calculate item's relative impact on work item's completeness. Should be set from a WI overall perspective. Default value is 1.

## Revision History WP template
Revision history for WP template only Note! Cell A3 shall always include the version of the latest version of the WP as used to set the WP template version in the WP scope worksheet.
Version | Date | Comment
v1.12.0 | RAN5#106 | No changes. Same as v1.11.0.
v1.11.0 | RAN5#105 | Editorial correction to WP template name in the WP scope sheet
v1.10.0 | RAN5#104 | No changes. Same as v1.9.0.
v1.9.0 | RAN5#103 | No changes. Same as v1.8.0.
v1.8.0 | RAN5#102 | No changes. Same as v1.7.0.
v1.7.0 | RAN5#101 | No changes. Same as v1.6.0.
v1.6.0 | RAN5#100 | No changes. Same as v1.5.0.
v1.5.0 | RAN5#99 | Initial version for WP NR CA PC1.5 FR1