## Cover sheet
3GPP TSG-RAN WG5 Meeting #107 | [7 empty] | R5-252406
St. Julian's, Malta, May 19th - May 23rd, 2025
Agenda Item: | 5.5.1.13
Source: | EchoStar
Title: | WP for variable Tx-Rx spacing conformance specs for IoT NTN bands
Work item code: | TEI18_Test
Release: | Rel-18
Document for: | Endorsement
RAN5 WP template v3.0.0
1. Introduction
<Description of work item and its scope>
2. Work item status
Estimation of WI overall completion:
Area |  | Completion | Number of new completed test cases (Note 1) | Number of new test cases | Comments
Overall completion
Completion Compensation |  | -
| Note 1: | Only test cases completed for all applicable WP areas and sub-areas are counted. For completed test cases per WP areas and WP sub-areas see below.
Estimation WI completion per area and sub-area:
|  | Completion | Number of new completed test cases | Number of new test cases | Comments
LTE (FDD)
FDD
Estimation of completion per TS (area):
|  | TS/TR overall completion |  |  | LTE
TS/TR Scope | TS/TR | Completion | Number of new completed test cases | Number of new test cases | FDD
[5 empty] | Completion | Number of new completed test cases | Number of new test cases
LTE
LTE Common
Common test environment | 36.508
UE specific test functions | 36.509
LTE RF/RRM
RF common parts | 36.521-1
RF Rx test cases | 36.521-1 Rx
RF Tx test cases | 36.521-1 Tx
RF Demod test cases | 36.521-1 Demod
Applicability RF. Demod/QSI and RRM test cases | 36.521-2
RRM test cases | 36.521-3
Test Tolerances analysis RRM test cases | 36.903
Test Tolerances analysis receiver test cases | 36.904
Test Point analysis receiver and transmitter test cases | 36.905
LTE RAN and CN protocols
Protocol test cases | 36.523-1
Applicability Protocol test cases | 36.523-2
Test suites (TTCN) | 36.523-3
5GS
5GS Common
Common test environment | 38.508-1
Common ICS | 38.508-2
UE specific test functions | 38.509
NR RF/RRM
FR1 RF common parts | 38.521-1
FR1 RF Tx test cases | 38.521-1 Tx
FR1 RF Rx test cases | 38.521-1 Rx
FR2 RF common parts | 38.521-2
FR2 RF Tx test cases | 38.521-2 Tx
FR2 RF Rx test cases | 38.521-2 Rx
FR1 and FR2 Interworking operation with other radios RF common parts | 38.521-3
FR1 and FR2 Interworking operation with other radios RF Tx test cases | 38.521-3 Tx
FR1 and FR2 Interworking operation with other radios RF Rx test cases | 38.521-3 Rx
RF Demod/QSI test cases | 38.521-4
RRM test cases | 38.533
Applicability RF. Demod/QSI and RRM test cases | 38.522
Test Tolerances analysis RRM and RF Rx test cases | 38.903
Test Point analysis receiver and transmitter test cases | 38.905
5GS RAN and CN protocols
Protocol test cases | 38.523-1
Applicability Protocol test cases | 38.523-2
Test suites (TTCN) | 38.523-3
UE Positioning
UE Positioning Min. Performance test cases | 37.571-1
UE Positioning Protocol test cases | 37.571-2
Applicability and ICS UE Positioning test cases | 37.571-3
UE Positioning Test sutes (TTCN) | 37.571-4
UE Positioning test scenarios and assistance data | 37.571-5
IMS
IMS over LTE protocol test cases | 34.229-1
IMS over 5GS protocol test cases | 34.229-5
Applicability and ICS IMS test cases | 34.229-2
IMS Test suite (TTCN) | 34.229-3
Mission Critical Services
MC Common test environment | 36.579-1
MCPTT UE test cases | 36.579-2
MC Server Application test cases | 36.579-3
Applicability and ICS MC test cases | 36.579-4
MC Test suite (TTCN) | 36.579-5
MC Video UE test cases | 36.579-6
MC Data UE test cases | 36.579-7
5 References
[1] RP-250600 | RAN4 CRs to Maintenance for Closed WIs/SIs for REL-18 and earlier – Batch 23
Note on B21: Overall completion of the work item reported at an earlier meeting will not be decreased if additional tasks are added or if corrections are made to the work plan. Instead the earlier reported completion status will be kept until necessary progress have been achieved such that completion exceeds the earlier reported completion level. The value of the Completion Compensation value represents the difference in the decrease caused by late additions or corrections to the work plan and the current estimated overall completion. '-' indicates that no compensation is applied.

## WP
WP Title: |  | WP for variable Tx-Rx spacing conformance specs for IoT NTN bands | [10 empty] | Start of workplan status columns. Note! Do not remove this column. | WP item status | End of workplan columns. Note! Do not remove this column.
WI code |  | TEI18_Test
WP Scope: |  | Make necessary updates to RF and Signalling Conformance Specs related to variable Tx-Rx spacing requirements specified in the core specifications of IoT NTN (36.102)
WP Resp: |  | Ojas Choksi |  |  | ojas.choksi@echostar.com | [5 empty] | WP item completion |  |  | LTE
TS Resp: |  | <TS responsible if a new TS is involved> |  |  | <Email to TS responsible>
WP Item ID | Is new test case? | TS/area | Clause | Title | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | Overall | LTE |  | FDD
0
0
5%
Start of work plan items. Note! Do not remove this row. Introduce new work plan rows/items below this row.
LTE
LTE Common
TS 36.508: Common test environment
|  | 36.508 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected).
1 |  | 36.508 | 4.3.1.1.253 | FDD reference test frequencies for operating band 253 |  |  | RAN5#109 (Oct-25) |  |  | 0.1
2 |  | 36.508 | 4.3.1.1.254 | FDD reference test frequencies for operating band 254 |  |  | RAN5#109 (Oct-25) |  |  | 0.1
3 |  | 36.508 | 4.3.1.1.255 | FDD reference test frequencies for operating band 255 |  |  | RAN5#109 (Oct-25) |  |  | 0.1
4 |  | 36.508 | 4.3.1.1.256 | FDD reference test frequencies for operating band 256 | Addition of RF test frequencies for variable tx-rx spacing for NTN band 256 | EchoStar | RAN5#107 (May-25) |  |  | 0.1
5 |  | 36.508 | 4.4.3.3 | Common contents of system information blocks | Include ul-CarrierFreq and condition in SIB2 | EchoStar | RAN5#107 (May-25) |  |  | 0.1
6 |  | 36.508 | 4.6.5 | Mobility control information elements | Include ul-CarrierFreq and condition in MobilityControlInfo-HO | EchoStar | RAN5#107 (May-25) |  |  | 0.1
7 |  | 36.508 | 6.2.3.1 | Test frequencies for signalling test | Addition of new set of test freq for variable tx-rx spacing |  | RAN5#108 (Aug-25) |  |  | 0.1
8 |  | 36.508 | 8.1.3.1.1 | NB-IoT FDD reference test for operating band 256 | Addition of new set of test freq for variable tx-rx spacing for band 256 | EchoStar | RAN5#107 (May-25) |  |  | 0.1
9 |  | 36.508 | 8.1.4.3.3 | NB-IoT Common contents of system information blocks | Include ul-CarrierFreq and condition in SIB2 | EchoStar | RAN5#107 (May-25) |  |  | 0.1
10 |  | 36.508 | 8.3.2.3.1 | NB-IoT FDD Mode Test frequencies for signalling test | Addition of test frequencies for variable tx-rx spacing |  | RAN5#109 (Oct-25) |  |  | 0.1
TS 36.509: UE specific testing functions
|  | 36.509 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected).
LTE RF/RRM
TS 36.521-4: RF NTN test cases - Common parts (general clauses, Annexes)
|  | 36.521-4 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected).
1 |  | 36.521-4 | 5.4.A3 | TX-RX frequency separation | Modification based on updates to core specs | EchoStar | RAN5#107 (May-25) |  |  | 0.5
2 |  | 36.521-4 | 5.4.B3 | TX-RX frequency separation | Modification based on updates to core specs | EchoStar | RAN5#107 (May-25) |  |  | 0.5
TS 36.521-4: RF test cases - Tx
|  | 36.521-4 Tx |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected).
TS 36.521-4: RF test cases - Rx
|  | 36.521-4 Rx |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected).
1 |  | 36.521-4 Rx | 7.1 | General | Modification based on updates to core specs | EchoStar | RAN5#107 (May-25) |  |  | 0.06
2 |  | 36.521-4 Rx | 7.3A.3 | Minimum conformance requirements | Modification based on updates to core specs | EchoStar | RAN5#107 (May-25) |  |  | 0.07
3 | Y | 36.521-4 Rx | 7.3A_1 | Reference sensitivity power level for UE category M1 for Tx-Rx frequency separation other than default | New test case to verify reference sensitivity for verify reference sensitivity conformance for variable tx-rx spacing for M1 NTN UEs | EchoStar | RAN5#107 (May-25) |  |  | 0.4
4 |  | 36.521-4 Rx | 7.3B.3 | Minimum conformance requirements | Modification based on updates to core specs | EchoStar | RAN5#107 (May-25) |  |  | 0.07
5 | Y | 36.521-4 Rx | 7.3B_1 | Reference sensitivity power level for UE category NB1 and NB2 for Tx-Rx frequency separation other than default | New test case to verify reference sensitivity for verify reference sensitivity conformance for variable tx-rx spacing for NB1 and NB2 NTN UEs | EchoStar | RAN5#107 (May-25) |  |  | 0.4
TS 36.521-4: Demod/CSI reporting test cases
|  | 36.521-4 Demod |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected).
TS 36.521-2: Applicability for RF, Demod/CSI reporting and RRM test cases
TBD |  | 36.521-2 | <Clause> | <Title> | Add new ICS statements. |  | TBD
1 |  | 36.521-2 | 4.3.1 | RF conformance test cases for NB-IoT/eMTC NTN | Applicability for the new test cases | EchoStar | RAN5#107 (May-25) |  |  | 0.5
2 |  | 36.521-2 | A.4.3 | Baseline Implementation Capabilties | Addition of PICS for variable tx-rx spacing capability | EchoStar | RAN5#107 (May-25) |  |  | 0.5
TS 36.521-3: RRM test cases
|  | 36.521-3 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected).
TR 36.903: Test Tolerances analysis RRM test cases
|  | 36.903 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected).
TR 36.904: Test Tolerances analysis receiver test cases
|  | 36.904 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected).
TR 36.905: Test Point analysis receiver and transmitter test cases
|  | 36.905 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected).
LTE RAN and CN protocols
TS 36.523-1: Protocol test cases
|  | 36.523-1 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected).
Idle Mode
Layer 2
RRC
NAS
TS 36.523-2: Applicability for Protocol test cases
TBD |  | 36.523-2 | <Clause> | <Title> | Add new ICS statements. |  | TBD
1 |  | 36.523-2 | 4 | Recommended Test Case Applicability | Incorporates variable tx-rx spacing PICS and PIXITs to relevant test cases and a new note to test for both default and non-default scenarios | EchoStar | RAN5#107 (May-25) |  |  | 0.5
2 |  | 36.523-2 | A.4.4 | Additional information | New PICS added | EchoStar | RAN5#107 (May-25) |  |  | 0.5
TS 36.523-3: Protocol test suites (TTCN)
|  | 36.523-3 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected).
1 |  | 36.523-3 | 9.1 | E-UTRAN PIXIT | Add new PIXIT to enable testing for both default and non-default tx-rx frequency separation for M1 NTN UEs | EchoStar | RAN5#107 (May-25) |  |  | 0.5
2 |  | 36.523-3 | 9.3 | NB-IoT PIXIT | Add new PIXIT to enable testing for both default and non-default tx-rx frequency separation for NB1 and NB2 NTN UEs | EchoStar | RAN5#107 (May-25) |  |  | 0.5
End of workplan items. Note! Do not remove this row. Introduce new work plan rows/items above this row.
Note on A6: Unique ID for WP items (unique within the sub-area work plan) Note! As WP item numbers may be referenced from outside of this WP that means: - Do not change number for WP items that have been published. - Do not re-use WP item numbers if a WP item is deleted
Note on B6: Set to Y if the WP item represents a new test case that will be specified in RAN5 test specifications as an executable test case else leave blank.
Note on K6: The WP item's weight number is used to set the reletive weights between WP items used in the overall calculation of completeness. Setting it to 0 for a WP item means that it will not be included at all in the calculation.