## Cover sheet
3GPP TSG-RAN WG5 Meeting #107 | [7 empty] | R5-253581
St. Julian's, Malta, May 19th - May 23rd, 2025
Agenda Item: | 5.5.1.13
Source: | EchoStar
Title: | WP for variable Tx-Rx spacing conformance specs for IoT NTN bands
Work item code: | TEI18_Test
Release: | Rel-18
Document for: | Endorsement
RAN5 WP template v3.0.0
1. Introduction
Variable Tx-Rx spacing was spacified for IoT NTN bands. Support for flexible Tx-Rx frequency separation is optional for Rel-17 and mandatory from Rel-18 onwards. This WP assesses the impact to various conformance speciification test clauses and tenative schedule for updating the affected clauses.
2. Work item status
Estimation of WI overall completion:
Area |  | Completion | Number of new completed test cases (Note 1) | Number of new test cases | Comments
Overall completion |  | 80% (+80%) | 1 (+1) | 1 (+1)
Completion Compensation |  | -
| Note 1: | Only test cases completed for all applicable WP areas and sub-areas are counted. For completed test cases per WP areas and WP sub-areas see below.
Estimation WI completion per area and sub-area:
|  | Completion | Number of new completed test cases | Number of new test cases | Comments
LTE (FDD) |  | 79.9% (+79.9%) | 1 (+1) | 1 (+1)
FDD |  | 79.9% (+79.9%) | 1 (+1) | 1 (+1)
Estimation of completion per TS (area):
|  | TS/TR overall completion |  |  | LTE
TS/TR Scope | TS/TR | Completion | Number of new completed test cases | Number of new test cases | FDD
[5 empty] | Completion | Number of new completed test cases | Number of new test cases
LTE
LTE Common
Common test environment | 36.508 | 70% (+70%) |  |  | 70% (+70%)
UE specific test functions | 36.509
LTE RF/RRM
RF common parts | 36.521-4 | 40% (+40%) |  |  | 40% (+40%)
RF Rx test cases | 36.521-4 Rx | 100% (+100%) | 1 (+1) | 1 (+1) | 100% (+100%) | 1 (+1) | 1 (+1)
RF Tx test cases | 36.521-4 Tx
RF Demod test cases | 36.521-4 Demod
Applicability RF. Demod/QSI and RRM test cases | 36.521-2 | 100% (+100%) |  |  | 100% (+100%)
RRM test cases | 36.521-3
Test Tolerances analysis RRM test cases | 36.903
Test Tolerances analysis receiver test cases | 36.904
Test Point analysis receiver and transmitter test cases | 36.905
LTE RAN and CN protocols
Protocol test cases | 36.523-1
Applicability Protocol test cases | 36.523-2 | 100% (+100%) |  |  | 100% (+100%)
Test suites (TTCN) | 36.523-3 | 100% (+100%) |  |  | 100% (+100%)
5 References
[1] RP-250600 | RAN4 CRs to Maintenance for Closed WIs/SIs for REL-18 and earlier – Batch 23
Note on B21: Overall completion of the work item reported at an earlier meeting will not be decreased if additional tasks are added or if corrections are made to the work plan. Instead the earlier reported completion status will be kept until necessary progress have been achieved such that completion exceeds the earlier reported completion level. The value of the Completion Compensation value represents the difference in the decrease caused by late additions or corrections to the work plan and the current estimated overall completion. '-' indicates that no compensation is applied.

## WP
WP Title: |  | WP for variable Tx-Rx spacing conformance specs for IoT NTN bands | [10 empty] | Start of workplan status columns. Note! Do not remove this column. | WP item status | End of workplan columns. Note! Do not remove this column.
WI code |  | TEI18_Test
WP Scope: |  | Make necessary updates to RF and Signalling Conformance Specs related to variable Tx-Rx spacing requirements specified in the core specifications of IoT NTN (36.102)
WP Resp: |  | Ojas Choksi |  |  | ojas.choksi@echostar.com | [5 empty] | WP item completion |  |  | LTE
TS Resp: |  | <TS responsible if a new TS is involved> |  |  | <Email to TS responsible>
WP Item ID | Is new test case? | TS/area | Clause | Title | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | Overall | LTE |  | FDD
79.9% (+79.9%)
18 (+18)
9 (+9)
5%
Start of work plan items. Note! Do not remove this row. Introduce new work plan rows/items below this row.
LTE
LTE Common
TS 36.508: Common test environment
1 |  | 36.508 | 8.1.3.1.1.253 | NB-IoT FDD reference test for operating band 253 | Addition of new set of test freq for variable tx-rx spacing for band 253 |  | RAN5#108 (Aug-25) |  |  | 0.1 | 0% | 0% |  | 0%
2 |  | 36.508 | 8.1.3.1.1.254 | NB-IoT FDD reference test for operating band 254 | Addition of new set of test freq for variable tx-rx spacing for band 254 |  | RAN5#108 (Aug-25) |  |  | 0.1 |  |  |  | 0%
3 |  | 36.508 | 8.1.3.1.1.255 | NB-IoT FDD reference test for operating band 255 | Addition of new set of test freq for variable tx-rx spacing for band 255 |  | RAN5#108 (Aug-25) |  |  | 0.1 |  |  |  | 0%
4 |  | 36.508 | 8.1.3.1.1.256 | NB-IoT FDD reference test for operating band 256 | Addition of new set of test freq for variable tx-rx spacing for band 256 | EchoStar | RAN5#107 (May-25) | R5-253189 |  | 0.3 |  |  |  | 100%
5 |  | 36.508 | 8.1.4.3.3 | NB-IoT Common contents of system information blocks | Include ul-CarrierFreq and condition in SIB2-NB | EchoStar | RAN5#107 (May-25) | R5-253189 |  | 0.2 |  |  |  | 100%
6 |  | 36.508 | 8.3.2.3.1 | NB-IoT FDD Mode Test frequencies for signalling test for all bands | Addition of test frequencies for variable tx-rx spacing | EchoStar | RAN5#108 (Aug-25) | R5-253189 |  | 0.2 |  |  |  | 100%
LTE RF/RRM
TS 36.521-4: RF NTN test cases - Common parts (general clauses, Annexes)
1 |  | 36.521-4 | 5.4.B3 | TX-RX frequency separation | Modification based on updates to core specs | CMCC, EchoStar | RAN5#107 (May-25) | R5-253601 |  | 0.4 | 100% (+100%) | 100% (+100%) |  | 100%
2 |  | 36.521-4 | Annex F.1.3 | Measurement of receiver | Add a row for the MU for the new Rx test case |  | RAN5#108 (Aug-25) |  |  | 0.3 |  |  |  | 0%
3 |  | 36.521-4 | Annex F.3.3 | Measurement of receiver | Add a row for TT for the new Rx test case |  | RAN5#108 (Aug-25) |  |  | 0.3 |  |  |  | 0%
TS 36.521-4: RF test cases - Rx
1 |  | 36.521-4 Rx | 7.1 | General | Modification based on updates to core specs | CMCC, EchoStar | RAN5#107 (May-25) | R5-253601 |  | 1 |  |  |  | 100%
2 |  | 36.521-4 Rx | 7.3B.3 | Minimum conformance requirements | Modification based on updates to core specs | CMCC, EchoStar | RAN5#107 (May-25) | R5-253601 |  | 1 | 100% (+100%) | 100% (+100%) |  | 100%
3 | Y | 36.521-4 Rx | 7.3B_1 | Reference sensitivity power level for UE category NB1 and NB2 for Tx-Rx frequency separation other than default | New test case to verify reference sensitivity for verify reference sensitivity conformance for variable tx-rx spacing for NB1 and NB2 NTN UEs | EchoStar | RAN5#107 (May-25) | R5-253610 |  | 1 | 100% (+100%) | 100% (+100%) |  | 100%
TS 36.521-2: Applicability for RF, Demod/CSI reporting and RRM test cases
1 |  | 36.521-2 | 4.3.1 | RF conformance test cases for NB-IoT/eMTC NTN | Applicability for the new test cases | EchoStar | RAN5#107 (May-25) | R5-253611 |  | 0.5 | 100% (+100%) | 100% (+100%) |  | 100%
2 |  | 36.521-2 | A.4.3 | Baseline Implementation Capabilties | Addition of PICS for variable tx-rx spacing capability | EchoStar | RAN5#107 (May-25) | R5-253611 |  | 0.5 | 100% (+100%) | 100% (+100%) |  | 100%
TR 36.905: Test Point analysis receiver and transmitter test cases
1 |  | 36.905 | 4.5 | Test points selection for test cases in TS 36.521-4 | Update Table 4.5-2 with the additional RefSens test case and associated test points |  | RAN5#108 (Aug-25) |  |  | 1 | 0% | 0% |  | 0%
LTE RAN and CN protocols
TS 36.523-1: Protocol test cases
|  | 36.523-1 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected).
Idle Mode
Layer 2
RRC
NAS
TS 36.523-2: Applicability for Protocol test cases
1 |  | 36.523-2 | 4 | Recommended Test Case Applicability | Incorporates variable tx-rx spacing PICS and PIXITs to relevant test cases and a new note to test for both default and non-default scenarios | EchoStar | RAN5#107 (May-25) | R5-253190 |  | 0.5 |  |  |  | 100%
2 |  | 36.523-2 | A.4.4 | Additional information | New PICS added | EchoStar | RAN5#107 (May-25) | R5-253190 |  | 0.5 |  |  |  | 100%
TS 36.523-3: Protocol test suites (TTCN)
1 |  | 36.523-3 | 9.3 | NB-IoT PIXIT | Update existing NB-IoT OperationMode PIXIT to enable testing for both default and non-default tx-rx frequency separation for NB1 and NB2 NTN UEs | EchoStar | RAN5#107 (May-25) | R5-253191 |  | 1 |  |  |  | 100%
End of workplan items. Note! Do not remove this row. Introduce new work plan rows/items above this row.
Note on A6: Unique ID for WP items (unique within the sub-area work plan) Note! As WP item numbers may be referenced from outside of this WP that means: - Do not change number for WP items that have been published. - Do not re-use WP item numbers if a WP item is deleted
Note on B6: Set to Y if the WP item represents a new test case that will be specified in RAN5 test specifications as an executable test case else leave blank.
Note on K6: The WP item's weight number is used to set the reletive weights between WP items used in the overall calculation of completeness. Setting it to 0 for a WP item means that it will not be included at all in the calculation.