## Cover sheet
3GPP TSG-RAN5 Meeting #108 | [10 empty] | R5-253725
Bengaluru, India, 25th Aug 2025 - 29th Aug 2025
Agenda Item: | 7.5.2
Source: | China Telecom
Title: | UE Conformance - MPS when access to EPC/5GC is WLAN
Work item code: | MPS_WLAN_UEConTest
Release: | Rel-18
Document for: | Information
RAN5 WP template v3.0.0
1. Introduction
This work item covers the protocol conformance testing for Rel-18 MPS when access to EPC/5GC is WLAN.
2. Work item status
Estimation of WI overall completion:
Area |  | Completion | Number of new completed test cases (Note 1) | Number of new test cases | Comments
Overall completion |  | 5% (+5%) | 0 | 2 (+2)
Completion Compensation |  | -
| Note 1: | Only test cases completed for all applicable WP areas and sub-areas are counted. For completed test cases per WP areas and WP sub-areas see below.
Estimation WI completion per area and sub-area:
|  | Completion | Number of new completed test cases | Number of new test cases | Comments
SA Option 2 (SA NR) |  | 5% (+5%) | 0 | 1 (+1)
FR1 |  | 5% (+5%) | 0 | 1 (+1)
FR2 |  | 5% (+5%) | 0 | 1 (+1)
LTE |  | 5% (+5%) | 0 | 1 (+1)
FR1 |  | 5% (+5%) | 0 | 1 (+1)
Estimation of completion per TS (area):
|  | TS/TR overall completion |  |  | SA Option 2 (SA NR) | [6 empty] | LTE
TS/TR Scope | TS/TR | Completion | Number of new completed test cases | Number of new test cases | FR1 |  |  | FR2 |  |  |  | FR1
[5 empty] | Completion | Number of new completed test cases | Number of new test cases | Completion | Number of new completed test cases | Number of new test cases |  | Completion | Number of new completed test cases | Number of new test cases
LTE
LTE Common
Common test environment | 36.508
UE specific test functions | 36.509
LTE RF/RRM
RF common parts | 36.521-1
RF Rx test cases | 36.521-1 Rx
RF Tx test cases | 36.521-1 Tx
RF Demod test cases | 36.521-1 Demod
Applicability RF. Demod/QSI and RRM test cases | 36.521-2
RRM test cases | 36.521-3
Test Tolerances analysis RRM test cases | 36.903
Test Tolerances analysis receiver test cases | 36.904
Test Point analysis receiver and transmitter test cases | 36.905
LTE RAN and CN protocols
Protocol test cases | 36.523-1 | 0% | 0 | 1 (+1) | [7 empty] | 0% | 0 | 1 (+1)
Applicability Protocol test cases | 36.523-2
Test suites (TTCN) | 36.523-3
5GS
5GS Common
Common test environment | 38.508-1
Common ICS | 38.508-2
UE specific test functions | 38.509
NR RF/RRM
FR1 RF common parts | 38.521-1
FR1 RF Tx test cases | 38.521-1 Tx
FR1 RF Rx test cases | 38.521-1 Rx
FR2 RF common parts | 38.521-2
FR2 RF Tx test cases | 38.521-2 Tx
FR2 RF Rx test cases | 38.521-2 Rx
FR1 and FR2 Interworking operation with other radios RF common parts | 38.521-3
FR1 and FR2 Interworking operation with other radios RF Tx test cases | 38.521-3 Tx
FR1 and FR2 Interworking operation with other radios RF Rx test cases | 38.521-3 Rx
RF Demod/QSI test cases | 38.521-4
RRM test cases | 38.533
Applicability RF. Demod/QSI and RRM test cases | 38.522
Test Tolerances analysis RRM and RF Rx test cases | 38.903
Test Point analysis receiver and transmitter test cases | 38.905
5GS RAN and CN protocols
Protocol test cases | 38.523-1 | 0% | 0 | 1 (+1) | 0% | 0 | 1 (+1) | 0% | 0 | 1 (+1)
Applicability Protocol test cases | 38.523-2
Test suites (TTCN) | 38.523-3
UE Positioning
UE Positioning Min. Performance test cases | 37.571-1
UE Positioning Protocol test cases | 37.571-2
Applicability and ICS UE Positioning test cases | 37.571-3
UE Positioning Test sutes (TTCN) | 37.571-4
UE Positioning test scenarios and assistance data | 37.571-5
IMS
IMS over LTE protocol test cases | 34.229-1
IMS over 5GS protocol test cases | 34.229-5
Applicability and ICS IMS test cases | 34.229-2
IMS Test suite (TTCN) | 34.229-3
Mission Critical Services
MC Common test environment | 36.579-1
MCPTT UE test cases | 36.579-2
MC Server Application test cases | 36.579-3
Applicability and ICS MC test cases | 36.579-4
MC Test suite (TTCN) | 36.579-5
MC Video UE test cases | 36.579-6
MC Data UE test cases | 36.579-7
5 References
[1] RP-250893 | New WID on UE Conformance MPS when access to EPC/5GC is WLAN
Note on B21: Overall completion of the work item reported at an earlier meeting will not be decreased if additional tasks are added or if corrections are made to the work plan. Instead the earlier reported completion status will be kept until necessary progress have been achieved such that completion exceeds the earlier reported completion level. The value of the Completion Compensation value represents the difference in the decrease caused by late additions or corrections to the work plan and the current estimated overall completion. '-' indicates that no compensation is applied.

## WP
WP Title: |  | UE_Conformance - MPS when access to EPC/5GC is WLAN | [11 empty] | Start of workplan status columns. Note! Do not remove this column. | WP item status |  |  | End of workplan columns. Note! Do not remove this column.
WI code |  | MPS_WLAN_UEConTest
WP Scope: |  | To define the UE conformance test for Rel-18 MPS | [13 empty] | vs Area
WP Resp: |  | Jing Zhao |  |  | zhaoj16@chinatelecom.cn | [5 empty] | WP item completion |  |  |  | SA Option 2 (SA NR) |  | LTE
TS Resp: |  | <TS responsible if a new TS is involved> |  |  | <Email to TS responsible>
WP Item ID | Is new test case? | TS/area | Clause | Title | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | Overall | SA Option 2 (SA NR) | LTE |  | FR1 | FR2 | FR1
[15 empty] | 5% (+5%) | 5% (+5%) | 5% (+5%)
[15 empty] | 4 (+4) | 4 (+4) | 4 (+4)
[15 empty] | 2.4 (+2.4) | 2.4 (+2.4) | 2.4 (+2.4)
5%
Start of work plan items. Note! Do not remove this row. Introduce new work plan rows/items below this row.
LTE
LTE RAN and CN protocols
TS 36.523-1: Protocol test cases
|  | 36.523-1 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
NAS
TBD | Y | 36.523-1 | 20.7 | IPsec tunnel establishment procedure/MPS Priority | ****TP1: [TS 24.302: 7.2.2.1]**** WITH: UE is configured for high priority access in the seleted PLMN and connects to an untrusted WLAN. WHEN: UE receives an IKE_SA_INIT response message. THEN: UE transmits an IKE_AUTH request message including HPA_INFO Notify payload with the MPS_PRI bit set as 1. |  | RAN5#110 (Feb-9) |  |  | 1 | 0% |  | 0% |  |  |  | 0%
TS 36.523-2: Applicability for Protocol test cases
TBD |  | 36.523-2 | <Clause> | <Title> | Add new ICS statements. |  | TBD |  |  | 0.2
TBD |  | 36.523-2 | <Clause> | <Title> | Add test case applicability statements for the new MPS test cases introduced in 36.523-1 |  | TBD |  |  | 0.2
TS 36.523-3: Protocol test suites (TTCN)
|  | 36.523-3 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
TBD |  | 36.523-3 | <Clause> | <Title of task> | <Describe task> |  | TBD |  |  | TBD
5GS
5GS Common
TS 38.508-2: Common ICS
|  | 38.508-2 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
TBD |  | 38.508-2 | <Clause> | Introduction of common implementation conformance statements for Rel-18 MPS testing | Add ICS as needed for the test case applicability statements for the new test cases introduced in RF, RRM and protocol test cases. |  | TBD |  |  | TBD
RAN and CN protocol
TS 38.523-1: Protocol test cases
|  | 38.523-1 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
NAS
TBD | Y | 38.523-1 | 9.2.1.3 | IKE SA and signalling IPsec SA establishment procedure/MPS Priority | ****TP1: [TS 24.502: 7.3.2.1]**** WITH: UE has a valid Access Identity 1. WHEN: UE connects to untrusted non-3GPP access network and finishes IKE_SA_INIT exchange and initiates an IKE_AUTH exchange. THEN: UE includes the HPA_INFO Notify payload in the initial IKE_AUTH request message. |  | RAN5#110 (Feb-9) |  |  | 1 | 0% | 0% |  |  | 0% | 0%
TS 38.523-2: Applicability for Protocol test cases
TBD |  | 38.523-2 | <Clause> | <Title> | Add new ICS statements. |  | TBD |  |  | 0.2
TBD |  | 38.523-2 | <Clause> | <Title> | Add Applicability Condition for Rel-18 MPS test cases introduced in 38.523-1 |  | TBD |  |  | 0.2
TS 38.523-3: Protocol test suites (TTCN)
|  | 38.523-3 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
TBD |  | 38.523-3 | <Clause> | <Title of task> | <Describe task> |  | TBD |  |  | TBD
End of workplan items. Note! Do not remove this row. Introduce new work plan rows/items above this row.
Note on A6: Unique ID for WP items (unique within the sub-area work plan) Note! As WP item numbers may be referenced from outside of this WP that means: - Do not change number for WP items that have been published. - Do not re-use WP item numbers if a WP item is deleted
Note on B6: Set to Y if the WP item represents a new test case that will be specified in RAN5 test specifications as an executable test case else leave blank.
Note on K6: The WP item's weight number is used to set the reletive weights between WP items used in the overall calculation of completeness. Setting it to 0 for a WP item means that it will not be included at all in the calculation.