## Cover sheet
3GPP TSG-RAN WG5 Meeting #108 | [7 empty] | R5-254169
Bengaluru, IN, 25th - 29th Aug 2025
Agenda Item: | 7.5.2
Source: | China Telecom, Intel, Nokia
Title: | WP for UE Conformance - NR channel BW less than 5MHz for FR1 Phase 2
Work item code: | NR_FR1_lessthan_5MHz_BW_Ph2-UEConTest
Release: | Rel-19
Document for: | Information
RAN5 WP template v3.0.0
1. Introduction
In Rel-18, RAN4 specified requirements to support deploying NR in spectrum allocations from approximately 3 MHz up to below 5 MHz, in bands including n100, n106, n26, n28, n31, n72 and n85. In Rel-19, NR_FR1_lessthan_5MHz_BW_Ph2 WI is approved to introduce new requirements for Carrier Aggregation and Dual Connectivity of a 3MHz carrier with one or more 3MHz or wider bandwidth carriers, to increase the total available network capacity, radio coverage and cell hand-over performance, which is particularly relevant for railway deployments. Under the Rel-19 parent WI, RAN4 has specified below requirements in the Core part: •common co-located and non-co-located inter-band NR CA/DC UE RF requirements with 3MHz CBW in the one band and 5MHz or 10MHz CBW in the other band (with CA/DC of 3/5MHz in band n100 and 5/10MHz in band n101 as example) •RRM requirements for inter-band CA and DC for combinations introduced in RF part. The overall completion level for the Core part of NR_FR1_lessthan_5MHz_BW_Ph2 is already 100% at the RAN#107 in March 2025 and the target completion date of Perf. part is June 2025. The corresponding UE conformance specifications are now required to be implemented in RAN5.
2. Work item status
Estimation of WI overall completion:
Area |  | Completion | Number of new completed test cases (Note 1) | Number of new test cases | Comments
Overall completion |  | 5% (+5%) | 0 | 8 (+8)
Completion Compensation |  | -
| Note 1: | Only test cases completed for all applicable WP areas and sub-areas are counted. For completed test cases per WP areas and WP sub-areas see below.
Estimation WI completion per area and sub-area:
|  | Completion | Number of new completed test cases | Number of new test cases | Comments
SA Option 2 (SA NR) (FR1) |  | 5% (+5%) | 0 | 8 (+8)
FR1 |  | 5% (+5%) | 0 | 8 (+8)
Estimation of completion per TS (area):
|  | TS/TR overall completion |  |  | SA Option 2 (SA NR)
TS/TR Scope | TS/TR | Completion | Number of new completed test cases | Number of new test cases | FR1
[5 empty] | Completion | Number of new completed test cases | Number of new test cases
5GS
5GS Common
Common test environment | 38.508-1 | 0% |  |  | 0%
Common ICS | 38.508-2 | 0% |  |  | 0%
NR RF/RRM
FR1 RF common parts | 38.521-1 | 0% |  |  | 0%
FR1 RF Tx test cases | 38.521-1 Tx | 0% |  |  | 0%
RRM test cases | 38.533 | 0% | 0 | 8 (+8) | 0% | 0 | 8 (+8)
Applicability RF. Demod/QSI and RRM test cases | 38.522 | 0% |  |  | 0%
Test Tolerances analysis RRM and RF Rx test cases | 38.903 | 0% |  |  | 0%
Test Point analysis receiver and transmitter test cases | 38.905
5 References
[1] RP-251455 | New WID on UE Conformance - NR channel BW less than 5MHz for FR1 Phase 2
Note on B21: Overall completion of the work item reported at an earlier meeting will not be decreased if additional tasks are added or if corrections are made to the work plan. Instead the earlier reported completion status will be kept until necessary progress have been achieved such that completion exceeds the earlier reported completion level. The value of the Completion Compensation value represents the difference in the decrease caused by late additions or corrections to the work plan and the current estimated overall completion. '-' indicates that no compensation is applied.

## WP
WP Title: |  | WP for UE Conformance - NR channel BW less than 5MHz for FR1 Phase 2 | [10 empty] | Start of workplan status columns. Note! Do not remove this column. | WP item status | End of workplan columns. Note! Do not remove this column.
WI code |  | NR_FR1_lessthan_5MHz_BW_Ph2-UEConTest
WP Scope: |  | The objective of this work item is to define the UE conformance requirements corresponding to the WID on NR channel BW less than 5MHz for FR1 Phase 2. This work item will cover RF and RRM conformance test specifications.
WP Resp: |  | Weichen Ning |  |  | ningwc@chinatelecom.cn | [5 empty] | WP item completion |  |  | SA Option 2 (SA NR)
TS Resp:
WP Item ID | Is new test case? | TS/area | Clause | Title | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | Overall | SA Option 2 (SA NR) |  | FR1
5% (+5%)
33 (+33)
18.9 (+18.9)
5%
Start of work plan items. Note! Do not remove this row. Introduce new work plan rows/items below this row.
5GS
5GS Common
TS 38.508-1: Common test environment
1 |  | 38.508-1 | 4 | Introduction of Test Environment | Add related Test Environment | All companies | RAN5#113 (Nov-16) |  |  | 0.1 | 0% | 0% |  | 0%
TS 38.508-2: Common ICS
2 |  | 38.508-2 | A.4 | ICS proforma tables | Add ICS as needed for the test case applicability statements for the new test cases introduced in RF, RRM and protocol test cases. | All companies | RAN5#113 (Nov-16) |  |  | 0.1 | 0% | 0% |  | 0%
NR RF/RRM
TS 38.521-1: FR1 RF test cases - Common parts (general clauses, Annexes)
3 |  | 38.521-1 | 5.2A.2.1 | Inter-band CA operating bands involving FR1 (two bands) | update CA configuration | China Telecom | RAN5#113 (Nov-16) |  |  | 1 | 0% | 0% |  | 0%
4 |  | 38.521-1 | 5.3.1 | General on UE channel bandwidth | update general description on UE channel bandwidth | China Telecom | RAN5#113 (Nov-16) |  |  | 1 | 0% | 0% |  | 0%
5 |  | 38.521-1 | 5.4.3.1 | Synchronization raster and numbering | update the note on GSCN parameters for the global frequency for 3 MHz channel bandwidth and Additional GSCN parameters for band n100 | China Telecom | RAN5#113 (Nov-16) |  |  | 1 | 0% | 0% |  | 0%
6 |  | 38.521-1 | 5.5A.3.1 | Configurations for inter-band CA (two bands) | update the table on NR CA configurations and bandwidth combinations sets defined for inter-band CA (two bands) | China Telecom | RAN5#113 (Nov-16) |  |  | 1 | 0% | 0% |  | 0%
7 |  | 38.521-1 | 5.5B | Configurations for DC | update the table on Inter-band NR-DC configurations (two bands) | China Telecom | RAN5#113 (Nov-16) |  |  | 1 | 0% | 0% |  | 0%
8 |  | 38.521-1 | D.1 | Add 3 MHz channel bandwidth into Annex D.1 | add 3 MHz channel bandwidth into Annex D.1 | China Telecom | RAN5#113 (Nov-16) |  |  | 1 | 0% | 0% |  | 0%
TS 38.521-1: FR1 RF test cases - Tx
9 |  | 38.521-1 Tx | 6.2A.1.0.3 | UE maximum output power for Inter-band CA | update the table on UE Power Class for uplink inter-band CA (two bands) | China Telecom | RAN5#113 (Nov-16) |  |  | 1 | 0% | 0% |  | 0%
10 |  | 38.521-1 Tx | 6.2A.4.0.2.3 | ΔTIB,c for Inter-band CA | update the table on ΔTIB,c due to NR CA (two bands) | China Telecom | RAN5#113 (Nov-16) |  |  | 1 | 0% | 0% |  | 0%
11 |  | 38.521-1 Tx | 6.2B.1.0.3 | UE maximum output power for inter-band NR-DC | update the table on UE Power Class for inter-band NR-DC | China Telecom | RAN5#113 (Nov-16) |  |  | 1 | 0% | 0% |  | 0%
12 |  | 38.521-1 Tx | 6.5A.3.2.0.3 | Spurious emissions for UE co-existence for Inter-band CA | add the table on Requirements for uplink inter-band carrier aggregation (two bands) Rel-19 | China Telecom | RAN5#113 (Nov-16) |  |  | 1 | 0% | 0% |  | 0%
TS 38.522: Applicability for RF, Demod/CSI reporting and RRM test cases
13 |  | 38.522 | 4.1.1 | RF/FR1 standalone conformance test cases | Add test case applicability statements for the new test cases introduced for 38.521-1 | China Telecom | RAN5#113 (Nov-16) |  |  | 0.1 | 0% | 0% |  | 0%
14 |  | 38.522 | 4.2 | RRM conformance test cases | Add test case applicability statements for the new test cases introduced for 38.533 | All companies | RAN5#113 (Nov-16) |  |  | 0.1 | 0% | 0% |  | 0%
TS 38.533: RRM test cases
15 |  | 38.533 | 6.3.1 | Handover |  |  | RAN5#113 (Nov-16) |  |  | TBD | 0% | 0% |  | 0%
16 | Y | 38.533 | 6.3.1.19 | NR SA FR1 handover with PSCell change delay where target PSCell is with 12PRB SSB bandwidth | 38.133 Requirements in Annex A.6.3.1.19 |  | RAN5#113 (Nov-16) |  |  | 1 | 0% | 0% |  | 0%
17 |  | 38.533 | 6.5.3 | Scell Activation and Deactivation Delay |  |  | RAN5#113 (Nov-16) |  |  | TBD | 0% | 0% |  | 0%
18 | Y | 38.533 | 6.5.3.17 | NR SA FR1 SCell Activation and deactivation of known SCell in FR1 in non-DRX for 160 ms SCell measurement cycle with less than 5MHz BW | 38.133 Requirements in Annex A.6.5.3.17 | Nokia | RAN5#113 (Nov-16) |  |  | 1 | 0% | 0% |  | 0%
19 |  | 38.533 | 6.5.11 | PSCell addition and Release Delay |  |  | RAN5#113 (Nov-16) |  |  | TBD | 0% | 0% |  | 0%
20 | Y | 38.533 | 6.5.11.2 | NR SA FR1 Addition and Release Delay of unknown NR FR1 PSCell with less than 5 MHz | 38.133 Requirements in Annex A.6.5.11.2 |  | RAN5#113 (Nov-16) |  |  | 1 | 0% | 0% |  | 0%
21 |  | 38.533 | 6.5.12 | PSCell addition and Release Delay |  |  | RAN5#113 (Nov-16) |  |  | TBD | 0% | 0% |  | 0%
22 | Y | 38.533 | 6.5.12.3 | NR SA FR1 Intra-frequency subsequent CPC from FR1-FR1 NR-DC to FR1-FR1 NR-DC with 12 PRB SSB bandwidth | 38.133 Requirements in Annex A.6.5.12.3 |  | RAN5#113 (Nov-16) |  |  | 1 | 0% | 0% |  | 0%
23 | Y | 38.533 | 6.5.12.4 | NR SA FR1 Inter-frequency subsequent CPA from FR1-FR1 NR-DC to FR1-FR1 NR-DC with 12 PRB SSB bandwidth | 38.133 Requirements in Annex A.6.5.12.4 |  | RAN5#113 (Nov-16) |  |  | 1 | 0% | 0% |  | 0%
24 |  | 38.533 | 6.6.1 | Intra-frequency Measurements |  |  | RAN5#113 (Nov-16) |  |  | TBD | 0% | 0% |  | 0%
25 | Y | 38.533 | 6.6.1.14 | NR SA FR1 Deactivated PSCell measurement test with 12 PRB SSB bandwidth in FR1 | 38.133 Requirements in Annex A.6.6.1.14 | Nokia | RAN5#113 (Nov-16) |  |  | 1 | 0% | 0% |  | 0%
26 | Y | 38.533 | 6.6.1.15 | NR SA FR1 event triggered reporting test without gap under non-DRX with SSB index reading and 12 PRB SSB for a deactivated SCell | 38.133 Requirements in Annex A.6.6.1.15 | Nokia | RAN5#113 (Nov-16) |  |  | 1 | 0% | 0% |  | 0%
27 |  | 38.533 | 6.6.9 | Idle mode CA/DC Measurements |  |  | RAN5#113 (Nov-16) |  |  | TBD | 0% | 0% |  | 0%
28 | Y | 38.533 | 6.6.9.5 | NR SA FR1 Idle mode CA/DC measurement with 12RB SSB | 38.133 Requirements in Annex A.6.6.9.5 | Nokia | RAN5#113 (Nov-16) |  |  | 1 | 0% | 0% |  | 0%
29 |  | 38.533 | Annex A | RRM test configurations | Adding RRM test and RMC configuration parameters | All companies | RAN5#113 (Nov-16) |  |  | 0.1 | 0% | 0% |  | 0%
30 |  | 38.533 | Annex E | Cell configuration mapping | Define cell configuration mapping | All companies | RAN5#113 (Nov-16) |  |  | 0.1 | 0% | 0% |  | 0%
31 |  | 38.533 | Annex F | Measurement uncertainties and test tolerances | Define measurement uncertainties and test tolerances | All companies | RAN5#113 (Nov-16) |  |  | 0.1 | 0% | 0% |  | 0%
32 |  | 38.533 | Annex H | Default message contents for RRM |  | All companies | RAN5#113 (Nov-16) |  |  | 0.1 | 0% | 0% |  | 0%
TR 38.903: Test Tolerances analysis RRM and RF Rx test cases
33 |  | 38.903 | 8 | Grouping of test cases defined in TS 38.533 | Add TT analysis for FR1 RRM Test cases | All companies | RAN5#113 (Nov-16) |  |  | 0.1 | 0% | 0% |  | 0%
TR 38.905: Test Point analysis receiver and transmitter test cases
34 |  | 38.905 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | x |  |  |  |  | TBD
End of workplan items. Note! Do not remove this row. Introduce new work plan rows/items above this row.
Note on A6: Unique ID for WP items (unique within the sub-area work plan) Note! As WP item numbers may be referenced from outside of this WP that means: - Do not change number for WP items that have been published. - Do not re-use WP item numbers if a WP item is deleted
Note on B6: Set to Y if the WP item represents a new test case that will be specified in RAN5 test specifications as an executable test case else leave blank.
Note on K6: The WP item's weight number is used to set the reletive weights between WP items used in the overall calculation of completeness. Setting it to 0 for a WP item means that it will not be included at all in the calculation.