## Cover sheet
3GPP TSG RAN5 Meeting #109 | [7 empty] | R5-256158
Dallas, US, Nov.17th – 21st 2025
Agenda Item: | 7.5.2
Source: | Huawei, Hisilicon
Title: | UE Conformance - Further RF requirements enhancement for NR and EN-DC in frequency range 1
Work item code: | NR_ENDC_RF_FR1_enh2-UEConTest
Release: | Rel-18
Document for: | Information
RAN5 WP template v3.0.0
1. Introduction
The objective of this work item is to define the conformance testing aspects for the Rel-18 Further RF requirements enhancement for NR and EN-DC in frequency range 1 WI, including RF, RRM, Demod and Protocol areas.For enhancements for 4Tx, example bands considered in core WI are n41, n77/n78, n1. For enhancements for 8Rx, example bands considered in core WI are n41, n77/n78, n79, n7. In conformance test WI, example bands and example configurations would be selected from the above list based on industry interest to complete the structure of new RF test cases. For lower-MSD improvement, RAN5 needs to decide whether the test framework is per-band-combination basis or general for all band combinations. If the test framework is decided as per-band-combination basis, example band combination(s) would be selected based on industry interest to complete the relevant RF work.
2. Work item status
Estimation of WI overall completion:
Area |  | Completion | Number of new completed test cases (Note 1) | Number of new test cases | Comments
Overall completion |  | 63% (+4%) | 51 | 88
Completion Compensation |  | -
| Note 1: | Only test cases completed for all applicable WP areas and sub-areas are counted. For completed test cases per WP areas and WP sub-areas see below.
Estimation WI completion per area and sub-area:
|  | Completion | Number of new completed test cases | Number of new test cases | Comments
SA Option 2 (SA NR) (FR1) |  | 75.6% (+3.2%) | 51 | 88
FR1 |  | 75.6% (+3.2%) | 51 | 88
NSA Option 3 (EN-DC) |  | 29.8% (+8.5%) | 0 | 21
FR1 |  | 29.8% (+8.5%) | 0 | 21
Estimation of completion per TS (area):
|  | TS/TR overall completion |  |  | SA Option 2 (SA NR) |  |  |  | NSA Option 3 (EN-DC)
TS/TR Scope | TS/TR | Completion | Number of new completed test cases | Number of new test cases | FR1 |  |  |  | FR1
[5 empty] | Completion | Number of new completed test cases | Number of new test cases |  | Completion | Number of new completed test cases | Number of new test cases
5GS
5GS Common
Common test environment | 38.508-1 | 100% |  |  | 100% |  |  |  | 100%
Common ICS | 38.508-2 | 100% |  |  | 100% |  |  |  | 100%
NR RF/RRM
FR1 RF common parts | 38.521-1 | 75% |  |  | 75%
FR1 RF Tx test cases | 38.521-1 Tx | 92.9% | 35 | 51 | 92.9% | 35 | 51
FR1 RF Rx test cases | 38.521-1 Rx | 100% | 16 | 16 | 100% | 16 | 16
FR1 and FR2 Interworking operation with other radios RF Rx test cases | 38.521-3 Rx | 0% | [6 empty] | 0%
RF Demod/QSI test cases | 38.521-4 | 26.6% (+12.3%) | 0 | 21 | 26.6% (+12.3%) | 0 | 21 |  | 26.6% (+12.3%) | 0 | 21
RRM test cases | 38.533 | 100% |  |  | 100%
Applicability RF. Demod/QSI and RRM test cases | 38.522 | 25.5% (+5%) |  |  | 31.7% (+5%) |  |  |  | 5% (+5%)
Test Point analysis receiver and transmitter test cases | 38.905 | 23.1% |  |  | 30% |  |  |  | 0%
5 References
[1] RP-240290 | New WID on UE Conformance - Further RF requirements enhancement for NR and EN-DC in frequency range 1
Note on B21: Overall completion of the work item reported at an earlier meeting will not be decreased if additional tasks are added or if corrections are made to the work plan. Instead the earlier reported completion status will be kept until necessary progress have been achieved such that completion exceeds the earlier reported completion level. The value of the Completion Compensation value represents the difference in the decrease caused by late additions or corrections to the work plan and the current estimated overall completion. '-' indicates that no compensation is applied.

## WP
WP Title: |  | UE Conformance - Further RF requirements enhancement for NR and EN-DC in frequency range 1 | [11 empty] | Start of workplan status columns. Note! Do not remove this column. | WP item status |  | End of workplan columns. Note! Do not remove this column.
WI code |  | NR_ENDC_RF_FR1_enh2-UEConTest
WP Scope: |  | The objective of this work item is to define the conformance testing aspects for the Rel-18 Further RF requirements enhancement for NR and EN-DC in frequency range 1 WI, including RF, RRM, Demod and Protocol areas. For enhancements for 4Tx, example bands considered in core WI are n41, n77/n78, n1. For enhancements for 8Rx, example bands considered in core WI are n41, n77/n78, n79, n7. In conformance test WI, example bands and example configurations would be selected from the above list based on industry interest to complete the structure of new RF test cases. For lower-MSD improvement, RAN5 needs to decide whether the test framework is per-band-combination basis or general for all band combinations. If the test framework is decided as per-band-combination basis, example band combination(s) would be selected based on industry interest to complete the relevant RF work.
WP Resp: |  | Xuesong Wang, Jingzhou Wu |  |  | cedar.wang@hisilicon.com; wujingzhou@chinatelecom.cn | [5 empty] | WP item completion |  |  |  | SA Option 2 (SA NR) | NSA Option 3 (EN-DC)
TS Resp: |  | N/A |  |  | N/A
WP Item ID | Is new test case? | TS/area | Clause | Title | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | Overall | SA Option 2 (SA NR) | NSA Option 3 (EN-DC) |  | FR1 | FR1
[15 empty] | 75.6% (+3.2%) | 29.8% (+8.5%)
[15 empty] | 137 | 64
[15 empty] | 110.3 | 41.3
5%
Start of work plan items. Note! Do not remove this row. Introduce new work plan rows/items below this row.
5GS
5GS Common
TS 38.508-1: Common test environment
1 |  | 38.508-1 | 4.6.3 | Radio resource control information elements | Updating message contents | Huawei, HiSilicon | RAN5#109 (Nov-25) | R5-247025 R5-253407 |  | 1 | 100% | 100% | 100% |  | 100% | 100%
2 |  | 38.508-1 | Annex A | Connection Diagrams | Introducing new connection diagrams | Huawei, HiSilicon | RAN5#109 (Nov-25) | R5-253640 |  | 1 | 100% | 100% | 100% |  | 100% | 100%
TS 38.508-2: Common ICS
3 |  | 38.508-2 | Annex A | ICS proforma for NR/5GS Generation User Equipment | Add ICS as needed for the test case applicability statements for the new test cases introduced in RF, RRM and protocol test cases. | Huawei, HiSilicon | RAN5#109 (Nov-25) | R5-245805 R5-247841 R5-253641 R5-254447 R5-256807 |  | 1 | 100% | 100% | 100% |  | 100% | 100%
NR RF/RRM
TS 38.521-1: FR1 RF test cases - Common parts (general clauses, Annexes)
4 |  | 38.521-1 | 3.2 | Symbols | Adding newly introduced symbols | Huawei, HiSilicon | RAN5#109 (Nov-25) | R5-250432 |  | 0.5 | 100% | 100% |  |  | 100%
5 |  | 38.521-1 | 4.2 | Applicability of minimum requirements | Updating the applicability of TxD minimum requirements (4Tx PC1.5) Ref: 38.101-1 clause 4.2 | Huawei, HiSilicon | RAN5#109 (Nov-25) |  | Core alignment | 0.5 | 0% | 0% |  |  | 0%
6 |  | 38.521-1 | Annex E | Global In-Channel TX-Test | Updating the method of global in-channel TX test for 4Tx Ref: 38.101-1 F.8 | Huawei, HiSilicon | RAN5#109 (Nov-25) | R5-254774 R5-256455 |  | 0.5 | 100% | 100% |  |  | 100%
7 |  | 38.521-1 | Annex F | Measurement uncertainties and Test Tolerances | Updating the MU/TT for 4T or 8R if needed | Huawei, HiSilicon | RAN5#109 (Nov-25) | R5-251528 R5-253642 R5-255351 | R5-251528 is MU for 8Rx blocking and ACS R5-255351 and R5-253642 are MU for 4T UL MIMO and TxD | 1 | 75% | 75% |  |  | 75%
TS 38.521-1: FR1 RF test cases - Tx
|  | 38.521-1 Tx | 6.2 | Transmitter power
152 |  | 38.521-1 Tx | 6.2.1 | UE maximum output power | Updating minimum requirement for TxD | Huawei, HiSilicon | RAN5#109 (Nov-25) | R5-254448 |  | 0.5 | 100% | 100% |  |  | 100%
8 |  | 38.521-1 Tx | 6.2.2 | UE maximum output power reduction | Updating minimum requirement for 4Tx |  | RAN5#109 (Nov-25) |  | Core alignment | 0.5 | 0% | 0% |  |  | 0%
9 |  | 38.521-1 | 6.2.4 | Configured transmitted power | Updating minimum requirement for 8Rx |  | RAN5#109 (Nov-25) | R5-247011 |  | 0.5 | 100% | 100% |  |  | 100%
|  | 38.521-1 Tx | 6.2D | Transmitter power for UL MIMO
10 | Y | 38.521-1 Tx | 6.2D.1_2 | UE maximum output power for UL MIMO for UE supporting 4Tx | Ref: 38.101-1 clause 6.2D.1 | Huawei, HiSilicon | RAN5#109 (Nov-25) | R5-252318 | This test are not testable due to lack of appropriate test points since there’s no configuration satisfying MPR=0dB requirements in TS 38.101-1 | 1 | 100% | 100% |  |  | 100%
11 | Y | 38.521-1 Tx | 6.2D.2_2 | UE maximum output power reduction for UL MIMO for UE supporting 4Tx | Ref: 38.101-1 clause 6.2D.2 | Huawei, HiSilicon | RAN5#109 (Nov-25) | R5-253405 |  | 1 | 100% | 100% |  |  | 100%
12 | Y | 38.521-1 Tx | 6.2D.3_2 | UE additional maximum output power reduction for UL MIMO for UE supporting 4Tx | Ref: 38.101-1 clause 6.2D.3 | Huawei, HiSilicon | RAN5#109 (Nov-25) | R5-255258 | Tests for network signalling values NS_50 for Power Class 1.5 are FFS | 1 | 100% | 100% |  |  | 100%
13 | Y | 38.521-1 Tx | 6.2D.4_2 | Configured transmitted power for UL MIMO for UE supporting 4Tx | Ref: 38.101-1 clause 6.2D.4 | Huawei, HiSilicon | RAN5#109 (Nov-25) | R5-254449 |  | 1 | 100% | 100% |  |  | 100%
|  | 38.521-1 Tx | 6.2G | Transmitter power for Tx Diversity
14 | Y | 38.521-1 Tx | 6.2G.1_1 | UE maximum output power for Tx Diversity for UE supporting 4Tx | Ref: 38.101-1 clause 6.2G.1 | Huawei, HiSilicon | RAN5#109 (Nov-25) | R5-252791 | No test points are defined for Power Class 1.5 UEs with 4Tx since there is no configuration satisfying MPR=0dB requirements in TS 38.101-1 | 1 | 100% | 100% |  |  | 100%
15 | Y | 38.521-1 Tx | 6.2G.2_1 | UE maximum output power reduction for Tx Diversity for UE supporting 4Tx | Ref: 38.101-1 clause 6.2G.2 | Huawei, HiSilicon | RAN5#109 (Nov-25) | R5-253419 |  | 1 | 100% | 100% |  |  | 100%
16 | Y | 38.521-1 Tx | 6.2G.3_1 | UE additional maximum output power reduction for Tx Diversity for UE supporting 4Tx | Ref: 38.101-1 clause 6.2G.3 | Huawei, HiSilicon | RAN5#109 (Nov-25) | R5-255354 |  | 1 | 100% | 100% |  |  | 100%
17 | Y | 38.521-1 Tx | 6.2G.4_1 | Configured transmitted power for Tx Diversity for UE supporting 4Tx | Ref: 38.101-1 clause 6.2G.4 | Huawei, HiSilicon | RAN5#109 (Nov-25) | R5-254449 |  | 1 | 100% | 100% |  |  | 100%
|  | 38.521-1 Tx | 6.3D | Output power dynamics for UL MIMO
18 | Y | 38.521-1 Tx | 6.3D.1_2 | Minimum output power UL MIMO for UE supporting 4Tx | Ref: 38.101-1 clause 6.3D.1 | Huawei, HiSilicon | RAN5#109 (Nov-25) | R5-253406 | MU/TT is FFS | 1 | 80% | 80% |  |  | 80%
19 | Y | 38.521-1 Tx | 6.3D.2_2 | Transmit OFF power for UL MIMO for UE supporting 4Tx | Ref: 38.101-1 clause 6.3D.2 | Huawei, HiSilicon | RAN5#109 (Nov-25) | R5-253408 R5-254451 |  | 1 | 100% | 100% |  |  | 100%
20 | Y | 38.521-1 Tx | 6.3D.3_2 | Transmit ON/OFF time mask for UL MIMO for UE supporting 4Tx | Ref: 38.101-1 clause 6.3D.3 | Huawei, HiSilicon | RAN5#109 (Nov-25) | R5-253408 R5-254451 |  | 1 | 100% | 100% |  |  | 100%
|  | 38.521-1 Tx | 6.3D.4 | Power control for UL MIMO
21 | Y | 38.521-1 Tx | 6.3D.4.1_2 | Absolute power tolerance for UL MIMO for UE supporting 4Tx | Ref: 38.101-1 clause 6.3D.4 | Huawei, HiSilicon | RAN5#109 (Nov-25) | R5-254614 |  | 1 | 100% | 100% |  |  | 100%
22 | Y | 38.521-1 Tx | 6.3D.4.2_2 | Relative power tolerance for UL MIMO for UE supporting 4Tx | Ref: 38.101-1 clause 6.3D.4 | Huawei, HiSilicon | RAN5#109 (Nov-25) | R5-254614 | MU/TT is FFS | 1 | 80% | 80% |  |  | 80%
23 | Y | 38.521-1 Tx | 6.3D.4.3_2 | Aggregate power tolerance for UL MIMO for UE supporting 4Tx | Ref: 38.101-1 clause 6.3D.4 | Huawei, HiSilicon | RAN5#109 (Nov-25) | R5-254614 |  | 1 | 100% | 100% |  |  | 100%
|  | 38.521-1 Tx | 6.3G | Output power dynamics for Tx Diversity
24 | Y | 38.521-1 Tx | 6.3G.1_1 | Minimum output power for Tx Diversity for UE supporting 4Tx | Ref: 38.101-1 clause 6.3G.1 | Huawei, HiSilicon | RAN5#109 (Nov-25) | R5-253430 | MU/TT is FFS | 1 | 80% | 80% |  |  | 80%
25 | Y | 38.521-1 Tx | 6.3G.2_1 | Transmit OFF power for Tx Diversity for UE supporting 4Tx | Ref: 38.101-1 clause 6.3G.2 | Huawei, HiSilicon | RAN5#109 (Nov-25) | R5-253431 R5-254451 |  | 1 | 100% | 100% |  |  | 100%
|  | 38.521-1 Tx | 6.3G.3 | Transmit ON/OFF time mask for Tx Diversity
26 | Y | 38.521-1 Tx | 6.3G.3.1_1 | General ON/OFF time mask for Tx Diversity for UE supporting 4Tx | Ref: 38.101-1 clause 6.3G.3.1 | Huawei, HiSilicon | RAN5#109 (Nov-25) | R5-253432 R5-254451 |  | 1 | 100% | 100% |  |  | 100%
27 | Y | 38.521-1 Tx | 6.3G.3.2_1 | PRACH time mask for Tx Diversity for UE supporting 4Tx | Ref: 38.101-1 clause 6.3G.3.2 | Huawei, HiSilicon | RAN5#109 (Nov-25) | R5-254450 |  | 1 | 100% | 100% |  |  | 100%
28 | Y | 38.521-1 Tx | 6.3G.3.3_1 | SRS time mask for Tx Diversity for UE supporting 4Tx | Ref: 38.101-1 clause 6.3G.3.3 | Huawei, HiSilicon | RAN5#109 (Nov-25) | R5-254450 |  | 1 | 100% | 100% |  |  | 100%
|  | 38.521-1 Tx | 6.3G.4 | Power control for Tx Diversity
29 | Y | 38.521-1 Tx | 6.3G.4.1_1 | Absolute power tolerance for Tx Diversity for UE supporting 4Tx | Ref: 38.101-1 clause 6.3G.4.1 | Huawei, HiSilicon | RAN5#109 (Nov-25) | R5-254614 |  | 1 | 100% | 100% |  |  | 100%
30 | Y | 38.521-1 Tx | 6.3G.4.2_1 | Relative power tolerance for Tx Diversity for UE supporting 4Tx | Ref: 38.101-1 clause 6.3G.4.2 | Huawei, HiSilicon | RAN5#109 (Nov-25) | R5-254614 | MU/TT is FFS | 1 | 80% | 80% |  |  | 80%
31 | Y | 38.521-1 Tx | 6.3G.4.3_1 | Aggregate power tolerance for Tx Diversity for UE supporting 4Tx | Ref: 38.101-1 clause 6.3G.4.3 | Huawei, HiSilicon | RAN5#109 (Nov-25) | R5-254614 |  | 1 | 100% | 100% |  |  | 100%
|  | 38.521-1 Tx | 6.4D | Transmit signal quality for UL MIMO
32 | Y | 38.521-1 Tx | 6.4D.1_2 | Frequency error for UL MIMO for UE supporting 4Tx | Ref: 38.101-1 clause 6.4D.1 | Huawei, HiSilicon | RAN5#109 (Nov-25) | R5-253410 R5-254556 |  | 1 | 100% | 100% |  |  | 100%
|  | 38.521-1 Tx | 6.4D.2 | Transmit modulation quality for UL MIMO
33 | Y | 38.521-1 Tx | 6.4D.2.1_2 | Error Vector Magnitude for UL MIMO for UE supporting 4Tx | Ref: 38.101-1 clause 6.4D.2.1 | Huawei, HiSilicon | RAN5#109 (Nov-25) | R5-255244 |  | 1 | 100% | 100% |  |  | 100%
34 | Y | 38.521-1 Tx | 6.4D.2.2_2 | Carrier leakage for UL MIMO for UE supporting 4Tx | Ref: 38.101-1 clause 6.4D.2.2 | Huawei, HiSilicon | RAN5#109 (Nov-25) | R5-255244 |  | 1 | 100% | 100% |  |  | 100%
35 | Y | 38.521-1 Tx | 6.4D.2.3_2 | In-band emissions for UL MIMO for UE supporting 4Tx | Ref: 38.101-1 clause 6.4D.2.3 | Huawei, HiSilicon | RAN5#109 (Nov-25) | R5-255244 |  | 1 | 100% | 100% |  |  | 100%
36 | Y | 38.521-1 Tx | 6.4D.2.4_2 | EVM equalizer spectrum flatness for UL MIMO for UE supporting 4Tx | Ref: 38.101-1 clause 6.4D.2.4 | Huawei, HiSilicon | RAN5#109 (Nov-25) | R5-255244 | For shaped Pi/2-BPSK modulated waveforms, the test requirements are FFS | 1 | 100% | 100% |  |  | 100%
37 | Y | 38.521-1 Tx | 6.4D.3_2 | Time alignment error for UL MIMO for UE supporting 4Tx | Ref: 38.101-1 clause 6.4D.3 | Huawei, HiSilicon | RAN5#109 (Nov-25) | R5-255246 |  | 1 | 100% | 100% |  |  | 100%
|  | 38.521-1 Tx | 6.4G | Transmit signal quality for Tx Diversity
39 | Y | 38.521-1 Tx | 6.4G.1_1 | Frequency error for Tx Diversity for UE supporting 4Tx | Ref: 38.101-1 clause 6.4G.1 | Huawei, HiSilicon | RAN5#109 (Nov-25) | R5-252658 |  | 1 | 100% | 100% |  |  | 100%
|  | 38.521-1 Tx | 6.4G.2 | Transmit modulation quality for Tx Diversity
40 | Y | 38.521-1 Tx | 6.4G.2.1_1 | Error Vector Magnitude for Tx Diversity for UE supporting 4Tx | Ref: 38.101-1 clause 6.4G.2.1 | Huawei, HiSilicon | RAN5#109 (Nov-25) | R5-255382 R5-256455 |  | 1 | 100% | 100% |  |  | 100%
41 | Y | 38.521-1 Tx | 6.4G.2.2_1 | Carrier leakage for Tx Diversity for UE supporting 4Tx | Ref: 38.101-1 clause 6.4G.2.2 | Huawei, HiSilicon | RAN5#109 (Nov-25) | R5-255382 |  | 1 | 100% | 100% |  |  | 100%
42 | Y | 38.521-1 Tx | 6.4G.2.3_1 | In-band emissions for Tx Diversity for UE supporting 4Tx | Ref: 38.101-1 clause 6.4G.2.3 | Huawei, HiSilicon | RAN5#109 (Nov-25) | R5-255382 |  | 1 | 100% | 100% |  |  | 100%
43 | Y | 38.521-1 Tx | 6.4G.2.4_1 | EVM equalizer spectrum flatness for Tx Diversity for UE supporting 4Tx | Ref: 38.101-1 clause 6.4G.2.4 | Huawei, HiSilicon | RAN5#109 (Nov-25) | R5-255382 |  | 1 | 100% | 100% |  |  | 100%
|  | 38.521-1 Tx | 6.5D | Output RF spectrum emissions for UL MIMO
44 | Y | 38.521-1 Tx | 6.5D.1_3 | Occupied bandwidth for UL MIMO for UE supporting 4Tx | Ref: 38.101-1 clause 6.5D.1 | Huawei, HiSilicon | RAN5#109 (Nov-25) | R5-252705 |  | 1 | 100% | 100% |  |  | 100%
|  | 38.521-1 Tx | 6.5D.2 | Out of band emission for UL MIMO
45 | Y | 38.521-1 Tx | 6.5D.2.2_2 | Spectrum emission mask for UL MIMO for UE supporting 4Tx | Ref: 38.101-1 clause 6.5D.2 | Huawei, HiSilicon | RAN5#109 (Nov-25) | R5-253405 | MU/TT is FFS | 1 | 80% | 80% |  |  | 80%
46 | Y | 38.521-1 Tx | 6.5D.2.3_1 | Additional spectrum emission mask for UL MIMO for UE supporting 4Tx | Ref: 38.101-1 clause 6.5D.2 | Huawei, HiSilicon | RAN5#109 (Nov-25) | R5-255258 | Test coverage for the NS_XXs other than NS_04 is FFS. MU and TT are FFS. | 1 | 80% | 80% |  |  | 80%
|  | 38.521-1 Tx | 6.5D.2.4 | Adjacent channel leakage ratio for UL MIMO
47 | Y | 38.521-1 Tx | 6.5D.2.4.1_2 | NR ACLR for UL MIMO for UE supporting 4Tx | Ref: 38.101-1 clause 6.5D.2 | Huawei, HiSilicon | RAN5#109 (Nov-25) | R5-253405 | MU/TT is FFS | 1 | 80% | 80% |  |  | 80%
48 | Y | 38.521-1 Tx | 6.5D.2.4.2_2 | UTRA ACLR for UL MIMO for UE supporting 4Tx | Ref: 38.101-1 clause 6.5D.2 | Huawei, HiSilicon | RAN5#109 (Nov-25) | R5-254450 | No test case details are specified. No applicable network signalling label for the UTRA ACLR requirements | 1 | 100% | 100% |  |  | 100%
49 |  | 38.521-1 Tx | 6.5D.3_3 | Spurious emissions for UL MIMO for UE supporting 4Tx | New sub-clause header |  |  | R5-252705 |  | 0.1 | 100% | 100% |  |  | 100%
50 | Y | 38.521-1 Tx | 6.5D.3_3.1 | General spurious emissions for UL MIMO for UE supporting 4Tx | Ref: 38.101-1 clause 6.5D.3 | Huawei, HiSilicon | RAN5#109 (Nov-25) | R5-252705 R5-254556 | MU/TT is FFS | 1 | 80% | 80% |  |  | 80%
51 | Y | 38.521-1 Tx | 6.5D.3_3.2 | Spurious emission for UE co-existence for UL MIMO for UE supporting 4Tx | Ref: 38.101-1 clause 6.5D.3 | Huawei, HiSilicon | RAN5#109 (Nov-25) | R5-253409 R5-254556 | MU/TT is FFS | 1 | 80% | 80% |  |  | 80%
52 | Y | 38.521-1 Tx | 6.5D.3_3.3 | Additional spurious emissions for UL MIMO for UE supporting 4Tx | Ref: 38.101-1 clause 6.5D.3 | Huawei, HiSilicon | RAN5#109 (Nov-25) | R5-255258 | There are NS-XXs other than NS_04 and NS_47 that are FFS. MU and TT are FFS. | 1 | 80% | 80% |  |  | 80%
52 | Y | 38.521-1 Tx | 6.5D.4_2 | Transmit intermodulation for UL MIMO for UE supporting 4Tx | Ref: 38.101-1 clause 6.5D.4 | Huawei, HiSilicon | RAN5#109 (Nov-25) | R5-252705 R5-254556 |  | 1 | 100% | 100% |  |  | 100%
|  | 38.521-1 Tx | 6.5G | Output RF spectrum emissions for Tx Diversity
53 | Y | 38.521-1 Tx | 6.5G.1_1 | Occupied bandwidth for Tx Diversity for UE supporting 4Tx | Ref: 38.101-1 clause 6.5G.1 | Huawei, HiSilicon | RAN5#109 (Nov-25) | R5-253429 |  | 1 | 100% | 100% |  |  | 100%
|  | 38.521-1 Tx | 6.5G.2 | Out of band emission for Tx Diversity
54 | Y | 38.521-1 Tx | 6.5G.2.1_1 | Spectrum emission mask for Tx Diversity for UE supporting 4Tx | Ref: 38.101-1 clause 6.5G.2 | Huawei, HiSilicon | RAN5#109 (Nov-25) | R5-253419 | MU/TT is FFS | 1 | 80% | 80% |  |  | 80%
55 | Y | 38.521-1 Tx | 6.5G.2.2_1 | Additional spectrum emission mask for Tx Diversity for UE supporting 4Tx | Ref: 38.101-1 clause 6.5G.2 | Huawei, HiSilicon | RAN5#109 (Nov-25) | R5-255354 | MU/TT is FFS | 1 | 80% | 80% |  |  | 80%
|  | 38.521-1 Tx | 6.5G.2.3 | Adjacent channel leakage ratio for Tx Diversity
57 | Y | 38.521-1 Tx | 6.5G.2.3.1_1 | NR ACLR for Tx Diversity for Tx Diversity for UE supporting 4Tx | Ref: 38.101-1 clause 6.5G.2 | Huawei, HiSilicon | RAN5#109 (Nov-25) | R5-253419 R5-254450 R5-254556 | MU/TT is FFS | 1 | 80% | 80% |  |  | 80%
58 | Y | 38.521-1 Tx | 6.5G.2.3.2_1 | UTRA ACLR for Tx Diversity for UE supporting 4Tx | Ref: 38.101-1 clause 6.5G.2 | Huawei, HiSilicon | RAN5#109 (Nov-25) | R5-254450 | No test case details are specified. No applicable network signalling label for the UTRA ACLR requirements. | 1 | 100% | 100% |  |  | 100%
|  | 38.521-1 Tx | 6.5G.3 | Spurious emission for Tx Diversity
59 | Y | 38.521-1 Tx | 6.5G.3.1_1 | General spurious emissions for Tx Diversity for UE supporting 4Tx | Ref: 38.101-1 clause 6.5G.3 | Huawei, HiSilicon | RAN5#109 (Nov-25) | R5-253433 | MU/TT is FFS | 1 | 80% | 80% |  |  | 80%
60 | Y | 38.521-1 Tx | 6.5G.3.2_1 | Spurious emissions for UE co-existence for Tx Diversity for UE supporting 4Tx | Ref: 38.101-1 clause 6.5G.3 | Huawei, HiSilicon | RAN5#109 (Nov-25) | R5-253434 | MU/TT is FFS | 1 | 80% | 80% |  |  | 80%
61 | Y | 38.521-1 Tx | 6.5G.3.3_1 | Additional spurious emissions for Tx Diversity for UE supporting 4Tx | Ref: 38.101-1 clause 6.5G.3 | Huawei, HiSilicon | RAN5#109 (Nov-25) | R5-255354 | MU/TT is FFS | 1 | 80% | 80% |  |  | 80%
62 | Y | 38.521-1 Tx | 6.5G.4_1 | Transmit intermodulation for Tx Diversity for UE supporting 4Tx | Ref: 38.101-1 clause 6.5G.4 | Huawei, HiSilicon | RAN5#109 (Nov-25) | R5-253429 R5-254451 R5-254556 |  | 1 | 100% | 100% |  |  | 100%
TS 38.521-1: FR1 RF test cases - Rx
63 |  | 38.521-1 Rx | 7.2 | Diversity characteristics | Adding 8Rx related description | Huawei, HiSilicon | RAN5#109 (Nov-25) | R5-247750 |  | 0.5 | 100% | 100% |  |  | 100%
64 |  | 38.521-1 Rx | 7.3 | Reference sensitivity | Updating the minimum requirement and testing part for 8Rx UE | Huawei, HiSilicon | RAN5#109 (Nov-25) | R5-247750 |  | 0.5 | 100% | 100% |  |  | 100%
151 |  | 38.521-1 Rx | 7.3A | Reference sensitivity for CA | Updating the minimum requirement and testing part for UE supporting 8Rx or Lower-MSD | Huawei, HiSilicon | RAN5#109 (Nov-25) | R5-247013 R5-247918 R5-247919 R5-251540 R5-247751 |  | 0.5 | 100% | 100% |  |  | 100%
149 |  | 38.521-1 Rx | 7.3C | Reference sensitivity for SUL | Updating the minimum requirement and testing part for 8Rx UE | Huawei, HiSilicon | RAN5#109 (Nov-25) | R5-247017 R5-250433 |  | 0.5 | 100% | 100% |  |  | 100%
|  | 38.521-1 Rx | 7.3D | Reference sensitivity for UL MIMO
66 | Y | 38.521-1 Rx | 7.3D.2_3 | Reference sensitivity power level for UL MIMO for UE supporting 4Tx | Ref: 38.101-1 clause 7.3D | Huawei, HiSilicon | RAN5#109 (Nov-25) | R5-252661 |  | 1 | 100% | 100% |  |  | 100%
|  | 38.521-1 Rx | 7.3G | Reference sensitivity for Tx Diversity
67 | Y | 38.521-1 Rx | 7.3G.1 | Reference sensitivity for Tx Diversity for UE supporting 4Tx | Ref: 38.101-1 clause 7.3G | Huawei, HiSilicon | RAN5#109 (Nov-25) | R5-247018 R5-252676 |  | 1 | 100% | 100% |  |  | 100%
68 | Y | 38.521-1 Rx | 7.4D_2 | Maximum input level for UL MIMO for UE supporting 4Tx | Ref: 38.101-1 clause 7.4D | Huawei, HiSilicon | RAN5#109 (Nov-25) | R5-255259 |  | 1 | 100% | 100% |  |  | 100%
|  | 38.521-1 Rx | 7.4G | Maximum input level for Tx Diversity |  |  |  | R5-255259 |  | 0.1 | 100% | 100% |  |  | 100%
69 | Y | 38.521-1 Rx | 7.4G.1 | Maximum input level for Tx Diversity for UE supporting 4Tx | Ref: 38.101-1 clause 7.4G | Huawei, HiSilicon | RAN5#109 (Nov-25) | R5-255259 |  | 1 | 100% | 100% |  |  | 100%
70 | Y | 38.521-1 Rx | 7.5D_2 | Adjacent channel selectivity for UL MIMO for UE supporting 4Tx | Ref: 38.101-1 clause 7.5D | Huawei, HiSilicon | RAN5#109 (Nov-25) | R5-252662 R5-254557 |  | 1 | 100% | 100% |  |  | 100%
|  | 38.521-1 Rx | 7.5G | Adjacent channel selectivity for Tx Diversity |  |  |  | R5-252706 |  | 0.1 | 100% | 100% |  |  | 100%
71 | Y | 38.521-1 Rx | 7.5G.1 | Adjacent channel selectivity for Tx Diversity for UE supporting 4Tx | Ref: 38.101-1 clause 7.5G | Huawei, HiSilicon | RAN5#109 (Nov-25) | R5-252706 R5-254557 |  | 1 | 100% | 100% |  |  | 100%
|  | 38.521-1 Rx | 7.6D | Blocking characteristics for UL MIMO
72 | Y | 38.521-1 Rx | 7.6D.2_2 | In-band blocking for UL MIMO for UE supporting 4Tx | Ref: 38.101-1 clause 7.6D | Huawei, HiSilicon | RAN5#109 (Nov-25) | R5-252663 R5-254557 |  | 1 | 100% | 100% |  |  | 100%
73 | Y | 38.521-1 Rx | 7.6D.3_2 | Out-of-band blocking for UL MIMO for UE supporting 4Tx | Ref: 38.101-1 clause 7.6D | Huawei, HiSilicon | RAN5#109 (Nov-25) | R5-252663 R5-254557 |  | 1 | 100% | 100% |  |  | 100%
74 | Y | 38.521-1 Rx | 7.6D.4_2 | Narrow band blocking for UL MIMO for UE supporting 4Tx | Ref: 38.101-1 clause 7.6D | Huawei, HiSilicon | RAN5#109 (Nov-25) | R5-252663 R5-254557 |  | 1 | 100% | 100% |  |  | 100%
|  | 38.521-1 Rx | 7.6G | Blocking characteristics for Tx Diversity |  |  |  | R5-252707 |  | 0.1 | 100% | 100% |  |  | 100%
75 | Y | 38.521-1 Rx | 7.6G.1 | In-band blocking for Tx Diversity for UE supporting 4Tx | Ref: 38.101-1 clause 7.6G | Huawei, HiSilicon | RAN5#109 (Nov-25) | R5-252707 R5-254557 |  | 1 | 100% | 100% |  |  | 100%
76 | Y | 38.521-1 Rx | 7.6G.2 | Out-of-band blocking for Tx Diversity for UE supporting 4Tx | Ref: 38.101-1 clause 7.6G | Huawei, HiSilicon | RAN5#109 (Nov-25) | R5-247021 R5-252322 R5-254557 |  | 1 | 100% | 100% |  |  | 100%
77 | Y | 38.521-1 Rx | 7.6G.3 | Narrow band blocking for Tx Diversity for UE supporting 4Tx | Ref: 38.101-1 clause 7.6G | Huawei, HiSilicon | RAN5#109 (Nov-25) | R5-247021 R5-252322 R5-254557 |  | 1 | 100% | 100% |  |  | 100%
78 | Y | 38.521-1 Rx | 7.7D_2 | Spurious response for UL MIMO for UE supporting 4Tx | Ref: 38.101-1 clause 7.7D | Huawei, HiSilicon | RAN5#109 (Nov-25) | R5-247752 R5-252664 R5-254557 |  | 1 | 100% | 100% |  |  | 100%
|  | 38.521-1 Rx | 7.7G | Spurious response for Tx Diversity |  |  |  |  | Title needs to be updated
79 | Y | 38.521-1 Rx | 7.7G.1 | Spurious response for Tx Diversity for UE supporting 4Tx | Ref: 38.101-1 clause 7.7G | Huawei, HiSilicon | RAN5#109 (Nov-25) | R5-252322 |  | 1 | 100% | 100% |  |  | 100%
|  | 38.521-1 Rx | 7.8D | Intermodulation characteristics for UL MIMO
80 | Y | 38.521-1 Rx | 7.8D.2_2 | Wide band Intermodulation for UL MIMO for UE supporting 4Tx | Ref: 38.101-1 clause 7.8D | Huawei, HiSilicon | RAN5#109 (Nov-25) | R5-254559 |  | 1 | 100% | 100% |  |  | 100%
|  | 38.521-1 Rx | 7.8G | Intermodulation characteristics for Tx Diversity |  |  |  | R5-254559 |  | 0.1 | 100% | 100% |  |  | 100%
81 | Y | 38.521-1 Rx | 7.8G.1 | Wide band Intermodulation for Tx Diversity for UE supporting 4Tx | Ref: 38.101-1 clause 7.7G | Huawei, HiSilicon | RAN5#109 (Nov-25) | R5-254559 |  | 1 | 100% | 100% |  |  | 100%
TS 38.521-3: FR1 and FR2 Interworking operation with other radios RF test cases - Rx
82 |  | 38.521-3 Rx | 7.1 | General | Adding general requirements for UE equipped with 8Rx |  | RAN5#109 (Nov-25) |  |  | 0.5 | 0% |  | 0% |  |  | 0%
83 |  | 38.521-3 Rx | 7.3B.1 | General | Adding general requirements for UE equipped with 8Rx |  | RAN5#109 (Nov-25) |  |  | 0.5 | 0% |  | 0% |  |  | 0%
84 |  | 38.521-3 Rx | 7.3B.2.0 | Minimum Conformance Requirements of Reference sensitivity for DC | Updating the minimum requirement for UE supporting 8Rx; adding requirements for lower-MSD for inter-band ENDC in FR1 |  | RAN5#109 (Nov-25) |  |  | 0.5 | 0% |  | 0% |  |  | 0%
85 |  | 38.521-3 Rx | 7.3B.2.3 | Reference sensitivity for Inter-band EN-DC within FR1 (2 CCs) | Updating the testing part for UE supporting 8Rx and lower-MSD |  | RAN5#109 (Nov-25) |  |  | 0.5 | 0% |  | 0% |  |  | 0%
86 |  | 38.521-3 Rx | 7.3B.2.3_1.1 | Reference sensitivity for EN-DC within FR1 (3 CCs) | Updating the testing part for UE supporting 8Rx and lower-MSD |  | RAN5#109 (Nov-25) |  |  | 0.5 | 0% |  | 0% |  |  | 0%
87 |  | 38.521-3 Rx | 7.4B | Maximum Input Level for DC | Updating the test priority in case of Rx antenna ports in the test case.7.4B.1 and 7,4B.2 for 8Rx UE | CAICT | RAN5#109 (Nov-25) |  |  | 0.5 | 0% |  | 0% |  |  | 0%
88 |  | 38.521-3 Rx | 7.5B.1 | Adjacent Channel Selectivity for intra-band contiguous EN-DC (2 CCs) | Updating the test priority in case of Rx antenna ports in the test case for 8Rx UE | CAICT | RAN5#109 (Nov-25) |  |  | 0.5 | 0% |  | 0% |  |  | 0%
89 |  | 38.521-3 Rx | 7.6B.2 | Inband blocking for DC | Updating the test priority in case of Rx antenna ports in the test case 7.6B.2.1 and 7.6B.2.3_1 for 8Rx UE | CAICT | RAN5#109 (Nov-25) |  |  | 0.5 | 0% |  | 0% |  |  | 0%
90 |  | 38.521-3 Rx | 7.6B.3 | Out-of-band blocking for DC | Updating the test priority in case of Rx antenna ports in the test case 7.6B.3.1, 7.6B.3.3 and 7.6b.3.3_1 for 8Rx UE | CAICT | RAN5#109 (Nov-25) |  |  | 0.5 | 0% |  | 0% |  |  | 0%
91 |  | 38.521-3 Rx | 7.6B.4 | Narrow band blocking for DC | Updating the test priority in case of Rx antenna ports in the test case 7.6B.4.1 and 7.6B.4.3_1 for 8Rx UE | CAICT | RAN5#109 (Nov-25) |  |  | 0.5 | 0% |  | 0% |  |  | 0%
92 |  | 38.521-3 Rx | 7.8B.2 | Wide band Intermodulation | Updating the test priority in case of Rx antenna ports in the test case 7.8B.2.1 and 7.8B.2.3_1 for 8Rx UE | CAICT | RAN5#109 (Nov-25) |  |  | 0.5 | 0% |  | 0% |  |  | 0%
TS 38.521-4: Demod/CSI reporting test cases
93 |  | 38.521-4 | Clause 1-3 | Definition of terms, symbols and abbreviations | Updating definition for Baseline SU-MIMO 8Rx Receiver and Simplified SU-MIMO 8Rx Receiver | ChinaTelecom | RAN5#109 (Nov-25) | R5-244205 |  | 0.1 | 100% | 100% | 100% |  | 100% | 100%
94 |  | 38.521-4 | 5.1.1.2 | Applicability of requirements for different number of RX antenna ports | Updating Applicability of requirements for UE supports 8Rx | ChinaTelecom | RAN5#109 (Nov-25) | R5-244206 R5-250413 |  | 0.5 | 100% | 100% | 100% |  | 100% | 100%
95 |  | 38.521-4 | 5.1.1.3 | Applicability of requirements for optional UE features | Updating Applicability of requirements for 8Rx related optional UE capabilities | ChinaTelecom | RAN5#109 (Nov-25) | R5-244206 R5-255654 |  | 0.5 | 100% | 100% | 100% |  | 100% | 100%
96 |  | 38.521-4 | 5.1.1.5.5 | Applicability and test rules for different CA configurations and bandwidth combination sets for 8Rx UE | Updating Applicability rule for different CA configurations and bandwidth combination sets for 8Rx UE | ChinaTelecom | RAN5#109 (Nov-25) | R5-244206 |  | 0.5 | 100% | 100% | 100% |  | 100% | 100%
97 |  | 38.521-4 | 5.1.1.5.6 | Applicability rule and antenna connection for CA tests with 8 RX | Updating Applicability rule and antenna connection for CA tests with 8 RX | ChinaTelecom | RAN5#109 (Nov-25) | R5-244206 |  | 0.5 | 100% | 100% | 100% |  | 100% | 100%
98 |  | 38.521-4 | 5.1.1.5.7 | Applicability rule for optional UE features for 8Rx | Updating Applicability rule for optional UE features for 8Rx | ChinaTelecom | RAN5#109 (Nov-25) | R5-244206 R5-255654 |  | 0.5 | 100% | 100% | 100% |  | 100% | 100%
99 |  | 38.521-4 | 5.2.4 | 8RX requirements | New sub-clause header |  |  | R5-256872 |  | 0.1 | 100% (+100%) | 100% (+100%) | 100% (+100%) |  | 100% | 100%
100 |  | 38.521-4 | 5.2.4.1 | FDD | New sub-clause header |  |  | R5-256872 |  | 0.1 | 100% (+100%) | 100% (+100%) | 100% (+100%) |  | 100% | 100%
101 | Y | 38.521-4 | 5.2.4.1.1_1 | 8Rx FDD FR1 PDSCH mapping Type A performance - 2x8 MIMO with baseline receiver for both SA and NSA | Ref: 38.101-4 clause 5.2.4.1.1, Test number 1-1 | Huawei, HiSilicon | RAN5#109 (Nov-25) | R5-256872 | This test case is incomplete. Following aspects are either missing or TBD -The connection diagram is TBD. -Message content is FFS. -Test applicability is FFS in 38.522. -MU/TT is pending and the final test requirement value is TBD. | 1 | 30% (+30%) | 30% (+30%) | 30% (+30%) |  | 30% | 30%
102 | Y | 38.521-4 | 5.2.4.1.1_2 | 8Rx FDD FR1 PDSCH mapping Type A performance - 4x8 MIMO with baseline receiver for both SA and NSA | Ref: 38.101-4 clause 5.2.4.1.1, Test number 3-1 | Huawei, HiSilicon | RAN5#109 (Nov-25) |  |  | 1 | 0% | 0% | 0% |  | 0% | 0%
103 | Y | 38.521-4 | 5.2.4.1.1_3 | 8Rx FDD FR1 PDSCH mapping Type A performance - 2x8 MIMO with simplified receiver for both SA and NSA | Ref: 38.101-4 clause 5.2.4.1.1, Test number 2-1 | Huawei, HiSilicon | RAN5#109 (Nov-25) |  |  | 1 | 0% | 0% | 0% |  | 0% | 0%
104 | Y | 38.521-4 | 5.2.4.1.1_4 | 8Rx FDD FR1 PDSCH mapping Type A performance - 4x8 MIMO with simplified receiver for both SA and NSA | Ref: 38.101-4 clause 5.2.4.1.1, Test number 4-1 | Huawei, HiSilicon | RAN5#109 (Nov-25) |  |  | 1 | 0% | 0% | 0% |  | 0% | 0%
105 | Y | 38.521-4 | 5.2.4.1.1_5 | 8Rx FDD FR1 PDSCH mapping Type A performance - 8x8 MIMO with baseline receiver for both SA and NSA | Ref: 38.101-4 clause 5.2.4.1.1, Test number 5-1 | Huawei, HiSilicon | RAN5#109 (Nov-25) |  |  | 1 | 0% | 0% | 0% |  | 0% | 0%
106 |  | 38.521-4 | 5.2.4.2 | TDD | New sub-clause header |  |  | R5-256867 |  | 0.1 | 100% (+100%) | 100% (+100%) | 100% (+100%) |  | 100% | 100%
107 | Y | 38.521-4 | 5.2.4.2.1_1 | 8Rx TDD FR1 PDSCH mapping Type A performance - 2x8 MIMO with baseline receiver for both SA and NSA | Ref: 38.101-4 clause 5.2.4.2.1, Test number 1-1 | Huawei, HiSilicon | RAN5#109 (Nov-25) |  |  | 1 | 0% | 0% | 0% |  | 0% | 0%
108 | Y | 38.521-4 | 5.2.4.2.1_2 | 8Rx TDD FR1 PDSCH mapping Type A performance - 4x8 MIMO with baseline receiver for both SA and NSA | Ref: 38.101-4 clause 5.2.4.2.1, Test number 3-1 | Huawei, HiSilicon | RAN5#109 (Nov-25) |  |  | 1 | 0% | 0% | 0% |  | 0% | 0%
109 | Y | 38.521-4 | 5.2.4.2.1_3 | 8Rx TDD FR1 PDSCH mapping Type A performance - 2x8 MIMO with simplified receiver for both SA and NSA | Ref: 38.101-4 clause 5.2.4.2.1, Test number 2-1 | Qualcomm | RAN5#109 (Nov-25) | R5-256867 | This test case is incomplete in the following aspects: - Initial conditions and message contents are FFS; - Connection diagram for 8Rx is TBD in 38.508-1 - MU/TT analysis pending | 1 | 50% (+50%) | 50% (+50%) | 50% (+50%) |  | 50% | 50%
110 | Y | 38.521-4 | 5.2.4.2.1_4 | 8Rx TDD FR1 PDSCH mapping Type A performance - 4x8 MIMO with simplified receiver for both SA and NSA | Ref: 38.101-4 clause 5.2.4.2.1, Test number 4-1 | Qualcomm | RAN5#109 (Nov-25) | R5-256867 | This test case is incomplete in the following aspects: - Initial conditions and message contents are FFS; - Connection diagram for 8Rx is TBD in 38.508-1 - MU/TT analysis pending | 1 | 50% (+50%) | 50% (+50%) | 50% (+50%) |  | 50% | 50%
111 | Y | 38.521-4 | 5.2.4.2.1_5 | 8Rx TDD FR1 PDSCH mapping Type A performance - 8x8 MIMO with baseline receiver for both SA and NSA | Ref: 38.101-4 clause 5.2.4.2.1, Test number 5-1 | Huawei, HiSilicon | RAN5#109 (Nov-25) |  |  | 1 | 0% | 0% | 0% |  | 0% | 0%
112 |  | 38.521-4 | 5.2A.4 | 8RX requirements | New sub-clause header |  |  |  |  | 0.1 | 0% | 0% | 0% |  | 0% | 0%
113 |  | 38.521-4 | 5.2A.4.1 | Requirements for 8RX normal PDSCH | New sub-clause header |  |  |  |  | 0.1 | 0% | 0% | 0% |  | 0% | 0%
114 |  | 38.521-4 | 5.2A.4.1.0 | Minimum conformance requirements for 8RX normal PDSCH | adding minimum requirements for 8Rx only | Huawei, HiSilicon | RAN5#109 (Nov-25) |  |  | 0.5 | 0% | 0% | 0% |  | 0% | 0%
115 | Y | 38.521-4 | 5.2A.4.1.1 | 8Rx Normal PDSCH Demodulation Performance with 8x8 MIMO with baseline receiver for CA (2DL CA) | Ref: 38.101-4 clause 5.2A.4.1, Table 5.2A.4.1-3, Table 5.2A.4.1-6 baseline receiver only | Huawei, HiSilicon | RAN5#109 (Nov-25) |  |  | 1 | 0% | 0% | 0% |  | 0% | 0%
116 | Y | 38.521-4 | 5.2A.4.1.2 | 8Rx Normal PDSCH Demodulation Performance with 8x8 MIMO with baseline receiver for CA (3DL CA) | Ref: 38.101-4 clause 5.2A.4.1, Table 5.2A.4.1-3, Table 5.2A.4.1-6 baseline receiver only | Huawei, HiSilicon | RAN5#109 (Nov-25) |  |  | 1 | 0% | 0% | 0% |  | 0% | 0%
117 | Y | 38.521-4 | 5.2A.4.1.3 | 8Rx Normal PDSCH Demodulation Performance with 8x8 MIMO with baseline receiver for CA (4DL CA) | Ref: 38.101-4 clause 5.2A.4.1, Table 5.2A.4.1-3, Table 5.2A.4.1-6 baseline receiver only | Huawei, HiSilicon | RAN5#109 (Nov-25) |  |  | 1 | 0% | 0% | 0% |  | 0% | 0%
118 |  | 38.521-4 | 5.2A.4A | 8RX with 2Rx or 4Rx requirements | New sub-clause header |  |  |  |  | 0.1 | 0% | 0% | 0% |  | 0% | 0%
119 |  | 38.521-4 | 5.2A.4A.1 | Requirements for 8RX with 2Rx or 4Rx normal PDSCH | New sub-clause header |  |  |  |  | 0.1 | 0% | 0% | 0% |  | 0% | 0%
120 |  | 38.521-4 | 5.2A.4A.1.0 | Minimum conformance requirements for 8RX with 2Rx or 4Rx normal PDSCH | Adding minimum requirements for 2Rx/4Rx - 8Rx CA band combinations applicable for CA combinations between 8Rx and 4Rx or 2Rx | Huawei, HiSilicon | RAN5#109 (Nov-25) |  |  | 0.5 | 0% | 0% | 0% |  | 0% | 0%
121 | Y | 38.521-4 | 5.2A.4A.1.1 | 8Rx with 2Rx or 4Rx Normal PDSCH Demodulation Performance with 2x8 MIMO for CA (2DL CA) | Ref: 38.101-4 clause 5.2A.4.1, Table 5.2A.4.1-1/2/4/5 Apply to both baseline and simplified receiver | Huawei, HiSilicon | RAN5#109 (Nov-25) |  |  | 1 | 0% | 0% | 0% |  | 0% | 0%
122 | Y | 38.521-4 | 5.2A.4A.1.2 | 8Rx with 2Rx or 4Rx Normal PDSCH Demodulation Performance with 2x8 MIMO for CA (3DL CA) | Ref: 38.101-4 clause 5.2A.4.1, Table 5.2A.4.1-1/2/4/5 Apply to both baseline and simplified receiver | Huawei, HiSilicon | RAN5#109 (Nov-25) |  |  | 1 | 0% | 0% | 0% |  | 0% | 0%
123 | Y | 38.521-4 | 5.2A.4A.1.3 | 8Rx with 2Rx or 4Rx Normal PDSCH Demodulation Performance with 2x8 MIMO for CA (4DL CA) | Ref: 38.101-4 clause 5.2A.4.1, Table 5.2A.4.1-1/2/4/5 Apply to both baseline and simplified receiver | Huawei, HiSilicon | RAN5#109 (Nov-25) |  |  | 1 | 0% | 0% | 0% |  | 0% | 0%
124 | Y | 38.521-4 | 5.5.1_1 | FR1 Sustained downlink data rate performance for single carrier for 8Rx | Adding separate SDR test for 8Rx capable UEs Ref: 38.101-4 clause 5.5.1 | Qualcomm | RAN5#109 (Nov-25) | R5-256869 | This test case is incomplete in the following aspects: - Initial conditions and message contents are FFS; - Connection diagram for 8Rx is TBD in 38.508-1 - MU/TT analysis pending | 1 | 50% (+50%) | 50% (+50%) | 50% (+50%) |  | 50% | 50%
125 | Y | 38.521-4 | 5.5.2_1 | FR1 Sustained downlink data rate performance for single carrier with DL1024QAM for 8Rx | Adding separate SDR test for 8Rx and DL1024QAM capable UEs Ref: 38.101-4 clause 5.5.2 | Qualcomm | RAN5#109 (Nov-25) |  |  | 1 | 0% | 0% | 0% |  | 0% | 0%
126 | Y | 38.521-4 | 5.5A.1.1_1 | FR1 SDR performance for CA (2DL CA) | Adding separate SDR test for 8Rx capable CA UEs Ref: 38.101-4 clause 5.5A.1 | Huawei, HiSilicon | RAN5#109 (Nov-25) |  |  | 1 | 0% | 0% | 0% |  | 0% | 0%
127 |  | 38.521-4 | 6.1.1.2 | Applicability of requirements for different number of RX antenna ports | Updating applicability of requirements for 8Rx Ref: 38.101-4 6.1.1.2 | Huawei, HiSilicon | RAN5#109 (Nov-25) |  |  | 0.5 | 0% | 0% | 0% |  | 0% | 0%
128 |  | 38.521-4 | 6.2.4 | 8RX requirements | New sub-clause header |  |  | R5-256868 |  | 0.1 | 100% (+100%) | 100% (+100%) | 100% (+100%) |  | 100% | 100%
129 |  | 38.521-4 | 6.2.4.1 | FDD | New sub-clause header |  |  | R5-256868 |  | 0.1 | 100% (+100%) | 100% (+100%) | 100% (+100%) |  | 100% | 100%
130 |  | 38.521-4 | 6.2.4.1.1 | CQI reporting definition under AWGN conditions | New sub-clause header |  |  |  |  | 0.1 | 0% | 0% | 0% |  | 0% | 0%
131 | Y | 38.521-4 | 6.2.4.1.1.1 | 8Rx FDD FR1 periodic CQI reporting under AWGN conditions for both SA and NSA | Ref: 38.101-4 clause 6.2.4.1.1.1 | Huawei, HiSilicon | RAN5#109 (Nov-25) |  |  | 1 | 0% | 0% | 0% |  | 0% | 0%
132 |  | 38.521-4 | 6.2.4.2 | TDD | New sub-clause header |  |  | R5-256868 |  | 0.1 | 100% (+100%) | 100% (+100%) | 100% (+100%) |  | 100% | 100%
133 |  | 38.521-4 | 6.2.4.2.1 | CQI reporting definition under AWGN conditions | New sub-clause header |  |  | R5-256868 |  | 0.1 | 100% (+100%) | 100% (+100%) | 100% (+100%) |  | 100% | 100%
134 | Y | 38.521-4 | 6.2.4.2.1.1 | 8Rx TDD FR1 periodic CQI reporting under AWGN conditions for both SA and NSA | Ref: 38.101-4 clause 6.2.4.2.1.1 | Qualcomm | RAN5#109 (Nov-25) | R5-256868 | Editor’s note: - Message contents is FFS | 1 | 90% (+90%) | 90% (+90%) | 90% (+90%) |  | 90% | 90%
135 |  | 38.521-4 | Annex A.3.2 | Reference measurement channels for PDSCH performance requirements | Introducing new PDSCH Reference Channel | ChinaTelecom | RAN5#109 (Nov-25) | R5-244204 R5-255656 |  | 0.5 | 100% | 100% | 100% |  | 100% | 100%
136 |  | 38.521-4 | Annex B.1.3 | UE Receiver with 8Rx | Adding channel matrices for 8Rx | ChinaTelecom | RAN5#109 (Nov-25) | R5-244203 |  | 0.5 | 100% | 100% | 100% |  | 100% | 100%
137 |  | 38.521-4 | Annex B.2.3.1 | MIMO Correlation Matrices using Uniform Linear Array (ULA) | Adding MIMO Correlation Matrices using Uniform Linear Array for 8Rx | ChinaTelecom | RAN5#109 (Nov-25) | R5-244203 R5-250416 |  | 0.5 | 100% | 100% | 100% |  | 100% | 100%
138 |  | 38.521-4 | Annex F | Measurement uncertainties and test tolerances | Updating Measurement uncertainties and test tolerances for 8Rx test cases | Huawei, HiSilicon | RAN5#109 (Nov-25) | R5-256867 R5-256868 R5-256869 |  | 1 | 15% (+15%) | 15% (+15%) | 15% (+15%) |  | 15% | 15%
TS 38.522: Applicability for RF, Demod/CSI reporting and RRM test cases
139 |  | 38.522 | 4.0 | Test case conditions and selection criteria | Add new ICS statements. |  | TBD |  |  | 1 | 0% | 0% | 0% |  | 0% | 0%
140 |  | 38.522 | 4.1.1 | FR1 standalone conformance test cases | Add test case applicability statements for the new test cases introduced for 38.521-1 | Huawei, HiSilicon | TBD | R5-253588 R5-255336 |  | 1 | 80% | 80% |  |  | 80%
141 |  | 38.522 | 4.1.3 | NR interworking between NR FR1 and NR FR2 and between NR and LTE conformance test cases | Add test case applicability statements for the new test cases introduced for 38.521-3 |  | TBD |  |  | 1 | 0% |  | 0% |  |  | 0%
142 |  | 38.522 | 4.1.4 | Performance conformance test cases | Add test case applicability statements for the new test cases introduced for 38.521-4 |  | TBD | R5-256557 |  | 1 | 15% (+15%) | 15% (+15%) | 15% (+15%) |  | 15% | 15%
TS 38.533: RRM test cases
143 |  | 38.533 | Annex D | Antenna connection for 8 Rx capable UEs | Adding antenna connection description for 8Rx UE | Huawei, HiSilicon | RAN5#109 (Nov-25) | R5-245881 |  | 1 | 100% | 100% |  |  | 100%
TR 38.905: Test Point analysis receiver and transmitter test cases
|  | 38.905 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
144 |  | 38.905 | <Clause> | <Title of new sub-clause header> | New sub-clause header |  | TBD |  |  | 0
145 |  | 38.905 | 4.1 | Test point analysis for FR1 test cases in TS 38.521-1 | Add TP analysis for test cases in 38.521-1 | Huawei, HiSilicon | RAN5#109 (Nov-25) | R5-252317 R5-253420 |  | 1 | 30% | 30% |  |  | 30%
146 |  | 38.905 | 4.3 | Test point analysis for test cases in TS 38.521-3 | Add TP analysis for test cases in 38.521-3 |  | RAN5#109 (Nov-25) |  |  | 1 | 0% |  | 0% |  |  | 0%
End of workplan items. Note! Do not remove this row. Introduce new work plan rows/items above this row.
Note on A6: Unique ID for WP items (unique within the sub-area work plan) Note! As WP item numbers may be referenced from outside of this WP that means: - Do not change number for WP items that have been published. - Do not re-use WP item numbers if a WP item is deleted
Note on B6: Set to Y if the WP item represents a new test case that will be specified in RAN5 test specifications as an executable test case else leave blank.
Note on K6: The WP item's weight number is used to set the reletive weights between WP items used in the overall calculation of completeness. Setting it to 0 for a WP item means that it will not be included at all in the calculation.