## Cover sheet
3GPP TSG-RAN WG5 Meeting #109 | [7 empty] | R5-256171
Dallas, US, 17 - 21 Nov 2025
Agenda Item: | 7.5.2
Source: | China Telecom, Huawei
Title: | WP for NR_channel_raster_enh-UEConTest
Work item code: | NR_channel_raster_enh-UEConTest
Release: | Rel-18
Document for: | Information
RAN5 WP template v3.0.0
1. Introduction
The objective of the present work item is to define the corresponding conformance requirements, the test cases, applicability, test environment and update the relevant conformance specifications for enhanced channel raster requirements introduced by RAN4.
2. Work item status
Estimation of WI overall completion:
Area |  | Completion | Number of new completed test cases (Note 1) | Number of new test cases | Comments
Overall completion |  | 5%(+5%)
Completion Compensation |  | -
| Note 1: | Only test cases completed for all applicable WP areas and sub-areas are counted. For completed test cases per WP areas and WP sub-areas see below.
Estimation WI completion per area and sub-area:
|  | Completion | Number of new completed test cases | Number of new test cases | Comments
SA Option 2 (SA NR) (FR1) |  | 5%(+5%)
FR1 |  | 5%(+5%)
Estimation of completion per TS (area):
|  | TS/TR overall completion |  |  | SA Option 2 (SA NR)
TS/TR Scope | TS/TR | Completion | Number of new completed test cases | Number of new test cases | FR1
[5 empty] | Completion | Number of new completed test cases | Number of new test cases
5GS
5GS Common
Common test environment | 38.508-1
Common ICS | 38.508-2
NR RF/RRM
FR1 RF common parts | 38.521-1
FR1 RF Rx test cases | 38.521-1 Rx
RF test cases for NTN | 38.521-5
Applicability RF. Demod/QSI and RRM test cases | 38.522
Test Point analysis receiver and transmitter test cases | 38.905
5GS RAN and CN protocols
Protocol test cases | 38.523-1
5 References
[1] RP-252544 | New WID on UE Conformance - Channel raster enhancement
Note on B21: Overall completion of the work item reported at an earlier meeting will not be decreased if additional tasks are added or if corrections are made to the work plan. Instead the earlier reported completion status will be kept until necessary progress have been achieved such that completion exceeds the earlier reported completion level. The value of the Completion Compensation value represents the difference in the decrease caused by late additions or corrections to the work plan and the current estimated overall completion. '-' indicates that no compensation is applied.

## WP
WP Title: |  | WP for NR_channel_raster_enh-UEConTest | [10 empty] | Start of workplan status columns. Note! Do not remove this column. | WP item status | End of workplan columns. Note! Do not remove this column.
WI code |  | NR_channel_raster_enh-UEConTest
WP Scope: |  | <WP Scope description>
WP Resp: |  | Lei GAO |  |  | gaol8@chinatelecom.cn | [5 empty] | WP item completion |  |  | SA Option 2 (SA NR)
TS Resp: |  | N/A |  |  | N/A
WP Item ID | Is new test case? | TS/area | Clause | Title | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | Overall | SA Option 2 (SA NR) |  | FR1
0
0
5%
Start of work plan items. Note! Do not remove this row. Introduce new work plan rows/items below this row.
5GS
5GS Common
TS 38.508-1: Common test environment
|  | 38.508-1 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
TBD |  | 38.508-1 | 4.3.1.1.1.1 | Reference test frequencies for NR operating band n1 | Addition of new set of test frequency for enhanced channel raster for band n1 | Ericsson | TBD |  |  | 1
TBD |  | 38.508-1 | 4.3.1.1.1.2 | Reference test frequencies for NR operating band n2 | Addition of new set of test frequency for enhanced channel raster for band n2 | Ericsson | TBD |  |  | TBD
TBD |  | 38.508-1 | 4.3.1.1.1.3 | Reference test frequencies for NR operating band n3 | Addition of new set of test frequency for enhanced channel raster for band n3 | Ericsson | TBD |  |  | 0
TBD |  | 38.508-1 | 4.3.1.1.1.5 | Reference test frequencies for NR operating band n5 | Addition of new set of test frequency for enhanced channel raster for band n5 | Ericsson | TBD |  |  | TBD
TBD |  | 38.508-1 | 4.3.1.1.1.7 | Reference test frequencies for NR operating band n7 | Addition of new set of test frequency for enhanced channel raster for band n7 | Ericsson | TBD |  |  | 0
TBD |  | 38.508-1 | 4.3.1.1.1.8 | Reference test frequencies for NR operating band n8 | Addition of new set of test frequency for enhanced channel raster for band n8 | Ericsson | TBD |  |  | TBD
TBD |  | 38.508-1 | 4.3.1.1.1.12 | Reference test frequencies for NR operating band n12 | Addition of new set of test frequency for enhanced channel raster for band n12 | Ericsson | TBD |  |  | 0
TBD |  | 38.508-1 | 4.3.1.1.1.13 | Reference test frequencies for NR operating band n13 | Addition of new set of test frequency for enhanced channel raster for band n13 | Ericsson | TBD |  |  | TBD
TBD |  | 38.508-1 | 4.3.1.1.1.14 | Reference test frequencies for NR operating band n14 | Addition of new set of test frequency for enhanced channel raster for band n14 | Ericsson | TBD |  |  | 0
TBD |  | 38.508-1 | 4.3.1.1.1.18 | Reference test frequencies for NR operating band n18 | Addition of new set of test frequency for enhanced channel raster for band n18 | Ericsson | TBD |  |  | TBD
TBD |  | 38.508-1 | 4.3.1.1.1.20 | Reference test frequencies for NR operating band n20 | Addition of new set of test frequency for enhanced channel raster for band n20 | Ericsson | TBD |  |  | 0
TBD |  | 38.508-1 | 4.3.1.1.1.24 | Reference test frequencies for NR operating band n24 | Addition of new set of test frequency for enhanced channel raster for band n24 | Ericsson | TBD |  |  | TBD
TBD |  | 38.508-1 | 4.3.1.1.1.25 | Reference test frequencies for NR operating band n25 | Addition of new set of test frequency for enhanced channel raster for band n25 | Ericsson | TBD |  |  | 0
TBD |  | 38.508-1 | 4.3.1.1.1.26 | Reference test frequencies for NR operating band n26 | Addition of new set of test frequency for enhanced channel raster for band n26 | Ericsson | TBD |  |  | TBD
TBD |  | 38.508-1 | 4.3.1.1.1.28 | Reference test frequencies for NR operating band n28 | Addition of new set of test frequency for enhanced channel raster for band n28 | Ericsson | TBD |  |  | 0
TBD |  | 38.508-1 | 4.3.1.1.1.29 | Reference test frequencies for NR operating band n29 | Addition of new set of test frequency for enhanced channel raster for band n29 | Ericsson | TBD |  |  | TBD
TBD |  | 38.508-1 | 4.3.1.1.1.30 | Reference test frequencies for NR operating band n30 | Addition of new set of test frequency for enhanced channel raster for band n30 | Ericsson | TBD |  |  | 0
TBD |  | 38.508-1 | 4.3.1.1.1.34 | Reference test frequencies for NR operating band n34 | Addition of new set of test frequency for enhanced channel raster for band n34 | Ericsson | TBD |  |  | TBD
TBD |  | 38.508-1 | 4.3.1.1.1.38 | Reference test frequencies for NR operating band n38 | Addition of new set of test frequency for enhanced channel raster for band n38 | Ericsson | TBD |  |  | 0
TBD |  | 38.508-1 | 4.3.1.1.1.39 | Reference test frequencies for NR operating band n39 | Addition of new set of test frequency for enhanced channel raster for band n39 |  | TBD |  |  | TBD
TBD |  | 38.508-1 | 4.3.1.1.1.40 | Reference test frequencies for NR operating band n40 | Addition of new set of test frequency for enhanced channel raster for band n40 |  | TBD |  |  | 0
TBD |  | 38.508-1 | 4.3.1.1.1.50 | Reference test frequencies for NR operating band n50 | Addition of new set of test frequency for enhanced channel raster for band n50 |  | TBD |  |  | TBD
TBD |  | 38.508-1 | 4.3.1.1.1.53 | Reference test frequencies for NR operating band n53 | Addition of new set of test frequency for enhanced channel raster for band n53 |  | TBD |  |  | 0
TBD |  | 38.508-1 | 4.3.1.1.1.65 | Reference test frequencies for NR operating band n65 | Addition of new set of test frequency for enhanced channel raster for band n65 |  | TBD |  |  | TBD
TBD |  | 38.508-1 | 4.3.1.1.1.66 | Reference test frequencies for NR operating band n66 | Addition of new set of test frequency for enhanced channel raster for band n66 |  | TBD |  |  | 0
TBD |  | 38.508-1 | 4.3.1.1.1.67 | Reference test frequencies for NR operating band n67 | Addition of new set of test frequency for enhanced channel raster for band n67 |  | TBD |  |  | TBD
TBD |  | 38.508-1 | 4.3.1.1.1.68 | Reference test frequencies for NR operating band n68 | Addition of new set of test frequency for enhanced channel raster for band n68 |  | TBD |  |  | 0
TBD |  | 38.508-1 | 4.3.1.1.1.70 | Reference test frequencies for NR operating band n70 | Addition of new set of test frequency for enhanced channel raster for band n70 |  | TBD |  |  | TBD
TBD |  | 38.508-1 | 4.3.1.1.1.71 | Reference test frequencies for NR operating band n71 | Addition of new set of test frequency for enhanced channel raster for band n71 |  | TBD |  |  | 0
TBD |  | 38.508-1 | 4.3.1.1.1.74 | Reference test frequencies for NR operating band n74 | Addition of new set of test frequency for enhanced channel raster for band n74 |  | TBD |  |  | TBD
TBD |  | 38.508-1 | 4.3.1.1.1.75 | Reference test frequencies for NR operating band n75 | Addition of new set of test frequency for enhanced channel raster for band n75 |  | TBD |  |  | 0
TBD |  | 38.508-1 | 4.3.1.1.1.80 | Reference test frequencies for NR operating band n80 | Addition of new set of test frequency for enhanced channel raster for band n80 |  | TBD |  |  | TBD
TBD |  | 38.508-1 | 4.3.1.1.1.81 | Reference test frequencies for NR operating band n81 | Addition of new set of test frequency for enhanced channel raster for band n81 |  | TBD |  |  | 0
TBD |  | 38.508-1 | 4.3.1.1.1.82 | Reference test frequencies for NR operating band n82 | Addition of new set of test frequency for enhanced channel raster for band n82 |  | TBD |  |  | TBD
TBD |  | 38.508-1 | 4.3.1.1.1.83 | Reference test frequencies for NR operating band n83 | Addition of new set of test frequency for enhanced channel raster for band n83 |  | TBD |  |  | 0
TBD |  | 38.508-1 | 4.3.1.1.1.84 | Reference test frequencies for NR operating band n84 | Addition of new set of test frequency for enhanced channel raster for band n84 |  | TBD |  |  | TBD
TBD |  | 38.508-1 | 4.3.1.1.1.85 | Reference test frequencies for NR operating band n85 | Addition of new set of test frequency for enhanced channel raster for band n85 |  | TBD |  |  | 0
TBD |  | 38.508-1 | 4.3.1.1.1.86 | Reference test frequencies for NR operating band n86 | Addition of new set of test frequency for enhanced channel raster for band n86 |  | TBD |  |  | TBD
TBD |  | 38.508-1 | 4.3.1.1.1.89 | Reference test frequencies for NR operating band n89 | Addition of new set of test frequency for enhanced channel raster for band n89 |  | TBD |  |  | 0
TBD |  | 38.508-1 | 4.3.1.1.1.90 | Reference test frequencies for NR operating band n90 | Addition of new set of test frequency for enhanced channel raster for band n90 |  | TBD |  |  | TBD
TBD |  | 38.508-1 | 4.3.1.1.1.91 | Reference test frequencies for NR operating band n91 | Addition of new set of test frequency for enhanced channel raster for band n91 |  | TBD |  |  | 0
TBD |  | 38.508-1 | 4.3.1.1.1.92 | Reference test frequencies for NR operating band n92 | Addition of new set of test frequency for enhanced channel raster for band n92 |  | TBD |  |  | TBD
TBD |  | 38.508-1 | 4.3.1.1.1.93 | Reference test frequencies for NR operating band n93 | Addition of new set of test frequency for enhanced channel raster for band n93 |  | TBD |  |  | 0
TBD |  | 38.508-1 | 4.3.1.1.1.94 | Reference test frequencies for NR operating band n94 | Addition of new set of test frequency for enhanced channel raster for band n94 |  | TBD |  |  | TBD
TBD |  | 38.508-1 | 4.3.1.1.1.95 | Reference test frequencies for NR operating band n95 | Addition of new set of test frequency for enhanced channel raster for band n95 |  | TBD |  |  | 0
TBD |  | 38.508-1 | 4.3.1.1.1.97 | Reference test frequencies for NR operating band n97 | Addition of new set of test frequency for enhanced channel raster for band n97 |  | TBD |  |  | TBD
TBD |  | 38.508-1 | 4.3.1.1.1.98 | Reference test frequencies for NR operating band n98 | Addition of new set of test frequency for enhanced channel raster for band n98 |  | TBD |  |  | 0
TBD |  | 38.508-1 | 4.3.1.1.1.99 | Reference test frequencies for NR operating band n99 | Addition of new set of test frequency for enhanced channel raster for band n99 |  | TBD |  |  | TBD
TBD |  | 38.508-1 | 4.3.1.1.1.100 | Reference test frequencies for NR operating band n100 | Addition of new set of test frequency for enhanced channel raster for band n100 |  | TBD |  |  | 0
TBD |  | 38.508-1 | 4.3.1.1.1.101 | Reference test frequencies for NR operating band n101 | Addition of new set of test frequency for enhanced channel raster for band n101 |  | TBD |  |  | TBD
TBD |  | 38.508-1 | 4.3.1.1.1.105 | Reference test frequencies for NR operating band n105 | Addition of new set of test frequency for enhanced channel raster for band n105 |  | TBD |  |  | 0
TBD |  | 38.508-1 | 4.3.1.1.1.109 | Reference test frequencies for NR operating band n109 | Addition of new set of test frequency for enhanced channel raster for band n109 |  | TBD |  |  | 1
TBD |  | 38.508-1 | 4.3.1.9 | Test frequencies for NR NTN operating bands | Addition of new set of test frequency for NTN operating band |  | TBD |  |  | 1
TBD |  | 38.508-1 | C.2 | Determination of test frequencies | update how to calculate the new frequencies | Ericsson | TBD |  |  | 1
TS 38.508-2: Common ICS
|  | 38.508-2 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
TBD |  | 38.508-2 | A.4.3.2 | Physical Layer Baseline Implementation Capabilities | Add ICS as needed for the enhanced channel raster. | Ericsson | RAN5#110 (Feb-26) |  |  | TBD
NR RF/RRM
TS 38.521-1: FR1 RF test cases - Common parts (general clauses, Annexes)
|  | 38.521-1 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
TBD |  | 38.521-1 | <Clause> | <Title of new sub-clause header> | New sub-clause header |  | TBD |  |  | 0
TBD |  | 38.521-1 | <Clause> | <Title of task> | <Describe task> |  | TBD |  |  | TBD
TS 38.521-1: FR1 RF test cases - Rx
TBD |  | 38.521-1 Rx | 7.3.2 | Reference sensitivity power level | introducing a note to the reference sensitivity test cases for the verification of UEs supporting enhanced channel raster. | China Telecom | RAN5#110 (Feb-26) |  |  | 1
TBD |  | 38.521-1 Rx | 7.3I.2 | Reference sensitivity power level for RedCap | introducing a note to the reference sensitivity test cases for the verification of UEs supporting enhanced channel raster. | China Telecom | RAN5#110 (Feb-26) |  |  | 1
TBD |  | 38.521-1 Rx | 7.3I.3 | Reference sensitivity power level for eRedCap | introducing a note to the reference sensitivity test cases for the verification of UEs supporting enhanced channel raster. | China Telecom | RAN5#110 (Feb-26) |  |  | 1
TS 38.521-5: RF test of the UE supporting satellite access operation
TBD |  | 38.521-5 | <Clause> | <Title> | Add new ICS statements. |  | TBD |  |  | TBD
TBD |  | 38.521-5 | 7.3.2 | Reference sensitivity | introducing a note to the reference sensitivity test cases for the verification of UEs supporting enhanced channel raster. | China Telecom | RAN5#110 (Feb-26) |  |  | 1
TS 38.522: Applicability for RF, Demod/CSI reporting and RRM test cases
TBD |  | 38.522 | <Clause> | <Title> | Add new ICS statements. |  | TBD |  |  | 0.1
TBD |  | 38.522 | <Clause> | <Title> | Add test case applicability statements for the new test cases introduced for 38.521-x and 38.533. |  | TBD |  |  | 0.1
TR 38.905: Test Point analysis receiver and transmitter test cases
|  | 38.905 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
TBD |  | 38.905 | <Clause> | <Title of new sub-clause header> | New sub-clause header |  | TBD |  |  | 0
RAN and CN protocol
TS 38.523-1: Protocol test cases
|  | 38.523-1 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
RRC
TBD |  | 38.523-1 | 8.1.5.1 | UE capability transfer | UE capability transfer |  | TBD |  |  | 1
End of workplan items. Note! Do not remove this row. Introduce new work plan rows/items above this row.
Note on A6: Unique ID for WP items (unique within the sub-area work plan) Note! As WP item numbers may be referenced from outside of this WP that means: - Do not change number for WP items that have been published. - Do not re-use WP item numbers if a WP item is deleted
Note on B6: Set to Y if the WP item represents a new test case that will be specified in RAN5 test specifications as an executable test case else leave blank.
Note on K6: The WP item's weight number is used to set the reletive weights between WP items used in the overall calculation of completeness. Setting it to 0 for a WP item means that it will not be included at all in the calculation.