## Cover sheet
3GPP TSG-RAN5 Meeting #109 | [7 empty] | R5-256547
Dallas, USA, Nov 17 - 21, 2025
Agenda Item: | 7.4.2
Source: | Qualcomm Inc
Title: | WP - UE Conformance - Requirement for NR frequency range 2 (FR2) multi-Rx chain DL reception
Work item code: | NR_FR2_multiRX_DL-UEConTest
Release: | Rel-18
Document for: | Information
RAN5 WP template v3.0.0
1. Introduction
At RAN#104 the WID Requirement for NR frequency range 2 (FR2) multi-Rx chain DL reception was approved. The purpose of this document is provide the work plan to introduce the requirement for Rel18 NR FR2 Multi-Rx chain DL in the RAN5 specification.
2. Work item status
Estimation of WI overall completion:
Area |  | Completion | Number of new completed test cases (Note 1) | Number of new test cases | Comments
Overall completion |  | 56% | 0 | 13
Completion Compensation |  | -
| Note 1: | Only test cases completed for all applicable WP areas and sub-areas are counted. For completed test cases per WP areas and WP sub-areas see below.
Estimation WI completion per area and sub-area:
|  | Completion | Number of new completed test cases | Number of new test cases | Comments
SA Option 2 (SA NR) (FR2) |  | 55.7% | 0 | 13
FR2 |  | 55.7% | 0 | 13
Estimation of completion per TS (area):
|  | TS/TR overall completion |  |  | SA Option 2 (SA NR)
TS/TR Scope | TS/TR | Completion | Number of new completed test cases | Number of new test cases | FR2
[5 empty] | Completion | Number of new completed test cases | Number of new test cases
5GS
5GS Common
Common test environment | 38.508-1 | 0% |  |  | 0%
Common ICS | 38.508-2 | 100% |  |  | 100%
UE specific test functions | 38.509
NR RF/RRM
FR2 RF common parts | 38.521-2 | 100% |  |  | 100%
FR2 RF Tx test cases | 38.521-2 Tx
FR2 RF Rx test cases | 38.521-2 Rx | 52.9% | 0 | 1 | 52.9% | 0 | 1
FR1 and FR2 Interworking operation with other radios RF common parts | 38.521-3
FR1 and FR2 Interworking operation with other radios RF Tx test cases | 38.521-3 Tx
FR1 and FR2 Interworking operation with other radios RF Rx test cases | 38.521-3 Rx
RF Demod/QSI test cases | 38.521-4 | 60.8% | 0 | 4 | 60.8% | 0 | 4
RRM test cases | 38.533 | 66.3% | 0 | 8 | 66.3% | 0 | 8
Applicability RF. Demod/QSI and RRM test cases | 38.522 | 75% |  |  | 75%
Test Tolerances analysis RRM and RF Rx test cases | 38.903 | 40% |  |  | 40%
Test Point analysis receiver and transmitter test cases | 38.905 | 20% |  |  | 20%
5GS RAN and CN protocols
Protocol test cases | 38.523-1
Applicability Protocol test cases | 38.523-2
Test suites (TTCN) | 38.523-3
5 References
[1] RP-241156 | New WID on UE Conformance - Requirement for NR frequency range 2 (FR2) multi-Rx chain DL reception
[2] R5-245285 | WP - UE Conformance - Requirement for NR frequency range 2 (FR2) multi-Rx chain DL
[3] R5-247135 | WP - UE Conformance - Requirement for NR frequency range 2 (FR2) multi-Rx chain DL
[4] R5-250540 | WP - UE Conformance - Requirement for NR frequency range 2 (FR2) multi-Rx chain DL
[5] R5-252983 | WP - UE Conformance - Requirement for NR frequency range 2 (FR2) multi-Rx chain DL
[5] R5-254875 | WP - UE Conformance - Requirement for NR frequency range 2 (FR2) multi-Rx chain DL
Note on B21: Overall completion of the work item reported at an earlier meeting will not be decreased if additional tasks are added or if corrections are made to the work plan. Instead the earlier reported completion status will be kept until necessary progress have been achieved such that completion exceeds the earlier reported completion level. The value of the Completion Compensation value represents the difference in the decrease caused by late additions or corrections to the work plan and the current estimated overall completion. '-' indicates that no compensation is applied.

## WP
WP Title: |  | WP - UE Conformance - Requirement for NR frequency range 2 (FR2) multi-Rx chain DL | [10 empty] | Start of workplan status columns. Note! Do not remove this column. | WP item status | End of workplan columns. Note! Do not remove this column.
WI code |  | NR_FR2_multiRX_DL-UEConTest
WP Scope: |  | This part of the work plan covers all applicable test cases for NR frequency range 2 (FR2) multi-Rx chain DL Work item
WP Resp: |  | Vijay Balasubramanian |  |  | vijayb@qti.qualcomm.com | [5 empty] | WP item completion |  |  | SA Option 2 (SA NR)
TS Resp: |  | <TS responsible if a new TS is involved> |  |  | <Email to TS responsible>
WP Item ID | Is new test case? | TS/area | Clause | Title | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | Overall | SA Option 2 (SA NR) |  | FR2
55.7%
35
38
5%
Start of work plan items. Note! Do not remove this row. Introduce new work plan rows/items below this row.
5GS
5GS Common
TS 38.508-1: Common test environment
|  | 38.508-1 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
1 |  | 38.508-1 | 4 | Common Test Environments | Introduction of General test environment for Rel18 FR2 DL Multi-Rx chain |  | RAN5#108 (Aug-25) |  |  | 1 | 0% | 0% |  | 0%
2 |  | 38.508-1 | 5 | Test environments for RF test | Introduction of RF test environment for Rel18 FR2 DL Multi-Rx chain |  | RAN5#108 (Aug-25) |  |  | 1 | 0% | 0% |  | 0%
3 |  | 38.508-1 | 7 | Test environments for RRM test | Introduction of RRM test environment for Rel18 FR2 DL Multi-Rx chain |  | RAN5#108 (Aug-25) |  |  | 1 | 0% | 0% |  | 0%
TS 38.508-2: Common ICS
|  | 38.508-2 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
4 |  | 38.508-2 | A.4 | ICS proforma tables | Add ICS as needed for the test case applicability statements for the new test cases introduced in RF, RRM and protocol test cases. |  | RAN5#107 (May-25) | R5-247154 R5-251692 R5-251693 R5-254847 R5-256505 |  | 1 | 100% | 100% |  | 100%
TS 38.509: UE specific testing functions
|  | 38.509 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
5 |  | 38.509 | 5 | UE special conformance test functions | Introduce any special conformance test function as needed to test the FR2 DL Multi-Rx requirements |  | RAN5#108 (Aug-25)
TBD |  | 38.509 | <Clause> | <Title of task> | <Describe task> |  | TBD |  |  | TBD
NR RF/RRM
TS 38.521-2: FR2 RF test cases - Common parts (general clauses, Annexes)
|  | 38.521-2 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
6 |  | 38.521-2 | 4 | General | New sub-clause header |  | RAN5#106 (Feb-25) |  |  | 0.2 | 100% | 100% |  | 100%
7 |  | 38.521-2 | 5 | Operating bands and channel arrangement | <Describe task> |  | RAN5#106 (Feb-25) | R5-254865 |  | 0.5 | 100% | 100% |  | 100%
TS 38.521-2: FR2 RF test cases - Tx
|  | 38.521-2 Tx |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
TS 38.521-2: FR2 RF test cases - Rx
|  | 38.521-2 Rx |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
8 |  | 38.521-2 Rx | 7.3K | Spherical coverage requirement for simultaneous reception from multiple directions | 7.3K of TS 38.133 |  | RAN5#108 (Aug-25) |  |  | 0.5 | 100% | 100% |  | 100%
9 | Y | 38.521-2 Rx | 7.3K.3 | 2AoA spherical coverage of power class 3 | 7.3K.3 of TS 38.133 | Apple | RAN5#108 (Aug-25) | R5-251518 R5-253462 R5-255273 | Editor’s note: This clause is incomplete. The following aspects are either missing or not yet determined: - . Some references within initial conditions shall be updated - Measurement Uncertainties and Test Tolerances are FFS for all power classes. - Test Methodology is FFS for Power Class 6 - Test Procedure details for 2AoA reception and measurements is FFS - Test Requirements is FFS | 1 | 65% | 65% |  | 65%
10 |  | 38.521-2 Rx | 7.3K.6 | 2AoA spherical coverage of power class 6 | 7.3K.3 of TS 38.133 |  |  |  | tracked as part of Enhanced NR support for high speed train scenario in frequency range 2 RAN5 WI
11 |  | 38.521-2 Rx | Annex A | Reference measurement channels |  |  | RAN5#108 (Aug-25) |  |  | 0.5 | 0% | 0% |  | 0%
12 |  | 38.521-2 Rx | Annex J.2 | Test conditions and angle definitions |  |  | RAN5#108 (Aug-25) |  |  | 0.5 | 0% | 0% |  | 0%
13 |  | 38.521-2 Rx | Annex K | Requirement metric for simultaneous reception from multiple directions |  |  | RAN5#108 (Aug-25) | R5-255273 |  | 0.5 | 60% | 60% |  | 60%
13 |  | 38.521-2 Rx | Annex N | UE coordinate system for simultaneous reception from multiple directions |  |  | RAN5#108 (Aug-25) | R5-247504 |  | 0.5 | 80% | 80% |  | 80%
TS 38.521-3: FR1 and FR2 Interworking operation with other radios RF test cases - Common parts (general clauses, Annexes)
|  | 38.521-3 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
TS 38.521-3: FR1 and FR2 Interworking operation with other radios RF test cases - Tx
|  | 38.521-3 Tx |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
TS 38.521-3: FR1 and FR2 Interworking operation with other radios RF test cases - Rx
|  | 38.521-3 Rx |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
TS 38.521-4: Demod/CSI reporting test cases
|  | 38.521-4 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
TBD |  | 38.521-4 | 7.1 | Applicability of requirements |  | Qualcomm | RAN5#106 (Feb-25) | R5-247156 |  | 0.2 | 80% | 80% |  | 80%
TBD |  | 38.521-4 | 7.2.2.2.5_0 | Minimum requirements for Multi-DCI non-overlapping based transmission scheme | Requirements in 7.2.2.2.5 of TS 38.101-4 | Qualcomm | RAN5#108 (Aug-25) |  |  | 0
TBD | Y | 38.521-4 | 7.2.2.2.5_1 | Multi-DCI non-overlapping based transmission scheme -MultiRx | Requirements in 7.2.2.2.5 of TS 38.101-4 | Qualcomm | RAN5#108 (Aug-25) | R5-252988 | Editor’s note: This test case is incomplete. Following aspects are pending - device positioning procedure - minimum test time - message exceptions | 1 | 60% | 60% |  | 60%
TBD |  | 38.521-4 | 7.2.2.2.6_0 | Minimum requirements for PDSCH Multi-DCI based transmission scheme | Requirements in 7.2.2.2.6 of TS 38.101-4 | Qualcomm | RAN5#108 (Aug-25) |  |  | 0
TBD | Y | 38.521-4 | 7.2.2.2.6_1 | PDSCH Multi-DCI based transmission scheme -MultiRx | Requirements in 7.2.2.2.6 of TS 38.101-4 | Qualcomm | RAN5#108 (Aug-25) | R5-252988 | Editor’s note: This test case is incomplete. Following aspects are pending - device positioning procedure - minimum test time - message exceptions | 1 | 60% | 60% |  | 60%
TBD | Y | 38.521-4 | 7.2.2.2.7_1 | Minimum requirements for PDSCH Single-DCI based SDM scheme -MultiRx | Requirements in 7.2.2.2.7 of TS 38.101-4 |  | RAN5#108 (Aug-25) | R5-252988 | Editor’s note: This test case is incomplete. Following aspects are pending - device positioning procedure - minimum test time - message exceptions | 1 | 60% | 60% |  | 60%
TBD | Y | 38.521-4 | 8.3.3.2.2.1 | 2Rx TDD FR2 Single PMI with 2TX TypeI-SinglePanel codebook Single-DCI based transmission scheme with simultaneous reception - MultiRx | Requirements in 8.3.3.2.2 of TS 38.101-4 |  | RAN5#108 (Aug-25) | R5-256974 | Editor’s note: This test case is incomplete. Following aspects are pending - device positioning procedure - minimum test time - message exceptions | 1 | 40% | 40% |  | 40%
TBD |  | 38.521-4 | Annex A | Reference measurement channels |  | Qualcomm | RAN5#108 (Aug-25) | R5-247156 R5-250557 |  | 0.5 | 80% | 80% |  | 80%
TBD |  | 38.521-4 | Annex B | Multi-path fading propagation conditions |  | Qualcomm | RAN5#108 (Aug-25) | R5-247156 |  | 0.5 | 80% | 80% |  | 80%
TS 38.522: Applicability for RF, Demod/CSI reporting and RRM test cases
TBD |  | 38.522 | 4 | Test case conditions and selection criteria | Add new ICS statements. | All contributing companies | RAN5#109 (Nov-25) | R5-251669 |  | 1 | 40% | 40% |  | 40%
TBD |  | 38.522 | 4.1.1 | FR1 standalone conformance test cases | Add test case applicability statements for the new test cases introduced for 38.521-2, 38.521-4 and 38.533. | All contributing companies | RAN5#109 (Nov-25) | R5-251669 R5-251669 R5-252989 R5-255395 R5-256508 R5-256559 |  | 1 | 75% | 75% |  | 75%
TS 38.533: RRM test cases
|  | 38.533 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | 5 | 100% | 100% |  | 100%
TBD |  | 38.533 | <Clause> | <Title of new sub-clause header> | New sub-clause header |  | TBD |  |  | 0
TBD |  | 38.533 | <Clause> | <Title of modified existing test case> | <Describe required change of the existing test case> |  | TBD |  |  | TBD
TBD | Y | 38.533 | 5.5.1.11 | Radio Link Monitoring Out-of-sync Test for FR2 PSCell configured with SSB-based RLM RS in non-DRX mode for UE supporting fast beam sweeping in multi-Rx | Requirements in A.5.5.1.11 | Qualcomm | RAN5#108 (Aug-25) | R5-251599 R5-256516 | Editor's Note: This test case is incomplete in following aspects: - MU and TT are missing - Annex F needs to be updated - Configuration of 3AoA setup and testability of the device is still FFS - UE positioning procedure is still FFS | 1 | 50% | 50% |  | 50%
TBD | Y | 38.533 | 7.5.1.10 | Radio Link Monitoring Out-of-sync Test for FR2 PCell configured with SSB-based RLM RS in non-DRX mode for UE supporting fast beam sweeping in multi-Rx | Requirements in A.7.5.1.10 | Qualcomm | RAN5#108 (Aug-25) | R5-251600 R5-256517 | Editor's Note: This test case is incomplete in following aspects: - MU and TT are missing - Annex F needs to be updated - Configuration of 3AoA setup and testability of the device is still FFS - UE positioning procedure is still FFS | 1 | 50% | 50% |  | 50%
TBD | Y | 38.533 | 7.5.5.14 | TRP specific Beam Failure Detection and Link Recovery for FR2 PCell configured with CSI-RS-based BFD and LR and multi-Rx operation in DRX mode | Requirements in A.7.5.5.14 |  | RAN5#108 (Aug-25) | R5-253500 R5-256518 | Editor's Note: This test case is incomplete in following aspects: - MU and TT are missing - Annex F needs to be updated - Configuration of 3AoA setup and testability of the device is still FFS - UE positioning procedure is still FFS - Test configures schedulingRequestID-BFR-SCell-r16, but there is no SCell | 1 | 50% | 50% |  | 50%
TBD | Y | 38.533 | 7.5.8.4 | DCI based active TCI state switch with m-DCI for simultaneous reception | Requirements in A.7.5.8.4 | Nokia | RAN5#109 (Nov-25) | R5-251752 | Editor’s note: FFS whether additional conditions are needed for tests. Dual TCI states will be indicated in one or two TCI state switch commands. The dual target TCI states are known if the following conditions are met: - Dual target TCI states are QCL-ed with typeD to reference signals in a resource group in the latest Rel-17 group based beam report - The dual target TCI states and all the RSs in the two QCL chains remain detectable during the TCI state switching period - SNR of the TCI state ≥ -3dB - RS resource group configured for dual target TCI states is reported in the last [1280] ms. - Test tolerance analysis and measurement uncertainty are missing - Test procedure is subject to change- Configuration of 3AoA setup and testability of the device is still FFS | 1 | 40% | 40% |  | 40%
TBD | Y | 38.533 | 7.5.8.5 | Single-DCI FR2 DCI based active TCI state switch with known target TCI states for simultaneous reception | Requirements in A.7.5.8.5 | Nokia | RAN5#109 (Nov-25) | R5-251598 | Editor’s note: This test case is incomplete. The following aspect is either missing or TBD: - Test tolerance analysis and measurement uncertainty are missing - Test procedure is subject to change - Setup configuration and testability needs to be further assessed - UE positioning procedure is still FFS | 1 | 40% | 40% |  | 40%
TBD | Y | 38.533 | 7.5.16 | UE L1-RSRP Scheduling and Measurement Restrictions on FR2-1 | Requirements in A.7.5.16 | Qualcomm | RAN5#108 (Aug-25) | R5-253589 | Editor’s Note: This test case is incomplete, and the following aspects need to be updated: - MU and TT are missing - Message contents may need to be updated - Test procedure needs to be updated - Applicability needs to be updated - Annex E and F need to be updated - UE positioning procedure is still FFS | 1 | 30% | 30% |  | 30%
TBD | Y | 38.533 | 7.7.14.1 | L1-RSRP measurement for group-based beam reporting - SSB based L1-RSRP measurement | Requirements in A.7.7.14.1 | Nokia | RAN5#109 (Nov-25) | R5-251596 R5-253499 | Editor’s note: This test case is incomplete. The following aspects are either missing or TBD: - Test requirement shall require an update - TT is missing. - Setup configuration and testability needs to be further assessed - UE positioning procedure is still FFS | 1 | 70% | 70% |  | 70%
TBD | Y | 38.533 | 7.7.14.2 | CSI-RS based L1-RSRP measurement on resource set with repetition off | Requirements in A.7.7.14.2 | Nokia | RAN5#109 (Nov-25) | R5-251597 | Editor’s note: This test case is incomplete. The following aspects are either missing or TBD: - Test requirement shall require an update. - TT is missing - Setup configuration and testability needs to be further assessed - UE positioning procedure is still FFS | 1 | 40% | 40% |  | 40%
TBD |  | 38.533 | Annex A.3.14 | Reference measurement channels |  | Qualcomm | RAN5#108 (Aug-25) |  |  | 0.2 | 0% | 0% |  | 0%
TBD |  | 38.533 | Annex A.3.15 | Setup for simultaneous reception |  | Qualcomm | RAN5#108 (Aug-25) | R5-250496 |  | 0.2 | 80% | 80% |  | 80%
TBD |  | 38.533 | Annex H | Common Message Contents |  | Qualcomm | RAN5#109 (Nov-25) | R5-256515 |  | 0.2 | 80% | 80% |  | 80%
TR 38.903: Test Tolerances analysis RRM and RF Rx test cases
|  | 38.903 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
TBD |  | 38.903 | 8 | Grouping of test cases defined in TS 38.533 | RRM MU Analysis | All contributing companies | TBD | R5-253639 R5-256887 |  | 8 | 40% | 40% |  | 40%
TBD |  | 38.903 | <Clause> | <Title of task> | <Describe task> |  | TBD |  |  | TBD
TR 38.905: Test Point analysis receiver and transmitter test cases
|  | 38.905 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
TBD |  | 38.905 | <Clause> | <Title of new sub-clause header> | New sub-clause header | All contributing companies | TBD | R5-251519 |  | 1 | 20% | 20% |  | 20%
RAN and CN protocol
TS 38.523-1: Protocol test cases
|  | 38.523-1 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
Idle Mode
TBD |  | 38.523-1 | <Clause> | <Title of new sub-clause header> | New sub-clause header |  | TBD |  |  | 0
TBD |  | 38.523-1 | <Clause> | <Title of modified existing test case> | <Describe required change of the existing test case> |  | TBD |  |  | TBD
TBD | Y | 38.523-1 | <Clause> | <Title of new test case> | Test Purpose(s): <Describe test purpose(s)> |  | TBD |  |  | 0
Layer 2
TBD |  | 38.523-1 | <Clause> | <Title of new sub-clause header> | New sub-clause header |  | TBD |  |  | 0
TBD |  | 38.523-1 | <Clause> | <Title of modified existing test case> | <Describe required change of the existing test case> |  | TBD |  |  | TBD
TBD | Y | 38.523-1 | <Clause> | <Title of new test case> | Test Purpose(s): <Describe test purpose(s)> |  | TBD |  |  | 0
RRC
TBD |  | 38.523-1 | <Clause> | <Title of new sub-clause header> | New sub-clause header |  | TBD |  |  | 0
TBD |  | 38.523-1 | <Clause> | <Title of modified existing test case> | <Describe required change of the existing test case> |  | TBD |  |  | TBD
TBD | Y | 38.523-1 | <Clause> | <Title of new test case> | Test Purpose(s): <Describe test purpose(s)> |  | TBD |  |  | 0
NAS
TBD |  | 38.523-1 | <Clause> | <Title of new sub-clause header> | New sub-clause header |  | TBD |  |  | 0
TBD |  | 38.523-1 | <Clause> | <Title of modified existing test case> | <Describe required change of the existing test case> |  | TBD |  |  | TBD
TBD | Y | 38.523-1 | <Clause> | <Title of new test case> | Test Purpose(s): <Describe test purpose(s)> |  | TBD |  |  | 0
TS 38.523-2: Applicability for Protocol test cases
TBD |  | 38.523-2 | <Clause> | <Title> | Add new ICS statements. |  | TBD |  |  | 0.1
TBD |  | 38.523-2 | <Clause> | <Title> | Add test case applicability statements for the new test cases introduced in 38.523-1 |  | TBD |  |  | 0.1
TS 38.523-3: Protocol test suites (TTCN)
|  | 38.523-3 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
TBD |  | 38.523-3 | <Clause> | <Title of task> | <Describe task> |  | TBD |  |  | TBD
End of workplan items. Note! Do not remove this row. Introduce new work plan rows/items above this row.
Note on A6: Unique ID for WP items (unique within the sub-area work plan) Note! As WP item numbers may be referenced from outside of this WP that means: - Do not change number for WP items that have been published. - Do not re-use WP item numbers if a WP item is deleted
Note on B6: Set to Y if the WP item represents a new test case that will be specified in RAN5 test specifications as an executable test case else leave blank.
Note on K6: The WP item's weight number is used to set the reletive weights between WP items used in the overall calculation of completeness. Setting it to 0 for a WP item means that it will not be included at all in the calculation.