## Cover sheet
3GPP TSG RAN WG5 Meeting #109 | [7 empty] | R5-256069
Dallas, USA, 17th Nov 2025 - 21st Nov 2025
Agenda Item: | 7.5.2
Source: | CMCC
Title: | WP UE Conformance - Rel-19 High power UE (power class 1.5 and 2) for NR FR1 TDD/FDD single band for handheld/FWA UEs, and high power UE operation (power class 2, 1.5 and 1) for FWVM (fixed-wireless/vehicle-mounted) use cases in a single NR band
Work item code: | HPUE_NR_FR1_bands_R19-UEConTest
Release: | Rel-19
Document for: | Information
RAN5 WP template v3.0.0
1. Introduction
At the RAN#108 meeting in June 2025 the Rel-19 RAN5 work item for UE Conformance of Rel-19 High power UE (power class 1.5 and 2) for NR FR1 TDD/FDD single band for handheld/FWA UEs, and high power UE operation (power class 2, 1.5 and 1) for FWVM (fixed-wireless/vehicle-mounted) use cases in a single NR band was approved [1]. The purpose of present document is to provide a work plan for the RAN5 work item to introduce the Rel-19 HPUE single band requirements into RAN5 test specifications. The work plan is updated after each RAN5 meeting to give the status of the work item. Section 2 gives an overview of the work item status. The work sheet 'WP' shows the status for each impacted/newly introduced test cases.
2. Work item status
Estimation of WI overall completion:
Area |  | Completion | Number of new completed test cases (Note 1) | Number of new test cases | Comments
Overall completion |  | 61% (+5%) | 6.5 (+0.5) | 11.7 (+0.5)
Completion Compensation |  | -
| Note 1: | Only test cases completed for all applicable WP areas and sub-areas are counted. For completed test cases per WP areas and WP sub-areas see below.
Estimation WI completion per area and sub-area:
|  | Completion | Number of new completed test cases | Number of new test cases | Comments
SA Option 2 (SA NR) (FR1) |  | 61% (+5.1%) | 6.5 (+0.5) | 11.7 (+0.5)
FR1 |  | 61% (+5.1%) | 6.5 (+0.5) | 11.7 (+0.5)
Estimation of completion per TS (area):
|  | TS/TR overall completion |  |  | SA Option 2 (SA NR)
TS/TR Scope | TS/TR | Completion | Number of new completed test cases | Number of new test cases | FR1
[5 empty] | Completion | Number of new completed test cases | Number of new test cases
LTE
LTE Common
Common test environment | 36.508
UE specific test functions | 36.509
LTE RF/RRM
RF common parts | 36.521-1
RF Rx test cases | 36.521-1 Rx
RF Tx test cases | 36.521-1 Tx
RF Demod test cases | 36.521-1 Demod
Applicability RF. Demod/QSI and RRM test cases | 36.521-2
RRM test cases | 36.521-3
Test Tolerances analysis RRM test cases | 36.903
Test Tolerances analysis receiver test cases | 36.904
Test Point analysis receiver and transmitter test cases | 36.905
LTE RAN and CN protocols
Protocol test cases | 36.523-1
Applicability Protocol test cases | 36.523-2
Test suites (TTCN) | 36.523-3
5GS
5GS Common
Common test environment | 38.508-1
Common ICS | 38.508-2 | 100% | 1 | 1 | 100% | 1 | 1
UE specific test functions | 38.509
NR RF/RRM
FR1 RF common parts | 38.521-1
FR1 RF Tx test cases | 38.521-1 Tx | 55% (+5%) | 4 | 8 | 55% (+5%) | 4 | 8
FR1 RF Rx test cases | 38.521-1 Rx | 100% | 1 | 1 | 100% | 1 | 1
FR2 RF common parts | 38.521-2
FR2 RF Tx test cases | 38.521-2 Tx
FR2 RF Rx test cases | 38.521-2 Rx
FR1 and FR2 Interworking operation with other radios RF common parts | 38.521-3
FR1 and FR2 Interworking operation with other radios RF Tx test cases | 38.521-3 Tx
FR1 and FR2 Interworking operation with other radios RF Rx test cases | 38.521-3 Rx
RF Demod/QSI test cases | 38.521-4
RRM test cases | 38.533
Applicability RF. Demod/QSI and RRM test cases | 38.522 | 0% | 0 | 0.2 | 0% | 0 | 0.2
Test Tolerances analysis RRM and RF Rx test cases | 38.903
Test Point analysis receiver and transmitter test cases | 38.905 | 0% | 0 | 1 | 0% | 0 | 1
5GS RAN and CN protocols
Protocol test cases | 38.523-1
Applicability Protocol test cases | 38.523-2
Test suites (TTCN) | 38.523-3
UE Positioning
UE Positioning Min. Performance test cases | 37.571-1
UE Positioning Protocol test cases | 37.571-2
Applicability and ICS UE Positioning test cases | 37.571-3
UE Positioning Test sutes (TTCN) | 37.571-4
UE Positioning test scenarios and assistance data | 37.571-5
IMS
IMS over LTE protocol test cases | 34.229-1
IMS over 5GS protocol test cases | 34.229-5
Applicability and ICS IMS test cases | 34.229-2
IMS Test suite (TTCN) | 34.229-3
Mission Critical Services
MC Common test environment | 36.579-1
MCPTT UE test cases | 36.579-2
MC Server Application test cases | 36.579-3
Applicability and ICS MC test cases | 36.579-4
MC Test suite (TTCN) | 36.579-5
MC Video UE test cases | 36.579-6
MC Data UE test cases | 36.579-7
5 References
[1] RP-251374 | New WID on UE Conformance - Rel-19 High power UE (power class 1.5 and 2) for NR FR1 TDD/FDD single band for handheld/FWA UEs, and high power UE operation (power class 1) for FWVM (fixed-wireless/vehicle-mounted) use cases in a single NR band
Note on B21: Overall completion of the work item reported at an earlier meeting will not be decreased if additional tasks are added or if corrections are made to the work plan. Instead the earlier reported completion status will be kept until necessary progress have been achieved such that completion exceeds the earlier reported completion level. The value of the Completion Compensation value represents the difference in the decrease caused by late additions or corrections to the work plan and the current estimated overall completion. '-' indicates that no compensation is applied.

## WP
WP Title: |  | UE Conformance - Rel-19 High power UE (power class 1.5 and 2) for NR FR1 TDD/FDD single band for handheld/FWA UEs, and high power UE operation (power class 2, 1.5 and 1) for FWVM (fixed-wireless/vehicle-mounted) use cases in a single NR band | [10 empty] | Start of workplan status columns. Note! Do not remove this column. | WP item status | End of workplan columns. Note! Do not remove this column.
WI code |  | HPUE_NR_FR1_bands_R19-UEConTest
WP Scope: |  | The purpose of this present document is to provide a work plan for the RAN5 work item UE Conformance for NR R19 HPUE single band support comprising the necessary updates to existing clauses/test cases and new clauses/test cases as appropriate, with the aim of provision of conformance testing to reflect the relevant core and performance requirement (relevant core spec WIs indicated in the WID).
WP Resp: |  | Luyang Zhao, CMCC |  |  | zhaoluyang@chinamobile.com | [5 empty] | WP item completion |  |  | SA Option 2 (SA NR)
TS Resp: |  | <TS responsible if a new TS is involved> |  |  | <Email to TS responsible>
WP Item ID | Is new test case? | TS/area | Clause | Title | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | Overall | SA Option 2 (SA NR) |  | FR1
61% (+5.1%)
14 (+1)
11.7 (+0.5)
5%
Start of work plan items. Note! Do not remove this row. Introduce new work plan rows/items below this row.
5GS
5GS Common
TS 38.508-1: Common test environment
|  | 38.508-1 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
TS 38.508-2: Common ICS
1 | Y | 38.508-2 | A.4.3.1 | RF Baseline Implementation Capabilities | If power classes PC1, PC1.5 or PC2 covered by the band addition work item then add the applicable NR power class Baseline Implementation Capabilities to the relevant table in clause A.4.3.1 PC1, PC1.5, PC2: Table A.4.3.1-4, Table A.4.3.1-4b and Table A.4.3.1-4e | CMCC(n104 PC1.5) Verizon (n5 PC2) | RAN5#110 (Feb-26) | For n104 PC1.5: R5-253911 For n5 PC2: R5-255212 | CMCC Luyang Zhao <zhaoluyang@chinamobile.com> Verizon Jinwen Ma <jinwen.ma@verizonwireless.com> | 1 | 100% | 100% |  | 100%
NR RF/RRM
TS 38.521-1: FR1 RF test cases - Common parts (general clauses, Annexes)
14 | Y | 38.521-1 Annex | I.1 | Indication of ModifiedMPR-Behaviour | Update the definitions of the bits in the field modifiedMPR-Behaviour | CMCC(n104 PC1.5) Verizon (n5 PC2) | RAN5#110 (Feb-26) | For n5 PC2: R5-256002 | CMCC Luyang Zhao <zhaoluyang@chinamobile.com> Verizon Jinwen Ma <jinwen.ma@verizonwireless.com> | 0.5 | 100% (+100%) | 100% (+100%) |  | 100%
TS 38.521-1: FR1 RF test cases - Tx
2 | Y | 38.521-1 Tx | 6.2.1 | UE maximum output power | Add minimum requirement and test requirement for the HPUE single band | CMCC(n104 PC1.5) Verizon (n5 PC2) | RAN5#110 (Feb-26) | For n104 PC1.5: R5-253912 For n5 PC2: R5-255252 | CMCC Luyang Zhao <zhaoluyang@chinamobile.com> Verizon Jinwen Ma <jinwen.ma@verizonwireless.com> | 1 | 100% | 100% |  | 100%
3 | Y | 38.521-1 Tx | 6.2.2 | UE maximum output power reduction | Add test requirement vs appliable power classes for the band and check if any channel bandwidths of the NR band need to be added to uplink configuration for almost contiguous allocation in Table 6.2.2.4.1-4. | CMCC(n104 PC1.5) Verizon (n5 PC2) | RAN5#110 (Feb-26) | For n5 PC2: R5-255252 | CMCC Luyang Zhao <zhaoluyang@chinamobile.com> Verizon Jinwen Ma <jinwen.ma@verizonwireless.com> | 1 | 100% | 100% |  | 100%
4 | Y | 38.521-1 Tx | 6.2.3 | UE additional maximum output power reduction | Add minimum requirement and test requirement if new NS value is introdcued by the new HPUE single band. | CMCC(n104 PC1.5) Verizon (n5 PC2) | RAN5#110 (Feb-26) | For n5 PC2: R5-256001 | CMCC Luyang Zhao <zhaoluyang@chinamobile.com> Verizon Jinwen Ma <jinwen.ma@verizonwireless.com> | 1 | 40% (+40%) | 40% (+40%) |  | 40%
5 | Y | 38.521-1 Tx | 6.2G.1 | UE maximum output power for Tx Diversity | Add minimum requirement and test requirement for the HPUE single band. | CMCC(n104 PC1.5) Verizon (n5 PC2) | RAN5#110 (Feb-26) | For n104 PC1.5: R5-253913 | CMCC Luyang Zhao <zhaoluyang@chinamobile.com> Verizon Jinwen Ma <jinwen.ma@verizonwireless.com> | 1 | 100% | 100% |  | 100%
6 | Y | 38.521-1 Tx | 6.2G.2 | UE maximum output power reduction for Tx Diversity | Add minimum requirement and test requirement for the HPUE single band. | CMCC(n104 PC1.5) Verizon (n5 PC2) | RAN5#110 (Feb-26) | For n104 PC1.5: R5-253914 | CMCC Luyang Zhao <zhaoluyang@chinamobile.com> Verizon Jinwen Ma <jinwen.ma@verizonwireless.com> | 1 | 100% | 100% |  | 100%
7 | Y | 38.521-1 Tx | 6.2G.3 | UE additional maximum output power reduction for Tx Diversity | Add minimum requirement and test requirement if new NS value is introdcued by the new HPUE single band. | CMCC(n104 PC1.5) Verizon (n5 PC2) | RAN5#110 (Feb-26) |  | CMCC Luyang Zhao <zhaoluyang@chinamobile.com> Verizon Jinwen Ma <jinwen.ma@verizonwireless.com> | 1 | 0% | 0% |  | 0%
8 | Y | 38.521-1 Tx | 6.5.3.3 | Additional spurious emissions | Add minimum requirement, test configuration and test requirement if new NS value is introdcued by the new HPUE single band | CMCC(n104 PC1.5) Verizon (n5 PC2) | RAN5#110 (Feb-26) |  | CMCC Luyang Zhao <zhaoluyang@chinamobile.com> Verizon Jinwen Ma <jinwen.ma@verizonwireless.com> | 1 | 0% | 0% |  | 0%
9 | Y | 38.521-1 Tx | 6.5G.3.3 | Additional spurious emissions for Tx Diversity | Update editor's note if new NS value is introdcued by the new HPUE single band. Also check if references in 6.5G.3.3.4 need to be updated | CMCC(n104 PC1.5) Verizon (n5 PC2) | RAN5#110 (Feb-26) |  | CMCC Luyang Zhao <zhaoluyang@chinamobile.com> Verizon Jinwen Ma <jinwen.ma@verizonwireless.com> | 1 | 0% | 0% |  | 0%
TS 38.521-1: FR1 RF test cases - Rx
13 | Y | 38.521-1 Rx | 7.3.2 | Reference sensitivity power level | Add minimum requirement and test requirement for the HPUE single band. | CMCC(n104 PC1.5) Verizon (n5 PC2) | RAN5#110 (Feb-26) | For n5 PC2: R5-255253 | CMCC Luyang Zhao <zhaoluyang@chinamobile.com> Verizon Jinwen Ma <jinwen.ma@verizonwireless.com> | 1 | 100% | 100% |  | 100%
TS 38.522: Applicability for RF, Demod/CSI reporting and RRM test cases
10 | Y | 38.522 | 4 | Test case conditions and selection criteria | Introduction of Test case conditions and selection criteria if necessary | CMCC(n104 PC1.5) Verizon (n5 PC2) | RAN5#110 (Feb-26) |  | CMCC Luyang Zhao <zhaoluyang@chinamobile.com> Verizon Jinwen Ma <jinwen.ma@verizonwireless.com> | 0.1 | 0% | 0% |  | 0%
11 | Y | 38.522 | 4.1.1 | FR1 standalone conformance test cases | Update test applicability for 38.521-1 Rel-19 HPUE single band test case if necessary. | CMCC(n104 PC1.5) Verizon (n5 PC2) | RAN5#110 (Feb-26) |  | CMCC Luyang Zhao <zhaoluyang@chinamobile.com> Verizon Jinwen Ma <jinwen.ma@verizonwireless.com> | 0.1 | 0% | 0% |  | 0%
TR 38.905: Test Point analysis receiver and transmitter test cases
12 | Y | 38.905 | 4.1.2.1 | A-MPR, A-SEM and A-SE FR1 test cases for single carrier and UL MIMO | Update the test point analysis If new NS value is introduced by the new HPUE single band | CMCC(n104 PC1.5) Verizon (n5 PC2) | RAN5#110 (Feb-26) |  | CMCC Luyang Zhao <zhaoluyang@chinamobile.com> Verizon Jinwen Ma <jinwen.ma@verizonwireless.com> | 1 | 0% | 0% |  | 0%
End of workplan items. Note! Do not remove this row. Introduce new work plan rows/items above this row.
Note on A6: Unique ID for WP items (unique within the sub-area work plan) Note! As WP item numbers may be referenced from outside of this WP that means: - Do not change number for WP items that have been published. - Do not re-use WP item numbers if a WP item is deleted
Note on B6: Set to Y if the WP item represents a new test case that will be specified in RAN5 test specifications as an executable test case else leave blank.
Note on K6: The WP item's weight number is used to set the reletive weights between WP items used in the overall calculation of completeness. Setting it to 0 for a WP item means that it will not be included at all in the calculation.