## Slide 1
RAN2 TU allocation at RAN#83
3GPP TSG RAN#83 Shenzhen, China, March 2019
RP‑190750
RAN2 chairman (Intel)

## Slide 2: NR TUs

## Slide 3: NR + LTE TUs

## Slide 4: Observations
NR over its original time budget by a very large margin
NR items have been accommodated by further use of the LTE time budget. This has consequences:
  At times in the meeting week there will be 3 parallel online sessions for NR
  Schedule conflicts for delegates more likely and more difficult to resolve
  Experts have reduced visibility across all the NR work => risks to quality
RAN2 is over the NR+LTE combined time budget by up to 2.5 TUs each meeting
For remainder of Release 16:
No proposal to increase time of existing WIs can be accommodated
  If your WI is under pressure then reduce the scope, don’t increase the time
No further WIs requiring RAN2 time can be agreed