## Slide 1: Considerations on Release 17 schedule
Agenda Item: 9.7
Source: Intel Corporation
Document for: Discussion
3GPP TSG RAN Meeting #89-e RP-201865
14-18 September 2020

## Slide 2: Rel-17 schedule
Rel-17 completion date
  RAN#88e concluded (in RP-201361):
    “Even though it is understood that further delay to the Release 17 timeline will be necessary, there are no changes to the above timeline [with stage 3 completion at Q3 2021] at this point
      Timeline changes will be addressed once firm detailed planning will be possible. This planning is not expected to happen before December 2020. “
  We don’t think anything has changed or any new information is available that would lead to a change in the agreement from RAN#88e.
  Proposal: RAN#88e conclusion on Release-17 completion remains valid. No need to re-discuss at RAN#89e

## Slide 3: Rel-17 SI completion dates (1)
Although re-discussion of Release 17 completion date is not needed this meeting, it is useful to review whether the completion dates for the SIs remain appropriate or whether additional time is required.
Important that sufficient conclusions can be drawn from the SI to create a well scoped WI (avoiding study aspects being carried over to the WI).
  NR above 52.6GHz SI:
    Need to conclude evaluations/(potential) solutions/channelization/RF study in RAN1 and RAN4
    Proposal: Extend SI by one quarter to Q1 2021
  NR RedCap SI:
    Need to extend is mainly for RAN2 aspects. Need to conclude the solutions on how to ensure Redcap UE is only used for the intended use cases, with some solutions also involving SA2 and CT1
    Proposal: Extend SI by one quarter to Q1 2021
  NR coverage enhancements SI:
    Can strive for completion as scheduled in December 2020
    Proposal: No change to SI completion date
  NR positioning enhancements SI:
    More time needed to have meaningful conclusion and to define a reasonable WI scope. KPI/use cases/applicable positioning modes integrity support, and solution direction for high accuracy/low latency should be concluded in the SI before moving to WI.
    Proposal: Extend SI by one quarter to Q1 2021

## Slide 4: Rel-17 completion dates (2)
  NR sidelink relay SI:
    RAN2 should complete definition of L2 relay and perform further comparison of L2 and L3 relays considering SA2/SA3 outcome.
    Proposal: Extend SI by one quarter to Q1 2021
  NR QoE SI:
    RAN2/3 need more time to conclude what QoE mechanism is needed for AR/VR video service, real-time gaming and uRLLC service.
    Proposal: Extend SI by one quarter to Q1 2021
  RAN Slicing SI:
    More time desirable for RAN2 to conclude solution direction in SI.
    Proposal: Extend SI by one quarter to Q1 2021
  NR XR evaluation SI, NB-IoT/MTC over NTN SI, and Further enhancements for data collection SI
    Longer SIs with completion dates later in 2021
    Proposal: No change to SI completion date

## Slide 5: Working group meeting schedule for 1H 2021
General view for WG meeting schedule
  A single 2 week e-meeting is preferable to two 1 week e-meetings per quarter.
  Two 2 week e-meetings is not acceptable from delegate workload point of view and may be counter-productive due to short gap between e-meetings.
Q1 meeting arrangements
  Original plan for 1 F2F WG meeting in Q1, plus a possible Ad Hoc meeting for has been mentioned.
  Lunar New Year holiday makes it impossible to have a single 2 week e-meetings in February.
  Proposal: Two 1-week e-meetings in January and February. Agenda should be split between the e-meetings. Acceptable for RAN3 to make a different RAN3 specific arrangement.
Q2 meeting arrangements
  Original plan for 2 F2F WG meetings in Q2.
  Proposal: Single 2-week meeting in May. Each WG can decide on 2 or 3 weeks. Full agenda for this meeting. (i.e. similar approach as planned for Q4 2020)

## Slide 6: Summary
Regarding Relase-17 completion:
  Proposal 1: RAN#88e conclusion on Release-17 completion remains valid. No need to re-discuss at RAN#89e
Regarding RAN WG meetings in 1H 2021
  Proposal 2: Two 1-week e-meetings in January and February. Agenda should be split between the e-meetings. Acceptable for RAN3 to make a different RAN3 specific arrangement.
  Proposal 3: Single 2-week meeting in May. Each WG can decide on 2 or 3 weeks. Full agenda for this meeting. (i.e. similar approach as planned for Q4 2020)
Regarding Release-17 study items within RAN:
  Proposal 4: Adjust the completion dates of the Rel-17 study items as proposed on slides 4 and 5