## Cover sheet
3GPP TSG-RAN WG5 Meeting #90-e | [10 empty] | R5-210719
Electronic Meeting, 22nd February - 5th March 2021
Agenda Item: | 7.4.2
Source: | Huawei, Hisilicon
Title: | WP UE Conformance Test Aspects for NR V2X
Work item code: | 5G_V2X_NRSL_eV2XARC-UEConTest
Release: | Rel-16
Document for: | Information
RAN5 WP template v2.0
1. Introduction
The core gropus Rel-16 WI 5G V2X with NR sidelink aims to specify enhancements to both Uu transport and PC5 transport in E-UTRAN/NR to support NR-based V2X (V2V, V2I/N, and V2P). The objective of the UE Conformance Test Aspects work item is to provide conformance test specifications for the core requirements of Rel-16 Security Aspects of eV2XARC, CT aspects of eV2XARC, and RAN aspects of 5G V2X with NR sidelink. The RAN5 areas of RF, RRM, Demodulation and Protocol conformance test specifications with NR-based V2X operation are to be covered. At the RAN#88 meeting in June 2020 the Rel-16 RAN5 work item for UE Conformance Test Aspects for NR V2X was approved [1]. The purpose of present document is to provide a workplan for the RAN5 work item on the conformance test cases for the core requirement introduced by the core and performance work items. The workplan is updated after each RAN5 meeting to give the status of the work item.
2. Work item status
Estimation of WI overall completion:
Area |  | Completion | Number of new completed test cases (Note 1) | Number of new test cases | Comments
Overall completion |  | 11% (+4%) | 0 | 165 (+48)
Completion Compensation |  | -
| Note 1: | Only test cases completed for all applicable WP areas and sub-areas are counted. For completed test cases per WP areas and WP sub-areas see below.
Estimation WI completion per area and sub-area:
|  | Completion | Number of new completed test cases | Number of new test cases | Comments
SA Option 2 (SA NR) |  | 13.6% (+7.6%) | 0 | 97 (+2)
FR1 |  | 13.6% (+7.6%) | 0 | 98 (+3)
FR2
FR1 + FR2
PX5 |  | 9.1% (+3.7%) | 0 | 91 (+46)
FR1 |  | 9.1% (+3.7%) | 0 | 91 (+46)
FR2
FR1 + FR2
Estimation of completion per TS (area):
|  | TS/TR overall completion |  |  | SA Option 2 (SA NR) | [8 empty] | PX5
TS/TR Scope | TS/TR | Completion | Number of new completed test cases | Number of new test cases | FR1 |  |  | FR2 |  |  | FR1 + FR2 |  |  | FR1 |  |  | FR2 |  |  | FR1 + FR2
[5 empty] | Completion | Number of new completed test cases | Number of new test cases | Completion | Number of new completed test cases | Number of new test cases | Completion | Number of new completed test cases | Number of new test cases | Completion | Number of new completed test cases | Number of new test cases | Completion | Number of new completed test cases | Number of new test cases | Completion | Number of new completed test cases | Number of new test cases
5GS
5GS Common
Common test environment | 38.508-1 | 30.9% (+30.9%) |  |  | 30.9% (+30.9%) | [8 empty] | 30.9% (+30.9%)
Common ICS | 38.508-2 | 0% |  |  | 0% | [8 empty] | 0%
UE specific test functions | 38.509
NR RF/RRM
FR1 RF common parts | 38.521-1 | 41.7% |  |  | 41.7%
FR1 RF Tx test cases | 38.521-1 Tx | 8% (+7.2%) | 0 | 64 | 8% (+7.2%) | 0 | 64
FR1 RF Rx test cases | 38.521-1 Rx | 0.5% (+0.2%) | 0 | 9 (+2) | 0.5% (+0.2%) | 0 | 10 (+3)
FR1 and FR2 Interworking operation with other radios RF common parts | 38.521-3 | 0% | [11 empty] | 0%
FR1 and FR2 Interworking operation with other radios RF Tx test cases | 38.521-3 Tx | 0% | 0 | 31 (+31) | [9 empty] | 0% | 0 | 31 (+31)
FR1 and FR2 Interworking operation with other radios RF Rx test cases | 38.521-3 Rx | 0% | 0 | 15 (+15) | [9 empty] | 0% | 0 | 15 (+15)
RF Demod/QSI test cases | 38.521-4
RRM test cases | 38.533
Applicability RF, Demod/QSI and RRM test cases | 38.522 | 1.2% (+1.2%) |  |  | 1.2% (+1.2%)
Test Tolerances analysis RRM and RF Rx test cases | 38.903
Test Point analysis receiver and transmitter test cases | 38.905
5GS RAN and CN protocols
Protocol test cases | 38.523-1 | 1% (-0.1%) | 0 | 46 | 1.2% | 0 | 24 | [6 empty] | 0.7% | 0 | 45
Applicability Protocol test cases | 38.523-2 | 0% |  |  | 0% | [8 empty] | 0%
Test suites (TTCN) | 38.523-3
5 References
[1] RP-200894 | New WID on UE conformance test aspects for 5G V2X with NR sidelink; Huawei, Hisilicon
Note on B21: Overall completion of the work item reported at an earlier meeting will not be decreased if additional tasks are added or if corrections are made to the work plan. Instead the earlier reported completion status will be kept until necessary progress have been achieved such that completion exceeds the earlier reported completion level. The value of the Completion Compensation value represents the difference in the decrease caused by late additions or corrections to the work plan and the current estimated overall completion. '-' indicates that no compensation is applied.

## WP
WP Title: |  | WP UE Conformance Test Aspects for NR V2X | [11 empty] | Start of workplan status columns. Note! Do not remove this column. | WP item status | [5 empty] | End of workplan columns. Note! Do not remove this column.
WI code |  | 5G_V2X_NRSL_eV2XARC-UEConTest
WP Scope: |  | Conformance test specifications for the core requirements of Rel-16 Security Aspects of eV2XARC, CT aspects of eV2XARC, and RAN aspects of 5G V2X with NR sidelink. The RAN5 areas of RF, RRM, Demodulation and Protocol conformance test specifications with NR-based V2X operation are to be covered. | [13 empty] | vs Area
WP Resp: |  | Wu, Yuchun (Huawei) |  |  | wuyuchun@huawei.com | [5 empty] | WP item completion |  |  |  | SA Option 2 (SA NR) |  |  | PX5
TS Resp: |  | n/a |  |  | n/a
WP Item ID | Is new test case? | TS/area | Clause | Title | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | Overall | SA Option 2 (SA NR) | PX5 |  | FR1 | FR2 | FR1 + FR2 | FR1 | FR2 | FR1 + FR2
[15 empty] | 13.6% (+7.6%) |  |  | 9.1% (+3.7%)
[15 empty] | 196 (+3) | 0 | 0 | 178 (+89) | 0 | 0
[15 empty] | 122 (-2.8) | 0 | 0 | 120.2 (+59.1) | 0 | 0
5%
Start of work plan items. Note! Do not remove this row. Introduce new work plan rows/items below this row.
5GS - RAN and CN
5GS Common
TS 38.508-1: Common test environment
|  | 38.508-1 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD | 0% | 0% | 0% |  | 0% |  |  | 0%
1 |  | 38.508-1 | 4.3.1 | Test frequencies for NR V2X test | To add Test frequencies for NR V2X test |  | RAN5#91-e (May-21) |  |  | 1 | 0% | 0% | 0% |  | 0% |  |  | 0%
2 |  | 38.508-1 | 4.4.3.1.2 | SI combination for NR V2X test | To add SI combination for NR V2X test | Huawei, Hisilicon | RAN5#91-e (May-21) | R5-211462 |  | 1 | 100% (+100%) | 100% (+100%) | 100% (+100%) |  | 100% |  |  | 100%
3 |  | 38.508-1 | 4.4.3.1.3 | Scheduling of SIBs for NR V2X test | To add Scheduling of SIBs for NR V2X test | Huawei, Hisilicon | RAN5#91-e (May-21) | R5-211462 |  | 1 | 100% (+100%) | 100% (+100%) | 100% (+100%) |  | 100% |  |  | 100%
4 |  | 38.508-1 | 4.4A | Test states for NR V2X test | To add Test states for NR V2X test |  | RAN5#91-e (May-21) |  |  | 1 | 0% | 0% | 0% |  | 0% |  |  | 0%
5 |  | 38.508-1 | 4.5 | Generic procedures for NR V2X test | To add Generic procedures for NR V2X test |  | RAN5#91-e (May-21) |  |  | 1 | 0% | 0% | 0% |  | 0% |  |  | 0%
6 |  | 38.508-1 | 4.6.1A | Contents of PC5 RRC messages | To add PC5 RRC messages used in PC5 unicast[Ref: 38.331 cl. 6.6.2] | Huawei, Hisilicon | RAN5#91-e (May-21) | R5-211337 R5-211338 R5-211339 |  | 1 | 45% (+45%) | 45% (+45%) | 45% (+45%) |  | 45% |  |  | 45%
7 |  | 38.508-1 | 4.6.2 | System information blocks | To update SIBs related to NR sidelink, i.e. SIB12[Ref: 38.331 cl. 6.3.1] | Huawei, Hisilicon | RAN5#91-e (May-21) |  |  | 1 | 0% | 0% | 0% |  | 0% |  |  | 0%
8 |  | 38.508-1 | 4.6.3 | Radio resource control information elements | To update and add Uu RRC IEs related to NR sidelink[Ref: 38.331 cl. 6.3.2] | Huawei, Hisilicon | RAN5#91-e (May-21) | R5-210713 R5-210714 |  | 1 | 50% (+50%) | 50% (+50%) | 50% (+50%) |  | 50% |  |  | 50%
9 |  | 38.508-1 | 4.6.4 | UE capability information elements | To update and add UE capability IEs to support NR sidelink related UE capability reporting[Ref: 38.331 cl. 6.3.3] | Huawei, Hisilicon | RAN5#91-e (May-21) |  |  | 1 | 0% | 0% | 0% |  | 0% |  |  | 0%
10 |  | 38.508-1 | 4.6.5 | Other information elements | To update other IEs related to NR sidelink, such as OtherConfig[Ref: 38.331 cl. 6.3.4] | Huawei, Hisilicon | RAN5#91-e (May-21) |  |  | 1 | 0% | 0% | 0% |  | 0% |  |  | 0%
11 |  | 38.508-1 | 4.6.6 | Sidelink information elements | To add NR sidelink ralated IEs used in Uu RRC messages and PC5 RRC messages[Ref: 38.331 cl. 6.3.5] | Huawei, Hisilicon | RAN5#91-e (May-21) | R5-210701 R5-211335 R5-210703 R5-210704 R5-210705 R5-210706 R5-210707 R5-210708 R5-210709 R5-210710 R5-210711 R5-211366 |  | 1 | 30% (+30%) | 30% (+30%) | 30% (+30%) |  | 30% |  |  | 30%
12 |  | 38.508-1 | 4.7.1 | Contents of 5GMM messages | To Update V2X related parameters into 5GMM capability IE in REGISTRATION REQUEST message | Huawei, Hisilicon | RAN5#91-e (May-21) |  |  | 1 | 0% | 0% | 0% |  | 0% |  |  | 0%
13 |  | 38.508-1 | 4.7.4 | Contents of V2X layer messages | To add default configuration of V2X layer messages [Ref TS 24.501 clause D.5, TS 24.587 clasue 7] | Huawei, Hisilicon | RAN5#91-e (May-21) |  |  | 1 | 0% | 0% | 0% |  | 0% |  |  | 0%
14 |  | 38.508-1 | 4.7.5 | Contents of V2X layer information elements | To add default configuration of V2X information elements [Ref TS 24.501 clause D.6, TS 24.588 clause 5] | Huawei, Hisilicon | RAN5#91-e (May-21) | R5-210699 |  | 1 | 50% (+50%) | 50% (+50%) | 50% (+50%) |  | 50% |  |  | 50%
15 |  | 38.508-1 | 4.8.3.3.3 | Modified contents of the USIM Elementary Files and additional USIM Elements files at the DFV2X level | To add default USIM configuration of V2X [Ref TS 31.102 clause 4.6.5] | Huawei, Hisilicon | RAN5#91-e (May-21) | R5-206408 |  | 1 | 20% (+20%) | 20% (+20%) | 20% (+20%) |  | 20% |  |  | 20%
228 |  | 38.508-1 | 4.10.1 | Pre-configuration for V2X | To add default configuration of V2X AS parameters [Ref TS 38.331 clause 9.3] | Huawei, Hisilicon | RAN5#90-e (Feb-21) | R5-210698 |  | 1 | 100% (+100%) | 100% (+100%) | 100% (+100%) |  | 100% |  |  | 100%
TS 38.508-2: Common ICS
|  | 38.508-2 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
16 |  | 38.508-2 | <Clause> | <Title> | Add ICS as needed for the test case applicability statements for the new test cases introduced in RF, RRM and protocol test cases. |  | TBD |  |  | 1 | 0% | 0% | 0% |  | 0% |  |  | 0%
TS 38.509: UE specific testing functions
|  | 38.509 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
TBD |  | 38.509 | <Clause> | <Title of new sub-clause header> | New sub-clause header |  | TBD |  |  | 0
TBD |  | 38.509 | <Clause> | <Title of task> | <Describe task> |  | TBD |  |  | TBD
NR RF/RRM
TS 38.521-1: FR1 RF test cases - Common parts (general clauses, Annexes)
|  | 38.521-1 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
17 |  | 38.521-1 | 2 | Reference | Define References made in TS | Bureau Veritas | RAN5#89-e (Nov-20) | R5-204839 |  | 0.1 | 100% | 100% |  |  | 100%
18 |  | 38.521-1 | 3 | Definitions, symbols and abbreviations | 3 subsections which define definitions, symbols and abbreaviations respectively | Bureau Veritas | RAN5#89-e (Nov-20) | R5-204839 |  | 0.1 | 100% | 100% |  |  | 100%
19 |  | 38.521-1 | 4 | General | define categories of test requirements | Bureau Veritas | RAN5#89-e (Nov-20) | R5-204839 |  | 0.1 | 100% | 100% |  |  | 100%
20 |  | 38.521-1 | 5 | Operating bands and Channel arrangement | define the frequency bands and channel arragement | Bureau Veritas | RAN5#89-e (Nov-20) | R5-204839 |  | 0.1 | 100% | 100% |  |  | 100%
21 |  | 38.521-1 | Annex A | measurement channels | define mesurement channels | Bureau Veritas | RAN5#91-e (May-21) | R5-205700 |  | 0.1 | 100% | 100% |  |  | 100%
22 |  | 38.521-1 | Annex B | Propagation conditions | Define propagation conditions | Bureau Veritas | RAN5#91-e (May-21) |  |  | 0.1 | 0% | 0% |  |  | 0%
23 |  | 38.521-1 | Annex C | Downlink physical channels | Define downlink physical channels |  | RAN5#91-e (May-21) |  |  | 0.1 | 0% | 0% |  |  | 0%
24 |  | 38.521-1 | Annex D | Characteristics of the interfering signal | Define characteristics of the interfering signal |  | RAN5#91-e (May-21) |  |  | 0.1 | 0% | 0% |  |  | 0%
25 |  | 38.521-1 | Annex E | Global In-Channel TX-Test | Specifiy the measurement of all relevant parameters that describe the in-channel quality of the output signal of the TX under test in a single measurement process |  | RAN5#91-e (May-21) |  |  | 0.1 | 0% | 0% |  |  | 0%
26 |  | 38.521-1 | Annex F | Measurement uncertainties and Test Tolerances | Define measurement uncertainties and TT |  | RAN5#91-e (May-21) |  |  | 0.1 | 0% | 0% |  |  | 0%
27 |  | 38.521-1 | Annex G | Uplink Physical Channels | Define uplink physical channels |  | RAN5#91-e (May-21) |  |  | 0.1 | 0% | 0% |  |  | 0%
28 |  | 38.521-1 | Annex H | Statistical Testing |  |  | RAN5#91-e (May-21) |  |  | 0.1 | 0% | 0% |  |  | 0%
TS 38.521-1: FR1 RF test cases - Tx
|  | 38.521-1 Tx |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
29 |  | 38.521-1 Tx | 6.2E | Transmitter power for V2X | Sub-clause heading |  | RAN5#89-e (Nov-20) |  |  | 0 | 100% | 100% |  |  | 100%
30 |  | 38.521-1 Tx | 6.2E.1 | UE maximum output power for V2X | Sub-clause heading |  | RAN5#89-e (Nov-20) |  |  | 0 | 100% | 100% |  |  | 100%
31 | Y | 38.521-1 Tx | 6.2E.1.1 | UE maximum output power for V2X / non-concurrent operation | TS 38.101-1 cl 6,2E.1.1 | Huawei, Hisiicon | RAN5#90-e (Feb-21) | R5-206764 |  | 1 | 50% | 50% |  |  | 50%
32 | Y | 38.521-1 Tx | 6.2E.1.1D | UE maximum output power for V2X / non-concurrent operation / SL-MIMO | TS 38.101-1 cl 6,2E.1.1 | Huawei, Hisiicon | RAN5#91-e (May-21) |  |  | 1 | 0% | 0% |  |  | 0%
33 | Y | 38.521-1 Tx | 6.2E.1.2 | UE maximum output power for V2X / con-current operation | TS 38.101-1 cl 6,2E.1.2 | Huawei, Hisiicon | RAN5#91-e (May-21) |  |  | 1 | 0% | 0% |  |  | 0%
34 |  | 38.521-1 Tx | 6.2E.2 | UE maximum output power reduction for V2X | Sub-clause heading |  | RAN5#90-e (Feb-21) |  |  | 0 | 0% | 0% |  |  | 0%
35 | Y | 38.521-1 Tx | 6.2E.2.1 | UE maximum output power reduction for V2X / non-concurrent operation | TS 38.101-1 cl 6,2E.2.1, 6.2E.2.2 | Huawei, Hisiicon | RAN5#90-e (Feb-21) |  |  | 1 | 0% | 0% |  |  | 0%
36 | Y | 38.521-1 Tx | 6.2E.2.1D | UE maximum output power reduction for V2X / non-concurrent operation / SL-MIMO | TS 38.101-1 cl 6,2E.2.1, 6.2E.2.2 | Huawei, Hisiicon | RAN5#90-e (Feb-21) |  |  | 1 | 0% | 0% |  |  | 0%
37 | Y | 38.521-1 Tx | 6.2E.2.2 | UE maximum output power reduction for V2X / con-current operation | TS 38.101-1 cl 6,2E.2.3 | Huawei, Hisiicon | RAN5#91-e (May-21) |  |  | 1 | 0% | 0% |  |  | 0%
38 |  | 38.521-1 Tx | 6.2E.3 | UE additional maximum output power reduction for V2X | Sub-clause heading |  | RAN5#90-e (Feb-21) |  |  | 0 | 0% | 0% |  |  | 0%
39 | Y | 38.521-1 Tx | 6.2E.3.1 | UE additional maximum output power reduction for V2X / non-concurrent operation | TS 38.101-1 cl 6,2E.3.1, 6.2E.3.2, 6.2E.3.3 | Huawei, Hisiicon | RAN5#90-e (Feb-21) |  |  | 1 | 0% | 0% |  |  | 0%
40 | Y | 38.521-1 Tx | 6.2E.3.1D | UE additional maximum output power reduction for V2X / non-concurrent operation / SL-MIMO | TS 38.101-1 cl 6,2E.3.1, 6.2E.3.2, 6.2E.3.3 | Huawei, Hisiicon | RAN5#90-e (Feb-21) |  |  | 1 | 0% | 0% |  |  | 0%
41 | Y | 38.521-1 Tx | 6.2E.3.2 | UE additional maximum output power reduction for V2X / con-current operation | TS 38.101-1 cl 6,2E.3.4 | Huawei, Hisiicon | RAN5#91-e (May-21) |  |  | 1 | 0% | 0% |  |  | 0%
42 |  | 38.521-1 Tx | 6.2E.4 | Configured transmitted power for V2X | Sub-clause heading |  | RAN5#90-e (Feb-21) |  |  | 0 | 0% | 0% |  |  | 0%
43 | Y | 38.521-1 Tx | 6.2E.4.1 | Configured transmitted power for V2X / non-concurrent operation | TS 38.101-1 cl 6,2E.4.1 | Huawei, Hisiicon | RAN5#90-e (Feb-21) |  |  | 1 | 0% | 0% |  |  | 0%
44 | Y | 38.521-1 Tx | 6.2E.4.1D | Configured transmitted power for V2X / non-concurrent operation / SL-MIMO | TS 38.101-1 cl 6,2E.4.1 | Huawei, Hisiicon | RAN5#90-e (Feb-21) |  |  | 1 | 0% | 0% |  |  | 0%
45 | Y | 38.521-1 Tx | 6.2E.4.2 | Configured transmitted power for V2X / con-current operation | TS 38.101-1 cl 6,2E.4.2 | Huawei, Hisiicon | RAN5#91-e (May-21) |  |  | 1 | 0% | 0% |  |  | 0%
46 |  | 38.521-1 Tx | 6.3E.1 | Minimum output power for V2X | Sub-clause heading |  | RAN5#90-e (Feb-21) |  |  | 0 | 0% | 0% |  |  | 0%
47 | Y | 38.521-1 Tx | 6.3E.1.1 | Minimum output power for V2X / non-concurrent operation | TS 38.101-1 cl 6,3E.1.1 | Huawei, Hisiicon | RAN5#90-e (Feb-21) |  |  | 1 | 0% | 0% |  |  | 0%
48 | Y | 38.521-1 Tx | 6.3E.1.1D | Minimum output power for V2X / non-concurrent operation / SL-MIMO | TS 38.101-1 cl 6,3E.1.1 | Huawei, Hisiicon | RAN5#90-e (Feb-21) |  |  | 1 | 0% | 0% |  |  | 0%
49 | Y | 38.521-1 Tx | 6.3E.1.2 | Minimum output power for V2X / con-current operation | TS 38.101-1 cl 6,3E.1.2 | Huawei, Hisiicon | RAN5#91-e (May-21) |  |  | 1 | 0% | 0% |  |  | 0%
50 |  | 38.521-1 Tx | 6.3E.2 | Transmit OFF power for V2X | Sub-clause heading |  | RAN5#90-e (Feb-21) |  |  | 0 | 0% | 0% |  |  | 0%
51 | Y | 38.521-1 Tx | 6.3E.2.1 | Transmit OFF power for V2X / non-concurrent operation | TS 38.101-1 cl 6,3E.2.1 | CAICT | RAN5#90-e (Feb-21) |  |  | 1 | 0% | 0% |  |  | 0%
52 | Y | 38.521-1 Tx | 6.3E.2.1D | Transmit OFF power for V2X / non-concurrent operation / SL-MIMO | TS 38.101-1 cl 6,3E.2.1 | CAICT | RAN5#90-e (Feb-21) |  |  | 1 | 0% | 0% |  |  | 0%
53 | Y | 38.521-1 Tx | 6.3E.2.2 | Transmit OFF power for V2X / con-current operation | TS 38.101-1 cl 6,3E.2.2 | CAICT | RAN5#91-e (May-21) |  |  | 1 | 0% | 0% |  |  | 0%
54 |  | 38.521-1 Tx | 6.3E.3 | Transmit ON/OFF time mask for V2X | Sub-clause heading |  | RAN5#90-e (Feb-21) |  |  | 0 | 0% | 0% |  |  | 0%
55 |  | 38.521-1 Tx | 6.3E.3.1 | General | TS 38.101-1 cl 6.3E.3.1 |  | RAN5#90-e (Feb-21) |  |  | 0.1 | 0% | 0% |  |  | 0%
56 |  | 38.521-1 Tx | 6.3E.3.2 | General time mask for V2X | Sub-clause heading |  | RAN5#90-e (Feb-21) |  |  | 0 | 0% | 0% |  |  | 0%
57 | Y | 38.521-1 Tx | 6.3E.3.2.1 | General time mask for V2X / non-concurrent operation | TS 38.101-1 cl 6.3E.3.2 | Samsung | RAN5#90-e (Feb-21) |  |  | 1 | 0% | 0% |  |  | 0%
58 | Y | 38.521-1 Tx | 6.3E.3.2.1D | General time mask for V2X / non-concurrent operation / SL-MIMO | TS 38.101-1 cl 6.3E.3.2 | Samsung | RAN5#90-e (Feb-21) |  |  | 1 | 0% | 0% |  |  | 0%
59 | Y | 38.521-1 Tx | 6.3E.3.2.2 | General time mask for V2X / con-current operation | TS 38.101-1 cl 6.3E.3.4 | Samsung | RAN5#91-e (May-21) |  |  | 1 | 0% | 0% |  |  | 0%
60 |  | 38.521-1 Tx | 6.3E.3.3 | S-SSB time mask for V2X | Sub-clause heading |  | RAN5#90-e (Feb-21) |  |  | 0 | 0% | 0% |  |  | 0%
61 | Y | 38.521-1 Tx | 6.3E.3.3.1 | S-SSB time mask for V2X / non-concurrent operation | TS 38.101-1 cl 6.3E.3.3 | Samsung | RAN5#90-e (Feb-21) |  |  | 1 | 0% | 0% |  |  | 0%
62 | Y | 38.521-1 Tx | 6.3E.3.3.1D | S-SSB time mask for V2X / non-concurrent operation / SL-MIMO | TS 38.101-1 cl 6.3E.3.3 | Samsung | RAN5#90-e (Feb-21) |  |  | 1 | 0% | 0% |  |  | 0%
63 | Y | 38.521-1 Tx | 6.3E.3.3.2 | S-SSB time mask for V2X / con-current operation | TS 38.101-1 cl 6.3E.3.4 | Samsung | RAN5#91-e (May-21) |  |  | 1 | 0% | 0% |  |  | 0%
64 |  | 38.521-1 Tx | 6.3E.4 | Power control for V2X | Sub-clause heading |  | RAN5#90-e (Feb-21) |  |  | 0 | 0% | 0% |  |  | 0%
65 |  | 38.521-1 Tx | 6.3E.4.1 | General | TS 38.101-1 cl 6,3E.4.1 |  | RAN5#90-e (Feb-21) |  |  | 0.1 | 0% | 0% |  |  | 0%
66 |  | 38.521-1 Tx | 6.3E.4.2 | Absolute power tolerance for V2X | Sub-clause heading |  | RAN5#90-e (Feb-21) |  |  | 0 | 0% | 0% |  |  | 0%
67 | Y | 38.521-1 Tx | 6.3E.4.2.1 | Absolute power tolerance for V2X / non-concurrent operation | TS 38.101-1 cl 6,3E.4.2 | Samsung | RAN5#90-e (Feb-21) |  |  | 1 | 0% | 0% |  |  | 0%
68 | Y | 38.521-1 Tx | 6.3E.4.2.1D | Absolute power tolerance for V2X / non-concurrent operation / SL-MIMO | TS 38.101-1 cl 6,3E.4.2 | Samsung | RAN5#90-e (Feb-21) |  |  | 1 | 0% | 0% |  |  | 0%
69 | Y | 38.521-1 Tx | 6.3E.4.2.2 | Absolute power tolerance for V2X / con-current operation | TS 38.101-1 cl 6,3E.4.3 | Samsung | RAN5#91-e (May-21) |  |  | 1 | 0% | 0% |  |  | 0%
70 |  | 38.521-1 Tx | 6.4E.1 | Frequency error for V2X | Sub-clause heading |  | RAN5#90-e (Feb-21) |  |  | 0 | 0% | 0% |  |  | 0%
71 | Y | 38.521-1 Tx | 6.4E.1.1 | Frequency error for V2X / non-concurrent operation | TS 38.101-1 cl 6,4E.1.1 | Huawei, Hisiicon | RAN5#90-e (Feb-21) |  |  | 1 | 0% | 0% |  |  | 0%
72 | Y | 38.521-1 Tx | 6.4E.1.1D | Frequency error for V2X / non-concurrent operation / SL-MIMO | TS 38.101-1 cl 6,4E.1.1 | Huawei, Hisiicon | RAN5#90-e (Feb-21) |  |  | 1 | 0% | 0% |  |  | 0%
73 | Y | 38.521-1 Tx | 6.4E.1.2 | Frequency error for V2X / con-current operation | TS 38.101-1 cl 6,4E.1.2 | Huawei, Hisiicon | RAN5#91-e (May-21) |  |  | 1 | 0% | 0% |  |  | 0%
74 |  | 38.521-1 Tx | 6.4E.2 | Transmit modulation quality for V2X | Sub-clause heading |  | RAN5#90-e (Feb-21) |  |  | 0 | 0% | 0% |  |  | 0%
75 |  | 38.521-1 Tx | 6.4E.2.1 | General | TS 38.101-1 cl 6,4E.2.1 | LG Electronics | RAN5#90-e (Feb-21) | R5-210419 |  | 0.1 | 100% (+100%) | 100% (+100%) |  |  | 100%
76 |  | 38.521-1 Tx | 6.4E.2.2 | Error Vector Magnitude for V2X | Sub-clause heading |  | RAN5#90-e (Feb-21) |  |  | 0 | 0% | 0% |  |  | 0%
77 | Y | 38.521-1 Tx | 6.4E.2.2.1 | Error Vector Magnitude for V2X / non-concurrent operation | TS 38.101-1 cl 6,4E.2.2 | LG Electronics | RAN5#90-e (Feb-21) | R5-210419 | Editor’s Note: - No test points are defined since there is no configuration satisfying MPR=0dB requirements in RAN4. - The test case is not completed due to the following aspects are not yet determined: - Uplink RMC is TBD in RAN4 - Connection diagram is TBD - Preconfiguration is TBD in 38.508-1 - Test state and generic procedure are TBD in 38.508-1 38.522:R5-211610 | 1 | 50% (+50%) | 50% (+50%) |  |  | 50%
78 | Y | 38.521-1 Tx | 6.4E.2.2.1D | Error Vector Magnitude for V2X / non-concurrent operation / SL-MIMO | TS 38.101-1 cl 6,4E.2.2 |  | RAN5#90-e (Feb-21) |  |  | 1 | 0% | 0% |  |  | 0%
79 | Y | 38.521-1 Tx | 6.4E.2.2.2 | Error Vector Magnitude for V2X / con-current operation | TS 38.101-1 cl 6,4E.2.6 |  | RAN5#91-e (May-21) |  |  | 1 | 0% | 0% |  |  | 0%
80 |  | 38.521-1 Tx | 6.4E.2.3 | Carrier leakage for V2X | Sub-clause heading |  | RAN5#90-e (Feb-21) |  |  | 0 | 0% | 0% |  |  | 0%
81 | Y | 38.521-1 Tx | 6.4E.2.3.1 | Carrier leakage for V2X / non-concurrent operation | TS 38.101-1 cl 6,4E.2.3 | Huawei, Hisiicon | RAN5#90-e (Feb-21) |  |  | 1 | 0% | 0% |  |  | 0%
82 | Y | 38.521-1 Tx | 6.4E.2.3.1D | Carrier leakage for V2X / non-concurrent operation / SL-MIMO | TS 38.101-1 cl 6,4E.2.3 | Huawei, Hisiicon | RAN5#90-e (Feb-21) |  |  | 1 | 0% | 0% |  |  | 0%
83 | Y | 38.521-1 Tx | 6.4E.2.3.2 | Carrier leakage for V2X / con-current operation | TS 38.101-1 cl 6,4E.2.6 | Huawei, Hisiicon | RAN5#91-e (May-21) |  |  | 1 | 0% | 0% |  |  | 0%
84 |  | 38.521-1 Tx | 6.4E.2.4 | In-band emissions for V2X | Sub-clause heading |  | RAN5#90-e (Feb-21) |  |  | 0 | 0% | 0% |  |  | 0%
85 | Y | 38.521-1 Tx | 6.4E.2.4.1 | In-band emissions for V2X / non-concurrent operation | TS 38.101-1 cl 6,4E.2.4 |  | RAN5#90-e (Feb-21) |  |  | 1 | 0% | 0% |  |  | 0%
86 | Y | 38.521-1 Tx | 6.4E.2.4.1D | In-band emissions for V2X / non-concurrent operation / SL-MIMO | TS 38.101-1 cl 6,4E.2.4 |  | RAN5#90-e (Feb-21) |  |  | 1 | 0% | 0% |  |  | 0%
87 | Y | 38.521-1 Tx | 6.4E.2.4.2 | In-band emissions for V2X / con-current operation | TS 38.101-1 cl 6,4E.2.6 |  | RAN5#91-e (May-21) |  |  | 1 | 0% | 0% |  |  | 0%
88 |  | 38.521-1 Tx | 6.4E.2.5 | EVM equalizer spectrum flatness for V2X | Sub-clause heading |  | RAN5#90-e (Feb-21) |  |  | 0 | 0% | 0% |  |  | 0%
89 | Y | 38.521-1 Tx | 6.4E.2.5.1 | EVM equalizer spectrum flatness for V2X / non-concurrent operation | TS 38.101-1 cl 6,4E.2.4 |  | RAN5#90-e (Feb-21) |  |  | 1 | 0% | 0% |  |  | 0%
90 | Y | 38.521-1 Tx | 6.4E.2.5.1D | EVM equalizer spectrum flatness for V2X / non-concurrent operation / SL-MIMO | TS 38.101-1 cl 6,4E.2.4 |  | RAN5#90-e (Feb-21) |  |  | 1 | 0% | 0% |  |  | 0%
91 | Y | 38.521-1 Tx | 6.4E.2.5.2 | EVM equalizer spectrum flatness for V2X / con-current operation | TS 38.101-1 cl 6,4E.2.6 |  | RAN5#91-e (May-21) |  |  | 1 | 0% | 0% |  |  | 0%
92 |  | 38.521-1 Tx | 6.5.3.2 | Spurious emissions for UE co-existence | TS 38.101-1 cl 6,5.3.2 Adding band n47 |  | RAN5#90-e (Feb-21) |  |  | 1 | 0% | 0% |  |  | 0%
93 |  | 38.521-1 Tx | 6.5E.1 | Occupied bandwidth for V2X | Sub-clause heading |  | RAN5#90-e (Feb-21) |  |  | 0 | 0% | 0% |  |  | 0%
94 | Y | 38.521-1 Tx | 6.5E.1.1 | Occupied bandwidth for V2X / non-concurrent operation | TS 38.101-1 cl 6,5E.1.1 | Huawei, Hisiicon | RAN5#90-e (Feb-21) |  |  | 1 | 0% | 0% |  |  | 0%
95 | Y | 38.521-1 Tx | 6.5E.1.1D | Occupied bandwidth for V2X / non-concurrent operation / SL-MIMO | TS 38.101-1 cl 6,5E.1.1 | Huawei, Hisiicon | RAN5#90-e (Feb-21) |  |  | 1 | 0% | 0% |  |  | 0%
96 | Y | 38.521-1 Tx | 6.5E.1.2 | Occupied bandwidth for V2X / con-current operation | TS 38.101-1 cl 6,5E.1.2 | Huawei, Hisiicon | RAN5#91-e (May-21) |  |  | 1 | 0% | 0% |  |  | 0%
97 |  | 38.521-1 Tx | 6.5E.2 | Out of band emission for V2X | Sub-clause heading |  | RAN5#90-e (Feb-21) |  |  | 0 | 0% | 0% |  |  | 0%
98 |  | 38.521-1 Tx | 6.5E.2.1 | General | TS 38.101-1 cl 6,5E.2.1 | Oppo | RAN5#90-e (Feb-21) | R5-211806 |  | 0.1 | 100% (+100%) | 100% (+100%) |  |  | 100%
99 |  | 38.521-1 Tx | 6.5E.2.2 | Spectrum emission mask for V2X | Sub-clause heading |  | RAN5#90-e (Feb-21) |  |  | 0 | 0% | 0% |  |  | 0%
100 | Y | 38.521-1 Tx | 6.5E.2.2.1 | Spectrum emission mask for V2X / non-concurrent operation | TS 38.101-1 cl 6,5E.2.2.1 | Oppo | RAN5#90-e (Feb-21) | R5-211806 | Editor’s Note: This clause is incomplete. The following aspects are either missing or not yet determined: - Test config table is FFS - Uplink RMC is TBD in RAN4 - Connection diagram is TBD - Preconfiguration is TBD in 38.508-1 - Test state and generic procedure are TBD in 38.508-1 | 1 | 50% (+50%) | 50% (+50%) |  |  | 50%
101 | Y | 38.521-1 Tx | 6.5E.2.2.1D | Spectrum emission mask for V2X / non-concurrent operation / SL-MIMO | TS 38.101-1 cl 6,5E.2.2.1 | Oppo | RAN5#90-e (Feb-21) | R5-210423 | Editor’s Note: - Test config table is FFS - Uplink RMC is TBD in RAN4 - Connection diagram is TBD - Preconfiguration is TBD in 38.508-1 - Test state and generic procedure are TBD in 38.508-1 | 1 | 50% (+50%) | 50% (+50%) |  |  | 50%
102 | Y | 38.521-1 Tx | 6.5E.2.2.2 | Spectrum emission mask for V2X / con-current operation | TS 38.101-1 cl 6,5E.2.2.2 | Oppo | RAN5#91-e (May-21) |  |  | 1 | 0% | 0% |  |  | 0%
103 |  | 38.521-1 Tx | 6.5E.2.3 | Additional Spectrum emission mask for V2X | Sub-clause heading |  | RAN5#90-e (Feb-21) |  |  | 0 | 0% | 0% |  |  | 0%
104 | Y | 38.521-1 Tx | 6.5E.2.3.1 | Additional Spectrum emission mask for V2X / non-concurrent operation | TS 38.101-1 cl 6,5E.2.3.1, 6,5E.2.3.2 | Oppo | RAN5#90-e (Feb-21) | R5-210424 | Editor’s Note: - Test config table is FFS - Uplink RMC is TBD in RAN4 - Connection diagram is TBD - Preconfiguration is TBD in 38.508-1 - Test state and generic procedure are TBD in 38.508-1 | 1 | 50% (+50%) | 50% (+50%) |  |  | 50%
105 | Y | 38.521-1 Tx | 6.5E.2.3.1D | Additional Spectrum emission mask for V2X / non-concurrent operation / SL-MIMO | TS 38.101-1 cl 6,5E.2.3.1, 6,5E.2.3.2 | Oppo | RAN5#90-e (Feb-21) | R5-210425 | Editor’s Note: - Test config table is FFS - Uplink RMC is TBD in RAN4 - Connection diagram is TBD - Preconfiguration is TBD in 38.508-1 - Test state and generic procedure are TBD in 38.508-1 | 1 | 50% (+50%) | 50% (+50%) |  |  | 50%
106 |  | 38.521-1 Tx | 6.5E.2.4 | Adjacent channel leakage ratio for V2X | Sub-clause heading |  | RAN5#90-e (Feb-21) |  |  | 0 | 0% | 0% |  |  | 0%
107 | Y | 38.521-1 Tx | 6.5E.2.4.1 | Adjacent channel leakage ratio for V2X / non-concurrent operation | TS 38.101-1 cl 6,5E.2.4.1 | Oppo | RAN5#90-e (Feb-21) | R5-210426 | Editor’s Note: - Test config table is FFS - Uplink RMC is TBD in RAN4 - Connection diagram is TBD - Preconfiguration is TBD in 38.508-1 - Test state and generic procedure are TBD in 38.508-1 | 1 | 50% (+50%) | 50% (+50%) |  |  | 50%
108 | Y | 38.521-1 Tx | 6.5E.2.4.1D | Adjacent channel leakage ratio for V2X / non-concurrent operation / SL-MIMO | TS 38.101-1 cl 6,5E.2.4.1 | Oppo | RAN5#90-e (Feb-21) | R5-210427 | Editor’s Note: - Test config table is FFS - Uplink RMC is TBD in RAN4 - Connection diagram is TBD - Preconfiguration is TBD in 38.508-1 - Test state and generic procedure are TBD in 38.508-1 | 1 | 50% (+50%) | 50% (+50%) |  |  | 50%
109 | Y | 38.521-1 Tx | 6.5E.2.4.2 | Adjacent channel leakage ratio for V2X / con-current operation | TS 38.101-1 cl 6,5E.2.4.2 | Oppo | RAN5#91-e (May-21) |  |  | 1 | 0% | 0% |  |  | 0%
110 |  | 38.521-1 Tx | 6.5E.3 | Spurious emissions for V2X | Sub-clause heading |  | RAN5#90-e (Feb-21) |  |  | 0 | 0% | 0% |  |  | 0%
111 |  | 38.521-1 Tx | 6.5E.3.1 | General spurious emissions for V2X | Sub-clause heading |  | RAN5#90-e (Feb-21) |  |  | 0 | 0% | 0% |  |  | 0%
112 | Y | 38.521-1 Tx | 6.5E.3.1.1 | General spurious emissions for V2X / non-concurrent operation | TS 38.101-1 cl 6,5E.3.1 | Huawei, Hisiicon | RAN5#90-e (Feb-21) |  |  | 1 | 0% | 0% |  |  | 0%
113 | Y | 38.521-1 Tx | 6.5E.3.1.1D | General spurious emissions for V2X / non-concurrent operation / SL-MIMO | TS 38.101-1 cl 6,5E.3.1 | Huawei, Hisiicon | RAN5#90-e (Feb-21) |  |  | 1 | 0% | 0% |  |  | 0%
114 |  | 38.521-1 Tx | 6.5E.3.2 | Spurious emissions for UE co-existence for V2X | Sub-clause heading |  | RAN5#90-e (Feb-21) |  |  | 0 | 0% | 0% |  |  | 0%
115 | Y | 38.521-1 Tx | 6.5E.3.2.1 | Spurious emissions for UE co-existence / non-concurrent operation | TS 38.101-1 cl 6,5E.3.2 | Oppo | RAN5#90-e (Feb-21) | R5-210428 | Editor’s Note: - Test config table is FFS - Uplink RMC is TBD in RAN4 - Connection diagram is TBD - Preconfiguration is TBD in 38.508-1 - Test state and generic procedure are TBD in 38.508-1 | 1 | 50% (+50%) | 50% (+50%) |  |  | 50%
116 | Y | 38.521-1 Tx | 6.5E.3.2.1D | Spurious emissions for UE co-existence / non-concurrent operation / SL-MIMO | TS 38.101-1 cl 6,5E.3.2 | Oppo | RAN5#90-e (Feb-21) | R5-210429 | Editor’s Note: - Test config table is FFS - Uplink RMC is TBD in RAN4 - Connection diagram is TBD - Preconfiguration is TBD in 38.508-1 - Test state and generic procedure are TBD in 38.508-1 | 1 | 50% (+50%) | 50% (+50%) |  |  | 50%
117 | Y | 38.521-1 Tx | 6.5E.3.2.2 | Spurious emissions for UE co-existence / con-current operation | TS 38.101-1 cl 6,5E.3.3 | Oppo | RAN5#91-e (May-21) |  |  | 1 | 0% | 0% |  |  | 0%
118 |  | 38.521-1 Tx | 6.5E.3.3 | Additional spurious emissions requirements for V2X | Sub-clause heading |  | RAN5#90-e (Feb-21) |  |  | 0 | 0% | 0% |  |  | 0%
119 | Y | 38.521-1 Tx | 6.5E.3.3.1 | Additional spurious emissions requirements for V2X / non-concurrent operation | TS 38.101-1 cl 6,5E.3.4.1, 6.5E.3.4.2, 6.5E.3.4.3 | Oppo | RAN5#90-e (Feb-21) |  |  | 1 | 0% | 0% |  |  | 0%
120 | Y | 38.521-1 Tx | 6.5E.3.3.1D | Additional spurious emissions requirements for V2X / non-concurrent operation / SL-MIMO | TS 38.101-1 cl 6,5E.3.4.1, 6.5E.3.4.2, 6.5E.3.4.3 | Oppo | RAN5#90-e (Feb-21) |  |  | 1 | 0% | 0% |  |  | 0%
121 |  | 38.521-1 Tx | 6.5E.4 | Transmit intermodulation for V2X | Sub-clause heading |  | RAN5#90-e (Feb-21) |  |  | 0 | 0% | 0% |  |  | 0%
122 | Y | 38.521-1 Tx | 6.5E.4.1 | Transmit intermodulation for V2X / non-concurrent operation | TS 38.101-1 cl 6.5E.4.1 | Huawei, Hisiicon | RAN5#90-e (Feb-21) |  |  | 1 | 0% | 0% |  |  | 0%
123 | Y | 38.521-1 Tx | 6.5E.4.1D | Transmit intermodulation for V2X / non-concurrent operation / SL-MIMO | TS 38.101-1 cl 6.5E.4.1 | Huawei, Hisiicon | RAN5#90-e (Feb-21) |  |  | 1 | 0% | 0% |  |  | 0%
124 | Y | 38.521-1 Tx | 6.5E.4.2 | Transmit intermodulation for V2X / con-current operation | TS 38.101-1 cl 6.5E.4.2 | Huawei, Hisiicon | RAN5#91-e (May-21) |  |  | 1 | 0% | 0% |  |  | 0%
125 | Y | 38.521-1 Tx | 6.6E.1 | Time alignment error for V2X / non-concurrent operation | TS 38.101-1 cl 6.6 |  | RAN5#90-e (Feb-21) |  |  | 1 | 0% | 0% |  |  | 0%
TS 38.521-1: FR1 RF test cases - Rx
|  | 38.521-1 Rx |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD | 0% | 0% |  |  | 0%
126 |  | 38.521-1 Rx | 7.3E | Reference sensitivity for V2X | Sub-clause heading |  | RAN5#90-e (Feb-21) |  |  | 0 | 0% | 0% |  |  | 0%
127 |  | 38.521-1 Rx | 7.3E.1 | General | TS 38.101-1 cl 7.3E.1 | Huawei, Hisiicon | RAN5#90-e (Feb-21) |  |  | 0.1 | 50% | 50% |  |  | 50%
128 | Y | 38.521-1 Rx | 7.3E.2 | Reference sensitivity for V2X / non-concurrent operation | TS 38.101-1 cl 7.3E.2 | Huawei, Hisiicon | RAN5#90-e (Feb-21) | R5-206765 |  | 0 | 0% | 0% |  |  | 0%
129 | Y | 38.521-1 Rx | 7.3E.3 | Reference sensitivity for V2X / con-current operation | TS 38.101-1 cl 7.3E.3 | Huawei, Hisiicon | RAN5#91-e (May-21) |  |  | 1 | 0% | 0% |  |  | 0%
130 |  | 38.521-1 Rx | 7.4E | Maximum input level for V2X | Sub-clause heading |  | RAN5#90-e (Feb-21) |  |  | 0 | 0% | 0% |  |  | 0%
131 | Y | 38.521-1 Rx | 7.4E.1 | Maximum input level for V2X / non-concurrent operation | TS 38.101-1 cl 7.4E.1 | Huawei, Hisiicon | RAN5#90-e (Feb-21) |  |  | 1 | 0% | 0% |  |  | 0%
132 | Y | 38.521-1 Rx | 7.4E.2 | Maximum input level for V2X / con-current operation | TS 38.101-1 cl 7.4E.2 | Huawei, Hisiicon | RAN5#91-e (May-21) |  |  | 0 | 0% | 0% |  |  | 0%
133 |  | 38.521-1 Rx | 7.5E | Adjacent channel selectivity for V2X | Sub-clause heading |  | RAN5#90-e (Feb-21) |  |  | 0 | 0% | 0% |  |  | 0%
134 | Y | 38.521-1 Rx | 7.5E.1 | Adjacent channel selectivity for V2X / non-concurrent operation | TS 38.101-1 cl 7.5E.1 | Huawei, Hisiicon | RAN5#90-e (Feb-21) |  |  | 1 | 0% | 0% |  |  | 0%
135 | Y | 38.521-1 Rx | 7.5E.2 | Adjacent channel selectivity for V2X / con-current operation | TS 38.101-1 cl 7.5E.2 | Huawei, Hisiicon | RAN5#91-e (May-21) |  |  | 0 | 0% | 0% |  |  | 0%
136 |  | 38.521-1 Rx | 7.6E | Blocking characteristics for V2X | Sub-clause heading |  | RAN5#90-e (Feb-21) |  |  | 0 | 0% | 0% |  |  | 0%
137 |  | 38.521-1 Rx | 7.6E.1 | General | TS 38.101-1 cl 7.6E.1 | CAICT | RAN5#90-e (Feb-21) |  |  | 0.1 | 0% | 0% |  |  | 0%
138 |  | 38.521-1 Rx | 7.6E.2 | In-band blocking for V2X | Sub-clause heading |  | RAN5#90-e (Feb-21) |  |  | 0 | 0% | 0% |  |  | 0%
139 | Y | 38.521-1 Rx | 7.6E.2.1 | In-band blocking for V2X / non-concurrent operation | TS 38.101-1 cl 7.6E.2.1 | CAICT | RAN5#90-e (Feb-21) |  |  | 1 | 0% | 0% |  |  | 0%
140 | Y | 38.521-1 Rx | 7.6E.2.2 | In-band blocking for V2X / con-current operation | TS 38.101-1 cl 7.6E.2.2 | CAICT | RAN5#91-e (May-21) |  |  | 0 | 0% | 0% |  |  | 0%
141 |  | 38.521-1 Rx | 7.6E.3 | Out-of-band blocking for V2X | Sub-clause heading |  | RAN5#90-e (Feb-21) |  |  | 0 | 0% | 0% |  |  | 0%
142 | Y | 38.521-1 Rx | 7.6E.3.1 | Out-of-band blocking for V2X / non-concurrent operation | TS 38.101-1 cl 7.6E.3.1 | CAICT | RAN5#90-e (Feb-21) |  |  | 1 | 0% | 0% |  |  | 0%
143 | Y | 38.521-1 Rx | 7.6E.3.2 | Out-of-band blocking for V2X / con-current operation | TS 38.101-1 cl 7.6E.3.2 | CAICT | RAN5#91-e (May-21) |  |  | 1 | 0% | 0% |  |  | 0%
144 |  | 38.521-1 Rx | 7.7E | Spurious response for V2X | Sub-clause heading |  | RAN5#90-e (Feb-21) |  |  | 0 | 0% | 0% |  |  | 0%
145 | Y | 38.521-1 Rx | 7.7E.1 | Spurious response for V2X / non-concurrent operation | TS 38.101-1 cl 7.7E.1 | CAICT | RAN5#90-e (Feb-21) |  |  | 1 | 0% | 0% |  |  | 0%
146 | Y | 38.521-1 Rx | 7.7E.2 | Spurious response for V2X / con-current operation | TS 38.101-1 cl 7.7E.2 | CAICT | RAN5#91-e (May-21) |  |  | 1 | 0% | 0% |  |  | 0%
147 |  | 38.521-1 Rx | 7.8E | Intermodulation characteristics for V2X | Sub-clause heading |  | RAN5#90-e (Feb-21) |  |  | 0 | 0% | 0% |  |  | 0%
148 |  | 38.521-1 Rx | 7.8E.1 | General | TS 38.101-1 cl 7.8E.1 | CAICT | RAN5#90-e (Feb-21) |  |  | 0.1 | 0% | 0% |  |  | 0%
149 |  | 38.521-1 Rx | 7.8E.2 | Wide band Intermodulation for V2X | Sub-clause heading |  | RAN5#90-e (Feb-21) |  |  | 0 | 0% | 0% |  |  | 0%
150 | Y | 38.521-1 Rx | 7.8E.2.1 | Wide band Intermodulation for V2X / non-concurrent operation | TS 38.101-1 cl 7.8E.2 | CAICT | RAN5#90-e (Feb-21) |  |  | 1 | 0% | 0% |  |  | 0%
151 | Y | 38.521-1 Rx | 7.8E.2.2 | Wide band Intermodulation for V2X / con-current operation | TS 38.101-1 cl 7.8E.3 | CAICT | RAN5#91-e (May-21) |  |  | 1 | 0% | 0% |  |  | 0%
TS 38.521-3: FR1 and FR2 Interworking operation with other radios RF test cases - Common parts (general clauses, Annexes)
|  | 38.521-3 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
229 |  | 38.521-3 | 2 | Reference | Define References made in TS | Bureau Veritas | RAN5#93 (Nov-21) |  |  | 1 | 0% |  | 0% |  |  |  |  | 0%
230 |  | 38.521-3 | 3 | Definitions, symbols and abbreviations | 3 subsections which define definitions, symbols and abbreaviations respectively | Bureau Veritas | RAN5#93 (Nov-21) |  |  | 1 | 0% |  | 0% |  |  |  |  | 0%
231 |  | 38.521-3 | 4 | General | define categories of test requirements | Bureau Veritas | RAN5#93 (Nov-21) |  |  | 1 | 0% |  | 0% |  |  |  |  | 0%
232 |  | 38.521-3 | 5 | Operating bands and Channel arrangement | define the frequency bands and channel arragement | Bureau Veritas | RAN5#93 (Nov-21) |  |  | 1 | 0% |  | 0% |  |  |  |  | 0%
233 |  | 38.521-3 | Annex A | measurement channels | define mesurement channels | Bureau Veritas | RAN5#93 (Nov-21) |  |  | 1 | 0% |  | 0% |  |  |  |  | 0%
234 |  | 38.521-3 | Annex B | Propagation conditions | Define propagation conditions | Bureau Veritas | RAN5#93 (Nov-21) |  |  | 1 | 0% |  | 0% |  |  |  |  | 0%
235 |  | 38.521-3 | Annex C | Downlink physical channels | Define downlink physical channels |  | RAN5#93 (Nov-21) |  |  | 1 | 0% |  | 0% |  |  |  |  | 0%
236 |  | 38.521-3 | Annex D | Characteristics of the interfering signal | Define characteristics of the interfering signal |  | RAN5#93 (Nov-21) |  |  | 1 | 0% |  | 0% |  |  |  |  | 0%
237 |  | 38.521-3 | Annex E | Global In-Channel TX-Test | Specifiy the measurement of all relevant parameters that describe the in-channel quality of the output signal of the TX under test in a single measurement process |  | RAN5#93 (Nov-21) |  |  | 1 | 0% |  | 0% |  |  |  |  | 0%
238 |  | 38.521-3 | Annex F | Measurement uncertainties and Test Tolerances | Define measurement uncertainties and TT |  | RAN5#93 (Nov-21) |  |  | 1 | 0% |  | 0% |  |  |  |  | 0%
239 |  | 38.521-3 | Annex G | Uplink Physical Channels | Define uplink physical channels |  | RAN5#93 (Nov-21) |  |  | 1 | 0% |  | 0% |  |  |  |  | 0%
240 |  | 38.521-3 | Annex H | Statistical Testing |  |  | RAN5#93 (Nov-21) |  |  | 1 | 0% |  | 0% |  |  |  |  | 0%
TS 38.521-3: FR1 and FR2 Interworking operation with other radios RF test cases - Tx
|  | 38.521-3 Tx |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
241 |  | 38.521-3 Tx | 6.2E | Transmitter power for V2X in FR1 | New sub-clause header |  | RAN5#93 (Nov-21) |  |  | 0 | 0% |  | 0% |  |  |  |  | 0%
242 |  | 38.521-3 Tx | 6.2E.1 | UE maximum output power for V2X | New sub-clause header |  | RAN5#93 (Nov-21) |  |  | 0 | 0% |  | 0% |  |  |  |  | 0%
243 | Y | 38.521-3 Tx | 6.2E.1.1 | UE maximum output power for Intra-band contiguous V2X | TS38.101-3 cl 6,2E.1.1 | Huawei | RAN5#93 (Nov-21) |  |  | 1 | 0% |  | 0% |  |  |  |  | 0%
244 | Y | 38.521-3 Tx | 6.2E.1.2 | UE maximum output power for Intra-band non-contuous V2X | TS38.101-3 cl 6,2E.1.2 | Huawei | RAN5#93 (Nov-21) |  |  | 1 | 0% |  | 0% |  |  |  |  | 0%
245 | Y | 38.521-3 Tx | 6.2E.1.3 | UE maximum output power for Inter-band V2X | TS38.101-3 cl 6,2E.1.3 | Huawei | RAN5#93 (Nov-21) |  |  | 1 | 0% |  | 0% |  |  |  |  | 0%
246 |  | 38.521-3 Tx | 6.2E.2 | UE maximum output power reduction for V2X | New sub-clause header |  | RAN5#93 (Nov-21) |  |  | 0 | 0% |  | 0% |  |  |  |  | 0%
247 | Y | 38.521-3 Tx | 6.2E.2.1 | UE maximum output power reduction for Intra-band V2X | TS 38.101-3 cl 6.2E.2.1 | Huawei | RAN5#93 (Nov-21) |  |  | 1 | 0% |  | 0% |  |  |  |  | 0%
248 | Y | 38.521-3 Tx | 6.2E.2.2 | UE maximum output power reduction for Inter-band V2X | TS 38.101-3 cl 6,2E.2.2 | Huawei | RAN5#93 (Nov-21) |  |  | 1 | 0% |  | 0% |  |  |  |  | 0%
249 |  | 38.521-3 Tx | 6.2E.3 | UE additional maximum output power reduction for V2X | New sub-clause header |  | RAN5#93 (Nov-21) |  |  | 0 | 0% |  | 0% |  |  |  |  | 0%
250 | Y | 38.521-3 Tx | 6.2E.3.1 | UE additional maximum output power reduction for Intra-band V2X | TS 38.101-3 cl 6,2E.3.1 | Huawei | RAN5#93 (Nov-21) |  |  | 1 | 0% |  | 0% |  |  |  |  | 0%
251 | Y | 38.521-3 Tx | 6.2E.3.2 | UE additional maximum output power reduction for Inter-band V2X | TS 38.101-3 cl 6,2E.3.2 | Huawei | RAN5#93 (Nov-21) |  |  | 1 | 0% |  | 0% |  |  |  |  | 0%
252 |  | 38.521-3 Tx | 6.2E.4 | Configured transmitted power for V2X | New sub-clause header |  | RAN5#93 (Nov-21) |  |  | 0 | 0% |  | 0% |  |  |  |  | 0%
253 | Y | 38.521-3 Tx | 6.2E.4.1 | UE configured output power for Intra-band V2X | TS 38.101-3 cl 6,2E.4.1 | Huawei | RAN5#93 (Nov-21) |  |  | 1 | 0% |  | 0% |  |  |  |  | 0%
254 | Y | 38.521-3 Tx | 6.2E.4.2 | UE configured output power for Inter-band V2X | TS 38.101-3 cl 6,2E.4.2 | Huawei | RAN5#93 (Nov-21) |  |  | 1 | 0% |  | 0% |  |  |  |  | 0%
255 |  | 38.521-3 Tx | 6.4E.1 | Frequency error for V2X | New sub-clause header |  | RAN5#93 (Nov-21) |  |  | 0 | 0% |  | 0% |  |  |  |  | 0%
256 | Y | 38.521-3 Tx | 6.4E.1.1 | Frequency error for V2X for Intra-band V2X | TS 38.101-3 cl 6,4E.1 |  | RAN5#93 (Nov-21) |  |  | 1 | 0% |  | 0% |  |  |  |  | 0%
257 | Y | 38.521-3 Tx | 6.4E.1.2 | Frequency error for V2X for Inter-band V2X | TS 38.101-3 cl 6,4E.1 |  | RAN5#93 (Nov-21) |  |  | 1 | 0% |  | 0% |  |  |  |  | 0%
258 |  | 38.521-3 Tx | 6.4E.2 | Transmit modulation quality for V2X | New sub-clause header |  | RAN5#93 (Nov-21) |  |  | 0 | 0% |  | 0% |  |  |  |  | 0%
259 |  | 38.521-3 Tx | 6.4E.2.1 | Error Vector Magnitude for V2X | New sub-clause header |  | RAN5#93 (Nov-21) |  |  | 0 | 0% |  | 0% |  |  |  |  | 0%
260 | Y | 38.521-3 Tx | 6.4E.2.1.1 | Error Vector Magnitude for intra-band V2X | TS 38.101-3 cl 6,4E.2.1.1 |  | RAN5#93 (Nov-21) |  |  | 1 | 0% |  | 0% |  |  |  |  | 0%
261 | Y | 38.521-3 Tx | 6.4E.2.1.1 | Error Vector Magnitude for inter-band V2X | TS 38.101-3 cl 6,4E.2.2 |  | RAN5#93 (Nov-21) |  |  | 1 | 0% |  | 0% |  |  |  |  | 0%
262 |  | 38.521-3 Tx | 6.4E.2.2 | Carrier leakage for V2X | New sub-clause header |  | RAN5#93 (Nov-21) |  |  | 0 | 0% |  | 0% |  |  |  |  | 0%
263 | Y | 38.521-3 Tx | 6.4E.2.1.2 | Carrier leakage for intra-band V2X | TS 38.101-3 cl 6,4E.2.1.2 |  | RAN5#93 (Nov-21) |  |  | 1 | 0% |  | 0% |  |  |  |  | 0%
264 | Y | 38.521-3 Tx | 6.4E.2.1.2 | Carrier leakage for inter-band V2X | TS 38.101-3 cl 6,4E.2.2 |  | RAN5#93 (Nov-21) |  |  | 1 | 0% |  | 0% |  |  |  |  | 0%
265 |  | 38.521-3 Tx | 6.4E.2.3 | In-band emissions for V2X | New sub-clause header |  | RAN5#93 (Nov-21) |  |  | 0 | 0% |  | 0% |  |  |  |  | 0%
266 | Y | 38.521-3 Tx | 6.4E.2.1.3 | In-band emissions for intra-band V2X | TS 38.101-3 cl 6,4E.2.1.3 |  | RAN5#93 (Nov-21) |  |  | 1 | 0% |  | 0% |  |  |  |  | 0%
267 | Y | 38.521-3 Tx | 6.4E.2.1.3 | In-band emissions for inter-band V2X | TS 38.101-3 cl 6,4E.2.2 |  | RAN5#93 (Nov-21) |  |  | 1 | 0% |  | 0% |  |  |  |  | 0%
268 |  | 38.521-3 Tx | 6.5E.1 | Occupied bandwidth for V2X | New sub-clause header |  | RAN5#93 (Nov-21) |  |  | 0 | 0% |  | 0% |  |  |  |  | 0%
269 | Y | 38.521-3 Tx | 6.5E.1.1 | Occupied bandwidth for intra-band V2X | TS 38.101-3 cl 6,5E.1.1 |  | RAN5#93 (Nov-21) |  |  | 1 | 0% |  | 0% |  |  |  |  | 0%
270 | Y | 38.521-3 Tx | 6.5E.1.2 | Occupied bandwidth for inter-band V2X | TS 38.101-3 cl 6,5E.1.2 |  | RAN5#93 (Nov-21) |  |  | 1 | 0% |  | 0% |  |  |  |  | 0%
271 |  | 38.521-3 Tx | 6.5E.2 | Out of band emission for V2X | New sub-clause header |  | RAN5#93 (Nov-21) |  |  | 0 | 0% |  | 0% |  |  |  |  | 0%
272 |  | 38.521-3 Tx | 6.5E.2.1 | Spectrum emission mask for V2X | New sub-clause header |  | RAN5#93 (Nov-21) |  |  | 0 | 0% |  | 0% |  |  |  |  | 0%
273 | Y | 38.521-3 Tx | 6.5E.2.1.1 | Spectrum emission mask for intra-band V2X | TS 38.101-3 cl 6,5E.2.1 |  | RAN5#93 (Nov-21) |  |  | 1 | 0% |  | 0% |  |  |  |  | 0%
274 | Y | 38.521-3 Tx | 6.5E.2.1.2 | Spectrum emission mask for inter-band V2X | TS 38.101-3 cl 6,5E.2.2 |  | RAN5#93 (Nov-21) |  |  | 1 | 0% |  | 0% |  |  |  |  | 0%
275 |  | 38.521-3 Tx | 6.5E.2.2 | Additional Spectrum emission mask for V2X | New sub-clause header |  | RAN5#93 (Nov-21) |  |  | 0 | 0% |  | 0% |  |  |  |  | 0%
276 | Y | 38.521-3 Tx | 6.5E.2.2.1 | Additional Spectrum emission mask for intra-band V2X | TS 38.101-3 cl 6,5E.2.1 |  | RAN5#93 (Nov-21) |  |  | 1 | 0% |  | 0% |  |  |  |  | 0%
277 | Y | 38.521-3 Tx | 6.5E.2.2.2. | Additional Spectrum emission mask for inter-band V2X | TS 38.101-3 cl 6,5E.2.2 |  | RAN5#93 (Nov-21) |  |  | 1 | 0% |  | 0% |  |  |  |  | 0%
278 |  | 38.521-3 Tx | 6.5E.2.3.1 | Adjacent channel leakage ratio for V2X | New sub-clause header |  | RAN5#93 (Nov-21) |  |  | 0 | 0% |  | 0% |  |  |  |  | 0%
279 | Y | 38.521-3 Tx | 6.5E.2.3.1 | Adjacent channel leakage ratio for intra-band V2X | TS 38.101-3 cl 6,5E.2.1 |  | RAN5#93 (Nov-21) |  |  | 1 | 0% |  | 0% |  |  |  |  | 0%
280 | Y | 38.521-3 Tx | 6.5E.2.3.2 | Adjacent channel leakage ratio for inter-band V2X | TS 38.101-3 cl 6,5E.2.2 |  | RAN5#93 (Nov-21) |  |  | 1 | 0% |  | 0% |  |  |  |  | 0%
281 |  | 38.521-3 Tx | 6.5E.3 | Spurious emissions for V2X | New sub-clause header |  | RAN5#93 (Nov-21) |  |  | 0 | 0% |  | 0% |  |  |  |  | 0%
282 |  | 38.521-3 Tx | 6.5E.3.1 | General spurious emissions for V2X | New sub-clause header |  | RAN5#93 (Nov-21) |  |  | 0 | 0% |  | 0% |  |  |  |  | 0%
283 | Y | 38.521-3 Tx | 6.5E.3.1.1 | General spurious emissions for intra-band V2X | TS 38.101-3 cl 6,5E.3.1.1 |  | RAN5#93 (Nov-21) |  |  | 1 | 0% |  | 0% |  |  |  |  | 0%
284 | Y | 38.521-3 Tx | 6.5E.3.1.2 | General spurious emissions for inter-band V2X | TS 38.101-3 cl 6,5E.3.1.2 |  | RAN5#93 (Nov-21) |  |  | 1 | 0% |  | 0% |  |  |  |  | 0%
285 |  | 38.521-3 Tx | 6.5E.3.2 | Spurious emissions band UE co-existence for V2X | New sub-clause header |  | RAN5#93 (Nov-21) |  |  | 0 | 0% |  | 0% |  |  |  |  | 0%
286 | Y | 38.521-3 Tx | 6.5E.3.2.1 | Spurious emissions band UE co-existence for intra-band V2X | TS 38.101-3 cl 6,5E.3.2.1 |  | RAN5#93 (Nov-21) |  |  | 1 | 0% |  | 0% |  |  |  |  | 0%
287 | Y | 38.521-3 Tx | 6.5E.3.2.2 | Spurious emissions band UE co-existence for inter-band V2X | TS 38.101-3 cl 6,5E.3.2.2 |  | RAN5#93 (Nov-21) |  |  | 1 | 0% |  | 0% |  |  |  |  | 0%
288 |  | 38.521-3 Tx | 6.5E.4 | Transmit intermodulation for V2X | New sub-clause header |  | RAN5#93 (Nov-21) |  |  | 0 | 0% |  | 0% |  |  |  |  | 0%
289 | Y | 38.521-3 Tx | 6.5E.4.1 | Transmit intermodulation for intra-band V2X | TS 38.101-3 cl 6.5E.4.1 |  | RAN5#93 (Nov-21) |  |  | 1 | 0% |  | 0% |  |  |  |  | 0%
290 | Y | 38.521-3 Tx | 6.5E.4.2 | Transmit intermodulation for inter-band V2X | TS 38.101-3 cl 6.5E.4.2 |  | RAN5#93 (Nov-21) |  |  | 1 | 0% |  | 0% |  |  |  |  | 0%
TS 38.521-3: FR1 and FR2 Interworking operation with other radios RF test cases - Rx
|  | 38.521-3 Rx |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
291 |  | 38.521-3 Rx | 7.3E | Reference sensitivity for V2X operation in FR1 | New sub-clause header |  | RAN5#93 (Nov-21) |  |  | 0 | 0% |  | 0% |  |  |  |  | 0%
292 |  | 38.521-3 Rx | 7.3E.1 | General | TS 38.101-3 cl 7.3E.1 | Huawei | RAN5#93 (Nov-21) |  |  | 0.1 | 0% |  | 0% |  |  |  |  | 0%
293 |  | 38.521-3 Rx | 7.3E.2 | Reference sensitivity for V2X | New sub-clause header |  | RAN5#93 (Nov-21) |  |  | 0 | 0% |  | 0% |  |  |  |  | 0%
294 | Y | 38.521-3 Rx | 7.3E.2.1 | Reference sensitivity for intra-band contiguous V2X | TS 38.101-3 cl 7.3E.2.1 | Huawei | RAN5#93 (Nov-21) |  |  | 1 | 0% |  | 0% |  |  |  |  | 0%
295 | Y | 38.521-3 Rx | 7.3E.2.2 | Reference sensitivity for intra-band non-contiguous V2X | TS 38.101-3 cl 7.3E.2.2 | Huawei | RAN5#93 (Nov-21) |  |  | 1 | 0% |  | 0% |  |  |  |  | 0%
296 | Y | 38.521-3 Rx | 7.3E.2.3 | Reference sensitivity for Inter-band V2X con-current operation | TS 38.101-3 cl 7.3E.2.3 | Huawei | RAN5#93 (Nov-21) |  |  | 1 | 0% |  | 0% |  |  |  |  | 0%
297 |  | 38.521-3 Rx | 7.4E | Maximum input level for V2X operation in FR1 | New sub-clause header |  | RAN5#93 (Nov-21) |  |  | 0 | 0% |  | 0% |  |  |  |  | 0%
298 | Y | 38.521-3 Rx | 7.4E.1 | Maximum input level for intra-band V2X | TS 38.101-3 cl 7.4E | Huawei | RAN5#93 (Nov-21) |  |  | 1 | 0% |  | 0% |  |  |  |  | 0%
299 | Y | 38.521-3 Rx | 7.4E.2 | Maximum input level for inter-band V2X | TS 38.101-3 cl 7.4E | Huawei | RAN5#93 (Nov-21) |  |  | 1 | 0% |  | 0% |  |  |  |  | 0%
300 |  | 38.521-3 Rx | 7.5E | Adjacent channel selectivity for V2X operation in FR1 | New sub-clause header |  | RAN5#93 (Nov-21) |  |  | 0 | 0% |  | 0% |  |  |  |  | 0%
301 | Y | 38.521-3 Rx | 7.5E.1 | Adjacent channel selectivity for intra-band V2X | TS 38.101-3 cl 7.5E | Huawei | RAN5#93 (Nov-21) |  |  | 1 | 0% |  | 0% |  |  |  |  | 0%
302 | Y | 38.521-3 Rx | 7.5E.2 | Adjacent channel selectivity for inter-band V2X | TS 38.101-3 cl 7.5E | Huawei | RAN5#93 (Nov-21) |  |  | 1 | 0% |  | 0% |  |  |  |  | 0%
303 |  | 38.521-3 Rx | 7.6E | Blocking characteristics for V2X in FR1 | New sub-clause header |  | RAN5#93 (Nov-21) |  |  | 0 | 0% |  | 0% |  |  |  |  | 0%
304 |  | 38.521-3 Rx | 7.6E.1 | In-band blocking for V2X | New sub-clause header |  | RAN5#93 (Nov-21) |  |  | 0 | 0% |  | 0% |  |  |  |  | 0%
305 | Y | 38.521-3 Rx | 7.6E.1.1 | In-band blocking for intra-band V2X | TS 38.101-3 cl 7.6E |  | RAN5#93 (Nov-21) |  |  | 1 | 0% |  | 0% |  |  |  |  | 0%
306 | Y | 38.521-3 Rx | 7.6E.1.2 | In-band blocking for inter-band V2X | TS 38.101-3 cl 7.6E |  | RAN5#93 (Nov-21) |  |  | 1 | 0% |  | 0% |  |  |  |  | 0%
307 |  | 38.521-3 Rx | 7.6E.2 | Out-of-band blocking for V2X | New sub-clause header |  | RAN5#93 (Nov-21) |  |  | 0 | 0% |  | 0% |  |  |  |  | 0%
308 | Y | 38.521-3 Rx | 7.6E.2.1 | Out-of-band blocking for intra-band V2X | TS 38.101-3 cl 7.6E |  | RAN5#93 (Nov-21) |  |  | 1 | 0% |  | 0% |  |  |  |  | 0%
309 | Y | 38.521-3 Rx | 7.6E.2.2 | Out-of-band blocking for inter-band V2X | TS 38.101-3 cl 7.6E |  | RAN5#93 (Nov-21) |  |  | 1 | 0% |  | 0% |  |  |  |  | 0%
310 |  | 38.521-3 Rx | 7.7E | Spurious response for V2X in FR1 | New sub-clause header |  | RAN5#93 (Nov-21) |  |  | 0 | 0% |  | 0% |  |  |  |  | 0%
311 | Y | 38.521-3 Rx | 7.7E.1 | Spurious response for intra-band V2X | TS 38.101-3 cl 7.7E |  | RAN5#93 (Nov-21) |  |  | 1 | 0% |  | 0% |  |  |  |  | 0%
312 | Y | 38.521-3 Rx | 7.7E.2 | Spurious response for inter-band V2X | TS 38.101-3 cl 7.7E |  | RAN5#93 (Nov-21) |  |  | 1 | 0% |  | 0% |  |  |  |  | 0%
313 |  | 38.521-3 Rx | 7.8E | Intermodulation characteristics for V2X operation in FR1 | New sub-clause header |  | RAN5#93 (Nov-21) |  |  | 0 | 0% |  | 0% |  |  |  |  | 0%
314 |  | 38.521-3 Rx | 7.8E.1 | Wide band Intermodulation for V2X | New sub-clause header |  | RAN5#93 (Nov-21) |  |  | 0 | 0% |  | 0% |  |  |  |  | 0%
315 | Y | 38.521-3 Rx | 7.8E.1.1 | Wide band Intermodulation for intra-band V2X | TS 38.101-3 cl 7.8E |  | RAN5#93 (Nov-21) |  |  | 1 | 0% |  | 0% |  |  |  |  | 0%
316 | Y | 38.521-3 Rx | 7.8E.1.2 | Wide band Intermodulation for inter-band V2X | TS 38.101-3 cl 7.8E |  | RAN5#93 (Nov-21) |  |  | 1 | 0% |  | 0% |  |  |  |  | 0%
TS 38.521-4: Demod/QSI reporting test cases
|  | 38.521-4 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
TBD |  | 38.521-4 | <Clause> | <Title of new sub-clause header> | New sub-clause header |  | TBD |  |  | 0
TBD |  | 38.521-4 | <Clause> | <Title of modified existing test case> | <Describe required change of the existing test case> |  | TBD |  |  | TBD
TBD | Y | 38.521-4 | <Clause> | <Title of new test case> | Test Purpose(s): <Describe test purpose(s)> |  | TBD |  |  | 1
TS 38.522: Applicability for RF, Demod/QSI reporting and RRM test cases
152 |  | 38.522 | 4.1.1 | FR1 standalone conformance test cases | Add test case applicability statements for the new test cases introduced for 38.101-1 |  | TBD | R5-211610 |  | 1 | 5% (+5%) | 5% (+5%) |  |  | 5%
153 |  | 38.522 | 4.1.3 | NR interworking between NR FR1 and NR FR2 and between NR and LTE conformance test cases | Add test case applicability statements for the new test cases introduced for 38.101-3. |  | TBD |  |  | 1 | 0% | 0% |  |  | 0%
317 |  | 38.522 | 4.1.4 | Performance conformance test cases | Add test case applicability statements for the new test cases introduced for 38.101-4. |  | TBD |  |  | 1 | 0% | 0% |  |  | 0%
318 |  | 38.522 | 4.2 | RRM conformance test cases | Add test case applicability statements for the new test cases introduced for 38.533. |  | TBD |  |  | 1 | 0% | 0% |  |  | 0%
TS 38.533: RRM test cases
|  | 38.533 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
TBD |  | 38.533 | <Clause> | <Title of new sub-clause header> | New sub-clause header |  | TBD |  |  | 0
TBD |  | 38.533 | <Clause> | <Title of modified existing test case> | <Describe required change of the existing test case> |  | TBD |  |  | TBD
TBD | Y | 38.533 | <Clause> | <Title of new test case> | Test Purpose(s): <Describe test purpose(s)> |  | TBD |  |  | 1
TR 38.903: Test Tolerances analysis RRM and RF Rx test cases
|  | 38.903 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
TBD |  | 38.903 | <Clause> | <Title of new sub-clause header> | New sub-clause header |  | TBD |  |  | 0
TBD |  | 38.903 | <Clause> | <Title of task> | <Describe task> |  | TBD |  |  | TBD
TR 38.905: Test Point analysis receiver and transmitter test cases
|  | 38.905 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
TBD |  | 38.905 | <Clause> | <Title of new sub-clause header> | New sub-clause header |  | TBD |  |  | 0
TBD |  | 38.905 | <Clause> | <Title of task> | <Describe task> |  | TBD |  |  | TBD
RAN and CN protocol
TS 38.523-1: Protocol test cases
|  | 38.523-1 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
AS
154 |  | 38.523-1 | 12 | NR sidelink | Sub-clause heading |  | RAN5#91-e (May-21) | R5-206411 |  | 0 | 100% |  | 100% |  |  |  |  | 100%
155 |  | 38.523-1 | 12.1 | PC5-only operation | Sub-clause heading |  | RAN5#91-e (May-21) | R5-206411 |  | 0 | 100% |  | 100% |  |  |  |  | 100%
156 |  | 38.523-1 | 12.1.1 | PC5-only operation / Sidelink communication | Sub-clause heading |  | RAN5#91-e (May-21) |  |  | 0 | 0% |  | 0% |  |  |  |  | 0%
157 | Y | 38.523-1 | 12.1.1.1 | PC5-only operation / Sidelink communication / Transmission | TP1:[TS 38.304: 8.2, TS 38.331: 5.8.8] WITH: UE being authorized for performing NR sidelink Communication. WHEN: UE is configured by upper layer to perform NR sidelink transmission. THEN: UE performs NR sidelink transmission using sl-TxPoolSelectedNormal included in pre-configuration. | Huawei, Hisilicon | RAN5#91-e (May-21) |  |  | 1 | 0% |  | 0% |  |  |  |  | 0%
158 | Y | 38.523-1 | 12.1.1.2 | PC5-only operation / Sidelink communication / Reception | TP1:[TS 38.304: 8.2, TS 38.331: 5.8.7] WITH: UE being authorized for performing NR sidelink Communication. WHEN: UE is configured by upper layer to perform NR sidelink reception. THEN: UE is able to monitor NR sidelink transmission using sl-RxPool included in pre-configuration. |  | RAN5#91-e (May-21) |  |  | 1 | 0% |  | 0% |  |  |  |  | 0%
159 |  | 38.523-1 | 12.1.2 | PC5-only operation / Sidelink synchronization related procedure | Sub-clause heading |  | RAN5#91-e (May-21) |  |  | 0 | 0% |  | 0% |  |  |  |  | 0%
160 | Y | 38.523-1 | 12.1.2.1 | PC5-only operation / Sidelink synchronization related procedure / SyncRef (Re)selection | TP1: [38.331: 5.8.6] WITH: UE is authorized to perform NR sidelink communication; WHEN: sl-SyncPriority is set as gnss in pre-configuration; THEN: UE selects GNSS as SyncRef and starts to send SL SSB with SLSSID 0; TP2: [38.331: 5.8.6] WITH: UE is authorized to perform NR sidelink communication; WHEN: GNSS is no longer reliable and UE detects a SyncRef UE whose PSBCH-RSRP exceeds the minimum requirementby sl-SyncRefMinHyst; THEN: UE reselects the SyncRef UE as SyncRef and starts to send SL SSB with SLSSID set according to the SLSSID included in the SL MIB of SyncRef UE. | Huawei, Hisilicon | RAN5#91-e (May-21) |  |  | 1 | 0% |  | 0% |  |  |  |  | 0%
161 | Y | 38.523-1 | 12.1.2.2 | PC5-only operation / Sidelink synchronization related procedure / SL-SSB transmission Initiation and Cease | TP1: [38.331: 5.8.5.2] WITH: UE is configured with syncTxThreshOoC, and UE uses SyncRef UE as SyncRef. WHEN: PSBCH-RSRP measurement value of SyncRef UE is above syncTxThreshOoC. THEN: UE doesn't transmit SL SSB. TP2: [38.331: 5.8.5.2] WITH: UE is configured with syncTxThreshOoC, and UE uses SyncRef UE as SyncRef. WHEN: PSBCH-RSRP measurement value of SyncRef UE is below syncTxThreshOoC. THEN: UE starts transmitting SL SSB. TP3: [38.331: 5.8.5.2] WITH: UE is authorized to perform sidelink communication. WHEN: UE uses GNSS as SyncRef. THEN: UE starts transmitting SL SSB. | Huawei, Hisilicon | RAN5#91-e (May-21) |  |  | 1 | 0% |  | 0% |  |  |  |  | 0%
162 |  | 38.523-1 | 12.1.3 | PC5-only operation / Measurement configuration and reporting via PC5 RRC | Sub-clause heading |  | RAN5#91-e (May-21) |  |  | 0 | 0% |  | 0% |  |  |  |  | 0%
163 | Y | 38.523-1 | 12.1.3.1 | PC5-only operation / Measurement configuration and reporting via PC5 RRC / PSBCH-RSRP measurement configuration | TP1: [38.331 cl.5.8.10.2] WITH: UE has established PC5 RRC connection with peer UE on unicast sidelink. WHEN: UE is configured by upper layer to configure periodical PSBCH-RSRP measurement. THEN: UE sends a RRCReconfigurationSidelink message to peer UE. |  | RAN5#91-e (May-21) |  |  | 1 | 0% |  | 0% |  |  |  |  | 0%
164 | Y | 38.523-1 | 12.1.3.2 | PC5-only operation / Measurement configuration and reporting via PC5 RRC / PSBCH-RSRP measurement reporting / Event S1 and S2 | TP1: [38.331: 5.8.10.2, 5.8.10.3, 5.8.10.4, 5.8.10.5] WITH: UE is configured to perform event S1 PSBCH-RSRP measurement on SL-SSB via PC5 RRC. WHEN: PSBCH-RSRP measurement results of SL SSB is below threshold. THEN: UE doesn't trigger PSBCH-RSRP measurement reporting. TP2: [38.331: 5.8.10.2, 5.8.10.3, 5.8.10.4, 5.8.10.5] WITH: UE is configured to perform event S1 PSBCH-RSRP measurement on SL-SSB via PC5 RRC. WHEN: PSBCH-RSRP measurement results of SL SSB is above threshold. THEN: UE triggers PSBCH-RSRP measurement reporting. TP3: [38.331: 5.8.10.2, 5.8.10.3, 5.8.10.4, 5.8.10.5] WITH: UE is configured to perform event S2 PSBCH-RSRP measurement on SL-SSB via PC5 RRC. WHEN: PSBCH-RSRP measurement results of SL SSB is above threshold. THEN: UE doesn't trigger PSBCH-RSRP measurement reporting. TP4: [38.331: 5.8.10.2, 5.8.10.3, 5.8.10.4, 5.8.10.5] WITH: UE is configured to perform event S2 PSBCH-RSRP measurement on SL-SSB via PC5 RRC. WHEN: PSBCH-RSRP measurement results of SL SSB is below threshold. THEN: UE triggers PSBCH-RSRP measurement reporting. |  | RAN5#91-e (May-21) |  |  | 1 | 0% |  | 0% |  |  |  |  | 0%
165 | Y | 38.523-1 | 12.1.3.3 | PC5-only operation / Measurement configuration and reporting via PC5 RRC / PSBCH-RSRP measurement reporting / Periodical reporting | TP1: [38.331: 5.8.10.2, 5.8.10.3, 5.8.10.4, 5.8.10.5] WITH: UE is configured to perform periodical PSBCH-RSRP measurement reporting on SL SSB via PC5 RRC. WHEN: The first measurement result is avaible and afterforth every time periodical timer expires. THEN: UE trigger PSBCH-RSRP measurement reporting. |  | RAN5#91-e (May-21) |  |  | 1 | 0% |  | 0% |  |  |  |  | 0%
166 |  | 38.523-1 | 12.1.4 | PC5-only operation / Sidelink Reconfiguration via PC5 RRC | Sub-clause heading |  | RAN5#91-e (May-21) |  |  | 0 | 0% |  | 0% |  |  |  |  | 0%
167 | Y | 38.523-1 | 12.1.4.1 | PC5-only operation / Sidelink Reconfiguration via PC5 RRC / SL DRB management / initiating UE side | TP1: [38.331: 5.8.9.1a.2] WITH: UE has established PC5 RRC connection with peer UE. WHEN: UE is configured by high layer to transmit a PC5 RRCReconfiguration message to establish a unicast SL DRB. THEN: UE sends a RRCReconfigurationSidelink message to peer UE. TP2: [38.331: 5.8.9.1a.2] WITH: UE has established PC5 RRC connection with peer UE. WHEN: UE is configured by high layer to transmit a PC5 RRCReconfiguration message to modify a unicast SL DRB. THEN: UE sends a RRCReconfigurationSidelink message to peer UE. TP3: [38.331: 5.8.9.1a.2] WITH: UE has established PC5 RRC connection with peer UE. WHEN: UE is configured by high layer to transmit a PC5 RRCReconfiguration message to release a unicast SL DRB. THEN: UE sends a RRCReconfigurationSidelink message to peer UE. TP4: [38.331: 5.8.9.1a.2] WITH: UE has established PC5 RRC connection with peer UE. WHEN: UE receive an RRCReconfigurationCompleteSidelink from peer UE. THEN: UE apply the parameters in RRCReconfigurationSidelink. | Lenovo, Motorola Mobility | RAN5#91-e (May-21) |  |  | 1 | 0% |  | 0% |  |  |  |  | 0%
168 | Y | 38.523-1 | 12.1.4.2 | PC5-only operation / Sidelink Reconfiguration via PC5 RRC / SL DRB management / Peer UE side | TP1: [38.331: 5.8.9.1a.2] WITH: UE has established PC5 RRC connection with peer UE. WHEN: UE receives an RRCReconfigurationSidelink that can comply to add an unicast SL DRB. THEN: UE applies the parameters in RRCReconfigurationSidelinksends and sends a RRCReconfigurationCompleteSidelink message to peer UE. TP2: [38.331: 5.8.9.1a.2] WITH: UE has established PC5 RRC connection with peer UE. WHEN: UE receives an RRCReconfigurationSidelink that can comply to modify an unicast SL DRB. THEN: UE applies the parameters in RRCReconfigurationSidelinksends and sends a RRCReconfigurationCompleteSidelink message to peer UE. TP3: [38.331: 5.8.9.1a.2] WITH: UE has established PC5 RRC connection with peer UE. WHEN: UE receives an RRCReconfigurationSidelink that can comply to release an unicast SL DRB. THEN: UE applies the parameters in RRCReconfigurationSidelinksends and sends a RRCReconfigurationCompleteSidelink message to peer UE. | Lenovo, Motorola Mobility | RAN5#91-e (May-21) |  |  | 1 | 0% |  | 0% |  |  |  |  | 0%
169 |  | 38.523-1 | 12.1.5 | PC5-only operation / Sidelink CSI reporting | Sub-clause heading |  | RAN5#91-e (May-21) |  |  | 0 | 0% |  | 0% |  |  |  |  | 0%
170 | Y | 38.523-1 | 12.1.5.1 | PC5-only operation / Sidelink CSI reporting / Configuration | TP1: [38.331 5.8.9.1.1] WITH: UE has established PC5 RRC connection with peer UE. WHEN: UE is configured by upper layer to configure SL CSI-RS resource to peer UE. THEN: UE sends an RRCReconfigurationSidelink message including sl-CSI-RS-Config to peer UE and starts to transmit SL CSI-RS. TP2: [38.331 5.8.9.1.1] WITH: UE has established PC5 RRC connection with peer UE. WHEN: UE is configured by upper layer to trigger SL CSI report. THEN: UE sends an SCI format 1-A to trigger SL CSI report. |  | RAN5#91-e (May-21) |  |  | 1 | 0% |  | 0% |  |  |  |  | 0%
171 | Y | 38.523-1 | 12.1.5.2 | PC5-only operation / Sidelink CSI reporting / Reporting | TP1: [38.331 5.8.9.1.1] WITH: UE has established PC5 RRC connection with peer UE and is configuredby peer UE to perform CSI measurement. WHEN: UE receives a SCI format 1-A to trigger SL CSI report. THEN: UE sends an CSI reporting MAC-CE to peer UE. |  | RAN5#91-e (May-21) |  |  | 1 | 0% |  | 0% |  |  |  |  | 0%
172 |  | 38.523-1 | 12.1.6 | PC5-only operation / Sidelink failure | Sub-clause heading |  | RAN5#91-e (May-21) |  |  | 0 | 0% |  | 0% |  |  |  |  | 0%
173 | Y | 38.523-1 | 12.1.6.1 | PC5-only operation / Sidelink failure / PC5 RRC reconfiguration failure / Initiating UE side | TP1: [38.331: 5.8.9.1.8] WITH: UE has established PC5 RRC connection with peer UE on unicast sidelink. WHEN: UE receives an RRCReconfigurationFailureSidelink from peer UE. THEN: UE continue using the configuration used prior to corresponding RRCReconfigurationSidelink message. | Lenovo, Motorola Mobility | RAN5#91-e (May-21) |  |  | 1 | 0% |  | 0% |  |  |  |  | 0%
174 | Y | 38.523-1 | 12.1.6.2 | PC5-only operation / Sidelink failure / PC5 RRC reconfiguration failure / Peer UE side | TP1: [38.331: 5.8.9.1.8] WITH: UE has established PC5 RRC connection with peer UE on unicast sidelink. WHEN: UE receives an RRCReconfigurationSidelink that UE can't comply from peer UE. THEN: UE continue using the configuration used prior to corresponding RRCReconfigurationSidelink message and sends a RRCReconfigurationFailureSidelink message. | Lenovo, Motorola Mobility | RAN5#91-e (May-21) |  |  | 1 | 0% |  | 0% |  |  |  |  | 0%
175 | Y | 38.523-1 | 12.1.6.3 | PC5-only operation / Sidelink failure / Sidelink radio link failure / Transmission side | TP1: [38.331: 5.8.9.3] WITH: UE has established PC5 RRC connection with peer UE on unicast sidelink. WHEN: UE sends a RRCReConfigurationSidelink message to peer UE and doesn't receive response before T400 expires THEN: UE indicates SL RLF to upper layers. TP2: [38.331: 5.8.9.3] WITH: UE has established PC5 RRC connection with peer UE on unicast sidelink. WHEN: UE fails the intergrity check of SL SRB 2. THEN: UE indicates SL RLF to upper layers. TP3: [38.331: 5.8.9.3] WITH: UE has established PC5 RRC connection with peer UE on unicast sidelink. WHEN: UE fails the intergrity check of SL SRB 3. THEN: UE indicates SL RLF to upper layers. TP4: [38.331: 5.8.9.3] WITH: UE has established PC5 RRC connection with peer UE on unicast sidelink. WHEN: Retransmission times of an AM SL DRB exceeds the maximum number. THEN: UE indicates SL RLF to upper layers. TP5: [38.331: 5.8.9.3] WITH: UE has established PC5 RRC connection with peer UE on unicast sidelink. WHEN: MAC detects number of continuous HARQ ACK/NACK DTX exceeds sl-MaxNumConsecutiveDT12. THEN: UE indicates SL RLF to upper layers. | Lenovo, Motorola Mobility | RAN5#91-e (May-21) |  |  | 1 | 0% |  | 0% |  |  |  |  | 0%
176 |  | 38.523-1 | 12.1.7 | PC5-only operation / Sidelink UE capability transfer via PC5 RRC | Sub-clause heading |  | RAN5#91-e (May-21) |  |  | 0 | 0% |  | 0% |  |  |  |  | 0%
177 | Y | 38.523-1 | 12.1.7.1 | PC5-only operation / Sidelink UE capability transfer via PC5 RRC / Initiating UE side | TP1: [38.331: 5.8.9.1.8] WITH: UE has established PC5 RRC connection with peer UE on unicast sidelink. WHEN: UE is configured by upper layer to initiate capability transfer procedure. THEN: UE sends a UECapabilityEnquirySidelink message to peer UE. TP2: [38.331: 5.8.9.1.8] WITH: UE has established PC5 RRC connection with peer UE on unicast sidelink. WHEN: UE is configured by upper layer to initiate capability transfer procedure and to provide UE radio access capabilities. THEN: UE sends a UECapabilityEnquirySidelink message with ue-CapabilityInformationSidelink to peer UE. | R&S | RAN5#91-e (May-21) |  |  | 1 | 0% |  | 0% |  |  |  |  | 0%
178 | Y | 38.523-1 | 12.1.7.2 | PC5-only operation / Sidelink UE capability transfer via PC5 RRC / Peer UE side | TP1: [38.331: 5.8.9.1.8] WITH: UE has established PC5 RRC connection with peer UE on unicast sidelink. WHEN: UE receives a UECapabilityEnquirySidelink message from peer UE. THEN: UE sends a SidelinkUEInformationNR message to peer UE. | R&S | RAN5#91-e (May-21) |  |  | 1 | 0% |  | 0% |  |  |  |  | 0%
179 |  | 38.523-1 | 12.2 | Inter-carrier concurrent operation | Sub-clause heading |  | RAN5#91-e (May-21) | R5-206411 |  | 0 | 100% | 100% | 100% |  | 100% |  |  | 100%
180 |  | 38.523-1 | 12.2.1 | Inter-carrier concurrent operation / Sidelink communication | Sub-clause heading |  | RAN5#91-e (May-21) | R5-206411 |  | 0 | 100% | 100% | 100% |  | 100% |  |  | 100%
181 | Y | 38.523-1 | 12.2.1.1 | Inter-carrier concurrent operation / Sidelink communication / RRC_IDLE and RRC_INACTIVE / Transmission | TP1:[TS 38.331:5.3.3.1a, 5.3.3.2, 5.3.3.3, 5.3.3.4] WITH: UE is in RRC_IDLE state and its serving cell broadcasts SIB12 which includes sl-FreqInfoList but no sl-TxPoolSelectedNormal. WHEN: UE is configured by upper layer to perform NR sidelink transmission on the frequency included in sl-FreqInfoList. THEN: UE sends an RRCSetup message. TP2:[TS 38.331:5.3.13.1a, 5.3.13.2, 5.3.13.3, 5.3.13.4] WITH: UE is in RRC_INACTIVE state and its serving cell broadcasts SIB12 which includes sl-FreqInfoList but no sl-TxPoolSelectedNormal. WHEN: UE is configured by upper layer to perform NR sidelink transmission on the frequency included in sl-FreqInfoList. THEN: UE sends an RRCResume message. TP3:[TS 38.304: 5.2.3.2, 5.2.4.1, 5.2.4.5, 8.2] WITH: UE is in RRC_IDLE state and the cell on which UE camps doesn't broadcast SIB12. WHEN: An neighbour cell starts broadcasting SIB12 which includes sl-TxPoolSelectedNormal and UE is configured by upper layer to perform NR sidelink transmission. THEN: UE reselects to neighbour cell and performs NR sidelink transmission using sl-TxPoolSelectedNormal included in SIB12. TP4:[TS 38.304: 8.2, TS 38.331: 5.8.8] WITH: UE is in RRC_IDLE state and the cell on which UE camps doesn't broadcast SIB12. WHEN: UE is configured by upper layer to perform NR sidelink transmission. THEN: UE performs NR sidelink transmission using sl-TxPoolSelectedNormal included in pre-configuration. TP5:[TS 38.331: 5.8.2, 5.3.3.2, 5.3.3.3, 5.3.3.4] WITH: UE is in RRC_IDLE state and is configured by upper layer to continuesly perform NR sidelink transmission, The cell on which UE camps broadcasts SIB12 which includes sl-TxPoolExceptional. WHEN: UE receives a Paging message including a matched identity ng-5G-S-TMSI. THEN: UE perform NR sidelink transmission using sl-TxPoolExceptional from the moment the UE initiates RRC connection establishment until receiving an RRCReconfiguration including sl-ConfigDedicatedNR. TP6:[TS 38.331: 5.8.2, 5.3.13.2, 5.3.13.3, 5.3.13.4] WITH: UE is in RRC_INACTIVE state and is configured by upper layer to continuesly perform NR sidelink transmission, The cell on which UE camps broadcasts SIB12 which includes sl-TxPoolExceptional. WHEN: UE receives a Paging message including a matched identity fullI-RNTI. THEN: UE perform NR sidelink transmission using sl-TxPoolExceptional from the moment the UE initiates RRC connection resumption until receiving an RRCReconfiguration including sl-ConfigDedicatedNR. | Huawei, Hisilicon | RAN5#91-e (May-21) |  |  | 1 | 0% | 0% | 0% |  | 0% |  |  | 0%
182 | Y | 38.523-1 | 12.2.1.2 | Inter-carrier concurrent operation / Sidelink communication / RRC_IDLE and RRC_INACTIVE / Reception | TP1:[TS 38.304: 5.2.3.2, 5.2.4.1, 5.2.4.5, 8.2, TS 38.331: 5.8.7] WITH: UE is in RRC_IDLE state and the cell on which UE camps doesn't broadcast SIB12. WHEN: An neighbour cell starts broadcasting SIB12 which includes sl-RxPool and UE is configured by upper layer to perform NR sidelink reception. THEN: UE reselects to neighbour cell and is able to monitor NR sidelink transmission using sl-RxPool included in SIB12. TP2:[TS 38.304: 8.2, TS 38.331: 5.8.7] WITH: UE is in RRC_IDLE state and the cell on which UE camps doesn't broadcast SIB12. WHEN: UE is configured by upper layer to perform NR sidelink reception. THEN: UE is able to monitor NR sidelink transmission using sl-RxPool included in pre-configuration. |  | RAN5#91-e (May-21) |  |  | 1 | 0% | 0% | 0% |  | 0% |  |  | 0%
183 | Y | 38.523-1 | 12.2.1.3 | Inter-carrier concurrent operation/Sidelink communication / RRC_CONNECTED / Transmission / Network scheduling | TP1:[TS 38.331: 5.8.3.2, 5.8.3.3] WITH: UE is in RRC_CONNECTED state and its serving cell broadcasts SIB12 including sl-ConfigCommonNR. WHEN: UE is configured by upper layer to perform NR sidelink transmission on the frequency included in sl-FreqInfoList. THEN: UE sends a SidelinkUEInfomationNR message to indicate it requires sidelink transmission resources. TP2:[TS 38.331: 5.8.3.2, 5.8.3.3] WITH: UE is in RRC_CONNECTED state and is configured by upper layer to perform NR sidelink transmission. WHEN: UE receives an RRCReconfiguration message which includes sl-ScheduledConfig and no sl-ConfiguredGrantConfigList. THEN: UE performs NR sidelink tranmission based on dynamic scheduling. TP3:[TS 38.331: 5.7.4.2, 5.7.4.3] WITH: UE is in RRC_CONNECTED state. WHEN: UE is configured by upper layer to provide configured grant assistance information for NR NR sidelink communication. THEN: UE sends a UEAssistanceInformation message includes sl-UE-AssistanceInformationNR. TP4:[TS 38.331: 5.7.4.2, 5.7.4.3] WITH: UE is in RRC_CONNECTED state and is configured by upper layer to perform NR sidelink transmission. WHEN: UE receives an RRCReconfiguration message which includes sl-ConfiguredGrantConfigList. THEN: UE performs NR sidelink tranmission using the configued grant included in sl-ConfiguredGrantConfigList. TP5:[TS 38.331: 5.3.5.14, 5.8.3.2, 5.8.3.3] WITH: UE is in RRC_CONNECTED state and is configured by upper layer to perform NR sidelink transmission. WHEN: UE is no longer configured by upper layer to perform NR sidelink tranmission. THEN: UE sends a SidelinkUEInfomationNR message to indicate it no longer requires NR sidelink transmission resources. | Huawei, Hisilicon | RAN5#91-e (May-21) | R5-206411 |  | 1 | 0% | 0% | 0% |  | 0% |  |  | 0%
184 | Y | 38.523-1 | 12.2.1.4 | Inter-carrier concurrent operation/Sidelink communication / RRC_CONNECTED / Transmission / Resource sensing | TP1:[TS 38.331: 5.8.8] WITH: UE is in RRC_CONNECTED state and its serving cell doesn't broadcast SIB12. WHEN: UE is configured by upper layer to perform NR sidelink transmission. THEN: UE performs NR sidelink transmission using sl-TxPoolSelectedNormal included in pre-configuration. TP2:[TS 38.331: 5.8.8] WITH: UE is in RRC_CONNECTED state and its serving cell broadcasts SIB12. WHEN: UE is configured by upper layer to perform NR sidelink transmission. THEN: UE performs NR sidelink transmission using sl-TxPoolSelectedNormal included in SIB12. TP3:[TS 38.331: 5.8.8] WITH: UE is in RRC_CONNECTED state and its serving cell broadcasts SIB12. WHEN: UE receives an RRCReconfiguration message which includes sl-UE-SelectedConfig. THEN: UE performs NR sidelink tranmission based on sensing using sl-TxPoolSelectedNormal included in sl-ConfigDedicatedNR. | Huawei, Hisilicon | RAN5#91-e (May-21) |  |  | 1 | 0% | 0% | 0% |  | 0% |  |  | 0%
185 | Y | 38.523-1 | 12.2.1.5 | Inter-carrier concurrent operation / Sidelink communication / RRC_CONNECTED / Transmission / Exceptional pool | TP1: [38.331: cl 5.8.8] WITH: UE is in RRC_CONNECTED state and is performing NR sidelink tranmission based on network scheduling, and sl-TxPoolExceptional is included in sl-ConfigDedicatedNR. WHEN: UE receives an RRCReconfiguration message includes reconfigurationWithSync THEN: UE performs NR sidelink transmission using sl-TxPoolExceptional included in sl-ConfigDedicatedNR during handover procedure TP2: [38.331: cl 5.8.8] WITH: UE is in RRC_CONNECTED state and is performing NR sidelink tranmission based on network scheduling, and sl-TxPoolExceptional is included in sl-ConfigDedicatedNR. WHEN: UE detecting radio link failure on expiring of timer T310 THEN: UE performs NR sidelink transmission using sl-TxPoolExceptional included in sl-ConfigDedicatedNR during RRC connection re-establishment procedure |  | RAN5#91-e (May-21) |  |  | 1 | 0% | 0% | 0% |  | 0% |  |  | 0%
186 | Y | 38.523-1 | 12.2.1.6 | Inter-carrier concurrent operation / Sidelink communication / RRC_CONNECTED / Reception | TP1:[TS 38.331: 5.8.7] WITH: UE is in RRC_CONNECTED state and its serving cell doesn't broadcast SIB12. WHEN: UE is configured by upper layer to perform NR sidelink reception. THEN: UE is able to monitor NR sidelink transmission using sl-RxPool included in pre-configuration. TP2:[TS 38.331: 5.8.7] WITH: UE is in RRC_CONNECTED state and its serving cell broadcasts SIB12. WHEN: UE is configured by upper layer to perform NR sidelink reception. THEN: UE is able to monitor NR sidelink transmission using sl-RxPool included in SIB12. TP3:[TS 38.331: 5.8.7] WITH: UE is in RRC_CONNECTED state and has received a RRCReconfiguration includes sl-RxPool. WHEN: UE is configured by upper layer to perform NR sidelink reception. THEN: UE is able to monitor NR sidelink transmission using sl-RxPool ncluded in sl-ConfigDedicatedNR. TP4:[TS 38.331: 5.8.7] WITH: UE is in RRC_CONNECTED state and is configured by upper layer to perform NR sidelink reception. WHEN: UE receives a RRCReconfiguration includes reconfigurationWithSync and sl-RxPool. THEN: UE is able to monitor NR sidelink transmission using sl-RxPool included in the recieved RRCReconfiguration message during handover procedure. |  | RAN5#91-e (May-21) |  |  | 1 | 0% | 0% | 0% |  | 0% |  |  | 0%
187 |  | 38.523-1 | 12.2.2 | Inter-carrier concurrent operation / Sidelink synchronization related procedure | Sub-clause heading |  | RAN5#91-e (May-21) |  |  | 0 | 0% | 0% | 0% |  | 0% |  |  | 0%
188 | Y | 38.523-1 | 12.2.2.1 | Inter-carrier concurrent operation / Sidelink synchronization related procedure / SyncRef (Re)selection | TP1: [38.331: 5.8.6] WITH: UE is in RRC_CONNECTED state; WHEN: UE receives an RRCReconfiguration with sl-SyncPriority set to gnbEnb and networkControlledSyncTx is configured and set to on; THEN: UE selects its serving cell as SyncRef and starts to send SL SSB with SLSSID set to the configured value; TP2: [38.331: 5.8.6] WITH: UE is in RRC_CONNECTED state; WHEN: UE receives an RRCReconfiguration to reconfigure sl-SyncPriority as gnss; THEN: UE selects GNSS as SyncRef and starts to send SL SSB with SLSSID 0; TP3: [38.331: 5.8.6] WITH: UE is in RRC_CONNECTED state; WHEN: GNSS is no longer reliable and UE detects a SyncRef UE whose PSBCH-RSRP exceeds the minimum requirementby sl-SyncRefMinHyst; THEN: UE reselects the SyncRef UE as SyncRef and starts to send SL SSB with SLSSID set according to the SLSSID included in the SL MIB of SyncRef UE. | Huawei, Hisilicon | RAN5#91-e (May-21) |  |  | 1 | 0% | 0% | 0% |  | 0% |  |  | 0%
189 | Y | 38.523-1 | 12.2.2.2 | Inter-carrier concurrent operation / Sidelink synchronization related procedure / SL-SSB transmission Initiation and Cease | TP1: [38.331: 5.8.5.2] WITH: UE is configured with syncTxThreshIC and no networkControlledSyncTx, and UE uses serving cell as SyncRef. WHEN: RSRP measurement value of serving cell is above syncTxThreshIC. THEN: UE doesn't transmit SL SSB. TP2: [38.331: 5.8.5.2] WITH: UE is configured with syncTxThreshIC and no networkControlledSyncTx, and UE uses serving cell as SyncRef. WHEN: RSRP measurement value of serving cell is below syncTxThreshIC. THEN: UE starts transmitting SL SSB. TP3: [38.331: 5.8.5.2] WITH: UE is configured with syncTxThreshOoC and no networkControlledSyncTx, and UE uses SyncRef UE as SyncRef. WHEN: PSBCH-RSRP measurement value of SyncRef UE is above syncTxThreshOoC. THEN: UE doesn't transmit SL SSB. TP4: [38.331: 5.8.5.2] WITH: UE is configured with syncTxThreshOoC and no networkControlledSyncTx, and UE uses SyncRef UE as SyncRef. WHEN: PSBCH-RSRP measurement value of SyncRef UE is below syncTxThreshOoC. THEN: UE starts transmitting SL SSB. |  | RAN5#91-e (May-21) |  |  | 1 | 0% | 0% | 0% |  | 0% |  |  | 0%
190 |  | 38.523-1 | 12.2.3 | Inter-carrier concurrent operation / Measurement configuration and reporting via Uu RRC | Sub-clause heading |  | RAN5#91-e (May-21) | R5-206412 |  | 0 | 100% | 100% | 100% |  | 100% |  |  | 100%
191 | Y | 38.523-1 | 12.2.3.1 | Inter-carrier concurrent operation / Measurement configuration and reporting via Uu RRC / CBR measurement reporting / Event C1 and C2 | TP1: [38.331: 5.5.2, 5.5.3, 5.5.4.11, 5.5.4.12, 5.5.5] WITH: UE is in NR RRC_CONNECTED state and is configured to perform event C1 triggered CBR measurement reporting on resource pool WHEN: CBR measurement result of indicated resource pool satisfies entering condition for event C1 THEN: UE sends MeasurementReport message to report CBR measurement results of indicated resource pool TP2: [38.331: 5.5.2, 5.5.3, 5.5.4.11, 5.5.4.12, 5.5.5] WITH: UE is in NR RRC_CONNECTED state and the periodical measurement reporting triggered by event C1 is ongoing WHEN: CBR measurement result of indicated resource pool satisfies leaving condition for event C1 THEN: UE stops sending MeasurementReport message TP3: [38.331: 5.5.2, 5.5.3, 5.5.4.11, 5.5.4.12, 5.5.5] WITH: UE is in NR RRC_CONNECTED state and is configured to perform event C2 triggered CBR measurement reporting on resource pool WHEN: CBR measurement result of indicated resource pool satisfies entering condition for event C1 THEN: UE sends MeasurementReport message to report CBR measurement results of indicated resource pool. TP4: [38.331: 5.5.2, 5.5.3, 5.5.4.11, 5.5.4.12, 5.5.5] WITH: UE is in NR RRC_CONNECTED state and the periodical measurement reporting triggered by event C2 is ongoing WHEN: CBR measurement result of indicated resource pool satisfies leaving condition for event C2 THEN: UE stops sending MeasurementReport message | Huawei, Hisilicon | RAN5#91-e (May-21) | R5-206412 |  | 1 | 30% | 30% | 30% |  | 30% |  |  | 30%
192 | Y | 38.523-1 | 12.2.3.2 | Inter-carrier concurrent operation / Measurement configuration and reporting via Uu RRC / CBR measurement reporting / Periodical reporting | TP1: [38.331: 5.5.2, 5.5.3, 5.5.4.11, 5.5.4.12, 5.5.5] WITH: UE is configured to perform periodical CBR measurement reporting on resource pools. WHEN: The first measurement result is avaible and afterforth every time periodical timer expires. THEN: UE trigger CBR measurement reporting. |  | RAN5#91-e (May-21) |  |  | 1 | 0% | 0% | 0% |  | 0% |  |  | 0%
193 |  | 38.523-1 | 12.2.4 | Inter-carrier concurrent operation / Sidelink Reconfiguration via Uu RRC | Sub-clause heading |  | RAN5#91-e (May-21) |  |  | 0 | 0% | 0% | 0% |  | 0% |  |  | 0%
194 | Y | 38.523-1 | 12.2.4.1 | Inter-carrier concurrent operation / Sidelink Reconfiguration via Uu RRC / SL DRB management | TP1: [38.331: 5.8.9.1a.2] WITH: UE has established PC5 RRC connection with peer UE. WHEN: UE receives an RRCReconfiguration message to establish a unicast SL DRB. THEN: UE establish a SL DRB and sends a RRCReconfigurationComplete message. TP2: [38.331: 5.8.9.1a.2] WITH: UE has established PC5 RRC connection with peer UE. WHEN: UE receives an RRCReconfiguration message to modify a unicast SL DRB. THEN: UE establish a SL DRB and sends a RRCReconfigurationComplete message. TP3: [38.331: 5.8.9.1a.2] WITH: UE has established PC5 RRC connection with peer UE. WHEN: UE receives an RRCReconfiguration message to release a unicast SL DRB. THEN: UE establish a SL DRB and sends a RRCReconfigurationComplete message. |  | RAN5#91-e (May-21) |  |  | 1 | 0% | 0% | 0% |  | 0% |  |  | 0%
195 |  | 38.523-1 | 12.2.5 | Inter-carrier concurrent operation / Measurement configuration and reporting via PC5 RRC | Sub-clause heading |  | RAN5#91-e (May-21) |  |  | 0 | 0% | 0% | 0% |  | 0% |  |  | 0%
196 | Y | 38.523-1 | 12.2.5.1 | Inter-carrier concurrent operation / Measurement configuration and reporting via PC5 RRC / PSBCH-RSRP measurement configuration | TP1: [38.331 cl.5.8.10.2] WITH: UE has established PC5 RRC connection with peer UE on unicast sidelink. WHEN: UE is configured by upper layer to configure periodical PSBCH-RSRP measurement. THEN: UE sends a RRCReconfigurationSidelink message to peer UE. | Huawei, Hisilicon | RAN5#91-e (May-21) |  |  | 1 | 0% | 0% | 0% |  | 0% |  |  | 0%
197 | Y | 38.523-1 | 12.2.5.2 | Inter-carrier concurrent operation / Measurement configuration and reporting via PC5 RRC / PSBCH-RSRP measurement reporting / Event S1 and S2 | TP1: [38.331: 5.8.10.2, 5.8.10.3, 5.8.10.4, 5.8.10.5] WITH: UE is configured to perform event S1 PSBCH-RSRP measurement on SL-SSB via PC5 RRC. WHEN: PSBCH-RSRP measurement results of SL SSB is below threshold. THEN: UE doesn't trigger PSBCH-RSRP measurement reporting. TP2: [38.331: 5.8.10.2, 5.8.10.3, 5.8.10.4, 5.8.10.5] WITH: UE is configured to perform event S1 PSBCH-RSRP measurement on SL-SSB via PC5 RRC. WHEN: PSBCH-RSRP measurement results of SL SSB is above threshold. THEN: UE triggers PSBCH-RSRP measurement reporting. TP3: [38.331: 5.8.10.2, 5.8.10.3, 5.8.10.4, 5.8.10.5] WITH: UE is configured to perform event S2 PSBCH-RSRP measurement on SL-SSB via PC5 RRC. WHEN: PSBCH-RSRP measurement results of SL SSB is above threshold. THEN: UE doesn't trigger PSBCH-RSRP measurement reporting. TP4: [38.331: 5.8.10.2, 5.8.10.3, 5.8.10.4, 5.8.10.5] WITH: UE is configured to perform event S2 PSBCH-RSRP measurement on SL-SSB via PC5 RRC. WHEN: PSBCH-RSRP measurement results of SL SSB is below threshold. THEN: UE triggers PSBCH-RSRP measurement reporting. | Huawei, Hisilicon | RAN5#91-e (May-21) |  |  | 1 | 0% | 0% | 0% |  | 0% |  |  | 0%
198 | Y | 38.523-1 | 12.2.5.3 | Inter-carrier concurrent operation / Measurement configuration and reporting via PC5 RRC / PSBCH-RSRP measurement reporting / Periodical reporting | TP1: [38.331: 5.8.10.2, 5.8.10.3, 5.8.10.4, 5.8.10.5] WITH: UE is configured to perform periodical PSBCH-RSRP measurement reporting on SL SSB via PC5 RRC. WHEN: The first measurement result is avaible and afterforth every time periodical timer expires. THEN: UE trigger PSBCH-RSRP measurement reporting. |  | RAN5#91-e (May-21) |  |  | 1 | 0% | 0% | 0% |  | 0% |  |  | 0%
199 |  | 38.523-1 | 12.2.6 | Inter-carrier concurrent operation / Sidelink Reconfiguration via PC5 RRC | Sub-clause heading |  | RAN5#91-e (May-21) |  |  | 0 | 0% | 0% | 0% |  | 0% |  |  | 0%
200 | Y | 38.523-1 | 12.2.6.1 | Inter-carrier concurrent operation / Sidelink Reconfiguration via PC5 RRC / SL DRB management / Initiating UE side | TP1: [38.331: 5.8.9.1a.2] WITH: UE has established PC5 RRC connection with peer UE. WHEN: UE is configured by high layer to transmit a PC5 RRCReconfiguration message to establish a unicast SL DRB. THEN: UE sends a RRCReconfigurationSidelink message to peer UE. TP2: [38.331: 5.8.9.1a.2] WITH: UE has established PC5 RRC connection with peer UE. WHEN: UE is configured by high layer to transmit a PC5 RRCReconfiguration message to modify a unicast SL DRB. THEN: UE sends a RRCReconfigurationSidelink message to peer UE. TP3: [38.331: 5.8.9.1a.2] WITH: UE has established PC5 RRC connection with peer UE. WHEN: UE is configured by high layer to transmit a PC5 RRCReconfiguration message to release a unicast SL DRB. THEN: UE sends a RRCReconfigurationSidelink message to peer UE. TP4: [38.331: 5.8.9.1a.2] WITH: UE has established PC5 RRC connection with peer UE. WHEN: UE receive an RRCReconfigurationCompleteSidelink from peer UE. THEN: UE apply the parameters in RRCReconfigurationSidelink. |  | RAN5#91-e (May-21) |  |  | 1 | 0% | 0% | 0% |  | 0% |  |  | 0%
201 | Y | 38.523-1 | 12.2.6.2 | Inter-carrier concurrent operation / Sidelink Reconfiguration via PC5 RRC / SL DRB management / Peer UE side | TP1: [38.331: 5.8.9.1a.2] WITH: UE has established PC5 RRC connection with peer UE. WHEN: UE receives an RRCReconfigurationSidelink that can comply to add an unicast SL DRB. THEN: UE applies the parameters in RRCReconfigurationSidelinksends and sends a RRCReconfigurationCompleteSidelink message to peer UE. TP2: [38.331: 5.8.9.1a.2] WITH: UE has established PC5 RRC connection with peer UE. WHEN: UE receives an RRCReconfigurationSidelink that can comply to modify an unicast SL DRB. THEN: UE applies the parameters in RRCReconfigurationSidelinksends and sends a RRCReconfigurationCompleteSidelink message to peer UE. TP3: [38.331: 5.8.9.1a.2] WITH: UE has established PC5 RRC connection with peer UE. WHEN: UE receives an RRCReconfigurationSidelink that can comply to release an unicast SL DRB. THEN: UE applies the parameters in RRCReconfigurationSidelinksends and sends a RRCReconfigurationCompleteSidelink message to peer UE. | Huawei, Hisilicon | RAN5#91-e (May-21) |  |  | 1 | 0% | 0% | 0% |  | 0% |  |  | 0%
202 |  | 38.523-1 | 12.2.7 | Inter-carrier concurrent operation / Sidelink CSI reporting | Add test case applicability to 38.523-2 Test Purpose(s): <Describe test purpose(s)> |  | RAN5#91-e (May-21) |  |  | 0 | 0% | 0% | 0% |  | 0% |  |  | 0%
203 | Y | 38.523-1 | 12.2.7.1 | Inter-carrier concurrent operation / Sidelink CSI reporting / Configuration | TP1: [38.331 5.8.9.1.1] WITH: UE has established PC5 RRC connection with peer UE. WHEN: UE is configured by upper layer to configure SL CSI-RS resource to peer UE. THEN: UE sends an RRCReconfigurationSidelink message including sl-CSI-RS-Config to peer UE and starts to transmit SL CSI-RS. TP2: [38.331 5.8.9.1.1] WITH: UE has established PC5 RRC connection with peer UE. WHEN: UE is configured by upper layer to trigger SL CSI report. THEN: UE sends an SCI format 1-A to trigger SL CSI report. |  | RAN5#91-e (May-21) |  |  | 1 | 0% | 0% | 0% |  | 0% |  |  | 0%
204 | Y | 38.523-1 | 12.2.7.2 | Inter-carrier concurrent operation / Sidelink CSI reporting / Reporting | TP1: [38.331 5.8.9.1.1] WITH: UE has established PC5 RRC connection with peer UE and is configuredby peer UE to perform CSI measurement. WHEN: UE receives a SCI format 1-A to trigger SL CSI report. THEN: UE sends an CSI reporting MAC-CE to peer UE. | Huawei, Hisilicon | RAN5#91-e (May-21) |  |  | 1 | 0% | 0% | 0% |  | 0% |  |  | 0%
205 |  | 38.523-1 | 12.2.8 | Inter-carrier concurrent operation / Sidelink failure | Sub-clause heading |  | RAN5#91-e (May-21) |  |  | 0 | 0% | 0% | 0% |  | 0% |  |  | 0%
206 | Y | 38.523-1 | 12.2.8.1 | Inter-carrier concurrent operation / Sidelink failure / PC5 RRC Reconfiguration Failure / Initiating UE side | TP1: [38.331: 5.8.9.1.8] WITH: UE has established PC5 RRC connection with peer UE on unicast sidelink. WHEN: UE receives an RRCReconfigurationFailureSidelink from peer UE. THEN: UE continue using the configuration used prior to corresponding RRCReconfigurationSidelink message and sends a SidelinkUEInformation message to indicate sidelink reconfiguration failure. | Huawei, Hisilicon | RAN5#91-e (May-21) |  |  | 1 | 0% | 0% | 0% |  | 0% |  |  | 0%
207 | Y | 38.523-1 | 12.2.8.2 | Inter-carrier concurrent operation / Sidelink failure / PC5 RRC Reconfiguration Failure / Peer UE side | TP1: [38.331: 5.8.9.1.8] WITH: UE has established PC5 RRC connection with peer UE on unicast sidelink. WHEN: UE receives an RRCReconfigurationSidelink that UE can't comply from peer UE. THEN: UE continue using the configuration used prior to corresponding RRCReconfigurationSidelink message and sends a RRCReconfigurationFailureSidelink message. |  | RAN5#91-e (May-21) |  |  | 1 | 0% | 0% | 0% |  | 0% |  |  | 0%
208 | Y | 38.523-1 | 12.2.8.3 | Inter-carrier concurrent operation / Sidelink failure / Sidelink radio link failure / transmission side | TP1: [38.331: 5.8.9.3] WITH: UE has established PC5 RRC connection with peer UE on unicast sidelink. WHEN: UE sends a RRCReConfigurationSidelink message to peer UE and doesn't receive response before T400 expires THEN: UE indicates SL RLF to upper layers and sends SidelinkUEInformationNR to indicate SL RLF. TP2: [38.331: 5.8.9.3] WITH: UE has established PC5 RRC connection with peer UE on unicast sidelink. WHEN: UE fails the intergrity check of SL SRB 2. THEN: UE indicates SL RLF to upper layers and sends SidelinkUEInformationNR to indicate SL RLF. TP3: [38.331: 5.8.9.3] WITH: UE has established PC5 RRC connection with peer UE on unicast sidelink. WHEN: UE fails the intergrity check of SL SRB 3. THEN: UE indicates SL RLF to upper layers and sends SidelinkUEInformationNR to indicate SL RLF. TP4: [38.331: 5.8.9.3] WITH: UE has established PC5 RRC connection with peer UE on unicast sidelink. WHEN: Retransmission times of an AM SL DRB exceeds the maximum number. THEN: UE indicates SL RLF to upper layers and sends SidelinkUEInformationNR to indicate SL RLF. TP5: [38.331: 5.8.9.3] WITH: UE has established PC5 RRC connection with peer UE on unicast sidelink. WHEN: MAC detects number of continuous HARQ ACK/NACK DTX exceeds sl-MaxNumConsecutiveDT12. THEN: UE indicates SL RLF to upper layers and sends SidelinkUEInformationNR to indicate SL RLF. | Huawei, Hisilicon | RAN5#91-e (May-21) |  |  | 1 | 0% | 0% | 0% |  | 0% |  |  | 0%
209 |  | 38.523-1 | 12.2.9 | Inter-carrier concurrent operation / Sidelink UE capability transfer via PC5 RRC | Sub-clause heading |  | RAN5#91-e (May-21) |  |  | 0 | 0% | 0% | 0% |  | 0% |  |  | 0%
210 | Y | 38.523-1 | 12.2.9.1 | Inter-carrier concurrent operation / Sidelink UE capability transfer via PC5 RRC / Initiating UE side | TP1: [38.331: 5.8.9.1.8] WITH: UE has established PC5 RRC connection with peer UE on unicast sidelink. WHEN: UE is configured by upper layer to initiate capability transfer procedure. THEN: UE sends a UECapabilityEnquirySidelink message to peer UE. TP2: [38.331: 5.8.9.1.8] WITH: UE has established PC5 RRC connection with peer UE on unicast sidelink. WHEN: UE is configured by upper layer to initiate capability transfer procedure and to provide UE radio access capabilities. THEN: UE sends a UECapabilityEnquirySidelink message with ue-CapabilityInformationSidelink to peer UE. TP3: [38.331: 5.8.9.1.8] WITH: UE has established PC5 RRC connection with peer UE on unicast sidelink. WHEN: UE receives a UECapabilityInformationSidelink message. THEN: UE sends a SidelinkUEInformationNR message to report sidelink UE capability information of peer UE. | Huawei, Hisilicon | RAN5#91-e (May-21) |  |  | 1 | 0% | 0% | 0% |  | 0% |  |  | 0%
211 | Y | 38.523-1 | 12.2.9.2 | Inter-carrier concurrent operation / Sidelink UE capability transfer via PC5 RRC / Peer UE side | TP1: [38.331: 5.8.9.1.8] WITH: UE has established PC5 RRC connection with peer UE on unicast sidelink. WHEN: UE receives a UECapabilityEnquirySidelink message from peer UE. THEN: UE sends a SidelinkUEInformationNR message to peer UE. TP2: [38.331: 5.8.9.1.8] WITH: UE has established PC5 RRC connection with peer UE on unicast sidelink. WHEN: UE receives a UECapabilityEnquirySidelink message with ue-CapabilityInformationSidelinkfrom peer UE. THEN: UE sends a SidelinkUEInformationNR message to report sidelink UE capability information of peer UE. |  | RAN5#91-e (May-21) |  |  | 1 | 0% | 0% | 0% |  | 0% |  |  | 0%
212 |  | 38.523-1 | 12.3 | Intra-carrier concurrent operation | Sub-clause heading |  | RAN5#91-e (May-21) |  |  | 0 | 0% | 0% | 0% |  | 0% |  |  | 0%
TBD |  | 38.523-1 | <Clause> | <Title> | <Task> |  | RAN5#91-e (May-21) |  |  | TBD
NAS
213 |  | 38.523-1 | 13 | V2X NAS layer | Sub-clause heading |  | RAN5#91-e (May-21) |  |  | 0 | 0% | 0% | 0% |  | 0% |  |  | 0%
214 |  | 38.523-1 | 13.1 | V2X policy provisioning | Sub-clause heading |  | RAN5#91-e (May-21) |  |  | 0 | 0% | 0% |  |  | 0%
215 | Y | 38.523-1 | 13.1.1 | V2X policy provisioning / Precedence / Validaty timer expires | **** TP1: [TS 24.587 clause 5.2.2] WITH: UE has V2XP over PC5 configured in the USIM and UE is in NR network coverage. WHEN: UE receives V2XP over PC5 from SS and then NR cell is off. THEN: UE conduct V2X communication according to parameters of V2XP over PC5 from SS **** TP2: [TS 24.587 clause 5.2.3] WITH: UE has received V2XP over PC5 from SS WHEN: Validaty timer expires and NR is on. THEN: UE initiate a UE-requested V2X policy provisioning procedure | Huawei, Hisilicon | RAN5#91-e (May-21) |  |  | 1 | 0% | 0% |  |  | 0%
216 |  | 38.523-1 | 13.2 | PC5 unicast | Sub-clause heading |  | RAN5#91-e (May-21) |  |  | 0 | 0% |  | 0% |  |  |  |  | 0%
217 | Y | 38.523-1 | 13.2.1 | PC5 unicast / link establishment / Reject / Conflict Layer 2 ID | **** TP1: [TS 24.587 clause 6.1.2.2] WITH: UE is out of coverage, Test loopback activation and V2X Setup. WHEN: UE has a V2X packet to be transmitted over PC5. THEN: UE initiate PC5 unicast link establishment procedure. **** TP2: [TS 24.587 clause 6.1.2.2.5] WITH: UE has transmitted PC5 unicast link establishment Request message. WHEN: The Layer 2 ID is conflicted. THEN: the PC5 unicast link establishment procedure failed. | Huawei, Hisilicon | RAN5#91-e (May-21) |  |  | 1 | 0% |  | 0% |  |  |  |  | 0%
218 | Y | 38.523-1 | 13.2.2 | PC5 unicast / link Security Mode | **** TP1: [TS 24.587 clause 6.1.2.7.3] WITH: UE receives a DIRECT LINK SECURITY MODE COMMAND message. WHEN: The 8 LSBs of K_NRP-sess ID of the DIRECT LINK SECURITY MODE COMMAND message is same to other UE's. THEN: UE transmits a DIRECT LINK SECURITY MODE REJECT message. | Huawei, Hisilicon | RAN5#91-e (May-21) |  |  | 1 | 0% |  | 0% |  |  |  |  | 0%
219 | Y | 38.523-1 | 13.2.3 | PC5 unicast / link modification | **** TP1: [TS 24.587 clause 6.1.2.3.2] WITH: UE has set up a V2X PDU session over PC5. WHEN: UE receives a DIRECT LINK MODIFICATION REQUEST to add a QoS flow. THEN: UE can communicate using the newly added QoS flow. **** TP2: [TS 24.587 clause 6.1.2.3.2] WITH: UE has set up a V2X PDU session over PC5. WHEN: UE receives a DIRECT LINK MODIFICATION REQUEST to modify a QoS flow. THEN: UE can communicate using the newly modified QoS flow. **** TP3: [TS 24.587 clause 6.1.2.3.2] WITH: UE has set up a V2X PDU session over PC5. WHEN: UE receives a DIRECT LINK MODIFICATION REQUEST to delete a QoS flow. THEN: No V2X data is communicated using the deleted QoS flow. | Lenovo, Motorola Mobility | RAN5#91-e (May-21) |  |  | 1 | 0% |  | 0% |  |  |  |  | 0%
220 | Y | 38.523-1 | 13.2.4 | PC5 unicast / link Release / Reestablish PC5 unicast link to same UE | **** TP1: [TS 24.587 clause 6.1.2.4.4] WITH: UE has established a V2X DIRECT LINK with a K_NRP ID to a SS-UE, and Release the DIRECT LINK after receiving a DIRECT LINK RELEASE REQUEST message. WHEN: UE has a V2X packet to be transmitted over PC5 to the same SS-UE. THEN: UE transmit DIRECT LINK ESTABLISHMENT REQUEST with same K_NRP ID. | Lenovo, Motorola Mobility | RAN5#91-e (May-21) |  |  | 1 | 0% |  | 0% |  |  |  |  | 0%
221 | Y | 38.523-1 | 13.2.5 | PC5 unicast / link identifier update | **** TP1: [TS 24.587 clause 6.1.2.5.6] WITH: UE has established a DIRECT LINK with Layer 2 ID-1 to a SS-UE. WHEN: UE receives a DIRECT LINK IDENTIFIER UPDATE REQUEST message with same Layer 2 ID-1. THEN: UE transmits a DIRECT LINK IDENTIFIER UPDATE REJECT message. **** TP2: [TS 24.587 clause 6.1.2.5.3, 6.1.2.5.4] WITH: UE has established a DIRECT LINK with old Layer 2 ID-1 to a SS-UE. UE receives a DIRECT LINK IDENTIFIER UPDATE REQUEST message and respond with a DIRECT LINK IDENTIFIER UPDATE ACCEPT message with new Layer 2 ID-2. WHEN: UE received a V2X packet from the SS-UE. THEN: the Layer 2 ID associated with the V2X packet should be old Layer 2 ID-1. **** TP3: [TS 24.587 clause 6.1.2.5.3, 6.1.2.5.4] WITH: UE has established a DIRECT LINK with old Layer 2 ID-1 to a SS-UE. UE receives a DIRECT LINK IDENTIFIER UPDATE REQUEST message and respond with a DIRECT LINK IDENTIFIER UPDATE ACCEPT message with new Layer 2 ID-2. WHEN: UE received a DIRECT LINK IDENTIFIER UPDATE ACK message from the SS-UE. THEN: UE transmit a V2X packet and the Layer 2 ID associated with the V2X packet should be new Layer 2 ID-2. |  | RAN5#91-e (May-21) |  |  | 1 | 0% |  | 0% |  |  |  |  | 0%
222 | Y | 38.523-1 | 13.2.6 | PC5 unicast / link keep alive | **** TP1: [TS 24.587 clause 6.1.2.8.5.1] WITH: UE transmitted a DIRECT LINK KEEPALIVE REQUEST message with Keep-alive counter value of n. WHEN: UE didn't receive DIRECT LINK KEEPALIVE RESPONSE message when T5003 expires. THEN: UE re-transmit a DIRECT LINK KEEPALIVE REQUEST message with same Keep-alive counter value of n. **** TP2: [TS 24.587 clause 6.1.2.8.5.2] WITH: UE received a first DIRECT LINK KEEPALIVE REQUEST message with Keep-alive counter value of n1, and UE responed a DIRECT LINK KEEPALIVE RESPONSE message. WHEN: UE received a second DIRECT LINK KEEPALIVE REQUEST message with Keep-alive counter value of n2 < n1 THEN: UE does not transmit a DIRECT LINK KEEPALIVE RESPONSE message for the second DIRECT LINK KEEPALIVE REQUEST message. | Huawei, Hisilicon | RAN5#91-e (May-21) |  |  | 1 | 0% |  | 0% |  |  |  |  | 0%
223 |  | 38.523-1 | 13.3 | PC5 groupcast | Sub-clause heading |  | RAN5#91-e (May-21) |  |  | 0 | 0% |  | 0% |  |  |  |  | 0%
TBD |  | 38.523-1 | <Clause> | <Title> | <Task> |  | RAN5#91-e (May-21) |  |  | TBD
224 |  | 38.523-1 | 13.4 | PC5 broadcast | Sub-clause heading |  | RAN5#91-e (May-21) |  |  | 0 | 0% |  | 0% |  |  |  |  | 0%
TBD |  | 38.523-1 | <Clause> | <Title> | <Task> |  | RAN5#91-e (May-21) |  |  | TBD
225 |  | 38.523-1 | 13.5 | Uu Unicast | Sub-clause heading |  | RAN5#91-e (May-21) |  |  | 0 | 0% |  | 0% |  |  |  |  | 0%
TBD |  | 38.523-1 | <Clause> | <Title> | <Task> |  | RAN5#91-e (May-21) |  |  | TBD
226 |  | 38.523-1 | 13.6 | PC5 Unicast security | Sub-clause heading |  | RAN5#91-e (May-21) |  |  | 0 | 0% |  | 0% |  |  |  |  | 0%
TBD |  | 38.523-1 | <Clause> | <Title> | <Task> |  | RAN5#91-e (May-21) |  |  | TBD
TS 38.523-2: Applicability for Protocol test cases
227 |  | 38.523-2 | <Clause> | <Title> | Add test case applicability statements for the new test cases introduced in 38.523-1 |  | TBD |  |  | 0.1 | 0% | 0% | 0% |  | 0% |  |  | 0%
TS 38.523-3: Protocol test suites (TTCN)
|  | 38.523-3 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
TBD |  | 38.523-3 | <Clause> | <Title of task> | <Describe task> |  | TBD |  |  | TBD
End of workplan items. Note! Do not remove this row. Introduce new work plan rows/items above this row.
Note on A6: Unique ID for WP items (unique within the sub-area work plan) Note! As WP item numbers may be referenced from outside of this WP that means: - Do not change number for WP items that have been published. - Do not re-use WP item numbers if a WP item is deleted
Note on B6: Set to Y if the WP item represents a new test case that will be specified in RAN5 test specifications as an executable test case else leave blank.
Note on K6: The WP item's weight number is used to set the reletive weights between WP items used in the overall calculation of completeness. Setting it to 0 for a WP item means that it will not be included at all in the calculation.