## TU_overview_after_RAN_86
|  |  |  | 1 TU = ~2h; RD: RRM/demodulation | [5 empty] | RAN | R1 | R2 | R4RF | R4RD | R1 | R2 | R3 | R4RF | R4RD | R6 | RAN | R1 | R2 | R3 | R4RF | R4RD | RAN | R1 | R1 | R2 | R3 | R4RF | R4RD | RAN | R1 | R2 | R3 | R4RF | R4RD | R1 | R2 | R3 | R4RF | R4RD | RAN | R1 | R2 | R3 | R4RF | R4RD | R1 | R2 | R3 | R4RF | R4RD | RAN | R1 | R2 | R3 | R4RF | R4RD | RAN
leading WG | RAT | WI code | WI or SI | Title | latest WID/SID | rapporteur | target | sum TUs | comment | 91 Mar.21 | 104bis | 113bis | 98bis | 98bis | 105 | 114 | 112 | 99 | 99 | 20 | 92 Jun.21 | 106 | 115 | 113 | 100 | 100 | 93 Sep.21 | 106bis | 107 | 116 | 114 | 101 | 101 | 94 Dec.21 | 107bis | 116bis | 114bis | 101bis | 101bis | 108 | 117 | 115 | 102 | 102 | 95 March.22 REL-17 freeze | 108bis | 117bis | 115bis | 102bis | 102bis | 109 | 118 | 116 | 103 | 103 | 96 June 22 REL-17 ASN.1 freeze | 110 | 119 | 117 | 104 | 104 | 97 Sep 22
R2 | NR | NR_IAB_enh-Core | WI | Core part: Enhancements to Integrated Access and Backhaul (IAB) for NR | RP-210758 | Qualcomm | Mar.22 | 25 | REL-17 |  | 0.5 | 1 | 0.25 |  | 1.5 | 1 | 1 | 0.5 | 0.25 |  |  | 1 | 1 | 1 | 1 | 0.5 |  | 1 | 1 | 1 | 2 | 1 | 0.5 |  |  | 1 | 1 | 1 | 0.5 |  | 1 | 2 | 1 | 0.5
R4 | NR | NR_IAB_enh-Perf | WI | Perf. part: Enhancements to Integrated Access and Backhaul (IAB) for NR | RP-210758 | Qualcomm | Sept 22 | 0.75 | REL-17 | [33 empty] | 0.5 | 0.25 |  |  |  |  | 0.5 | 0.5 |  |  |  | 0.5 | 0.5 |  |  |  |  | 0.5 | 0.5
e.g. R1, R2, R3, R4 (note: no TUs for R5) | e.g. NR, LTE, UTRA, GERAN (see #) | optional for new WIs/SIs (as proposal) but mandatory for already approved WIs/SIs | SI or WI | title acc. to the new WID/SID or for approved WIs/SIs acc. to the 3GPP workplan | leave empty for new WIs/SIs; but mandatory to fill in Tdoc number for already approved WIs/SIs | company name of the rapporteur | target date of the WI/SI? note: To be in line with WID/SID (if new) or status report (if existing). |  | if there is anything you need to add
examples:
R3 | NR | FS_NR_blabla | SI | Study on blabla for NR | RP-201234 | XY Telecom | Dec. 20 | [5 empty] | 1
R2 | LTE | LTE_bloblo | WI | Core part: bloblo for LTE | RP-203456 | UVW Telecom | Dec. 20 |  |  |  |  | 1.5 | 0.5 | 0.5
R1 | NR | NR_blubblub-Core | WI | Core part: blubblub for NR | RP-204567 | ABC Networks | June 21 |  |  |  | 1 | 1.5 | 1 | 0.5 |  |  | 1 | 1 | 0.5 | 0.5 |  |  |  | 0.5 | 0.5 | 0.5 |  |  | 0.5 | 0.5 | 1
R4 | NR | NR_blubblub-Perf | WI | Perf. part: blubblub for NR | RP-204567 | ABC Networks | Sep.21 | [7 empty] | 0.5 | [5 empty] | 0.5 | [5 empty] | 0.5 |  |  |  |  | 1
Instructions:
0. Please read the examples and explanations given above.
1. If you have a SI, then please fill out line 3.
2. If you have a Core part only WI, then please fill out line 3. for the Core part.
3. If you have a Perf. part only WI, then please fill out line 3 for the Perf. part.
4. If you have a Core part & Perf. part, then please fill out line 3 for Core part and line 4 for Perf. part.
5. If this Excel list is an attachment to a status report where you want to modify time budgets endorsed at a previous RAN meeting, then please make clear which fields you have changed (e.g. use a different text colour).
special case: WIs/SIs for multiple RATs (#):
a. Time budget wise your WI/SI will compete with other WIs/SIs in the highest RAT (NR > LTE > UTRA > GERAN)
b. If you want to request explicit time budget for a lower RAT, then please duplicate corresponding line, make clear via column B which line corresponds to which RAT and fill out the time units