## RAN WG1
NB-CIoT - Green indicates information anticipated to be stable from TR45.820. If NB-LTE, RAN1 work is expected to be higher as physical channels are not yet finalised.
| WG1#82bis [5 - 9 October 2015] | WG1#83 [16-20 November 2015] | RAN#70 | WG1 ad hoc [14 - 18 December 2015] | WG1 ad hoc[11 -15 January 2016] | WG1#84[15-19 February 2016] | RAN#71
| (Malmo, Sweden) | (Anaheim, California) | Sitges | (TBD) | ( TBD) | Malta | Goteborg
XY.201 - Physical layer General description
Note: An overview document.
Comment: Get specific details & updates from other RAN1 specs
Comment ( ):
| Task 1.1 Skeleton/Scope/ToC of Spec | Task 2.1 General description of Layer 1 |  | Task 3.1 General description of Layer 1 | Task 4.1 General description of Layer 1 | Task 5.1 - Finalise General Desc
| Present skeleton, scope and initial brief description | General description of layer 1 - Mod, coding, channels |  | Further updates to the description | Revision CRs | Revision CRs
| Task 1.2 Structure of PHY specs | Task 2.2 Services provided to higher layer |  | Revision CRs
| Provide overview of PHY specifications structure | List services provided to higher layers |  | Task 3.2 Services provided to higher layer |  | Task 5.2 Finalise Services provided
|  | Task 2.3 Physical channels and modulation |  | Revision CRs |  | Revision CRs
|  | List all the PHY channels |  | Task 3.3 Physical channels and modulation | Task 4.2 Physical channels and modulation | Task 5.3 Finalise PHY channels and modulation
|  |  |  | Further updates to the PHY channels and modulation description |  | Revision CRs
|  |  |  | Revision CRs | Revision CRs
XY.211 - Physical channels and modulation
Note:
Comment: Basic desricption available in TR (could be used). Still a complex one. Ideally, done before RRC.
Comment ( ):
Task 1.1 Skeleton/Scope/ToC of Spec
Present skeleton, scope and initial brief description
| Task 1.2 Frame structure | Task 2.1: Details of Frame structure |  | Task 3.1: Details of Frame structure | Task 4.1 Details of Frame structure | Task 5.1 Finalise Frame Structure
| Use Frame Structure from TR | Details of Frame structure |  | Further updates to Frame structure + Revision CRs | Revision CRs | Revision CRs
| Task1.3: UL PHY channels overview | Task 2.2: Details of UL PHY channels |  | Task 3.2: Details of UL PHY channels | Task 4.2: Details of UL PHY channels | Task 5.2 Finalise details of UL PHY
| Provide overview of UL PHY Shared & Control ch | Detailed description of UL PHY channels |  | Further updates to channel descriptions + Revision CRs | Revision CRs | Revision CRs
| Task1.3: DL PHY channels overview | Task2.3: Details of DL PHY channels |  | Task3.3: Details of DL PHY channels | Task 4.3: Details of DL PHY channels | Task 5.3 Finalise details of DL PHY
| Provide overview of DL PHY Shared & Control ch | Detailed description of UL PHY channels |  | Further updates to channel descriptions | Revision CRs | Revision CRs
|  | Task2.4: Modulation overview |  | Task3.4: Modulation Details | Task 4.4: Modulation Details | Task 5.4 Finalise Modulation details
|  | Provide overview of modulation schemes |  | Detailed description of Modulation | Further details of Modulation + Revision CRs | Revision CRs
|  | Task 2.5: Precoding and mapping to RE |  | Task 3.5: Precoding and mapping to RE | Task 4.5: Precoding and mapping to RE | Task 5.5 Finalise Precoding and mapping
|  | Provide overview of precoding and mapping to resource elements |  | Detailed description of precoding | Further details of precoding + Revision CRs | Revision CRs
XY.212 - Multiplexing and Channel Coding
Note:
Comment: Basic description available in TR.
Comment ( ):
Task 1.1 Skeleton/Scope/ToC of Spec
Present skeleton, scope and initial brief description
| Task 1.2 General Coding and multiplexing | Task 2.1: Details of Channel Coding, Multiplexing & CRCs |  | Task 3.1: Details of Channel Coding, Multiplexing & CRCs | Task 4.1 Details of Channel Coding, Multiplexing & CRCs | Task 5.1 Finalise details of channel coding
| Provide overview of coding schemes | Details for both UL and DL transport and signalling |  | Revision CRs | Revision CRs | Revision CRs
XY.213 - Physical layer procedures
Note: Detailed specification of PHY layer procedures.
Comment: Basic description of PHY layer procedures in TR. CHECK if L1 procedures (RACH etc) can be developed in parallel with RAN2. Need to be broadly complete before RRC encoding?
Comment ( ):
Task 1.1 Skeleton/Scope/ToC of Spec
Present skeleton, scope and initial brief description
| Task 1.2 PHY Procedures (overview) | Task 2.1 Details of synchronisation and cell search |  | Task 3.1 Details of synchronisation and cell search | Task 4.1 Details of synchronisation and cell search
| Provide overview of PHY procedures | Provide synchronisation and cell search procedures |  | Further details | Revision CRs
| Provide UL shared channel procedures | Task 2.2 Details of random access procedures |  | Task 3.2 Details of random access procedures | Task 4.2 Details of random access procedures | Task 5.1 Finalise RACH
| Provide DL shared channel procedures | Provide details of RACH procedures |  | Further details of RACH procedures | Revision CRs | Revision CRs
| Provide control channel procedures | Task 2.3 Details of UE receiving shared channel proc |  | Task 3.3 Details of UE receiveing shared channel proc | Task 4.3 Details of UE receiveing shared channel proc | Task 5.2 Finalise UE share ch proc
| Provide Power control procedures | Provide details of DL PHY shared channel procedures |  | Further details of DL PHY shared channel procedures | Revision CRs | Revision CRs
| Coverage class overview | Task 2.4 Details of UE receving control channel proc |  | Task 3.4 Details of UE receving control channel proc | Task 4.4 Details of UE receving control channel proc | Task 5.3 Finalise UE control ch proc
|  | Provide details of DL PHY control channel procedures |  | Further details of DL PHY control channel procedures | Revision CRs | Revision CRs
|  | Task 2.5 Details of Coverage Class procedures |  | Task 3.5 Details of Coverage Class procedures | Task 4.5 Details of Coverage Class procedures | Task 5.4 Details of Coverage Class procedures
|  | UE reporting, RAN determination and commands |  | Further details of UL reporting procedures | Revision CRs | Revision CRs
|  | Task 2.6 Details of Power Control procedures |  | Task 3.6 Details of Power Control procedures | Task 4.6 Details of Power Control procedures
|  | Open loop uplink power control |  | Further details of power control procedures | Revision CRs
XY.214 - Measurements
Note: UE / RAN measurement abilities
Comment: Relatively small LTE spec. For CIoT, even smaller as no inter-RAT measurement and only UE autonomous cell reselection. Output of this work needed by RAN 4?
Comment ( ):
Task 1.1 Skeleton/Scope/ToC of Spec
Present skeleton, scope and initial brief description
| Task 1.2 UE & RAN measurement capabilites |  |  |  |  | Task 5.1 Finalise UE measurement
| Overview of measurements for UE autonomous cell reselection |  |  |  |  | Revision CRs
|  | Task 2.1 UE measurement capabilities |  | Task 3.1 UE measurement |  | Task 5.2 Finalise CIoT measurement
|  | details of UE measurement of base station |  | Revision CRs |  | Revision CRs

## RAN WG2
Green indicates information anticipated to be stable from TR45.820. Both NB CIoT and NB LTE proposals are expected to reuse L2/L3 extensively - but with carefully optised for small data.
| WG2#91bis [5 - 9 October 2015] | WG2#92 [16-20 November 2015] | RAN#70 | WG2 ad hoc [14 - 18 December 2015] | WG2 ad hoc[11 -15 January 2016] | WG2#93[15-19 February 2016] | RAN#71
| (Malmo, Sweden) | (Anaheim, California) | Sitges | (TBD) | ( TBD) | Malta | Goteborg
XY.300 - Overall description Stage 2
Note: Important and should aim for 80% complete by Oct-Nov meetings.
Comment: Major dependency on architecture (Gb vs S1 vs "S1 with eNB caching UE context" vs "S1&small data over NAS") decision by RAN#69. This impacts the design of RRC; usage of SNDCP; and impacts on the needed CT1 NAS protocol enhancements).
Comment ( ):
| Task 1.1 Skeleton/Scope/ToC of Spec | Task 2.1 Overview of architecture |  | Task 3.1 Overview of architecture | Task 4.1 Overview of architecture | Task 5.1 Finalise Overview of arch
| Present skeleton, scope and initial brief description | Updates to architecture and functional splits |  | Finalise architectural design | Revision CRs | Revision CRs
| Task 1.2 Overview of architecture | Task 2.2 Overview of Layer 1 |  | Updates and Revision CRs | Task 4.2 Layer 1 | Task 5.2 Finalise Layer 1
| Provide overview of architecture | Updates and details to Layer 1 |  | Task 3.2 Layer 1 | Revision CRs | Revision CRs
| Provide functional split | [Sync with RAN1] |  | Updates to Layer 1 functions - finalise | Revision CRs
| Task 1.3 Overview of Layer 1 | Task 2.3 Layer 2 |  | Revision CRs | Task 4.3. Layer 2 | Task 5.3 Finalise Layer 2
| Provide overview of Layer 1 | Detailed functions of MAC, RLC, PDCP and RRC |  | Task 3.3. Layer 2 | Updates to Layer 2 functions | Revision CRs
| Task 1.4 Layer 2 | Task 2.4 Scheduling |  | Updates to Layer 2 functions (MAC, RLC, PDCP and RRC) | Revision CRs
| some text in TR Section 7.3.4.3 | Provide details of SI scheduling |  | Task 3.4 Scheduling | Task 4.4 Scheduling | Task 5.4 Finalise Scheduling
|  |  |  | Updates to SI scheduling | Revision CRs | Revision CRs
XY.302 - Services provided by the physical layer
Note: Fairly smaller specification
Comment:
Comment ( ):
Task 1.1 Skeleton/Scope/ToC of Spec
Present skeleton, scope and initial brief description
| Task 1.2 Services | Task 2.1: Model of physical layer (downlink) |  | Task 3.1: Model of physical layer (downlink) | Task 4.1: Model of physical layer (downlink) | Task 5.1 Finalise model of PHY UL
| Services and functions of PHY layer | Downlink shared channel model |  | Update details of downlink shared channel model | Revision CRs
|  | Task 2.2: Model of physcial layer (uplink) |  | Task 3.2: Model of physcial layer (uplink) | Task 4.2: Model of physcial layer (uplink) | Task 5.2 Finalise model of PHY DL
|  | Uplink shared channel model |  | Update details of uplink shared channel model | Revision CRs
XY.304 - User equipment (UE) procedures in idle mode
Note: Fairly smaller specification. Removal of emergency state
Comment:
Comment ( ):
Task 1.1 Skeleton/Scope/ToC of Spec
Present skeleton, scope and initial brief description
|  | Task 2.1: Cell selection and reselection |  | Task 3.1: Cell selection and reselection | Task 4.1 Cell selection and reselection | Task 5.1 Finalise
|  | Details of cell selection and reselection procedure |  | Finalise-cell selection and reselection | Revision CRs | Revision CRs
Task 2.2: PLMN selection
XY.306 - User equipment (UE) radio access capabilities
Note: Fairly smaller specification.
Comment: Should we think of 13dBm Tx power - is that a subscription parameter?
Comment ( ):
Task 1.1 Skeleton/Scope/ToC of Spec
Present skeleton, scope and initial brief description
|  | Task 2.1 UE radio access capabilities |  | Task 3.1 UE radio access capabilities | Task 4.1 UE radio access capabilities | Task 5.1 Finalise UE capabilities
|  | Provide details of PHY parameters |  | Provide updated details of PHY parameters | Revision CRs | Revision CRs
|  | Provide details of MAC, PDCP, RRC parameters |  | Provide updated details of MAC, PDCP, RRC parameters
XY.321 - Medium Access Control (MAC) protocol specifications
Note:
Comment:
Comment ( ):
Task 1.1 Skeleton/Scope/ToC of Spec
Present skeleton, scope and initial brief description
| Task 1.2 MAC architecture | Task 2.1 MAC architecture |  | Task 3.1 MAC architecture | Task 4.1 MAC architecture | Task 5.1 Finalise MAC architecture
| Provide overview of MAC services and functions | Details of MAC services and functions |  | Updated details of MAC services and functions | Revision CRs | Revision CRs
| Task 1.3 MAC procedures | Task 2.2 MAC procedures |  | Task 3.2 MAC procedures | Task 4.2 MAC procedures | Task 5.2 Finalise MAC procedures
| Overview of Random Access procedures | Details of random access procedures |  | Updated details of random access procedures | Revision CRs | Revision CRs
| Overview of DL data transfer procedure | Details of DL data transfer procedure |  | Updated details of DL data transfer procedure
| Overview of UL data transfer procedure | Details of UL data transfer procedure |  | updated details of UL data transfer procedure
| Task 1.4 MAC PDU and formats | Task 2.3 MAC PDU and formats |  | Task 3.3 MAC PDU and formats | Task 4.3 MAC PDU and formats | Task 5.3 MAC PDU and formats
| Overview of MAC PDU formats/parameters | Details of MAC PDU formats/parameters |  | Updated details of MAC PDU formats/parameters | Revision CRs | Revision CRs
XY.322 - Radio Link Control (RLC) protocol specifications
Note:
Comment: Scope of RLC specification is being worked out
Comment ( ):
Task 1.1 Skeleton/Scope/ToC of Spec
Present skeleton, scope and initial brief description
| Task 1.2 RLC architecture | Task 2.1 RLC architecture |  | Task 3.1 RLC architecture | Task 4.1 RLC architecture | Task 5.1 Finalise RLC architecture
| Provide overview of RLC services and functions | Details of RLC services and functions |  | Updated details of RLC services and functions | Revision CRs | Revision CRs
|  | Task 2.2 RLC procedures |  | Task 3.2 RLC procedures | Task 4.2 RLC procedure | Task 5.2 Finalise RLC procedure
|  | Segmentation and reassembly |  | Updated details of segmentation and reassembly | Revision CRs | Revision CRs
|  | Task 2.3 RLC PDU and formats |  | Task 3.3 RLC PDU and formats | Task 4.3 RLC PDU and formats | Task 5.3 Finalise RLC PDU and formats
|  | Details of RLC PDU formats/parameters |  | Updated details of RLC PDU formats/parameters | Revision CRs | Revision CRs
XY.323 - Packet Data Convergence Protocol (PDCP) specification
Note:
Comment: If S1-based, PDCP
Comment ( ):
Task 1.1 Skeleton/Scope/ToC of Spec
Present skeleton, scope and initial brief description
| Task 1.2 PDCP architecture | Task 2.1 PDCP architecture |  | Task 3.1 PDCP architecture | Task 4.1 PDCP architecture | Task 5.1 Finalise PDCP architecture
| ProvidePDCP services and functions | Details of PDCP services and functions |  | Updated details of PDCP services and functions | Revision CRs | Revision CRs
| Task 1.3 PDCP procedures | Task 2.2 PDCP procedures |  | Task 3.2 PDCP procedures | Task 4.2 PDCP procedures | Task 5.2 Finalise PDCP procedures
|  | Details of UL data transfer procedure |  | Updated details of UL data transfer procedure | Revision CRs | Revision CRs
|  | Details of DL data transfer procedure |  | Updated details of DL data transfer procedure
|  | Task 2.3 PDCP PDU and formats |  | Task 3.3 PDCP PDU and formats | Task 4.3 PDCP PDU and formats | Task 5.3 Finalise PDCP PDU and formats
|  | Details of PDCP PDU formats/parameters |  | Updated details of PDCP PDU formats/parameters | Revision CRs | Revision CRs
XY.331 - Radio Resource Control (RRC); protocol specification
Note:
Comment: Aim to provide simplified RRC (with minimal message sequences). Depends on SA2 architecture design outcome.
Comment ( ):
Task 1.1 Skeleton/Scope/ToC of Spec
Present skeleton, scope and initial brief description
| Task 1.2 System Information | Task 2.1 System Information |  | Task 3.1 System Information | Task 4.1 System information | Task 5.1 Finalise RRC spec
| Overview of system information (necessary changes) | Details of Service Information |  | Updated details of Service Information | Revision CRs | Revision CRs
| Task 1.3 RRC services | Task 2.2 RRC Procedures |  | Task 3.2 RRC Procedures | Task 4.2 RRC procedures | Task 5.2 Finalise RRC procedures
| Overview of RRC services - messages | Details of RRC procedures/messages |  | Updated details of RRC procedures/messages | Revision CRs | Revision CRs
[5 empty] | Task 4.3 ASN.1 freezing | Task 5.3 Freeze ASN.1
[5 empty] | Initiate offline ASN.1 freezing task | conclude freezing task

## RAN WG3
| WG3#89bis [5 - 9 October 2015] | WG3#90 [16-20 November 2015] | RAN#70 | WG3#91[15-19 February 2016] | RAN#71
| (Sophia Antipolis, France) | (Anaheim, California) | Sitges | Malta | Goteborg
TS 36.413 - S1 Application Protocol (S1AP)
Note:
Comment:
Comment ( ):
| Task 1.1 CRs on S1AP functions | Task 2.1 CRs on S1AP procedures |  | Task 3.1 CRs on S1AP procedures
| List changes to functions | Updates to S1AP procedures |  | Fruther updates to S1AP procedures
| Task 1.2 CRs on S1AP procedures | Task 2.2 CRs on S1AP procedures |  | Task 3.2 CRs on S1AP procedures
| Present overview of S1AP procedures | Updates and details to Layer 1 |  | Further updates and details to Layer 1

## RAN WG4
| WG4#76bis [12- 16 October 2015] | WG4#77 [16-20 November 2015] | RAN#70 | WG4 ad hoc [11 -15 January 2016] | WG4#78 [15-19 February 2016] | RAN#71
| (Sophia Antipolis, France) | (Anaheim, California) | Sitges | ( TBD) | Malta | Goteborg
37.104 - E-UTRA, UTRA and GSM/EDGE; Multi-Standard Radio (MSR) Base Station (BS) radio transmission and reception
Note:
Comment:
Comment ( ):
| Task 1.1 Min Requirements: BS power classes | Task 2.1: Min Requirements / power classes |  | Task 3.1 Min requirements | Task 4.1 Finalise min requirements
| CRs on min requirements, BS classes/ power classes | CRs on details of requirements, BS classes, UE power classes |  | Further details + Revision CRs | Revision CRs
| Task 1.2 Operating Bands | Task 2.2: Operating Bands |  | Task 3.2 Operating Bands | Task 4.2 Finalise operating bands
| Bands, channel bandwidth, channel spacing | Details of Bands, channel BW, channel spacing |  | Further details of bands, channel BW, channel spacing | Revision CRs
| Task 1.3 Transmitter Characteristics | Task 2.3 Transmitter Characteristics |  | Revision CRs.
| Max/min BS transmit power, power control | Details of BS transmit power, power control |  | Task 3.3 Transmitter characteristics | Task 4.3 Finalise transmitter characteristics
| ACLR , spectrum emission masks | Details of ACLR and spectrum emission masks |  | Further details of BS Tx power, power control | Revision CRs
| Task 1.4 Receiver Characteristics | Task 2.4 Receiver Characteristics |  | Further details of ACLR and masks + Revision CRs
| Max input level, ACS, blocking characteristics | Details of max input level, ACS, blocking characteristics |  | Task 3.4 Receiver characterisitics | Task 4.4 Receiver characteristics
| Spurious responses, intermodulation characteristics | Details of spurious responses, intermodulation |  | Further details of ACS, blocking, spurious, IM | Revision CRs
|  | Task 2.5 Performance Requirements |  | Task 3.5 Performance Requirements | Task 4.5 Performance requirements
|  | Performance requirement for BS |  | Details of performance requirement | Revision CRs
TS 37.141 - E-UTRA, UTRA and GSM/EDGE; Multi-Standard Radio (MSR) Base Station (BS) conformance testing
Note:
Comment: Testing methods and conformance requirements (for the items listed in 37.104)
Comment ( ):
| Task 1.1 Test methods and conformance requirements | Task 2.1 Test methods and conformance requirements |  | Task 3.1 Test methods and conformance requirements | Task 4.1 Finalise test methods and conformance
| Define testing methods and conformance requirements | CRs |  | CRs | Revision CRs
| Task 1.2 Operating Bands | Task 2.2 Operating Bands |  | Task 3.2 Operating Bands | Task 4.2 Finalise Operating bands
| BS testing requirements | BS testing requirements |  | Further CRs on BS testing requirements | Revision CRs
| Task 1.3 Transmitter characteristics | Task 2.3 Transmitter characteristics |  | Task 3.3 Transmitter characteristics | Task 4.3 Finalise tranmitter characteristics
| Test requirements for Tx char | CRs on test requirements for Tx char |  | Further CRs on test requirements for Tx char | Revision CRs
| Task 1.4 Receiver characterisitics | Task 2.4 Receiver characterisitics |  | Task 3.4 Receiver characterisitics | Task 4.4 Finalise receiver characteristics
| Test requirements for Rx char | CRs on test requirements for Rx char |  | Further CRs on test requirements for Rx char | Revision CRs
XY.101 - User Equipment (UE) radio transmission and reception
Note:
Comment:
Comment ( ):
Task 1.1 Skeleton/Scope/ToC of Spec
Present skeleton, scope and initial brief description
| Task 1.2 Min Requirements: power classes | Task 2.1: Min Requirements / power classes |  | Task 3.1 Min requirements | Task 4.1 Finalise min requirements
| Define min requirements, BS classes/ power classes | Details of requirements, BS classes, UE power classes |  | Further details + Revision CRs | Revision CRs
| Task 1.3 Operating Bands | Task 2.2: Operating Bands |  | Task 3.2 Operating Bands | Task 4.2 Finalise operating bands
| Bands, channel bandwidth, channel spacing | Details of Bands, channel BW, channel spacing |  | Further details of bands, channel BW, channel spacing | Revision CRs
| Task 1.4 Transmitter Characteristics | Task 2.3 Transmitter Characteristics |  | Revision CRs.
| Max/min transmit power, power control | Details of transmit power, power control |  | Task 3.3 Transmitter characteristics | Task 4.3 Finalise transmitter characteristics
| Output RF (OOB emissions) , spectrum emission masks | Details of output RF and spectrum emission masks |  | Further details of Tx power, power control | Revision CRs
| Task 1.5 Receiver Characteristics | Task 2.4 Receiver Characteristics |  | Further details of o/p RF and masks + Revision CRs
| Max input level, ACS, blocking characteristics | Details of max input level, ACS, blocking characteristics |  | Task 3.4 Receiver characterisitics | Task 4.4 Receiver characteristics
| Spurious responses, intermodulation characteristics | Details of spurious responses, intermodulation |  | Further details of ACS, blocking, spurious, IM | Revision CRs
|  | Task 2.5 Performance Requirements |  | Task 3.5 Performance Requirements | Task 4.5 Performance requirements
|  | Performance requirement for CIoT device |  | Details of performance requirement | Revision CRs
XY.104 - Base Station (BS) radio transmission and reception
Note:
Comment:
Comment ( ):
Task 1.1 Skeleton/Scope/ToC of Spec
Present skeleton, scope and initial brief description
| Task 1.2 Min Requirements: BS power classes | Task 2.1: Min Requirements / power classes |  | Task 3.1 Min requirements | Task 4.1 Finalise min requirements
| Define min requirements, BS classes/ power classes | Details of requirements, BS classes, UE power classes |  | Further details + Revision CRs | Revision CRs
| Task 1.3 Operating Bands | Task 2.2: Operating Bands |  | Task 3.2 Operating Bands | Task 4.2 Finalise operating bands
| Bands, channel bandwidth, channel spacing | Details of Bands, channel BW, channel spacing |  | Further details of bands, channel BW, channel spacing | Revision CRs
| Task 1.4 Transmitter Characteristics | Task 2.3 Transmitter Characteristics |  | Revision CRs.
| Max/min BS transmit power, power control | Details of BS transmit power, power control |  | Task 3.3 Transmitter characteristics | Task 4.3 Finalise transmitter characteristics
| ACLR , spectrum emission masks | Details of ACLR and spectrum emission masks |  | Further details of BS Tx power, power control | Revision CRs
| Task 1.5 Receiver Characteristics | Task 2.4 Receiver Characteristics |  | Further details of ACLR and masks + Revision CRs
| Max input level, ACS, blocking characteristics | Details of max input level, ACS, blocking characteristics |  | Task 3.4 Receiver characterisitics | Task 4.4 Receiver characteristics
| Spurious responses, intermodulation characteristics | Details of spurious responses, intermodulation |  | Further details of ACS, blocking, spurious, IM | Revision CRs
|  | Task 2.5 Performance Requirements |  | Task 3.5 Performance Requirements | Task 4.5 Performance requirements
|  | Performance requirement for BS |  | Details of performance requirement | Revision CRs
XY.133 - Requirements for support of radio resource management
Note:
Comment:
Comment ( ):
Task 1.1 Skeleton/Scope/ToC of Spec
Present skeleton, scope and initial brief description
| Task 1.2 RRC Idle mode | Task 2.1 RRC Idle mode |  | Task 3.1 RRC Idle mode | Task 4.1 Finalise RRC Idle mode
| Cell selection, reselection | Details of measurement for cell selection, reselection |  | Further details of measurements for cell selection/reselection | Revision CRs
| Task 1.3 Timing and signalling | Task 2.2 Timing and signalling |  | Task 3.2 Timing and signalling | Task 4.2 Finalise timing and signalling
| Time synchronization and timing advance | Details of timing sync and TA. |  | Further details of sync and TA | Revision CRs
| Task 1.4 Measurements peformance requirement | Task 2.3 Measurements performance requirement |  | Task 3.3 Measurements performance requirement | Task 4.3 Finalise measurement performance requirement
| Any measurements pref requirement in RAN and CIoT | Details of measurements perf requirement (CIoT) |  | Further details of measurements perf requirement (CIoT)
|  | Details of measurements perf requirement (RAN) |  | Details of measurements perf requirement (RAN)