3GPP TSG-RAN WG3 Meeting #127bis	R3-251732

Wuhan, China, 07 – 11 April 2025

Agenda item:	21.1

Source:	Nokia, Qualcomm (Rapporteurs)

Title:	Rapporteur Inputs on workplan

WID/SID:	NR_XR_Ph3-Core - Release 19

Document for:	Discussion and Decision

# 1	Introduction

This document contains the work plan per the WID updated at RAN#107 [RP-250107]:

The Rel-19 XR Phase 3 objectives are as follows (RAN3 part is highlighted):

-	Support and specify multi-modality awareness for QoS flows in both DL and UL RAN [RAN3]:

-	Specify enhancements to enable transmission/reception in gaps/restrictions that are caused by RRM measurements (from inter-frequency RRM measurement gaps, or intra-frequency measurements, or other scheduling restrictions etc). [RAN1, RAN2, RAN4]

-	Specify the corresponding measurement gap and scheduling restriction to enable the identified enhancements with RRM performance impact taken into consideration, work being triggered by LS. [RAN4]

-	Specify Enhancements for support of UL scheduling to enable high XR capacity while meeting delay requirements/avoiding too late PDUs, as follows [RAN2]:

-	Specify additional Logical Channel priority handling using delay/deadline information of packets;

-	Specify enhanced DSR (Delay Status Report) reporting with multiple pairs of remaining time and buffer size for an LCG.

-	Specify the following user plane enhancements [RAN2]:

-	RLC re-transmission related enhancements for operation of RLC Acknowledged Mode (AM) with small packet delay budget.

-	Extend Release 18 standalone mechanism to support NR-NR dual connectivity as follows [RAN3]:

-	PDU set based handling;

-	ECN marking;

-	Burst Arrival Time reporting, if needed;

-	PSI Discard coordination, if needed;

NOTE:	No RAN2 impact from above items.

-	Specify uplink congestion signalling [RAN2, RAN3]:

-	Specify in MAC layer XR rate control signalling over downlink per QoS flow/per DRB and the associated F1 signalling, if any, to enable faster source rate adaption to uplink congestion.

-	Support of PDU set based QoS handling enhancement [RAN3]:

-	Support of DL PDU Set marking without PDU Set QoS

-	Support of Alternative PDU Set QoS, which may contain UL and/or DL PDU Set QoS Parameters (i.e. UL PSDB, DL PSDB, UL PSER and/or DL PSER).

-	QoS Handling when Traffic Characteristics Change Dynamically [RAN3]

-	TTNB and burst size to be provided over GTP-U

-	Support of exposure of available data rate [RAN3]

Note: Coordination with SA2, as needed

# 2	Workplan

A workplan corresponding to the objectives and allocated TUs is suggested the table below.

Table 3-1: Workplan for the XR WI

| Date | RAN1 | RAN2 | RAN3 | RAN4 | RAN |
| --- | --- | --- | --- | --- | --- |
| 2024-02 | RAN1#116 Start discussion on a design of the enhancement feature(s) to enable transmission/reception in gaps/restrictions that are caused by RRM measurements. |  |  |  |  |
| 2024-03 |  |  |  |  | RAN#103 Status Report (target of 2% corresponding to 0.5 TU spent over an initial allocation of 24.8) |
| 2024-04 | RAN1#116bis Continue the discussion on the design of the enhancement feature(s) to enable transmission/reception in gaps/restrictions that are caused by RRM measurements. Start agreeing on solution(s). | RAN2#125bis Endorse workplan Start the work on all 4 objectives except measurement gaps, for which RAN1 conclusions first need to be reached. For multi-modality and scheduling enhancements, start the study phase. | RAN3#123bis Start discussion on RAN3 related objectives on NR-DC, e.g. PDU set based handling, ECN marking, etc. Agree the DC bearer types to be supported. Designate responsible companies for BL Stage-2 & 3 CRs. |  |  |
| 2024-05 | RAN1#117 Continue developing the solution(s) to enable transmission/reception in gaps/restrictions that are caused by RRM measurements. | RAN2#126 Continue the work on all 3 objectives. | RAN3#124 Finalize the solution on required enhancements. Finalize Stage-2 CR(s) Agree the skeleton of Stage-3 CR(s). |  |  |
| 2024-06 |  |  |  |  | RAN#104 Status Report (target of 18% corresponding to 4.5 TUs spent over an initial allocation of 24.8) Take into account outcome of SA2 study if available. |
| 2024-08 | RAN1#118 Continue the work on the details of the agreed solution(s) to enable transmission/reception in gaps/restrictions that are caused by RRM measurements. | RAN2#127 Continue the work on all 3 objectives. For multi-modality and scheduling enhancements, conclude the study phase and convey the outcome to RAN#105. | RAN3#125 Agree Stage-2 CR(s) and Stage-3 CR(s) | RAN4#112 Approval of workplan Initial discussion on scenarios for measurement skipping based on RAN1 conclusions. |  |
| 2024-09 |  |  |  |  | RAN#105 Status Report (target of 30% corresponding to 7.5 TUs spent over an initial allocation of 24.8) Checkpoints: 1. Multi-modality (RAN2) 2. Scheduling enhancements (RAN2) |
| 2024-10 | RAN1#118bis Continue the work on the details of the agreed solution(s) to enable transmission/reception in gaps/restrictions that are caused by RRM measurements. Check if RAN1 involvement related to objective on multi-modality is needed. | RAN2#127bis Check with RAN1 the progress on measurement gaps and start discussing in RAN2. Continue the work on UL scheduling enhancements according to the refined objective. Start the work on uplink congestion signalling. | RAN3#125bis Discuss multi-modality when handling incoming LS (no additional TU allocated to the new objective). | RAN4#112bis Conclusions on scenarios for measurement skipping based on RAN1 conclusions. Discussion on the need for UE assistance information regarding measurements occasions needed. |  |
| 2024-11 | RAN1#119 Continue the work on the details of the agreed solution(s) to enable transmission/reception in gaps/restrictions that are caused by RRM measurements. | RAN2#128 Narrow down possible solutions. First version of Stage 2 CR | RAN3#126 Discuss LS on PDU Set Information Marking Support without QoS parameters, and usage of multi-modality information (no additional TU allocated to the new objective). | RAN4#113 Discussion on RRM requirements with measurement skipping. Discussion on the necessary UE assistance information. |  |
| 2024-12 |  |  |  |  | RAN#106 Status Report (target of 55% corresponding to 13.5 TUs spent over an initial allocation of 24.8) Checkpoint on multi-modality (including possible allocation of additional TUs for RAN3) |
| 2025-02 | RAN1#120 Finalize, if not already, the discussion on the design of the enhancement feature(s) to enable transmission/reception in gaps/restrictions that are caused by RRM measurements. Provide RAN1 input to RAN2 on RRC configuration parameters, UE capabilities, and Stage 2 TPs. | RAN2#129 Continue the work on the details of the agreed solutions. First versions of Stage 2 & 3 CR. | RAN3#127 Discuss LS on UL bit rate control, available data rate reporting and multi-modality awareness (no additional TU allocated to the new objective). | RAN4#114 Conclusion on RRM requirements with measurement skipping. Discussion on the need for UE assistance information regarding measurement skipping. Agreement of CR work split. |  |
| 2025-03 |  |  |  |  | RAN#107 Checkpoint on multi-modality (including possible allocation of additional TUs for RAN3) Status Report (target of 67% corresponding to 16.5 TUs spent over an initial allocation of 24.8) |
| 2025-04 | RAN1#120bis XR will not be discussed. | RAN2#129bis Continue the work on the details of the agreed solutions for all objectives. Reflect new agreements in running Stage 2 & 3 CRs. | RAN3#127bis Start discussion on RAN3 related objectives on uplink rate control, PDU set based QoS handling enhancement, TTNB and burst size, exposure of available data rate etc. Designate responsible companies for Stage-2 & 3 BL CRs. | RAN4#114bis Conclusion on the necessary UE assistance information. First Draft CRs for RRM core requirements (draft CRs for 38.133 expected) First big Draft CR. |  |
| 2025-05 | RAN1#121 | RAN2#130 Continue the work on the details of the agreed solutions for all objectives. Reflect new agreements in running Stage 2 & 3 CRs. | RAN3#128 Continue the work on the details of the agreed solutions for all objectives. Reflect new agreements in Stage 2 & 3 BL CRs. | RAN4#115 Discussion on remaining open issues for RRM core. |  |
| 2025-06 |  |  |  |  | RAN#108 Status Report (target of 91% corresponding to 22.5 TUs spent over an initial allocation of 24.8) |
| 2025-08 |  | RAN2#131 Finalise Stage 2 & 3 CRs Agree Stage 2 & 3 CRs | RAN3#129 Finalise Stage 2 & 3 CRs Agree Stage 2 & 3 CRs | RAN4#116 Discussion on remaining open issues for RRM core. Revision of CRs for RRM core requirements. Planning of RRM performance. Initial discussion on RRM test cases. |  |
| 2025-09 |  |  |  |  | RAN#109 Status Report (target of 100% corresponding to 24.8 TUs spent over an initial allocation of 24.8) CRs received for approval. |

# 3	Proposal for new BL CR owner

Based on companies’ interest, it is proposed to assign the following BL CR owner for the new affected specs listed in the WID.

It is proposed to capture following in the MCC notes:

|  | BL CR owner |
| --- | --- |
| 38.413 | Lenovo |
| 38.415 | China Telecom |
| 37.483 | China Mobile |