3GPP TSG-RAN WG3 #128	          R3-253759

Malta, MT, 19th – 23th May  2025

Agenda item:	23.1

Source:	EBU (Rapporteur)

Title:	Rapporteur Inputs on workplan

WID/SID:	LTE_terr_bcast_Ph2 - Release 19

Document for:	Discussion and Decision

# 1    Introduction

This document contains the work plan per the WID updated at RAN#107 [RP-250794]:

The Rel-19 LTE-based 5G Broadcast Phase 2 objectives are as follows:

For MBMS-dedicated cells, specify time-frequency interleavers [RAN1] and corresponding signaling [RAN2, RAN3]:

- For the time-interleaving part of 5G Broadcast TFI, one transport block is mapped to multiple non-consecutive subframes, following the principles of NR TBoMS. The following steps are followed:

  - Scale the TBS by a factor of N, where N is the number of subframes over which the TB is mapped.

    - RAN1 to discuss the details of the scaling, the value(s) for N and the set of subframes over which the TB is mapped, including how to schedule the TBs.

  - Within one subframe, the transmitted rate matched bits are read consecutively from the circular buffer.

    - In a given subframe, the procedure in TS 36.212 Section 5.1.4.1.2 applies (except for the parameter k0 which needs to be modified according to point 3 below)

    - Before frequency interleaving (if applied), the mapping from coded bits to RE follows the current specification.

  - Across subframes belonging to the same TB, the starting point for reading from the circular buffer (k0 in TS 36.212 Section 5.1.4.1.2) is to be decided by RAN1

  - NOTE 1: The maximum TBS after scaling and soft buffer size should follow limitations imposed by current LTE categories. RAN1 to discuss how to capture this limitation.

  - NOTE 2: Time interleaving is not applied for PMCH carrying MSI and/or MCCH.

- For the frequency-interleaving part of 5G Broadcast TFI, interleaving is performed via a row-column interleaving with the following steps:

  - Data symbols in an OFDM symbol are written column-wise.

    - RAN1 to decide what is the unit over which data symbols are written (e.g. a single RE, four REs, etc.)

  - The rows and elements in each row may be permuted, with details to be decided by RAN1.

  - Data symbols in an OFDM symbol are read row-wise.

    - RAN1 to decide the number of {rows, columns} of the interleaver.

NOTE: Time-frequency interleaving is not applicable to 0.37kHz SCS.

This document contains the following rapporteur’s input to this meeting:

-	An updated Workplan factoring the RAN agreements in.

# 2	Workplan

A workplan corresponding to the objectives and allocated TUs is suggested the table below.

Table 3-1: Workplan for the LTE_terr_bcast_Ph2 WI

| Date | RAN1 | RAN2 | RAN3 | RAN4 | RAN |
| --- | --- | --- | --- | --- | --- |
| 2025-02 | RAN1#120 Start discussion on Time-frequency interleaver design for MBMS dedicated cells. Capture set of options for all the items.Start agreeing on solution(s). |  |  |  |  |
| 2025-03 |  |  |  |  | RAN#107 Status Report (target of 12.5% corresponding to 0.5 TUs spent over an initial allocation of 4) |
| 2025-04 | RAN1#120bis Continue the discussion on Time-frequency interleaver design for MBMS dedicated cells. - Finalize details on scaling of TBS, values for N - Finalize the number of row (& columns) in the interleaver. - Finalize the unit over which elements are written. Further discuss how to capture the TBS / soft buffer size limitation, how to schedule the TBs, and how to perform permutation of rows / elements in a row, and the equation for 𝑘_0 Starting discussion on RRC configuration parameters, UE capabilities. |  |  |  |  |
| 2025-05 | RAN1#121 Finalize details of TFI on remaining open issues [R1-2503143], including: - Finalize details of the permutation of rows / elements in a row. - Finalize details on how to schedule the TBs. - Finalize details for 𝑘0 Consolidate list of RRC parameters from RAN1 perspective. Continue discussion on UE capabilities. | RAN2#130 Start the discussion on signalling impacts to support the feature, based on the agreements made in RAN1 - Initial discussion and draft CRs to capture the new features in TS 36.321 (MSI) and 36.331 NOTE: Changes to MSI may be needed based on RAN1 decision on how to schedule the TBs. | RAN3#128 Present the work plan for the WI. Start discussion on RAN3 related objectives on LTE based 5G Broadcast.. Designate responsible companies for Stage-2 & 3 BL CRs. |  |  |
| 2025-06 |  |  |  |  | RAN#108 Status Report (target of 50% corresponding to 2 TUs spent over an initial allocation of 4) |
| 2025-08 |  | RAN2#131 Finalize impact on for TS 36.321 and 36.331. | RAN3#129 Finalise Stage 2 & 3 CRs Agree Stage 2 & 3 CRs | RAN4#116 Agree on evaluation assumptions & reference channel. |  |
| 2025-09 |  |  |  |  | RAN#109 Status Report (target of 75% corresponding to 3 TUs spent over an initial allocation of 4) |
| 2025-10 |  |  |  | RAN4#116bis Initial discussion on evaluation results |  |
| 2025-11 |  |  |  | RAN4#117 Finalize requirements |  |
| 2025-12 |  |  |  |  | RAN#110 Status Report (target of 100% corresponding to 4 TUs spent over an initial allocation of 4) CRs received for approval. |

# 3	Conclusion

This contribution has provided:

-	An update to the workplan.