3GPP TSG-RAN WG3 Meeting #129	R3-255684

Bengaluru, India, 25th ~29th Aug, 2025

Agenda Item:	19.1

Source:	Rapporteur (Huawei, Samsung)

Title:	Updated workplan for Evolution of NR Duplex Operation

Document for:	Information

Introduction

The updated work item on evolution of NR duplex operation was approved in RAN#108 [1] and the objectives are shown below

- For subband non-overlapping full duplex (SBFD) operation at gNB side within a TDD carrier: - Specify semi-static indication of time location of SBFD subbands to UEs in RRC_CONNECTED mode [RAN1, RAN2] - Indication of time location of SBFD subbands in SIB is not precluded - Specify semi-static indication of frequency domain location of SBFD subbands to UEs in RRC_CONNECTED mode [RAN1, RAN2] - Indication of frequency domain location of SBFD subbands in SIB is not precluded - Specify SBFD operation to support random access in SBFD symbols by UEs in RRC CONNECTED mode and RRC_IDLE/INACTIVE mode [RAN1, RAN2] - Specify UE transmission, reception and measurement behavior and procedures in SBFD symbols and/or non-SBFD symbols for SBFD aware UE [RAN1, RAN2] - Transmission and reception behaviours on SBFD subbands configured in DL and/or flexible symbol indicated by TDD-UL-DL-ConfigCommon - UL transmissions within UL subband only - DL receptions within DL subband(s) only, except for CLI measurement by the UE outside of the DL subbands Note: When flexible symbols are used, it is not expected that any legacy Uplink symbol is converted to Downlink/SBFD symbols - Enhancement on resource allocation in frequency domain in SBFD symbols, including - resource allocation in frequency domain for PDSCH/CSI-RS across two DL subbands in SBFD symbols - handling of unaligned boundaries between SBFD subband(s) and RBG, CSI reporting subband, CSI-RS resource, PRG - Enhancements on physical channels/signals and procedure across SBFD symbols and non-SBFD symbols in different slots, where each transmission/reception within a slot has either all SBFD or all non-SBFD symbols, including - resource allocation in frequency domain for transmission or reception in SBFD symbols and non-SBFD symbols with different available frequency resource in different slots - CSI report of which associated CSI-RS instances occur in both SBFD symbols and non-SBFD symbols in different slots - Configurations for SRS, PUCCH and PUSCH on SBFD symbols and non-SBFD symbols, e.g., resources, frequency hopping parameters, UL power control parameters and/or beam/spatial relation - Collision handling between DL reception in DL subband(s) and UL transmission in UL subband in a SBFD symbol - Followings are assumed based on TR 38.858 - SBFD at the gNB side - Half duplex operation at the UE side - FR1 and FR2-1 - SBFD operation Option 4, i.e., both time and frequency locations of subbands for SBFD operation are known to SBFD aware UEs - Coexistence between non-SBFD aware UEs (including legacy UEs) and SBFD aware UEs in the cell operating SBFD at gNB side - SBFD scheme within a single configured DL and UL BWP pair with aligned center frequencies - One UL subband for SBFD operation in an SBFD symbol (excluding legacy UL symbol/slot) within a TDD carrier - Mechanisms for SBFD operation shall also consider the adjacent channel coexistence between two operators - Specify enhancements for CLI handling [RAN1, RAN2, RAN3, RAN4]: - Information exchange among gNBs, including [RAN3] - Semi-static cell-specific SBFD time and frequency location configuration - Measurement resource configuration, i.e., SSB and/or periodic NZP CSI-RS - Strongest DL beam information - CLI-mitigation request - One or more SRS resource configurations - UL resource muting for PUSCH, including [RAN1, RAN2, RAN4] - Indication/determination of UL resource muting for PUSCH based on semi-static configuration, assuming comb-2 for both DFT-S-OFDM and CP-OFDM in each allocated PRB and up to 2 symbols in time domain - PUSCH resource mapping, i.e., rate-matching around the muted REs - UCI resource determination in symbols with muted REs - L1 based UE-to-UE CLI measurement and reporting based on existing CSI framework, including [RAN1, RAN2, RAN4] - Periodic, semi-persistent, or aperiodic measurement resource (set), i.e., SRS-RSRP resource or CLI-RSSI resource, and configuration/determination of ‘typeD’ QCL assumptions for the CLI measurement resource - At least aperiodic reporting - New report quantities, e.g., L1-SRS-RSRP, L1-CLI-RSSI and/or measurement resource indices - UCI bits generation - Priority rules for multiple CSI reporting - CLI measurement accuracy requirement - Note: Without dedicated optimization for dynamic/flexible TDD. - Specify BS RF requirements for SBFD operation at gNB [RAN4] - Specify applicable RRM core requirements for CLI handling mechanisms [RAN4] - Specify other RRM core requirements for SBFD operation, if identified [RAN4] - Note: RAN3 will not specify enhancements to network signalling to support inter-operator coordination for CLI handling - Notes: Following are assumed for information exchange among gNBs - No normative behavior is implied for the gNB receiving the CLI-mitigation request. No need to further send a stop message for CLI mitigation. Detailed signaling can be discussed in RAN3 - The information exchanges are subject to RAN3’s assessment of feasibility and specification impact - Notes: Following are assumed for UL resource muting - No new DCI field / MAC CE is introduced for indication/determination of UL resource muting - No impact on data and control multiplexing as defined in section 6.2.7, TS 38.212 - UL resource muting does not apply for Msg A PUSCH and Msg 3 PUSCH - UL resource muting applies only for UEs in RRC_CONNECTED mode - UE assumes that the UL resource muting pattern does not overlap UL DMRS or PT-RS in the same symbol - Power boosting is assumed for REs in the symbol with UL resource muting. PUSCH transmit power does not change across symbols - No changes on TBS determination for PUSCH - Check impact on transmit signal quality/MPR requirement, if any, with RAN4 - This feature is subject to UE capability - Notes: Following are assumed for L1 based UE-to-UE CLI measurement and reporting - The measurement resources for SRS-RSRP are based on the existing legacy RS patterns. No RAN1/RAN2/RAN4 specification impact due to SRS configuration information exchange between gNBs - Periodic and semi-persistent reporting can be considered in addition to aperiodic reporting - For the new reporting quantities, at least wideband reporting is supported - The existing CSI processing unit, CPU occupation rule and timeline for L1 beam reporting are reused for L1 UE-to-UE CLI measurement and reporting as starting point

The work plan for this work item is provided in section 2, based on the noted one in [2].

Work Plan

The work plan for WGs is provided in Table 1.

Table 1: WI plan for Evolution of NR duplex operation

| Schedule and TU | Work plan |
| --- | --- |
| February, 2024 RAN1#116 (2 TU) | RAN1 - Start discussion on indication of time and frequency location of SBFD subbands - Start discussion on SBFD operation to support random access in SBFD symbols including the study for UEs in RRC_IDLE/INACTIVE mode - Discuss the potential benefits, issues and evaluations of supporting random access in SBFD symbols for UEs in RRC_IDLE/INACTIVE mode - Start discussion on down-selection of gNB-to-gNB CLI handling scheme(s) and UE-to-UE CLI handling scheme(s) - Identify the candidate schemes and the corresponding specification impacts - Discuss and agree on the high-level principles of further down-selection |
| April, 2024 RAN1#116bis (2 TU) RAN4#110bis (0.25 TU) | RAN1 - Continue discussion on indication of time and frequency location of SBFD subbands - Start discussion on UE transmission, reception and measurement behavior and procedures in SBFD symbols and/or non-SBFD symbols for SBFD aware UE - Focus on transmission and reception behaviours on SBFD subbands configured in DL and/or flexible symbol indicated by TDD-UL-DL-ConfigCommon - Continue discussion on SBFD operation to support random access in SBFD symbols including the study for UEs in RRC_IDLE/INACTIVE mode - Continue discussion on down-selection of gNB-to-gNB CLI handling scheme(s) and UE-to-UE CLI handling scheme(s) RAN4 - Start discussion on BS RF requirements for SBFD operation at gNB - Discuss on SBFD operation impact on existing BS RF requirements - Discuss on the necessity of introducing new requirements for SBFD operation, identified in study item |
| May, 2024 RAN1#117 (2 TU) RAN4#111 (0.25 TU) | RAN1 - Agree on the detailed design of indication of time and frequency location of SBFD subbands - Continue discussion on SBFD operation to support random access in SBFD symbols and finalize the study for UEs in RRC_IDLE/INACTIVE mode - Continue discussion on UE transmission, reception and measurement behavior and procedures in SBFD symbols and/or non-SBFD symbols for SBFD aware UE - Finalize discussion on transmission and reception behaviours on SBFD subbands configured in DL and/or flexible symbol indicated by TDD-UL-DL-ConfigCommon - Start discussion on enhancement on resource allocation in frequency domain in SBFD symbols - Start discussion on enhancements on physical channels/signals and procedure across SBFD symbols and non-SBFD symbols in different slots - Finalize the down-selection of gNB-to-gNB CLI handling scheme(s) and UE-to-UE CLI handling scheme(s) - Send LS to RAN3 to inform the RAN1 agreements on down-selection of gNB-to-gNB CLI handling scheme(s) and UE-to-UE CLI handling scheme(s) RAN4 - Continue discussion on BS RF requirements for SBFD operation at gNB - Continue discussion on SBFD operation impact on existing BS RF requirements - Continue discussion on the necessity of introducing new requirements for SBFD operation, identified in study item |
| August, 2024 RAN1#118 (2 TU) RAN2#127 (0.5 TU) RAN4#112 (1.5 + 0.5 TU) | RAN1 - Finalizing any remaining issues on indication of time and frequency location of SBFD subbands - Continue discussion on SBFD operation to support random access in SBFD symbols for UEs in RRC_CONNECTED mode and for UEs in RRC_IDLE/INACTIVE mode if agreed - Continue discussion on UE transmission, reception and measurement behavior and procedures in SBFD symbols and/or non-SBFD symbols for SBFD aware UE - Continue discussion on enhancement on resource allocation in frequency domain in SBFD symbols - Continue discussion on enhancements on physical channels/signals and procedure across SBFD symbols and non-SBFD symbols in different slots - Start discussion on configurations for SRS, PUCCH and PUSCH on SBFD symbols and non-SBFD symbols - Start discussion on collision handling between DL reception in DL subband(s) and UL transmission in UL subband in a SBFD symbol - Start discussion on gNB-to-gNB CLI handling scheme(s) and UE-to-UE CLI handling scheme(s) RAN2 - Start discussion on indication of time and frequency location of SBFD subbands and assessment of RAN2 impacts of potential solutions - Start discussion on SBFD operation to support random access in SBFD symbols and assessment of RAN2 impacts of potential solutions RAN4 - Continue discussion on BS RF requirements for SBFD operation at gNB - Progress achieved on SBFD operation impact on some of existing BS RF requirements - Progress achieved on the necessity for some of new requirements for SBFD operation, identified in study item - Start discussion on RRM core requirements for CLI handling mechanism(s) - Discuss the necessity of measurement requirement(s) for CLI handling scheme(s), including gNB-to-gNB and/or UE-to-UE scheme(s) down-selected - Start discussion on other RRM core requirements impact identified for SBFD operation |
| October,2024 RAN1#118bis (2 TU) RAN2#127bis (0.5 TU) RAN3#125bis (0.25 TU) RAN4#112bis (1.5 + 0.5 TU) | RAN1 - Continue discussion on SBFD operation to support random access in SBFD symbols for UEs in RRC_CONNECTED mode and for UEs in RRC_IDLE/INACTIVE mode if agreed - Continue discussion on UE transmission, reception and measurement behavior and procedures in SBFD symbols and/or non-SBFD symbols for SBFD aware UE - Continue discussion on enhancement on resource allocation in frequency domain in SBFD symbols - Continue discussion on enhancements on physical channels/signals and procedure across SBFD symbols and non-SBFD symbols in different slots - Continue discussion on configurations for SRS, PUCCH and PUSCH on SBFD symbols and non-SBFD symbols - Continue discussion on collision handling between DL reception in DL subband(s) and UL transmission in UL subband in a SBFD symbol - Continue discussion on gNB-to-gNB CLI handling scheme(s) and UE-to-UE CLI handling scheme(s). RAN2 - Continue discussion on indication of time and frequency location of SBFD subbands and RAN2 impacts of the potential solutions - Continue discussion on SBFD operation to support random access in SBFD symbols and RAN2 impacts of the potential solutions - Start discussion on UE transmission, reception and measurement behavior and procedures in SBFD symbols and/or non-SBFD symbols for SBFD aware UEs and assessment of RAN2 impacts of potential solutions - Start discussion on gNB-to-gNB CLI handling scheme(s) and UE-to-UE CLI handling scheme(s) and assessment of RAN2 impacts of potential solutions RAN3 - Start discussion on RAN3 impact of gNB-to-gNB CLI handling scheme(s) RAN4 - Continue discussion on BS RF requirements for SBFD operation at gNB - Progress achieved on SBFD operation impact on some of existing BS RF requirements - Progress achieved on the necessity for some of new requirements for SBFD operation, identified in study item - Continue discussion on RRM core requirements for CLI handling mechanism(s) - Further discuss the necessity of measurement requirement(s) for CLI handling scheme(s), including gNB-to-gNB and/or UE-to-UE scheme(s) down-selected - Continue discussion on other RRM core requirements impact identified for SBFD operation |
| November, 2024 RAN1#119 (2 TU) RAN2#128 (0.5 TU) RAN3#126 (0.25 TU) RAN4#113 (1.5 + 0.5 TU) | RAN1 - Continue discussion on SBFD operation to support random access in SBFD symbols for UEs in RRC_CONNECTED mode and for UEs in RRC_IDLE/INACTIVE mode if agreed - Continue discussion on UE transmission, reception and measurement behavior and procedures in SBFD symbols and/or non-SBFD symbols for SBFD aware UE - Finalize discussion on enhancement on resource allocation in frequency domain in SBFD symbols - Finalize discussion on enhancements on physical channels/signals and procedure across SBFD symbols and non-SBFD symbols in different slots - Continue discussion on configurations for SRS, PUCCH and PUSCH on SBFD symbols and non-SBFD symbols - Continue discussion on collision handling between DL reception in DL subband(s) and UL transmission in UL subband in a SBFD symbol - Continue discussion on gNB-to-gNB CLI handling scheme(s) and UE-to-UE CLI handling scheme(s). RAN2 - Continue discussion and conclude stage-2 details of the solutions and RAN2 impacts RAN3 - Continue discussion on RAN3 impact of gNB-to-gNB CLI handling scheme(s) RAN4 - Continue discussion on BS RF requirements for SBFD operation at gNB - Progress achieved on SBFD operation impact on some of existing BS RF requirements - Agree on whether new requirements for SBFD operation identified in study item are introduced - Continue discussion on RRM core requirements for CLI handling mechanism(s) - Progress achieved on the necessity of measurement requirement(s) for CLI handling scheme(s), including gNB-to-gNB and/or UE-to-UE scheme(s) down-selected - Continue discussion on other RRM core requirements impact identified for SBFD operation |
| February, 2025 RAN1#120 (2 TU) RAN2#129 (0.5 TU) RAN3#127 (0.5 TU) RAN4#114 (1.5 + 0.5 TU) | RAN1 - Continue discussion on SBFD operation to support random access in SBFD symbols for UEs in RRC_CONNECTED mode and for UEs in RRC_IDLE/INACTIVE mode if agreed - Continue discussion on UE transmission, reception and measurement behavior and procedures in SBFD symbols and/or non-SBFD symbols for SBFD aware UE - Finalize discussion on configurations for SRS, PUCCH and PUSCH on SBFD symbols and non-SBFD symbols - Finalize discussion on collision handling between DL reception in DL subband(s) and UL transmission in UL subband in a SBFD symbol - Continue discussion on gNB-to-gNB CLI handling scheme(s) and UE-to-UE CLI handling scheme(s). RAN2 - Continue the discussion on the stage-2 and stage-3 details of the solutions and RAN2 impacts - Start drafting and endorsing stage-2 skeleton CRs RAN3 - Continue the discussion on the stage-2 and stage-3 details of the solutions and RAN3 impacts RAN4 - Continue discussion on BS RF requirements for SBFD operation at gNB: - Agree on SBFD operation impact on all existing BS RF requirements - Agree on new requirements identified to be introduced for SBFD operation. - Continue discussion on RRM core requirements for CLI handling mechanism(s) - Progress achieved on the necessity of measurement requirement(s) for CLI handling scheme(s), including gNB-to-gNB and/or UE-to-UE scheme(s) down-selected - Continue discussion on other RRM core requirements impact identified for SBFD operation |
| April, 2025 RAN1#120bis (2 TU) RAN2#129bis (0.75 TU) RAN3#127bis (0.5 TU) RAN4#114bis (1.5 + 0.5 TU) | RAN1 - Finalize discussion on SBFD operation to support random access in SBFD symbols for UEs in RRC_CONNECTED mode and for UEs in RRC_IDLE/INACTIVE mode if agreed - Finalize discussion on UE transmission, reception and measurement behavior and procedures in SBFD symbols and/or non-SBFD symbols for SBFD aware UE - Finalize discussion on gNB-to-gNB CLI handling scheme(s) and UE-to-UE CLI handling scheme(s). RAN2 - Finalize the details of the solutions and RAN2 impacts - Update and endorse running stage-2 CRs - Start drafting stage-3 running CRs RAN3 - Continue the discussion on the stage-2 and stage-3 details of the solutions and RAN3 impacts - Start drafting and endorse BL CRs RAN4 - Continue discussion on BS RF requirements for SBFD operation at gNB - Draft CR(s) on existing BS RF requirements’ impact for SBFD operation are provided for discussion - Draft CR(s) on new BS RF requirements for SBFD operation, if necessity identified, are provided for discussion - Continue discussion on RRM core requirements for CLI handling mechanism(s) and other identified impact(s) - Draft CR(s) on measurement requirement(s) for CLI handling scheme(s), if necessity identified - Draft CR(s) on RRM core requirements impact identified for SBFD operation |
| May, 2025 RAN1#121 (2 TU) RAN2#130 (0.75 TU) RAN3#128 (0.5 TU) RAN4#115 (1.5 + 0.5 TU) | RAN1 - Resolve remaining issues on SBFD operation to support random access in SBFD symbols for UEs in RRC_CONNECTED mode and for UEs in RRC_IDLE/INACTIVE mode if agreed - Resolve remaining issues on UE transmission, reception and measurement behavior and procedures in SBFD symbols and/or non-SBFD symbols for SBFD aware UE - Resolve remaining issues on gNB-to-gNB CLI handling scheme(s) and UE-to-UE CLI handling scheme(s) RAN2 - Resolve remaining issues, and update running CRs RAN3 - Resolve remaining issues, and stabilize the BLCRs RAN4 (core) - Finalize discussion and endorse draft CR(s) on BS RF requirements and RRM requirements for SBFD operation at gNB RAN4 (performance) - Begin discussion on - BS RF conformance requirements to support SBFD operation at gNB - RRM performance requirements to support SBFD operation - SBFD-capable BS and/or SBFD-aware UE demodulation performance requirements to support SBFD operation |
| August, 2025 RAN2#131 (0.75 TU) RAN3#129 (0.5 TU) RAN4#116 (1.5 + 0.5 TU) | RAN2 - Resolve remaining issues, if any, and approve stage-2 and stage-3 CRs RAN3 - Resolve remaining issues, if any; - Address the added objective in RAN#108 and approve corresponding TPs if agreeable or, remove the added bullet if no consensus; - Approve the BLCRs RAN4 (core) - Resolve remaining issues on BS RF requirements and RRM requirements for SBFD operation at gNB, and CR updates RAN4 (performance) - Continue discussion on - test issues identified for BS RF conformance requirements to support SBFD operation at gNB - RRM performance requirements to support SBFD operation - SBFD-capable BS and/or SBFD-aware UE demodulation performance requirements to support SBFD operation |
| October, 2025 RAN4#116bis (0.5 + 1 TU) | RAN4 (performance) - Continue discussion and prepare draft CR(s) on - BS RF conformance requirements to support SBFD operation at gNB - RRM performance requirements to support SBFD operation - SBFD-capable BS and/or SBFD-aware UE demodulation performance requirements to support SBFD operation |
| November, 2025 RAN4#117 (0.5 + 1 TU) | RAN4 (performance) - Finalize discussion and endorse draft CR(s) for - BS RF conformance requirements to support SBFD operation at gNB - RRM performance requirements to support SBFD operation - SBFD-capable BS and/or SBFD-aware UE demodulation performance requirements to support SBFD operation |
| January, 2026 RAN4#118 (0.5 + 1 TU) | RAN4 (performance) - Resolve remaining issues and CR updates on introduced performance requirements |

The BL CR assignment:

38.473: SS

38.423: HW

38.470: CATT

38.420: CMCC

38.300: E///

38.401: ZTE

- References

RP-251874, Revised WID: Evolution of NR duplex operation: Sub-band full duplex (SBFD)

R3-252212, Updated workplan for Evolution of NR Duplex Operation (Huawei, Samsung)