3GPP TSG RAN WG4 Meeting #111	R4-2408529

Fukuoka City, Japan, May 20th – May 24th, 2024

Agenda Item:	10.6.1

Source: 	Ericsson

Title:	Work plan for NR Radio Resource Management (RRM) Phase 5

Document for:	Approval

- Introduction

The WI NR Radio Resource Management (RRM) for Rel-19 was approved from RAN 103 meeting.

According to the WID [1], RAN4 is required to complete all the necessary RRM core and performance requirements related to the RRM enhancement phase 5 by core requirement by RAN# 109 and performance requirement by RAN #111 meeting [1].

This contribution provides the work plan and timeline breakdown across to ensure timely completion of the performance part of the WI.

The objective is :

- Fast SCell activation for UE supporting Rel-18 EMR

  - Study and, if feasible, to reduce the SCell activation delay with valid EMR reporting

  - Apply fast scell activation in FR1 and FR2-1

  - Note: RAN4 to start this work from Q3’2024 and aim for completion in Dec’2024. Workplan for this bullet can be discussed in May’2024

# Work plan and timeline

- RAN4#111:

  - Objective 2 Fast SCell activation for UE supporting Rel-18 EMR

    - Work plan discussion and agreement

- RAN4#112

  - Objective 2 Fast SCell activation for UE supporting Rel-18 EMR

    - Discussion on the feasibility to use the EMR report for Scell activation delay reduction.

    - Identify the feasible scenarios both in FR1 and FR2-1

    - Agreement on the scenarios applicable to use EMR report enhance Scell activation unknown target cell.

- RAN4#112 bis

  - Objective 2 Fast SCell activation for UE supporting Rel-18 EMR

    - Delay requirement proposals for both FR1 and FR2-1 feaible scenarios.

    - Discussion for side conditions to apply for potential delay requirements enhancement.

    - Discussion for potential signalling enhancement needed from other working group and trigger the LS work.

- RAN4#113

  - Objective 2 Fast SCell activation for UE supporting Rel-18 EMR

    - Delay requirement proposals for both FR1 and FR2-1 feaible scenarios.

    - Discussion for side conditions to apply for potential delay requirements enhancement.

    - Discussion for potential signalling enhancement needed from other working group and trigger the LS work.

- RAN4#114

  - Objective 2 Fast SCell activation for UE supporting Rel-18 EMR

    - Agreement on the enhanced Scell activation delay requirements

    - Agreement for UE side conditions to apply for applicable delay requirements.

    - Agreement on CRs to update the requirements and side conditions.

- RAN4#114 bis

  - Objective 2 Fast SCell activation for UE supporting Rel-18 EMR

    - Maintenance for the core part requirements.

    - Discussion on RRM performance test case list proposals

- RAN4#115

  - Objective 2 Fast SCell activation for UE supporting Rel-18 EMR

    - Maintenance for the core part requirements.

    - Agreement on RRM performance test case list and work split

- RAN4#116

  - Objective 2 Fast SCell activation for UE supporting Rel-18 EMR

    - Maintenance for the core part requirements.

    - Agreement on CRs for RRM performance test case

# References

- RP-240830, NR Radio Resource Management (RRM) Phase 5