3GPP TSG-RAN WG4 Meeting #116-bis                                                           R4-2514294

Prague, Czech Republic, 13th – 17th October, 2025

Agenda item:	7.8.2

Source:	TELUS, Samsung, Apple

Title:	Work plan for enhancement of low NR band carrier aggregation via switching

Release:	Rel-20

Document for:	Approval

# 1	Introduction

During the RAN #109 meeting, the work item on enhancement of low NR band carrier aggregation via switching was approved in [1] with the following objectives:

The core part of WI: - Specify the necessary UE RF and RRM core requirements to allow switching between {case 1, case 3} to enable low band carrier aggregation via switching for the dual downlink scenario between FDD band and SDL band [RAN4]. - Case 1: Tx/Rx on FDD carrier 1 and no Rx on SDL carrier 2. - Case 3: Rx on both FDD carrier 1 and SDL carrier 2 and no Tx on FDD carrier 1. - Example band combinations: CA_n12A-n29A and CA_n28A-n67A, additional FDD+SDL band combinations can be added in the specific basket WI after this WI is completed. - Reuse the time mask requirements defined in Rel-19 for low-band CA via switching as much as possible - Note: Case 2 is specified in Rel-19 WID of NR_LBCA_Sw - Reuse the semi-static switching mechanism based on RRC configuration defined in Rel-19 for low-band CA via switching - Consider the following deployment constraints: - The carrier frequency for all cases is <1GHz. - Co-located and synchronized network deployment for both carriers. - Both carriers are in a single TAG. - SCS 15Khz on both carriers. - No in-gap interference between DL carriers is expected Note 1: Reuse Rel-19 LB-CA RAN4 requirements as much as possible. The performance part of WI: - Specify RRM test case(s) corresponding to the RRM core requirements.

This contribution provides the Rapporteur’s work plan.

# 2	Work Plan

Based on the time budget in RP-252953, the following work plan is proposed:

| Meeting | Tasks |
| --- | --- |
| RAN4 #116-bis (RF, 0.25 TU) (RRM, 0.25 TU) | General - Approval of workplan RF (core) - Discuss reference architecture for Case 3 - Discuss switching time applicable to Case 3 RRM (core) - Preliminary analysis on RRM working scope for Rel-20 dual DL LB CA via switching scenario |
| RAN4 #117 (RF, 0.25 TU) (RRM, 0.25 TU) | RF (core) - Conclude reference architecture and switching time for Case 3 - Discuss scope of impact of Case 3 on the remaining RF requirements RRM (core) - Continue discussion and conclude on RRM working scope for Rel-20 dual DL LB CA via switching scenario - Initial discussion on - Applicability of Rel-19 LB CA RRM core requirements in Rel-20 dual DL LB CA via switching scenario - RRM core requirements impact identified for Rel-20 dual DL LB CA via switching scenario |
| RAN4 #118 (RF, 0.25 TU) (RRM, 0.5 TU) | RF (core) - Continue discussion of RF requirements and impact on the specification RRM (core) Continue discussion on - Applicability of Rel-19 LB CA RRM core requirements in Rel-20 dual DL LB CA via switching scenario - RRM core requirements impact identified for Rel-20 dual DL LB CA via switching scenario |
| RAN4 #118-bis (RF, 0.25 TU) (RRM, 0.5 TU) | RF (core) - Conclude the RF requirement discussion and endorse a draft CR RRM (core) - Continue discussion and conclude on the applicability of Rel-19 LB CA RRM core requirements in Rel-20 dual DL LB CA via switching scenario - Continue discussion on RRM core requirements impact identified for Rel-20 dual DL LB CA via switching scenario |
| RAN4 #119 (RF, 0.25 TU) (RRM, 0.5 TU) | RF (core) - Agree on a formal CR RRM (core) Continue discussion on RRM core requirements impact identified for Rel-20 dual DL LB CA via switching scenario |
| RAN4 #120 (RF, 0.25 TU) (RRM, 0.5 TU) | RRM (core) - Continue discussion on RRM core requirements impact identified for Rel-20 dual DL LB CA via switching scenario and agree on the identified impacts - Discuss spec impacts of RRM core requirements and agree on the work split of draft CR(s) |
| RAN4 #120-bis (RF, 0.25 TU) (RRM, 0.5 TU) | RRM (core) - Update or specify new RRM core requirements for Rel-20 dual DL LB CA via switching scenario - Discussion on draft CR(s) if available |
| RAN4 #121 (RF, 0.25 TU) (RRM, 0.5 TU) | RRM (core) Finalize discussion and endorse draft CR(s) on RRM core requirements for Rel-20 dual DL LB CA via switching scenario |
| RAN4 #122 (RF, 0.25 TU) (RRM, 0.25 TU): | RRM (core) - Agree on formal CR(s) - Resolve remaining issues on RRM requirements for Rel-20 dual DL LB CA via switching scenario if any and close the WI |

NOTE: TR 38.768 will continue to be used to capture relevant RF and RRM technical background during this work item. The TR is now under revision control, and change requests are encouraged via the draft CR / formal CR process.

Proposal 1: It is proposed to approve the work plan for the work item on enhancement of low NR band carrier aggregation via switching.

# 3 Reference

[1] 	RP-252953, New WID on enhancement of low NR band carrier aggregation via switching, Moderator (Huawei)