## Slide 1: RAN4 Way Forward on 6G Study Item
Source: AT&T (Rapporteur)
Agenda: 8.2
3GPP TSG RAN WG4 Meeting #116bis R4-2514649
Prague, Czech, Oct 13th – 17th, 2025

## Slide 2: Introduction
RAN4 initiated its work on the 6G Radio Study Item with a discussion of the draft 6G Workplan [1]
[1] is a joint RAN1/2/3/4 contribution presented for information only.
The material in [1] is derived from the RAN4 6G topic planning presented by the RAN4 chair in [2]
The following issues were raised during the review of [1]
  Misalignment of the time plan between RAN1 and RAN4
  Contribution planning for future meetings
  Study topic omission

## Slide 3: RAN1/RAN4 time plan alignment
RAN1 topics started at RAN1#122 (August 2025)
Overview of 6GR air interface
Waveform
Frame structure
Channel coding
Modulation, joint channel coding and modulation
Energy efficiency
AI/ML
RAN1 topics planned to start at RAN1#124 (February 2026)
Initial access
MIMO
Physical layer control, data scheduling, and HARQ operation
Duplexing
6G spectrum utilization and aggregation
NTN
Other physical layer signals, channel and procedures
RAN1 topic(s) planned to start at RAN1#126bis (October 2026)
Sensing
Proposal 1: Present a revised workplan at RAN4#117 based on the agreements in RAN4#116bis.

## Slide 4: Contribution planning for future meetings
Review of feature lead notes for 6GR SI topics indicates that feature leaders establish way-forwards as a part of the discussion
  Feature lead create WFs based on individual formats and organization
  WFs are very detail-oriented
Combination of individual WFs is not advised
  Redundancy
  Opportunities for introducing errors
  Difficult to align format and organization between topics
Difficult to foresee progress beyond a certain number of meetings.
  Propose to adjust workplan based on progress
Proposal 2Contribution planning for future meetings to be managed by feature leads
Proposal 3: Indicate (in the revised workplan to be presented at RAN4#117) that the workplan for meetings beyond RAN#112 is TBD

## Slide 5: Study topic omission
BS energy efficiency
  Energy efficiency is absent from the time-line chart at the beginning of [1], but is mentioned in the text descriptions for each meeting
    E.g., under BS RF and coexistence for RAN4#116bis:
      Begin discussions on improvements for BS efficiency specification.
  Conclusion: BS efficiency topic is included
Overall AI/ML Framework
  RAN4 text only mentions use-cases
  6GR SI [3] indicates RAN4 participation in LCM and framework study
  Conclusion: Add AI/ML framework as a study topic for RAN4
Proposal 4: Add AI/ML framework as a study topic for RAN4 in the revised workplan to be presented at RAN4#117

## Slide 6: Conclusion
Proposal 1: Present a revised workplan at RAN4#117 based on the agreements in RAN4#116bis.
Proposal 2: Contribution planning for future meetings to be managed by feature leads
Proposal 3: Indicate (in the revised workplan to be presented at RAN4#117) that the workplan for meetings beyond RAN#112 is TBD
Proposal 4: Add AI/ML framework as a study topic for RAN4 in the revised workplan to be presented at RAN4#117

## Slide 7: References
[1] R4-2514091, Workplan for Rel-20 Study of 6GR, NTT DOCOMO, China Mobile, AT&T, Vodafone, RAN4#116bis, October 2025
[2] R4-2511652, Plan on RAN4 6G discussion and meeting arrangement in Rel-20, RAN4 Chair, RAN4#116, August 2025
[3] RP-251881, New SID: Study on 6G Radio, RAN#108, June 2025