## Slide 1: RAN4#94 E-meeting Arrangements and Guidelines
RAN4 Chair: Steven Chen
Vice Chairs: Haijie Qiu, Andrey Chervyakov
3GPP TSG-RAN WG4 Meeting #94-e R4-2000001
Electronic Meeting, 24 Feb. – 6 Mar., 2020
Agenda Item: 3

## Slide 2: General Aspects
The tdoc submission deadline is 11:59pm UTC on Fri Feb. 14th 2020
The E-meeting will take place during Feb. 24 – Mar. 6 (i.e. two weeks) using email discussions. No conference calls will be used.
Email discussions will be carried out on RAN4 email reflector 3GPP_TSG_RAN_WG4@LIST.ETSI.ORG
The focus is on completing R16 work and providing R15 critical maintenance
This E-meeting shall have full decision power, i.e. decisions made during the E-meeting need not be ratified at RAN4#94 bis

## Slide 3: Scope
Some topics will be excluded from agenda. Please refer to the revised agenda for details
Guidelines for R16 topics
  R16 RF/RRM: Focus on Core part completion
  R16 Demod: Focus on initial test scope, simulation results to facilitate Rel-16 performance requirements, and further alignment of simulation assumptions

## Slide 4: Scope (cont.)
CR handling
  Only the following CRs are allowed:
    LTE/NR spectrum related topics, i.e. basket WIs, adding channel bandwidths to a band, new bands, etc.,
    R15 NR maintenance CRs will be allowed.
    For R16 WIs, please use your good judgement to submit necessary CRs. CRs to WIs far from completion shall be deferred to RAN4#94bis
  More instructions on CR (see slide 10 for CR guidelines)
LS handling
  As usual, all the incoming LSs will be noted. But critical/urgent issues raised in the incoming LSs, if not excluded from the agenda, will be treated, including reply LSs
WF handling
  No WF submission before the start of the e-meeting.
  During the meeting session chair will assign WF if needed

## Slide 5: Email discussion procedures/timelines
Thursday Feb 13
  Initial list of email discussion threads including basket WIs will be provided by RAN4 leadership
  Additional guidance on email discussion scoping and priorities will be provided.
Week before the E-meeting (Feb. 17 - 21)
  Monday (Feb. 17): email discussion moderators will be announced by session chairs (aligned template will be provided and used)
  Tuesday – Friday (Feb. 18-21): moderators prepare summary materials for email discussion
    Moderators shall identify key open issues, summarize proposals and recommend topics/questions to be handled via email discussions

## Slide 6: Email discussion procedures/timelines
  E-meeting (Feb. 24 – Mar. 6)
  Stage 0: Session chairs announce the set of email threads (no later than Monday 8am UTC, Feb. 24)
  Stage 1: Moderators trigger email discussion (Monday Feb. 24)
  Stage 2: Companies provide comments for the 1st round (Feb. 24 – Wednesday 5pm UTC Feb. 26)
  Stage 3: Moderators summarize the status and possible proposals, recommending what decisions can be made for 1st round. A formal t-doc will be used (Thursday 5pm UTC, Feb. 27)
  Stage 4: After receiving the summary from moderators, session chair may approve documents, make agreements or assign new CRs, WFs, LSs, etc. Then, session chair announces 2nd round discussion with tdoc status update (no later than Monday 8am UTC, March 2)
  Stage 5: Companies provide comments for 2nd round and moderators provide second round summary (Monday Mar. 2 – Thursday 5pm UTC Mar. 5)
    Note: Formal version of stable tdocs shall be uploaded to the Inbox (except Cat A CRs) before Stage 6
  Stage 6: Session Chair announces conclusions (no later than 5pm UTC, March 6)

## Slide 7: RAN4#94 e-meeting procedures/timelines
Pre e-meeting preparing
Session Chairs announce moderators assignment (Feb.17 )
Moderators preparing email discussion with aligned format (Feb.17 – 21)
1st round discussion
Stage 0: Session Chairs announce sets of email discussions (8am UTC, Feb.24 )
Stage 1 : Moderators provide initial summary to trigger email discussion (Feb.24)
Stage 2: Companies provide comments for 1st round (Feb. 24 – 5pm UTC Feb.26)
Stage 3: Moderators summarize the status and possible proposals (5pm UTC, Feb.27)
2nd round discussion
Stage 4: Session chair announces 2nd round discussion with T-doc status update (8am UTC, Mar.2)
Stage 5:Companies provide comments for 2nd round and moderators provide second round summary (Mar. 2 - 5pm UTC Mar. 5)
Stage 6: Session chairs announce final conclusion with t-doc status update (5pm UTC, Mar.6)
Feb.14t
T-doc submit
Feb.24
Mar.6
Feb.17
Work split Declare
E-meeting start
E-meeting close
Feb.27
1st round
View collection
2nd round
Discussion and revision
Pre e-meeting preparing
Mar.2
Mar.5
Feb.26

## Slide 8: Basket WIs Email discussion procedures/timelines
Handling of basket WIs (LTE baskets, i.e. AI 7.1 – 7.7, and NR baskets, i.e. AI 9.1 – 9.13) related draft CRs/TPs will follow the following process and timelines. Note: there is only one round of email discussion for basket WIs.
Tuesday Feb. 18: basket WI moderator will provide a list of contributions for email discussion (i.e. for flagging). The flag deadline is Friday 5pm UTC Feb. 21
Companies can flag contributions using the basket email thread title and the specific reason(s) of flag in the email, e.g.,
Tdoc Title Reason for discussion
R4-20xxxxx xxxx xxxx

## Slide 9: Basket WIs Email discussion procedures/timelines (cont.)
Monday Feb. 24: basket WI moderator will provide the updated list of contributions, in which:
  those that were not flagged will be considered “agreeable”
  those that were flagged will be revised. The authors are encouraged to share the revisions as soon as possible for further comments.
By Friday 5pm UTC, Feb. 28, basket WI moderators will provide a summary of the status of those flagged and revised tdocs. This summary should capture the following info:
  the reason for flagging
  if the revision is available
  if the revision is agreeable by addressing received comments).
Based on the summary, session chair will announce decisions by Tuesday 5pm UTC, March 3

## Slide 10: Notes on email discussions
Delegates are strongly encouraged to provide comments/concerns asap
  Silence within a reasonable timeframe means no objection
It is strongly encouraged that each company/delegate consolidate their comments/views and send them out in one email for each email thread

## Slide 11: Notes on email discussions (cont.)
Each email thread needs to use a clear and consistent thread title for easy tracking (the title for each thread is to be announced)
      E.g., if not done appropriately, after a while an email thread may become something like:
        RE: xxxx
        RE: RE: xxxx
        回复:RE: xxxx
        [External] RE: xxxx
        Etc.
        which makes it very hard to track. PLEASE fix it to RE: xxxx!
Some instruction how to get “RE:” in Word:
https://www.extendoffice.com/documents/outlook/4495-outlook-reply-subject-prefix.html

## Slide 12: Others
Please share your drafts in the server: ftp://3gpp.org/tsg_ran/WG4_Radio/TSGR4_94_e/Inbox/Drafts/ Avoid using email attachment (especially large attachments) for sharing drafts, which may cause email problems. In the Drafts folder, each email discussion thread will have its own sub-folder
  Note if delegates experience persistent problems or issues when uploading the drafts, they can email it to Kai-Erik.
To upload drafts to ftp://3gpp.org/tsg_ran/WG4_Radio/TSGR4_94_e/Inbox/Drafts/ or formal tdocs to ftp://3gpp.org/tsg_ran/WG4_Radio/TSGR4_94_e/Inbox/ , delegates need to use their EOL account credentials.
No tdoc revisions, except that:
  To correct technical errors
  CRs or TPs

## Slide 13: CR guidelines (applicable to all meetings)
Encourage to read MCC CR guidelines in https://www.3gpp.org/specifications/84-change-requests
CR formatting
  Make sure that all fields in the CR coversheet are filled in and filled in correctly
  Use the latest MCC CR template
  Encourage to use 3GU pre-filled coversheets which are available after tdoc reservation
CR coversheet errors handling
  No CR allocation / revision to fix CR coversheet errors will be allowed after tdoc submission deadline and before the meeting.
  CRs with coversheet errors need to be corrected during the meeting (before the CR is agreed / endorsed)
  CR revisions allocated during the meeting only (subject to session chair decision)