3GPP TSG-RAN WG4 Meeting #97-e                       	 R4-2014366

Electronic Meeting, 2 Nov. – 13 Nov., 2020

Agenda Item:	12.9.1

Source:	MediaTek Inc.

Title:	Work Plan of R17 UE Power Saving Enhancements WI

Document for:	Approval

# Introduction

A new Work Item of “R17 UE power saving enhancements” has been approved in RAN Plenary #86 meeting. The objectives of the latest version are quoted [1] as below,

The following objective are considered in this WI: - Specify enhancements for idle/inactive-mode UE power saving, considering system performance aspects [RAN2, RAN1] - Study and specify paging enhancement(s) to reduce unnecessary UE paging receptions, subject to no impact to legacy UEs [RAN2, RAN1] - NOTE: RAN1 to check and update, if needed, evaluation methodology in RAN1 #102-e meeting - Specify means to provide potential TRS/CSI-RS occasion(s) available in connected mode to idle/inactive-mode UEs, minimizing system overhead impact [RAN1] - NOTE: Always-on TRS/CSI-RS transmission by gNodeB is not required - Study and specify, if agreed, enhancements on power saving techniques for connected-mode UE, subject to minimized system performance impact [RAN1, RAN4] - Study and specify, if agreed, extension(s) to Rel-16 DCI-based power saving adaptation during DRX Active Time for an active BWP, including PDCCH monitoring reduction when C-DRX is configured [RAN1] - NOTE: Rel-15 and Rel-16 available power saving solutions should be supported by the UE and included in the evaluation. RAN1 will ask the confirmation from RAN2 that Rel-15 and Rel-16 available power saving solutions are properly utilized. - Study the feasibility and performance impact of relaxing UE measurements for RLM and/or BFD, particularly for low mobility UE with short DRX periodicity/cycle, and specify, if agreed, relaxation in the corresponding requirements [RAN4] - NOTE: Supplementary RAN2 work, if needed, can be triggered by RAN4 LS

In this contribution, we provide a work plan for the RAN4 led item (2)-b, relating to relaxing UE measurements for RLM and/or BFD.

# Work plan for R17 UE Power Saving Enhancements

In this paper, we will only focus on the work plan discussion as per chairman’s guidance. Based on the status report agreed in RAN #89-e meeting [2], there are only 5 meetings provided for RAN4 core part discussion. However, according to the updated “release, meeting, and TU planning” provided by the chairmen [3], it is possible that the final core part discussion meeting will be postponed to 2020 Q1. Therefore, here we provide 2 different work plans based on the old timeline and new timeline, respectively.

Work plan based on timeline agreed in [2]: (for approval)

Considering that RAN4 only has 5 meetings for the core part discussion, we plan to split them into two parts: 2 meetings for the study phase and 3 meetings for the work phase.

- 3GPP RAN4 #97e meeting (November, 2020, Study phase)

  - Discuss and conclude, if agreed:

    - Work plan

    - Candidate relaxation method(s), e.g., extended RLM/BFD evaluation period

    - Evaluation methodology:

      - Determine SLS assumption(s) and performance metric(s)

- 3GPP RAN4 #98e meeting (January, 2021, Study phase)

  - Calibration on the evaluation results for RLM/BFD measurement relaxation

  - Discuss and conclude, if agreed, beneficial relaxation method and the corresponding criteria for UE to enter the relaxation mode

- 3GPP RAN4 #98b-e meeting (April, 2021, Work phase)

  - Discuss and specify, if agreed:

    - Relaxation method and the corresponding criteria and scenarios for RLM/BFD

    - LS initial RRC parameters to RAN2, if needed

- 3GPP RAN4 #99e meeting (May, 2021, Work phase)

  - Discuss and specify, if agreed:

    - Relaxation method and the corresponding criteria and scenarios for RLM/BFD

    - Initial draft CR(s) on core part in TS38.133

- 3GPP RAN4 #100e meeting (August, 2021, Work phase)

  - Discuss and finalize RRM core part change and the corresponding draft CR(s) on core part in TS38.133

Work plan based on timeline in [3]: (for information)

If R17 timeline can be extended in RAN Plenary #90 e-meeting (Dec. 2020) as suggested in [3], the work plan can be extended by adding 1 more meeting for study phase and 2 more meetings for work phase, as shown in Figure 1. A detailed schedule can be found in the Appendix.

Figure 1: Extended plan w.r.t chairmen’s R17 timeline proposal [3] in RAN #89-e (decision expected in Dec. 2020)

By the above, we have the following proposal:

Proposal 1: RAN4 to endorse the RRM work plan for R17 UE powers saving enhancements as presented in this contribution.

- Note: If R17 timeline suggested in [3] is agreed in RAN Plenary #90 e-meeting, there will add one more meeting for study phase and two more meeting for work phase.

# Summary

In this contribution, we provided RAN4 RRM work plan for R17 UE power saving enhancements for endorsement.

Proposal 1: RAN4 to endorse the RRM work plan for R17 UE powers saving enhancements as presented in this contribution.

- Note: If R17 timeline suggested in [3] is agreed in RAN Plenary #90 e-meeting, there will add one more meeting for study phase and two more meeting for work phase.

# References

- RP-200938, “Revised WID UE Power Saving Enhancements for NR”, MediaTek Inc., RANP #88e meeting, Jun. 2020.

- RP-201701, “Status Report to TSG”, RANP #89e meeting, Sep., 2020.

- RP-202111, “Release, Meeting and TU planning”, RANP #89e meeting, Sep. 2020.

# Appendix

For information:

- 3GPP RAN4 #97e meeting (November, 2020, Study phase)

  - Discuss and conclude, if agreed:

    - Work plan

    - Candidate relaxation method(s), e.g., extended RLM/BFD evaluation period

    - Evaluation methodology:

      - Determine SLS assumption(s) and performance metric(s)

- 3GPP RAN4 #98e meeting (January, 2021, Study phase)

  - Calibration on the evaluation results for RLM/BFD measurement relaxation

  - Identify effective and feasible relaxation methods

  - Study the corresponding criteria or conditions for UE to enter the relaxation mode

- 3GPP RAN4 #98b-e meeting (April, 2021, Study phase)

  - Discuss and conclude, if agreed, beneficial relaxation method and the corresponding criteria for UE to enter the relaxation mode

    - A way forward to capture the RAN4 conclusion in study phase

- 3GPP RAN4 #99e meeting (May, 2021, Work phase)

  - Discuss and specify, if agreed:

    - Relaxation method and the corresponding criteria and scenarios for RLM/BFD

- 3GPP RAN4 #100e meeting (August, 2021, Work phase)

  - Discuss and specify, if agreed:

    - Relaxation method and the corresponding criteria and scenarios for RLM/BFD

    - LS initial RRC parameters to RAN2, if needed

- 3GPP RAN4 #100bis meeting (October, 2021, Work phase)

  - Discuss and specify, if agreed:

    - Relaxation method and the corresponding criteria and scenarios for RLM/BFD

    - Initial draft CR(s) on core part in TS38.133

- 3GPP RAN4 #101 meeting (November, 2021, Work phase)

  - Discuss and specify, if agreed:

    - LS final RRC parameters to RAN2, if needed

    - draft CR(s) on core part in TS38.133

- 3GPP RAN4 #102 meeting (January, 2022, Work phase)

- Discuss and finalize RRM core part change and the corresponding final CR(s) on core part in TS38.133